## W-3
TIME SCHEDULE
Package No - CCRIP/KHUL/UNR/2014/W-03
Sl. | Name of work | Days
No. |  | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156 | 168 | 180 | 192 | 204 | 216 | 228 | 240 | 252 | 264 | 276 | 288 | 300 | 312 | 324 | 336 | 348 | 365
1 | Clearing by removal and disposal at a safe distance of everything above ground level
2 | Earth work in box cutting on road crest up to 450mm depth with proper grade, camber and
3 | Providing and maintaining adequate portable water supply and sanitation facilities in labur
4 | Labour charge for picking up the existing brick on end edging (75mm across) including
5 | Sand (FM 0.50) filling on the road bed in the improved sub-grade with sand free from
6 | Providing compacted aggregate sand sub-base course with 38mm down Crusher run
7 | Brick on end edging (125mm across) with 1st class/picked bricks including cutting
8 | Prime coat with cut back bitumen to be prepared by cutting back 60/70 or 80/100
9 | 25mm thick compacted pre-mixed bituminous carpeting to be prepared using 16mm down
10 | 7mm thick compacted pre-mixed bituminous seal coat to be prepared using 6.33mm down
11 | Reinforced Cement Concrete work in bottom and top slab of box culvert of any height
12 | First class brick works in cement mortar (1:4) in staining of wells with sand (minimum
13 | Supplying and fabrication of M.S High strength deformed bar/ Twisted bar reinforcement
14 | Minimum 12mm thick cement plaster (1:4) to dado and plinth wall up to 150mm below
15 | Supplying, fitting & fixing 2 nos signboard (1.5m x 0.9m) including writing the name &
16 | Earth filling work with specified soil in any type of embankment including cutting, carrying
17 | Construction, Installing and fixing in position including painting & writing with plastic/synthetic

## W-2
TIME SCHEDULE
Package No - CCRIP/KHUL/VR/2014/W-02
Sl. | Name of work | Days
No. |  | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156 | 168 | 180 | 192 | 204 | 216 | 228 | 240 | 252 | 264 | 276 | 288 | 300 | 312 | 324 | 336 | 348 | 365
1 | Clearing by removal and disposal at a safe distance of everything above ground level
2 | Earth work in box cutting on road crest up to 450mm depth with proper grade, camber and
3 | Providing and maintaining adequate portable water supply and sanitation facilities in labur
4 | Labour charge for picking up the existing brick on end edging (75mm across) including
5 | Sand (FM 0.50) filling on the road bed in the improved sub-grade with sand free from
6 | Providing compacted aggregate sand sub-base course with 38mm down Crusher run
7 | Brick on end edging (125mm across) with 1st class/picked bricks including cutting
8 | Prime coat with cut back bitumen to be prepared by cutting back 60/70 or 80/100
9 | 25mm thick compacted pre-mixed bituminous carpeting to be prepared using 16mm down
10 | 7mm thick compacted pre-mixed bituminous seal coat to be prepared using 6.33mm down
11 | Reinforced Cement Concrete work in bottom and top slab of box culvert of any height
12 | First class brick works in cement mortar (1:4) in staining of wells with sand (minimum
13 | Supplying and fabrication of M.S High strength deformed bar/ Twisted bar reinforcement
14 | Minimum 12mm thick cement plaster (1:4) to dado and plinth wall up to 150mm below
15 | Supplying, fitting & fixing 2 nos signboard (1.5m x 0.9m) including writing the name &
16 | Earth filling work with specified soil in any type of embankment including cutting, carrying
17 | Construction, Installing and fixing in position including painting & writing with plastic/synthetic

## W-1
TIME SCHEDULE
Package No - CCRIP/KHUL/VR/2014/W-01
Sl. | Name of work | Days
No. |  | 12 | 24 | 36 | 48 | 60 | 72 | 84 | 96 | 108 | 120 | 132 | 144 | 156 | 168 | 180 | 192 | 204 | 216 | 228 | 240 | 252 | 264 | 276 | 288 | 300 | 312 | 324 | 336 | 348 | 365
1 | Clearing by removal and disposal at a safe distance of everything above ground level
2 | Earth work in box cutting on road crest up to 450mm depth with proper grade, camber and
3 | Providing and maintaining adequate portable water supply and sanitation facilities in labur
4 | Labour charge for picking up the existing brick on end edging (75mm across) including
5 | Sand (FM 0.50) filling on the road bed in the improved sub-grade with sand free from
6 | Providing compacted aggregate sand sub-base course with 38mm down Crusher run
7 | Brick on end edging (125mm across) with 1st class/picked bricks including cutting
8 | Prime coat with cut back bitumen to be prepared by cutting back 60/70 or 80/100
9 | 25mm thick compacted pre-mixed bituminous carpeting to be prepared using 16mm down
10 | 7mm thick compacted pre-mixed bituminous seal coat to be prepared using 6.33mm down
11 | Reinforced Cement Concrete work in bottom and top slab of box culvert of any height
12 | First class brick works in cement mortar (1:4) in staining of wells with sand (minimum
13 | Supplying and fabrication of M.S High strength deformed bar/ Twisted bar reinforcement
14 | Minimum 12mm thick cement plaster (1:4) to dado and plinth wall up to 150mm below
15 | Supplying, fitting & fixing 2 nos signboard (1.5m x 0.9m) including writing the name &
16 | Earth filling work with specified soil in any type of embankment including cutting, carrying
17 | Construction, Installing and fixing in position including painting & writing with plastic/synthetic