## Joypurhat
Contract Status of Rural Road Maintenance (GoB Maintenance), FY: 2018-2019
District : |  | Joypurhat | [14 empty] | Date of Reporting: | 2026-08-05
Sl. No. | Category of Maintenance | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Upazila: |  | 1. Joypurhat Sadar
1 | Re-Seal | 228525 W-01 | 1 | 138472003 | khajurtali RHD–Durgadaha GC Road | M/S Rasel Traders Gulshan Road,Joypurhat | 5350 | 6350 | 1000 | 1465042 | 1391789.9 | 1391678 | 2018-11-25 | 2019-01-24 | 4683% | 100% | - | Final bill paid |  | 60 | 2810
2 | Re-Seal | 228526 W-02 | 1 | 138472007 | Khutibari RHD-Salpara GC at Beltali Road | M/S A S Bricks Sardarpara, Joypurhat | 5150 | 7400 | 2250 | 2859715 | 2716729.25 | 2708632 | 2018-11-20 | 2019-01-19 | 4692% | 100% | - | Final bill paid |  | 60 | 2815
3 | Re-Seal | 228527 W-3 | 1 | 138474035 | BIDC-Madhaberghat Road | M/S Shikto Enterprise Sugarmill Road, Joypurhat | 1500 | 2000 | 500 | 497128 | 472271.6 | 472173 | 2018-11-30 | 2019-02-28 | 3117% | 100% | - | Final bill paid |  | 90 | 2805
4 | Re-Seal | 228528 W-04 | 1 | 138474046 | Amdai U.P Office-Sundarpur Road | M/S Parthona & Protoy Profesorpara,Joypurhat | 0 | 1157 | 1157 | 1455092 | 1382337.4 | 1379384 | 2018-12-02 | 2019-02-01 | 4595% | 100% | - | Final bill paid |  | 61 | 2803
5 | Over-Lay | 231534 W-22 | 1 | 138472001 | Mirgram RHD-Madhainagar GC Road | Mst.Moriom Bagum Adamdighi,Bogra | 0 | 1310 | 1310 | 7227412 | 6866041.4 |  | 2019-01-01 | 2019-03-15 | 3799% | 50% | Time Expired | on going |  | 73 | 2773
6 | Over-Lay | 231535 W-23 | 1 | 138472004 | Madhainagar GC-Puranapail RHD Road | M/S Classic Construction Rupnagar, Joypurhat | 8180 | 10080 | 1900 | 6009150 | 5708692.5 | 5701468 | 2018-12-01 | 2019-02-14 | 3739% | 100% | - | Final bill paid |  | 75 | 2804
7 | Over-Lay | 231536 W-24 | 1 | 138472005 | Mongalbari RHD-Salpara GC via Chalkbarkot Road | M/S Patwary Construction Sadar,Joypurhat | 7800 | 10350 | 2550 | 5520805 | 5244764.75 | 5243512 | 2018-12-03 | 2019-02-17 | 3687% | 100% | - | Final bill paid |  | 76 | 2802
8 | Over-Lay | 228486 W-36 | 1 | 138472005 | Mongalbari RHD-Salpara GC via Chalkbarkot Road | M/S Asmaul Husna Latifpur,Coloni,Bogra | 5500 | 7800 | 2300 | 4928586 | 4682156.7 | 4681186 | 2018-11-21 | 2019-01-20 | 4690% | 100% | - | Final bill paid |  | 60 | 2814
9 | Over-Lay | 231537 W-25 | 1 | 138472011 | Khanjanpur RHD-Rukindipur Gc via Nurpur Road | Md.Azizul Islam Sultanganjpara,Bogra. | 2500 | 5750 | 3250 | 5978619 | 5679688.05 |  | 2018-12-03 | 2019-02-17 | 3687% | 100% | - | Work Completed |  | 76 | 2802
10 | Over-Lay | 231528 W-16 | 1 | 138474019 | Tajpur-Tatoli Road | M/S Mayesha Enterprise Narayanpara,Joypurhat. | 0 | 1170 | 1170 | 2882625 | 2738493.75 | 2736390 | 2018-12-02 | 2019-02-01 | 4595% | 100% | - | Final bill paid |  | 61 | 2803
11 | Over-Lay | 231529 W-17 | 1 | 138474021 | Joypurhat (Pachurchalk)-Hanail Road | M/S Joy Traders Aramnagar,Joypurhat. | 0 | 1535 | 1535 | 2607972 | 2477573.4 | 2477278 | 2018-12-20 | 2019-02-19 | 4566% | 100% | - | Final bill paid |  | 61 | 2785
12 | Over-Lay | 231527 W-15 | 1 | 138474042 | Teghore-Pali Road | M/S Mimi Enterprise Santinagar,Joypurhat. | 0 | 209 | 209 | 596284 | 566469.8 | 566469 | 2018-12-02 | 2019-01-17 | 6093% | 100% | - | Final bill paid |  | 46 | 2803
13 | Over-Lay | 231526 W-14 | 1 | 138474048 | Teghore Charmatha-Shahapur Road | Md.Abdul Alim Taghore,Joypurhat. | 0 | 215 | 215 | 566746 | 538408.7 | 530985 | 2018-11-30 | 2019-01-29 | 4675% | 100% | - | Final bill paid |  | 60 | 2805
14 | CO Road | 170659 W-81 | 1 | 138474035 | BIDC-Madhaberghat Road | M/S Uzzal Traders Suzanagar,Pabna | 0 | 2250 | 2250 | 1076955 | 1076955 | 1076955 |  | 2018-06-17 | - | 100% | - | Final bill paid |  | 43268 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
14 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 21.596 | 43672131 | 41542372.2 | 28966110 | Fin. Pgr. (%) | 69.73% |  | 91.74%
Upazila: |  | 2. Akkelpur
1 | Re-Seal | 228483 W-34 | 1 | 138132009 | Jamalgonj Charmatha RHD-Rukindipur GC Road | M/S Sefali Traders Nutonhat,Joypurhat | 0 | 2220 | 2220 | 3375082 | 3206327.9 |  | 2018-12-03 | 2019-02-02 | 4593% | 100% | - | Work Completed |  | 61 | 2802
2 | Re-Seal | 228532 W-08 | 1 | 138133002 | Sonamukhi Hat-Gopinathpur UP Office via Bhanurkanda Road | M/S Hossain chaul Kall Santahar, Bogra | 0 | 1000 | 1000 | 954471 | 906747.45 | 906747 | 2018-11-27 | 2019-01-26 | 4680% | 100% | - | Final bill paid |  | 60 | 2808
3 | Re-Seal | 228530 W-06 | 1 | 138133012 | Gopinathpur UP office-Kashira Hat Road | M/S Reliance Builders Dhanmondi,Joypurhat | 0 | 1010 | 1010 | 1041194 | 989134.3 | 988004 | 2018-11-21 | 2019-01-20 | 4690% | 100% | - | Final bill paid |  | 60 | 2814
4 | Re-Seal | 228531 W-07 | 1 | 138133014 | Rukindipur UP office-Battali Hat Road | M/S Samiha Traders Adamdighi,Bogra | 0 | 1868 | 1868 | 2020824 | 1919782.8 | 1919166 | 2018-11-08 | 2019-01-19 | 3926% | 100% | - | Final bill paid |  | 72 | 2827
5 | Over-Lay | 228474 W-27 | 1 | 138132001 | Akkelpur-Tilakpur GC Road | M/S AkashTraders Kazipur,Sirajgoanj | 0 | 6000 | 6000 | 18610875 | 17680331.25 | 17569912 | 2018-12-25 | 2019-04-24 | 2317% | 100% | - | Work Completed |  | 120 | 2780
6 | Over-Lay | 228475 W-28 | 1 | 138132001 | Akkelpur-Tilakpur GC Road | Ram Babu Guduri Bazar,Thakurgaon. | 6000 | 12798 | 6798 | 20691136 | 17558034 | 17553924 | 2019-01-13 | 2019-05-12 | 2320% | 100% | - | Final bill paid |  | 119 | 2761
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
6 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 18.896 | 46693582 | 42260357.7 | 38937753 | Fin. Pgr. (%) | 92.14% |  | 100%
Upazila: |  | 3. Kalai
1 | Over-Lay | 228476 W-29 | 1 | 138582001 | Kalai-Molamgari GC Road | Ram Babu Guduri Bazar,Thakurgaon. | 2464 | 6750 | 4286 | 22983880 | 19652633 |  | 2019-01-17 | 2019-05-16 | 2317% | 50% | Time Expired | on going |  | 119 | 2757
2 | Over-Lay | 228477 W-30 | 1 | 138582002 | Molamgari GC-Dhap GC Road (Kalai portion) Road | Md.Abdul Momin Sonatola,Bogra. | 0 | 3150 | 3150 | 13370100 | 12701595 | 12700710 | 2018-12-20 | 2019-04-19 | 2321% | 100% | - | Final bill paid |  | 120 | 2785
3 | Structure Maintenance | 231530 W-18 | 1 | 138582009 | Kalai-Boiragipara Matrai GC Road | M/S Rawshanara Enterprise Panchbibi,Joypurhat. | 9450 | 9600 | 150 | 899940 | 854943 | 854835 | 2018-12-03 | 2019-01-18 | 6091% | 100% | - | Final bill paid |  | 46 | 2802
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
3 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 7.586 | 37253920 | 33209171 | 13555545 | Fin. Pgr. (%) | 40.82% |  | 70.41%
Upazila: |  | 4. Khetlal
1 | Re-Seal | 231533 W-21 | 1 | 138612003 | Itkhola GC-Jamalgonj RHD Road | M/S Konaok Traders & Polti Farm Kalai,Joypurhat. | 3600 | 8700 | 5100 | 8554981 | 8127231.95 | 8126794 | 2018-11-27 | 2019-03-04 | 2895% | 100% | - | Final bill paid |  | 97 | 2808
2 | Re-Seal | 228533 W-09 | 1 | 138612007 | Matirghor RHD-Hope Hat GC Road | M/S Shibam Enterprise Maroaripatti,Joypurhat. | 3080 | 4072 | 992 | 928062 | 881658.9 | 881367 | 2018-11-25 | 2019-01-24 | 4683% | 100% | - | Final bill paid |  | 60 | 2810
3 | Re-Seal | 228484 W-35 | 1 | 138612010 | Moushumi Bazar (RHD ) -Rukindipur GC Via Sannyash Ghat (Khetlal Portion ) Road | M/S Zaman Bricks Sadar Road,Joypurhat. | 0 | 6900 | 6900 | 3523492 | 3347317.4 | 3346850 | 2018-11-22 | 2019-01-21 | 4688% | 100% | - | Final bill paid |  | 60 | 2813
4 | Re-Seal | 228534 W-10 | 1 | 138613009 | Borail UP office-Chowmohoni Bazar Road | M/S Motahar Ali Khetlal,Joypurhat. | 1740 | 2480 | 740 | 548541 | 521113.95 | 520831 | 2018-12-09 | 2019-02-08 | 4584% | 100% | - | Final bill paid |  | 61 | 2796
5 | Re-Seal | 228535 W-11 | 1 | 138614007 | Dewgaon-Uddar pukur(Ashrayan Project) Road | M/S Baby Traders Puranapail,Joypurhat. | 0 | 500 | 500 | 403363 | 383194.85 | 342166 | 2018-11-27 | 2019-02-26 | 3086% | 100% | - | Final bill paid |  | 91 | 2808
6 | Re-Seal | 231524 W-12 | 1 | 138614018 | Kazipara-Borail U.P Office Road | M/S Sajan Kumar Jajodia Main Road,Joypurhat. | 0 | 935 | 935 | 1090068 | 1035564.6 | 1033883 | 2018-12-03 | 2019-02-02 | 4593% | 100% | - | Final bill paid |  | 61 | 2802
7 | Re-Seal | 231525 W-13 | 1 | 138614024 | Shakharanjo shahpara more-Basota more via Nashipur Hat Road | Kalicharan Agarwala Old hospital Road, Joypurhat. | 8466 | 9380 | 914 | 750566 | 713037.7 | 712307 | 2018-12-19 | 2019-02-18 | 4567% | 100% | - | Final bill paid |  | 61 | 2786
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
7 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 16.081 | 15799073 | 15009119.35 | 14964198 | Fin. Pgr. (%) | 99.7% |  | 100%
Upazila: |  | 5. Panchbibi
1 | Re-Seal | 228478 W-31 | 1 | 138742002 | Panchbibi GC-Salpara GC Road | M/S Shaumik Enterprise Joypurhat | 3200 | 5820 | 2620 | 3162362 | 3004243.9 | 2914090 | 2018-11-29 | 2019-01-28 | 4677% | 100% | - | Final bill paid |  | 60 | 2806
2 | Re-Seal | 231531 W-19 | 1 | 138742005 | Panchbibi GC(St.at Chotomanik)-Koria- Khangoir hat- Atapara RHD Road | M/S Chomok Enterprise Sardarpara,Joypurhat | 0 | 7765 | 7765 | 7844374 | 7452155.3 | 7450819 | 2018-11-28 | 2019-02-27 | 3085% | 100% | - | Final bill paid |  | 91 | 2807
3 | Re-Seal | 228482 W-33 | 1 | 138742013 | Chanpara RHD-Kamdia GC Road | M/S Sreete Construction Dupchancha,Bogra | 0 | 2460 | 2460 | 4940338 | 4693321.1 | 4692975 | 2018-12-29 | 2019-02-28 | 4551% | 100% | - | Final bill paid |  | 61 | 2776
4 | Re-Seal | 231532 W-20 | 1 | 138743002 | Balighata UP office-Jibonpur hat Road | M/S Milu Constraction Debipur,Joypurhat | 700 | 8250 | 7550 | 6754422 | 6416700.9 | 6416259 | 2018-12-03 | 2019-02-07 | 4245% | 100% | - | Final bill paid |  | 66 | 2802
5 | Re-Seal | 228480 W-32 | 1 | 138743004 | Bagzana Up office -Jibonpur-Mazhina hat Road | M/S Abdus Salam Panchbibi,Joypurhat | 1695 | 5030 | 3335 | 3072538 | 2918911.1 | 2918619 | 2018-11-19 | 2019-01-18 | 4693% | 100% | - | Final bill paid |  | 60 | 2816
6 | Re-Seal | 228529 W-05 | 1 | 138744020 | Boropukuria-Madainagar Road | M/S Defence Enterprise Aramnagar,Joypurhat, | 1700 | 2710 | 1010 | 830528 | 789001.6 | 788796 | 2018-11-27 | 2019-01-26 | 4680% | 100% | - | Final bill paid |  | 60 | 2808
7 | Over-Lay | 228473 W-26 | 1 | 138743001 | Aolai Up(Chatinali)-Peara-Kamdia GC Road | M/S Zahirul Islam Adomdighi,Bogra | 0 | 3985 | 3985 | 11516889 | 10941044.55 |  | 2018-12-26 | 2019-04-25 | 2316% | 40% | Time Expired | on going |  | 120 | 2779
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
7 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 28.725 | 38121451 | 36215378.45 | 25181558 | Fin. Pgr. (%) | 69.53% |  | 81.87%
District Office
1 | Off-Pavement | N/A | 5 |  | All Upazila |  |  |  | 0 | 6000000 | 6000000 | 3048850 | 2018-07-01 | 2019-06-30 | 812.4% | 77% | Time Expired |  |  | 364 | 2957
2 | On-Pavement | 222465 MS-03 | 1 | N/A | Supplying of Bitumen Emulsion Bitumen,Crushed Stone chips 20mm &12mm Down graded,1st class bricks,sand fm 2.5 & sand fm0.5 etc. | M/S Juthi Traders Bishnopur,Joypurhat |  |  | 0 | 1000000 | 959498.05 | 475000 | 2018-12-18 | 2019-02-17 | 4569% | 100% | - | Work Completed |  | 61 | 2787
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
2 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 0 | 7000000 | 6959498.05 | 3523850 | Fin. Pgr. (%) | 50.63% |  | 80.17%
37 | Grand Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 92.884 | 188540157 | 175195896.75 | 125129014 | Fin. Pgr. (%) | 71.42% |  | 87.9% |  |  |  | 28/2
Fund Received: | [15 empty] | Cash in Hand: | 44870986
Date: | 2018-09-13 |  | 2018-12-19 |  | 2019-01-23 | 2019-02-13 | 2019-03-11 |  |  | 2019-03-18 | [7 empty] | Total:
Tk. | 25000000 |  | 40000000 |  | 30000000 | 15000000 | 30000000 |  |  | 30000000 | [7 empty] | 170000000
Comments if any:
[12 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  | Amount Required upto June (Tk.) | Remarks
[12 empty] | - |  | - |  |  | 5195897
Re-Seal
Over-Lay
Structure Maintenance
Re-Hab. Road
Re-Hab. Structure
Widening Road
Widening Structure
EM Road
EM Structure
CO Road
CO Structure
Off-Pavement
On-Pavement
1. Joypurhat Sadar
2. Akkelpur
3. Kalai
4. Khetlal
5. Panchbibi