## Joypurhat
Contract Status of Flood & Disaster Damaged Rural Road Infrastructure Rehabilitation Project (FDDRIRP), FY: 2018-2019
District : |  | Joypurhat | [14 empty] | Date of Reporting: | 2019-07-12
Sl. No. | Name of Upazila | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Contract's Name | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
A. Rehabilitation Road [Strengthening/Widening]
1 | Joypurhat Sadar | W01 | 1 | 138473002 | Bambu UP office -Shuktahar Bazar Road via Dharki (L = 6.80 km ) | M/S Naumee Enterprise Sultanganj Para,Sadar,Bogura | 0 | 3000 | 3000 | 15413038 | 14642386.1 | 14641172 | 2018-06-28 | 2018-12-28 | 207.1% | 100% | - |  |  | 183 | 379
2 | Kalai | W02 | 1 | 138582009 | Kalai-Boiragipara-Matrai GC Road. | M/S Sourav Enterprise Sadar Road, Joypurhat. | 6565 | 9765 | 3200 | 21691509 | 20606933.55 | 20606291 | 2018-06-28 | 2018-12-28 | 207.1% | 100% | - |  |  | 183 | 379
3 | Panchbibi | W03 | 1 | 138742006 | Panchbibi GC-Kotoalibag--Ratonpur-Atapara RHD | M/S Kazol Enterprise Md.Imdadul Haque JV Akkelpur,Joypurhat. | 0 | 8705 | 8705 | 55002719 | 45149248.04 | 31250387 | 2019-02-19 | 2019-07-11 | 100.7% | 75% | Time Expired |  |  | 142 | 143
4 | Khetlal | W04 | 1 | 138613004 | Tulshigonga UP -Dhantola Bazar Road. | M/S Alef Enterprise Sultangoanjpara.Bogra. | 0 | 4200 | 4200 | 15705917 | 14920621.15 | 14690963 | 2019-01-23 | 2019-04-22 | 191% | 100% | - |  |  | 89 | 170
5 | Akkelpur | W05 | 1 | 138132010 | Akkelpur HQ -Rukindipur Pachmatha RHD via Battali hat | M/S. Rahman Traders, Bogura | 0 | 9076 | 9076 | 12714016 | 12078000 | 11811187 | 2019-04-01 | 2019-09-01 | 66.67% | 100% | - |  |  | 153 | 102
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
5 | Sub-Total (A): | 0 |  |  | Not Contacted Amount | 0 |  |  | 28.181 | 120527199 | 107397188.84 | 93000000 | Fin. Pgr. (%) | 86.59% |  | 89.49%
B. Rehabilitation Structure [Bridges/Culverts]
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
0 | Sub-Total (B): | 0 |  |  | Not Contacted Amount | 0 |  |  | 0 | 0 | 0 | 0 | Fin. Pgr. (%) | - |  | 0
5 | Grand Total: | 0 |  |  | Not Contacted Amount | 0 |  |  |  | 120527199 | 107397188.84 | 93000000 | Fin. Pgr. (%) | 86.59% |  | 89.49% |  |  |  | June
Fund Received: | [5 empty] | Structure | 0 | m | Road | 28.181 | km |  |  |  |  | Cash in Hand: |  | 0
Date: | [17 empty] | Total:
Tk. | 93000000 | [16 empty] | 93000000
Comments if any:
| Total No of Scheme Nos: 05(Five) Copleted Schee Nos: 04(Four) Progress of incompleted Schmes = 75% | [10 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  |  | Amount Required upto June'17 (Tk.)
[12 empty] | - |  | - |  |  |  | 0
Joypurhat Sadar
Akkelpur
Kalai
Khetlal
Panchbibi