## GPBRIDP
Greater Pabna-Bogra Rural Infrastructure Development Project (GPBRIDP)
Monthly Progress Report (Physical & Financial)
District: Joypurhat.
Reporting Date: 25-04-2019
Sl. No. | Constituency No. | Upazila | Package No. | Name of Scheme with location (Chainage)/ Road ID No. | Quantity |  |  | Estimated Cost (Tk.) |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk.) | Physical Progress (%) | Pland/Actual Date of Completion | Payment Status |  |  | Remarks
[5 empty] | Road (km) | Protec. (m) | Stru(m) | Road (Tk) | Str. (Tk) | Total (Tk) | [6 empty] | Final bill (Tk.) | Payment made (Tk.) | Remaining Payment (Tk.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Category -01
1 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-462 | Improvement of Dharanji UP Office-Khangoirhat Road ch.1400m-2352m,ID No:138743012. [Panchbibi] | 1 | 0 | 0 | 5286531 | 0 | 5286531 | 24/02/2016 | M/S Bahar Traders Panchbibi,Joypurhat. | 17/03/2016 | 5275521 | 100% | 14/02/2017 | 5275521 | 5275521 | 0 | Final
2 | Joypurhat-1 | Sadar | GPBRIDP/Rd-425 | Improvement of Joypurhat(Khanjanpur)-Rukindipur via Nurpur Road ch.5850m-7180m(ID No:138472011). [Sadar] | 1.33 | 0 | 0 | 7531153.03 | 0 | 7531153.03 | 23/02/2016 | M/S Zaman Bricks Sadar Road,Joypurhat. | 22/03/2016 | 7509662.498 | 100% | 18/11/2016 | 7508859 | 7508859 | 0 | Final
3 | Joypurhat-1 | Sadar | GPBRIDP/Mw-112 | Maintenance of Simulia road ch.00-1600m (ID No: 1384 75018) [Sadar] | 1.6 | 26 | 0 | 7135988 | 107773 | 7243761 | 2016-10-03 | M/S Didarul Haque & Sonce Jamalganj Bazar,Akkelpur, Joypurhat. | 25/04/2016 | 7236160.058 | 100% | 2016-08-12 | 6956646 | 6956646 | 0 | Final
4 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-460 | Improvement of Atapur UP Office(Uchai Bazar)-Feska hat Road ch.3000-4300m(ID No:138743010) [Panchbibi] | 1.3 | 0 | 0 | 6872490 | 0 | 6872490 | 24/02/2016 | M/S Liton Traders Sadar Road,Joypurhat. | 2016-03-04 | 6862370.45 | 100% | 2017-08-01 | 6861999 | 6861999 | 0 | Final
5 | Joypurhat-1 | Sadar | GPBRIDP/Rd-426 | Improvement of Dogachi UP Office-Jamtali via Dalaher Road ch.1314m-2314m ,(ID No:13847 3003). [Sadar] | 1 | 0 | 0 | 5816046.93 | 0 | 5816046.93 | 23/02/2016 | M/S Zahid Traders Dewanpara,Sadar,Joypurhat. | 28/03/2016 | 5812026.998 | 100% | 20/09/2016 | 5704159 | 5704159 | 0 | Final
6 | Joypurhat-1 | Sadar | GPBRIDP/Rd-423 | Improvement of Khejurtali-Durgadaha Road ch. 4320m -5320m (ID No: 138472003)[Sadar] | 1 | 0 | 0 | 6665047.48 | 0 | 6665047.48 | 23/02/2016 | M/S Jabbar Traders, Nischinta bazar, Kheetlal,Joypurhat. | 29/03/2016 | 5864561.478 | 100% | 2016-06-12 | 5864008 | 5864008 | 0 | Final
7 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-459 | Improvement of Bagzana-Jibonpur-Mazhinahat Road ch. 5150m-6150m,(ID No:138743004) [Panchbibi] | 1 | 0 | 0 | 5286531 | 0 | 5286531 | 23/02/2016 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/03/2016 | 5274362 | 100% | 2017-05-04 | 5274362 | 5274362 | 0 | Final
8 | Joypurhat-1 | Sadar | GPBRIDP/Rd-424 | Improvement of Puranapoil-R&H via Tajpur Road ch. 1600m-2600m,(ID No:138472008) [Sadar] | 1 | 0 | 0 | 5865631.7 | 0 | 5865631.7 | 23/02/2016 | M/S Khalequzzaman Traders Sadar Road,Joypurhat. | 24/03/2016 | 5856074.267 | 100% | 2016-09-10 | 5855090 | 5855090 | 0 | Final
9 | Joypurhat-1 | Sadar | GPBRIDP/Rd-430 | Improvement of Dogachi (Uttor Joypur)-Baguan road Ch 750-1250m (ID No:138475013) [Sadar] | 0.5 | 10 | 0 | 2647919 | 298947 | 2946866 | 2016-10-03 | M/S Zahid Traders Dewanpara,Sadar,Joypurhat. | 2016-08-05 | 2946366 | 100% | 30/05/2017 | 2939404 | 2939404 | 0 | Final
10 | Joypurhat-1 | Sadar | GPBRIDP/Rd-427 | Improvement of Chalkbarkat UP Office-Pagladawan Hat road ch.00-1480m (ID No:138473004) [Sadar] | 1.48 | 100 | 0 | 8109479 | 414513 | 8523992 | 2016-10-03 | M/S Azam Builders Bazar goli,Joypurhat sadar. | 20/04/2016 | 8515084.699 | 100% | 27/05/2017 | 8514827 | 8514827 | 0 | Final
11 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-461 | Improvement of Atapur UP Office-Mazhina Road ch. 1584m-2450m,(ID No: 138743011).[Panchbibi] | 1 | 0 | 0 | 5286531 | 0 | 5286531 | 24/02/2016 | M/S Rawshanara Enterprise Balighata,Panchbibi,Joypurhat. | 30/03/2016 | 5052589 | 100% | 27/10/2017 | 5052193 | 5052193 | 0 | Final
12 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-463 | Improvement of Nondail-Dharanji Road ch.00m-500m (ID No: 138744001).[Panchbibi] | 0.5 | 0 | 0 | 2660370.27 | 0 | 2660370.27 | 24/02/2016 | M/S Defence Enterprise Biswaspara,Joypurhat. | 2016-10-04 | 2659439.415 | 100% | 26/10/2017 | 2659315 | 2659315 | 0 | Final
13 | Joypurhat-1 | Sadar | GPBRIDP/Rd-431 | Improvement of Thiot-Nengapir road ch 00-500m (ID No:138474008) [Sadar] | 0.5 | 0 | 0 | 2504435 | 0 | 2504435 | 2016-05-04 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/05/2016 | 2496451.678 | 100% | 2017-12-11 | 2489181 | 2489181 | 0 | Final
14 | Joypurhat-1 | Sadar | GPBRIDP/Rd-432 | Improvement of Kadamtoli-Kallyanpur road ch 00-500m (ID No:138474001) [Sadar] | 0.5 | 0 | 0 | 3069843 | 0 | 3069843 | 2016-05-04 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/05/2016 | 3060010.254 | 100% | 2017-09-11 | 3057777 | 3057777 | 0 | Final
15 | Joypurhat-1 | Sadar | GPBRIDP/Rd-433 | Improvement of Shalpara-DharanjeeUP Office Via Koria road ch 1168-2168m (ID No:138474027) [Sadar] | 1 | 0 | 0 | 2728642 | 0 | 2728642 | 2016-05-04 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/05/2016 | 2720496.629 | 100% | 2017-07-11 | 2719365 | 2719365 | 0 | Final
16 | Joypurhat-1 | Sadar | GPBRIDP/Rd-434 | Improvement of Kadamtali more-Dargaghat-(Koria BOP) road ch 00-500m (ID No:138474071) [Sadar] | 0.5 | 0 | 0 | 2263540 | 0 | 2263540 | 2016-05-04 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/05/2016 | 2255538.252 | 100% | 2017-07-11 | 2255538 | 2255538 | 0 | Final
17 | Joypurhat-1 | Sadar | GPBRIDP/Rd-435 | Improvement of Dostopur more-Halloti Govt.Pry. School road ch 00-500m (ID No:138475033) [Sadar] | 0.5 | 0 | 0 | 2969027 | 0 | 2969027 | 2016-05-04 | M/S Haque Nirmata Sadar Road,Joypurhat. | 30/05/2016 | 2965135.108 | 100% | 2017-07-11 | 2927860 | 2927860 | 0 | Final
18 | Joypurhat-1 | Sadar | GPBRIDP/Rd-428 | Improvement of Durgadah-Pakarmatha via Moham mad UP road ch.4225-5395munder Sadar Upazila District Joypurhat. ID No 138473006 | 1.17 | 0 | 0 | 6255946 | 0 | 6255946 | 17/05/2017 | M/S Zahid Traders Dewanpara,Sadar,Joypurhat. | 2017-04-07 | 6253338.984 | 100% | 2018-09-02 | 6236232 | 6236232 | 0 | Final
19 | Joypurhat-1 | Sadar | GPBRIDP/Rd-503 | (a) Improvement of Uttar Joypur-Baguan Road , from ch. 1250-1550m,ID.138475013 (b) Improvement of Paschim Dogachi-Pakurtoli Road, from ch. 00-700m, ID No:13847 5013(Salvage Value:BDT.413644.00) under Upazila: sadar, District:Joypurhat. | 1 | 0 | 0 | 5269924 | 0 | 5269924 | 2017-08-11 | M/S Mahadi Construction Main Road,C.O.Colony, Joypurhat. | 28/12/17 | 5192643.174 | 100% | 2018-11-04 | 5109080 | 5109080 | 0 | Final
20 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-514 | mprovement of Atapur UP Office(Uchai Bazar)-Faska Hat road at (ch.4355-5250m)ID No:13874 3010 under Panchbibi Upazila District: Joypurhat | 0.895 | 0 | 0 | 5680532 | 0 | 5680532 | 19/12/2017 | M/S Kazol Enterprise Akkelpur, Joypurhat. | 30/01/2018 | 5632006.476 | 100% | 2018-05-06 | 5626367 | 5626367 | 0 | Final
21 | Joypurhat-1 | Sadar | GPBRIDP/Rd-504 | Improvement of Salpara GC-Dharanji UP Office via Koria Hat Road from ch.1700-2800m (ID No:1384730 08) under Upazila:Joypurhat sadar, District: Joypurhat | 1.1 | 0 | 0 | 6352331 | 0 | 6352331 | 2017-08-11 | M/S Liton Traders Sadar Road,Joypurhat. | 28/12/17 | 6010180.11 | 100% | 2018-11-06 | 6009372 | 6009372 | 0 | Final
22 | Joypurhat-1 | Sadar | GPBRIDP/Rd-489 | Improvement of Kadamtali-Dargahat road at ch500-1000m ID No.138474071 ID NO.138474071.under Joypurhat Sadar Upazila District Joypurhat. | 0.5 | 0 | 0 | 2212797 | 0 | 2212797 | 20/06/2017 | M/S Defence Enterprise Aramnagar, Sadar, Joypurhat. | 25/07/2017 | 2169881.627 | 100% | 13/06/2018 | 2166881 | 2166881 | 0 | Final
23 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-464 | Improvement of Aymarasulpur-Shimultali road ch.1162-1662m under Panchbibi Upazila District Joypurhat. ID No 138744004 | 0.5 | 0 | 0 | 2645020 | 0 | 2645020 | 17/05/2017 | M/S Rahman Traders Jhowtola, Bogra. | 21/06/2017 | 2578669.55 | 100% | 14/06/2018 | 2578669 | 2578669 | 0 | Final
24 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-465 | Improvement of Shimultali-Birnagar via Kashpur road ch.520-1020m Salvage Value Tk. 81779.00 under Panchbibi Upazila DistrictJoypurhat IDNo. 138744007 | 0.5 | 0 | 0 | 2639579 | 0 | 2639579 | 17/05/2017 | M/S Rahman Traders Jhowtola, Bogra. | 21/06/2017 | 2573455.633 | 100% | 18/06/2018 | 2571523 | 2571523 | 0 | Final
25 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-467 | Improvement of Golakata-Angra road Ch.1500-2000m under Panchbibi Upazila DistrictJoypurhat. ID No 13874 4013 | 0.5 | 0 | 0 | 2638567 | 0 | 2638567 | 17/05/2017 | M/S Rahman Traders Jhowtola, Bogra. | 21/06/2017 | 2598538.158 | 100% | 18/06/2018 | 2597309 | 2597309 | 0 | Final
26 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-487, 488 | a. Improvement of Dargahat-Kadamtali road at ch00-525m ID NO 138744059. b.Improvement of Karia-Lakma road at ch1000-1200m ID NO 138745038. under Panchbibi Upazila District Joypurhat. | 0.725 | 0 | 0 | 3899061 | 0 | 3899061 | 20/06/2017 | M/S Rahman Traders Jhowtola, Bogra. | 23/07/2017 | 3842653.521 | 100% | 18/06/2018 | 3841806 | 3841806 | 0 | Final
27 | Joypurhat-1 | Sadar | GPBRIDP/Rd-501 | Improvement of Helkunda-Halatti Road from ch. 00m-1745m. ID No:138475037 under upazila : Sadar , District: Joypurhat | 1.745 | 0 | 0 | 8909851 | 0 | 8909851 | 2017-08-11 | M/S Progoti Nirman East Janier Bagan,Joypurhat. | 28/12/17 | 8881237.396 | 100% | 18/06/2018 | 8839223 | 8839223 | 0 | Final
28 | Joypurhat-1 | Sadar | GPBRIDP/Rd-502 | Improvement of Chaksyme-Uttar Joypur Road from ch. 00m-1000m,ID No:138474016 (Salvage value: BDT. 673232.00) under Upazila: sadar, District: Joypurhat | 1 | 0 | 0 | 6082643 | 0 | 6082643 | 2017-08-11 | M/S Azam Builders Bazar goli,Joypurhat sadar. | 28/12/17 | 5776023.584 | 100% | 18/06/2018 | 5770758 | 5770758 | 0 | Final
29 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-513 | Improvement of Nandael-Dharabge road at (ch.500-1355m) ID No:138744001 under Panchbibi Upazila District: Joypurhat | 0.855 | 0 | 0 | 5073031 | 0 | 5073031 | 19/12/2017 | M/S Kazol Enterprise Akkelpur, Joypurhat. | 30/01/2018 | 5017719.989 | 100% | 30/09/2018 | 5015785 | 5015785 | 0 | Final
30 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-466 | A.Improvement of Sikta-Sonapur road Ch.00-500m. ID No.138744004 under Panchbibi Upazila District Joypur hat. B.Improvement of BairaKhidirpur-Dugurpara road Ch.950-1450m.ID No.138744042 under Panchbibi Upazila District:Joypurhat. | 1 | 0 | 0 | 5743046 | 0 | 5743046 | 20/06/2017 | M/S Rahman Traders Jhowtola, Bogra. | 23/07/2017 | 5607632.913 | 100% | 13/09/2018 | 5607497 | 5607497 | 0 | Final
Category -02
31 | Joypurhat-1 | Panchbibi | GPBRIDP/Rd-505 | Improvement of Dharanjee UP Office-Salpara GC Via koria hat Road from ch.00-2000m (ID No: 138743013) Under Upazila: Panchbibi, District: Joypurhat. | 2 | 0 | 0 | 12740881 | 0 | 12740881 | 2017-08-11 | M/S Sukra Enterprise Chakshutrapur,Badurtola, Bogra. | 28/12/17 | 12740963.744 | 100% | 30/06/2019 | 12739398 | 11828350 | 912613.744 | Work Completed
Category -03
Category -04
|  |  |  | Constituency wise sub TotalJoypurhat-1: | 29.2 | 136 | 0 | 158842414.41 | 821233 | 159663647.41 |  |  |  | 157236794.643 | 100 |  | 156626004 | 155714956 | 912613.744
Category -01
32 | Joypurhat-2 | Kalai | GPBRIDP/Mw-115 | Maintenance of Kalai- Boiragipara -Matrai road ch.3300-5000m (ID No:138582011) [Kalai] | 1.7 | 0 | 0 | 2253453 | 0 | 2253453 | 2016-10-03 | M/S Masfa Enterprise 1 No.Rail Gate,Bogra. | 27/04/2016 | 1845581.61 | 100% | 2016-10-06 | 1845325 | 1845325 | 0 | Final
33 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-469 | Improvement of Sonamukhi Hat-Gopinathpur UP Office via Vnurkanda Road ch.2482m-3500m (ID No: 1381330 02) [Akkelpur] | 1.018 | 0 | 0 | 5290798.8 | 0 | 5290798.8 | 24/02/2016 | M/S Rina Enterprise Akkelpur, Joypurhat. | 22/03/2016 | 5198212.763 | 100% | 2016-02-12 | 5198212 | 5198212 | 0 | Final
34 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-473 | Improvement of Gopinathpur UP Office-Kuranu Hat Via Madertali Ghat Road ch.4500m-5500m (IDNo:1381 330 09)[Akkelpur] | 1 | 0 | 0 | 5994365.18 | 0 | 5994365.18 | 25/02/2016 | M/S Rina Enterprise Akkelpur, Joypurhat. | 22/03/2016 | 5992764.807 | 100% | 17/12/2016 | 5992440 | 5992440 | 0 | Final
35 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-480 | Improvement of Rukindipur UP Office-Bottolihat Road ch.1860m-2860m,(ID No:138133014). [Akkelpur] | 1 | 0 | 0 | 6118528.73 | 0 | 6118528.73 | 2016-08-03 | M/S Kazol Enterprise Akkelpur, Joypurhat. | 26/04/2016 | 6107282.463 | 100% | 2016-02-11 | 6105782 | 6105782 | 0 | Final
36 | Joypurhat-2 | Khetlal | GPBRIDP/Mw-114 | Maintenance of Benai Milghar-fashitola Via Benai Govt. Primary School road ch.00-1300m (ID No: 1386 14011) Khetlal] | 1.3 | 0 | 0 | 2303141 | 0 | 2303141 | 2016-10-03 | Kalicharan Agarwala Old Hospital Road,Joypurhat. | 21/04/2016 | 2295290.815 | 100% | 24/12/2016 | 2295002 | 2295002 | 0 | Final
37 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-439 | Improvement of Monjharhat-Dhantola Mamudpur UP Office Road ch.00m-1700m,(IDNo:138613004) [Khetlal] | 1.7 | 0 | 0 | 9239655.9 | 0 | 9239655.9 | 2016-03-05 | Zia International Enterprise Arafat Nagar,Joypurhat. | 29/06/2016 | 9197446.85 | 100% | 2017-11-05 | 9197446 | 9197446 | 0 | Final
38 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-436 | Improvement of Matigar-hope Hat road ch.946-2966m (ID No:138612007) [Khetlal] | 2 | 20 | 0 | 13302086 | 383284 | 13685370 | 2016-10-03 | M/S Progoti Nirman East Janier Bagan,Joypurhat. | 27/04/2016 | 14129716 | 100% | 2017-01-05 | 14100074 | 14100074 | 0 | Final
39 | Joypurhat-2 | Kalai | GPBRIDP/Rd-448 | Improvement of Molamgari-Atmul-Shibgonj Road ch. 2351m-2562m,2799m-2830m & 3092m-3230m,(ID No: 138582011).[Kalai] | 0.38 | 0 | 0 | 2881727.45 | 0 | 2881727.45 | 2016-09-03 | M/S Rubina Construction Kalai, Joypurhat. | 27/04/2016 | 2874444.885 | 100% | 2017-08-10 | 2796015 | 2796015 | 0 | Final
40 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-478 | Improvement of Gopinathpur UP Office(Karitoli)-Raikali UP Office Road ch.1525m-2525m(ID No: 1381 33010) [Akkelpur] | 1 | 0 | 0 | 5477159.49 | 0 | 5477159.49 | 2016-08-03 | Kalicharan Agarwala Old Hospital Road,Joypurhat. | 27/04/2016 | 5465147.079 | 100% | 30/10/2017 | 5398276 | 5398276 | 0 | Final
41 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-470 | Improvement of Tilokpur UP Office-Sujaldighi Hat Via Marma Road ch.2270m-3270m (ID No: 138133004) . [Akkelpur] | 1 | 0 | 0 | 5401013.85 | 0 | 5401013.85 | 2016-05-04 | M/S Kazol Enterprise Akkelpur, Joypurhat. | 25/05/2016 | 5349273.858 | 100% | 23/12/2017 | 5349089 | 5349089 | 0 | Final
42 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-438 | Improvement of MamudpuUP Office-Sannastola Ghat road ch.5000-6000m (ID No:138613006) [Khetlal] | 1 | 0 | 0 | 5286531 | 0 | 5286531 | 2016-10-03 | M/S Kazol Enterprise Akkelpur, Joypurhat. | 26/04/2016 | 5279229 | 100% | 13/10/2017 | 5279229 | 5279229 | 0 | Final
43 | Joypurhat-2 | Kalai | GPBRIDP/ Rd-452 | Improvement of Moslemgonj-Panitola Road ch.1960m-3360m(ID No:138583002).[Kalai] | 1.4 | 0 | 0 | 8254149.37 | 0 | 8254149.37 | 2016-09-03 | M/S Zia Enterprise BattaliBazar,Khetlal,Joypurhat. | 27/04/2016 | 8253821.445 | 100% | 26/12/2017 | 8178127 | 8178127 | 0 | Final
44 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-471 | Improvement of Mohonpur Hat-Sonamukhi UP Via Koya Village Road ch.1655m-2655m IDNo:13813 3007 [Akkelpur] | 1 | 0 | 0 | 5537752.75 | 0 | 5537752.75 | 25/02/2016 | M/S Mondal Traders Chalkbaria,Naogoan. | 30/03/2016 | 5537474.426 | 100% | 25/02/2018 | 5536646 | 5536646 | 0 | Final
45 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-476 | Improvement of Sonamukhi UP Office (Simultali More)-Raikali UP Office (Munjia)Road ch.3450m-4550m,(ID No:138133005).[Akkelpur] | 1.1 | 0 | 0 | 5815184.1 | 0 | 5815184.1 | 2016-08-03 | M/S Mondal Traders Chalkbaria,Naogoan. | 2016-05-05 | 5815047.15 | 100% | 15/03/2018 | 5804474 | 5804474 | 0 | Final
46 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-472 | Improvement of Raikali UP Office-Horisadi Hat Via Pun duria Road 1920m-2990m(ID No:138133008) Akkelpur. | 1.07 | 0 | 0 | 6010755.54 | 0 | 6010755.54 | 2016-03-05 | M/S Rina Enterprise Akkelpur, Joypurhat. | 28/06/2016 | 6312284.234 | 100% | 2018-04-04 | 6310791 | 6310791 | 0 | Final
47 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-483 | Improvement of Raikali-Debishawal road with link Road ch.1215m-1715m,(ID No:138134009). [Akkelpur] | 0.5 | 0 | 0 | 2747796.6 | 0 | 2747796.6 | 17/08/2016 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 2016-06-10 | 2666790 | 100% | 28/02/2018 | 2666730 | 2666730 | 0 | Final
48 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-474 | Improvement of Tilokpur UP-Chatiangram Ht Road ( Akkelpur Portion)ch.2370m-2746m(ID No: 138133011) Akkelpur. | 0.376 | 0 | 0 | 2070502.63 | 0 | 2070502.63 | 26/05/2016 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 28/06/2016 | 2053529.124 | 100% | 26/02/2018 | 2052519 | 2052519 | 0 | Final
49 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-440 | Improvement of Moushumi Bazar RHD-Gopinath pur GC via Samantahar-Barail GPS road Khetlal part Ch.2475-3100m Salvage Value Tk.63903.ID No.1386 12009 Old ID No.138613007.under Khetlal Upazila ,District-Joypurhat. | 0.625 | 0 | 0 | 3550524 | 0 | 3550524 | 20/06/2017 | M/S Sukra Enterprise Chalk Sutrapur,Badurtola,Bogra. | 14/07/2017 | 3720508.989 | 100% | 30/05/2018 | 3720103 | 3720103 | 0 | Final
50 | Joypurhat-2 | Kalai | GPBRIDP/Rd-455 | Improvement of Silimpur-Binsara roadCh. 1800-2300m under Kalai Upazila DistrictJoypurhat.ID No 138474008 | 0.5 | 0 | 0 | 3165628 | 0 | 3165628 | 17/05/2017 | M/S Nazrul Islam Kalai,Joypurhat. | 2017-05-07 | 3267506.982 | 100% | 2018-10-04 | 3267138 | 3267138 | 0 | Final
51 | Joypurhat-2 | Kalai | GPBRIDP/Rd-451 | Improvement of Kalai Chinema hall-Gongadashpur Road ch.3320m-4320m,(ID No:138583001).[Kalai] | 1 | 0 | 0 | 6415445.82 | 0 | 6415445.82 | 2016-09-03 | M/S Rubina Construction Kalai, Joypurhat. | 24/04/2016 | 6403737.791 | 100% | 2018-02-05 | 6403737 | 6403737 | 0 | Final
52 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-475 | Improvement of Vikoni Hat -Sonamukhi UP Office Road ch.575m-1735m,(ID No:138133013) [Akkelpur] | 1.16 | 0 | 0 | 6262062.96 | 0 | 6262062.96 | 2016-08-03 | M/S Rina Enterprise Akkelpur, Joypurhat. | 24/04/2016 | 6399323.739 | 100% | 26/04/2018 | 6397998 | 6397998 | 0 | Final
53 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-509 | Improvement of Karimpur-Damghor-Noshipur Road Jamghor-Nashipur Road from ch.836-1336m,ID No:13868 615074 Under Upazila: Khetlal, District: Joypurhat | 0.5 | 0 | 0 | 3017201 | 0 | 3017201 | 2017-08-11 | M/S Progoti Nirman Moon Super Market, Sadar, Joypurhat. | 2018-12-02 | 3046581.145 | 100% | 14/06/2018 | 3046199 | 3046199 | 0 | Final
54 | Joypurhat-2 | Kalai | GPBRIDP/Rd-457 | Improvement of Bafalgari-Shikta-Dingapara road ch.2026-2526m Salvage Value Tk.732141under Kalai Upazila District Joypurhat.ID No.138474005 | 0.5 | 0 | 0 | 3154766 | 0 | 3154766 | 17/05/2017 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 21/06/2017 | 2975912.172 | 100% | 2018-05-06 | 2975903 | 2975903 | 0 | Final
55 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-446 | Improvement of Dakhin Hatshaher-Mainam Bandighi road ch.590-1090m ID No.138614013 under Khetlal Upazila, District-Joypurhat. | 0.5 | 0 | 0 | 2668923 | 0 | 2668923 | 20/06/2017 | M/S Defence Enterprise Aramnagar, Sadar, Joypurhat. | 25/07/2017 | 2605057.817 | 100% | 30/08/2018 | 2605057 | 2605057 | 0 | Final
56 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-447 | Improvement of JamgghoKarimpur Bazarr-Nasirpur road Ch.336-836m.ID No.138615014 under Khetlal Upazila District-Joypurhat. | 0.5 | 0 | 0 | 2732227 | 0 | 2732227 | 20/06/2017 | M/S Defence Enterprise Aramnagar, Sadar, Joypurhat. | 25/07/2017 | 2666884.094 | 100% | 30/08/2018 | 2664382 | 2664382 | 0 | Final
57 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-529 | Improvement of Akkelpur College hat-Kesobpur Embank ment Road (ch.188-585m) (Road ID: 138134022) under Upazila : Akkelpur District : Joypurhat. | 0.397 | 0 | 0 | 2073243 | 0 | 2073243 | 16/04/2018 | Md. Mostafizur Rahman Paksi Ishordi,Pabna. | 20/05/2018 | 1969580.85 | 100% | 13/08/2018 | 1969580 | 1969580 | 0 | Final
58 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-481 | Improvement of Tilakpur karamje Noagar Road ch500-1030m Salvage ValueTk. 140149 under Akkelpur Upazila DistrictJoypurhat.ID No 138134006 | 0.53 | 0 | 0 | 2934100 | 0 | 2934100 | 17/05/2017 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 21/06/2017 | 2843292.972 | 100% | 27/06/2018 | 2843292 | 2843292 | 0.972 | Final
59 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-482 | Improvement of Kathalbari-Halholia road Ch.500-745 & 2025-2280m under Akkelpur Upazila District Joypurhat. ID No 138134012 | 0.5 | 0 | 0 | 2643266 | 0 | 2643266 | 17/05/2017 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 21/06/2017 | 2548773.25 | 100% | 27/06/2018 | 2548773 | 2548773 | 0.25 | Final
60 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-486 | Improvement of Akkelpur- Tilokpur Upazila road to Kadoa Kholagari road ch.700-1192m Salvage Value Tk.33963 under Akkelpur Upazila District Joypurhat. ID No 138134021 | 0.492 | 0 | 0 | 2663447 | 0 | 2663447 | 17/05/2017 | M/S Alaya Construction Sultangoanjpara,Goalgary, Bogra | 21/06/2017 | 2538303.274 | 100% | 27/06/2018 | 2479168 | 2479168 | 59135.274 | Final
61 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-506 | Improvement of Tilokpur-Baragram Upazila Road Road to Bamnigram Village Road from ch.00-820m ID No:1381350 26(Salvage Value:BDT.697334.00) Under Upazila: Akkelpur, District:Joypurhat | 0.82 | 0 | 0 | 6805457 | 0 | 6805457 | 2017-08-11 | M/S Sukra Enterprise Chalk Sutrapur,Badurtola,Bogra. | 28/12/17 | 6405460.934 | 100% | 2018-10-11 | 6316057 | 6316057 | 89403.934 | Final
62 | Joypurhat-2 | Kalai | GPBRIDP/Rd-458 | Improvement of Itail-Panchgram road ch.00-764m under Kalai Upazila DistrictJoypurhat.ID No 138474006 | 0.764 | 0 | 0 | 4132565 | 0 | 4132565 | 17/05/2017 | M/S Nazrul Islam Kalai,Joypurhat. | 21/06/2017 | 4289094.998 | 100% | 2018-05-11 | 4289094 | 4289094 | 0.998 | Final
63 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-441 | Improvement of Shakaranja Shapmara More Basota more via Nashinpur hat road Ch.3970-4970m ID No.13 86140 24. under Khetlal Upazila District Joypurhat | 1 | 0 | 0 | 5381331 | 0 | 5381331 | 20/06/2017 | M/S Sukra Enterprise Chalk Sutrapur, Badurtola,Bogra. | 14/07/2017 | 5639474.35 | 100% | 25/11/2018 | 5639220 | 5639220 | 254.35 | Final
64 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-507 | Improvement of Sreerampur Bridge (Gonipur) Holholia Railway Bridge Road from ch.00-1000m (ID No.1381350 97) Under Upazila: Akkelpur, District: Joypurhat. | 1 | 0 | 0 | 5684054 | 0 | 5684054 | 2017-08-11 | M/S Mondal Traders Chalkbaria,Naogoan. | 28/12/17 | 5620000.718 | 100% | 29/11/2018 | 5619999 | 5619999 | 1.718 | Final
65 | Joypurhat-2 | Kalai | GPBRIDP/Rd-450 | Improvement of Moslemgonj(st.Mandai)-Chottro gram Road ch.950m -2450m, (ID No:13858 3005).[Kalai] | 1.5 | 0 | 0 | 8720666.26 | 0 | 8720666.26 | 2016-09-03 | M/S Nazrul Islam Kalai,Joypurhat. | 27/04/2016 | 9156056.567 | 100% | 30/06/2018 | 9155897 | 9155897 | 159.567 | Final
66 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-479 | Improvement of Gopinathpur UP Office-Kashira Hat Road ch.1010m-2010m(ID No:138133012). [Akkelpur] | 1 | 0 | 0 | 5769107.85 | 0 | 5769107.85 | 2016-08-03 | M/S Mondal Traders Chalkbaria,Naogoan. | 2016-05-05 | 5775067.334 | 100% | 30/12/2018 | 5774393 | 5774393 | 674.334 | Final
67 | Joypurhat-2 | Kalai | GPBRIDP/Rd-508 | Improvement of Katahar-Hatior road from ch.3282-4282m ID No:138584010Under Upazila: Kalai , District: Joypurhat | 1 | 0 | 0 | 6177096 | 0 | 6177096 | 2017-08-11 | Md.Munjurul Alam Mohon Chalk Sutrapur,Bogra. | 18/02/2018 | 5989900.161 | 100% | 24/02/2019 | 5937424 | 5937424 | 52476.161 | Final
68 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-515 | Improvement of Kanupur GPS (Porbari Kanupur Kanda) (ch.00m-845m) ID NO: 138135085 .Salvage value: BDT. 712913.00 under,Akkelpur,Upazila, District:Joypurhat. | 0.845 | 0 | 0 | 6160686 | 0 | 6160686 | 19/12/2017 | M/S Mondal Traders Chalkbaria,Naogoan. | 2018-06-02 | 5841316.051 | 100% | 2019-05-02 | 5551920 | 5551920 | 289396.051 | Final As per work done
Category -02
69 | Joypurhat-2 | Kalai | GPBRIDP/Rd-449 | Improvement of Matrai-Beala-Aligram-Kamdia Road ch. 3340m-4480m, (ID No:138583004). [Kalai] | 1.04 | 0 | 0 | 6827009.15 | 0 | 6827009.15 | 2016-09-03 | M/S Nazrul Islam Kalai,Joypurhat. | 24/04/2016 | 7169515.203 | 100% | 30/06/2018 |  | 6815231 | 354284.203 | Work Completed
70 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-442 | Improvement of Borotara Up Office-UttarhatShahor-Gorshal Road Ch. 1500- 2000m ID No 138613008 under Khetlal Upazila DistrictJoypurhat. | 0.5 | 0 | 0 | 2866649 | 0 | 2866649 | 20/06/2017 | M/S Defence Enterprise Aramnagar, Sadar, Joypurhat. | 25/07/2017 | 2830564.319 | 100% | 30/08/2018 |  | 2778574 | 51990.319 | Work Completed
71 | Joypurhat-2 | Akkelpur | GPBRIDP/BRG-33 | Construction of 69m Long Bridge at ch.100m on Lengapir Mazar (Sonamukhi Ghat)-Rajkanda Mallapara Road, ID No. 138135032 (Akkelpur). | 0 | 0 | 69 | 0 | 32386846 | 32386846 | 25.10.2016 | M/S Mondal Traders Chalkbaria,Naogoan. | 28/11/2016 | 25793873.49 | 100% | 30/12/2018 |  | 22304534 | 3489339.49 | Work Completed Variation
Category -03
72 | Joypurhat-2 | Khetlal | GPBRIDP/Rd-510 | Improvement of Shakharanjo Shahpara more to Basotamore via Nashipur hat Road from ch.2113-2766m and ch.4970-5317m ID No:138614024 Under Upazila: Khetlal,District: Joypurhat | 1 | 0 | 0 | 6008722 | 0 | 6008722 | 2017-08-11 | Md.Munjurul Alam Mohon Chalk Sutrapur,Bogra. | 18/02/2018 | 5827807.053 | 70% | 30/04/2019 |  | 4078769 | 1749038.053 | Time Extention Approved by Xen.
73 | Joypurhat-2 | Akkelpur | GPBRIDP/Rd-530 | (Part-A).Improvement of Kalanja-Ambari road Ch.00-1300m.(Salvage Value: BDT.1692260.00) (Road ID: 13813 4008),(Part-B).03 Nos U-Drain (625mmx600mm) on the same road at ch. 6m,205m & 603m,Road ID: 138134008(Part-C).Improvement of Kalanja Commu nity Clinic- house of Mizanur Rahman road ch.00-560m(Salvage Value:BDT. 66183.00) Road ID:1381350 45,(Part-D).01 No U-drain (625mmx600mm) on the same road at ch.90m Road ID: 138135045 under Akkelpur Upazila, District: Joypurhat | 1.86 | 0 | 0 | 10812287 | 0 | 10812287 | 16/04/2018 | Multifarious Engineers Jolesharitola,Bogra | 30/05/2018 | 10271672.65 | 40% | 2019-05-06 |  | 0 | 10271672.65
74 | Joypurhat-2 | Akkelpur | GPBRIDP/BRG-32 | Construction of 42.00 m long RCC girder bridge on Rukindi pur UP office Battala hat road at Ch. 5190 m (Road ID: 138133014 ) Under Upazila: Akkelpur District: Joypurhat | 0 | 0 | 42 | 0 | 20369242 | 20369242 | 16/04/2018 | M/S Binoy Chandra Akkelpur,Joypurhat. | 15/05/2018 | 19443020.08 | 80% | 21/05/2019 |  | 14217585 | 5225435.08
Category -04
|  |  |  | Constituency wise sub Total Joypurhat-2: | 38.077 | 20 | 111 | 210611065.43 | 53139372 | 263750437.43 |  |  |  | 255411623.492 | 97.4419 |  | 183311511 | 233506204 | 21633263.404
|  |  |  | Constituency wise Grand Total (Joypurhat-1+2) : | 67.277 | 156 | 111 | 369453479.84 | 53960605 | 423414084.84 |  |  |  | 412648418.135 | 98.7209 |  | 339937515 | 389221160 | 22545877.148
Summary
| Constituency | Category-1 | Category-2 | Category-3 | Category-4 | Total
| Joypurhat-1 | 30 | 0 | 1 | 0 | 31
| Joypurhat-2 | 37 | 3 | 3 | 0 | 43
| Total | 67 | 3 | 4 | 0 | 74
|  |  |  | Accountant |  |  |  | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  |  | Executive Engineer
|  |  |  | LGED, Joypurhat. |  |  |  | LGED, Joypurhat. |  |  |  | LGED, Joypurhat. |  |  |  |  | LGED, Joypurhat.