## Information
Project Full Name: Important Rural Infrastructure Development Project on Priority Basis.
Project Short Name: IRIDP (If Exist)
Upazila Name: Kamrangirchar
Sl. No. | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | IRIDP/Dhk/W-91 | Improvement of Charwashpur-Poultry Firm via H/O Chehlal by B.C road (Ch. 00-1000m) under Kamrangirchar Thana, District-Dhaka (Estimate No. 210/10-11) ID No. 326734183 | 1 | 4553874 | M/S. Aman Traders | 4553874 | 2011-09-11 | 2011-12-16 | 35
2 | IRIDP/Dhk/W-45 | Improvement of Shyampur Rail line to Culvert Shahid Muktijodda Moktar Hossain road Ch. 00-1032m by RCC i/c Side Drain under Kodomtoli Thana, District-Dhaka. Ch. 0450-1032m (Estimate No. 40/10-11) | 1.03 | 7392114 | M/S. Mollika Son's Engineers | 7392114 | 2010-12-20 | 2011-04-26 | 75
3 | IRIDP/Dhk/W-46 | Improvement of Shekh Rasel road to Mohammadbag Chowrasta Ch. 00-400m by RCC i/c Side Drain under Kodomtoli Thana, District-Dhaka. (Estimate No. 41/10-11) | 0.4 | 3066648 | M/S. Rocky Enterprise | 3051315 | 2010-11-28 | 2011-03-04 | 35 |  | 1133000
4 | IRIDP/Dhk/W-44 | Improvement of Paterbagh Donia road to Donia B.M College & Madrasha road by RCC (Ch.00-320m) under Kodomtoli Thana, District-Dhaka. | 0.32 | 2163391 | [7 empty] | Dropped MP-4
5 | IRIDP/Dhk/W-87 | Improvement of Shampur Rail Line to Culvert Shahid Moktijodda Moktar Hossain road (Ch. 00-450m) by RCC i/c drain under Kadamtoly Thana, District-Dhaka. ID No. 326734369 | 0.45 | 5075718 | M/S. Mollika Son's Engineers | 5075741 | 2011-07-20 | 2011-11-26 | 0 |  | 700000
Project Full Name: Improvement of Approach Roads for Bridge/Culverts Project.
Project Short Name: IARP (If Exist)
Upazila Name: Nawabgonj
6 | IARP/DHK-05/09-10 | a) Repair of footbridge on Charigram GC (Singair) via Chandrakhola Balukhanda road under Nawabgonj Upazila, District:Dhaka. (ch. 2200) b) Repair of footbridge on Charigram GC (Singair) via Chandrakhola Balukhanda road under Nawabgonj Upazila, District:Dhaka | 2.2 | 1468085 | M/S Talukdar Enterprise | 1251215 | 2010-01-04 | 2010-05-20 | 21 |  | 262000
7 | IARP/DHK-10 | Construction of 4x4.40x5.00m RCC Box Culvert on Komorgonj GC-Paragram GC via Koilail UP road at (Ch. 4200m & 5000m) under Nawabgonj Upazila, District-Dhaka. (Estimate No. 32/11-12) | 5 | 6534037 | M/S S M Bhuiya International | 6207335 | 2012-02-19 | 2012-06-25 | 25
8 | IARP/DHK-11 | Construction of 4x4.50x5.00m RCC Box Culvert on Patiljhap-Abdani road over Sholanagor Khal at (Ch. 480m) under Nawabgonj Upazila, District-Dhaka. (Estimate No. 33/11-12) | 0.48 | 3165562 | M/S Chanchal Enterprise | 3007283 | 2012-03-07 | 2012-06-13 | 0

## Instruction
Sl No | Instruction
1 | Please Mention the Project Full Name as Provided By LGED
2 | Please Mention the Project Short Name as Provided By LGED (If Exist)
3 | All Data should be in English (No Bangla Data will allow)
4 | Project Full Name, Upazila Name and Package No Must contain Data
5 | Font Name: Arial; Font Size: 12.