## Scheme Format
Project Full Name: Important Rural Infrastructure Development Project on Priority Basis.
Project Short Name: IRIDP (If Exist)
Project Code: 41
Upazila Name: Keraniganj
Upazila Code: 178
Sl. No. | Package No | Name | Road ID | Start Chainage | End Chainage | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | IRIDP/Dhk/W-91 | Improvement of Charwashpur-Poultry Firm via H/O Chehlal by B.C road (Ch. 00-1000m) under Kamrangirchar Thana, District-Dhaka (Estimate No. 210/10-11) ID No. 326734183 |  |  |  | 4553874 | M/S. Aman Traders | 4553874 | 2011-09-11 | 2011-12-16 | 35
2 | IRIDP/Dhk/W-45 | Improvement of Shyampur Rail line to Culvert Shahid Muktijodda Moktar Hossain road Ch. 00-1032m by RCC i/c Side Drain under Kodomtoli Thana, District-Dhaka. Ch. 0450-1032m (Estimate No. 40/10-11) |  |  |  | 7392114 | M/S. Mollika Son's Engineers | 7392114 | 2010-12-20 | 2011-04-26 | 75
3 | IRIDP/Dhk/W-46 | Improvement of Shekh Rasel road to Mohammadbag Chowrasta Ch. 00-400m by RCC i/c Side Drain under Kodomtoli Thana, District-Dhaka. (Estimate No. 41/10-11) |  |  |  | 3066648 | M/S. Rocky Enterprise | 3051315 | 2010-11-28 | 2011-03-04 | 35 |  | 1133000
4 | IRIDP/Dhk/W-44 | Improvement of Paterbagh Donia road to Donia B.M College & Madrasha road by RCC (Ch.00-320m) under Kodomtoli Thana, District-Dhaka. |  |  |  | 2163391 | [7 empty] | Dropped MP-4
5 | IRIDP/Dhk/W-87 | Improvement of Shampur Rail Line to Culvert Shahid Moktijodda Moktar Hossain road (Ch. 00-450m) by RCC i/c drain under Kadamtoly Thana, District-Dhaka. ID No. 326734369 |  |  |  | 5075718 | M/S. Mollika Son's Engineers | 5075741 | 2011-07-20 | 2011-11-26 | 0 |  | 700000
Project Full Name: Improvement of Approach Roads for Bridge/Culverts Project.
Project Short Name: IARP (If Exist)
Project Code : 38
Upazila Name: Nawabgonj
Upazila Code : 177
6 | IARP/DHK-05/09-10 | a) Repair of footbridge on Charigram GC (Singair) via Chandrakhola Balukhanda road under Nawabgonj Upazila, District:Dhaka. (ch. 2200) b) Repair of footbridge on Charigram GC (Singair) via Chandrakhola Balukhanda road under Nawabgonj Upazila, District:Dhaka |  |  |  | 1468085 | M/S Talukdar Enterprise | 1251215 | 2010-01-04 | 2010-05-20 | 21 |  | 262000
7 | IARP/DHK-10 | Construction of 4x4.40x5.00m RCC Box Culvert on Komorgonj GC-Paragram GC via Koilail UP road at (Ch. 4200m & 5000m) under Nawabgonj Upazila, District-Dhaka. (Estimate No. 32/11-12) |  |  |  | 6534037 | M/S S M Bhuiya International | 6207335 | 2012-02-19 | 2012-06-25 | 25
8 | IARP/DHK-11 | Construction of 4x4.50x5.00m RCC Box Culvert on Patiljhap-Abdani road over Sholanagor Khal at (Ch. 480m) under Nawabgonj Upazila, District-Dhaka. (Estimate No. 33/11-12) |  |  |  | 3165562 | M/S Chanchal Enterprise | 3007283 | 2012-03-07 | 2012-06-13 | 0

## Instruction
Sl No | Instruction
1 | Please Mention the Project Full Name as Provided By LGED
2 | Please Mention the Project Short Name as Provided By LGED (If Exist)
3 | All Data should be in English (No Bangla Data will allow)
4 | Project Full Name, Upazila Name, Upazila Code and Package No. Must contain Data
5 | Font Name: Arial; Font Size: 12.
6 | Upazila Code will get from Upazila List Sheet in this document
7 | For Updating data (Those who gave data before), don't change the Package No field Data
Click on Project to get Project code
Will Get Project Details with project code on address bar (Image show in Red marking)

## Upazila List
Upazila Code | Upazila Name | District Code | District Name
1 | galachipa | 1 | patuakhali
19 | bauphal | 1 | patuakhali
12 | kalapara | 1 | patuakhali
13 | mirjaganj | 1 | patuakhali
14 | patuakhali-s | 1 | patuakhali
15 | dumki | 1 | patuakhali
10 | dashmina | 1 | patuakhali
484 | Rangabali | 1 | patuakhali
16 | amtali | 2 | barguna
17 | bamna | 2 | barguna
18 | barguna-s | 2 | barguna
2 | betagi | 2 | barguna
40 | patharghata | 2 | barguna
9 | perojpur-s | 3 | perojpur
3 | zianagar | 3 | perojpur
11 | nazirpur | 3 | perojpur
28 | nesarabad | 3 | perojpur
35 | bhandaria | 3 | perojpur
36 | kawkhali | 3 | perojpur
37 | mothbaria | 3 | perojpur
30 | daulatkhan | 4 | bhola
4 | bhola-s | 4 | bhola
5 | charfassion | 4 | bhola
6 | lalmohan | 4 | bhola
7 | monpura | 4 | bhola
8 | tazumuddin | 4 | bhola
39 | borhanuddin | 4 | bhola
20 | banaripara | 5 | barisal
21 | agailjhara | 5 | barisal
22 | gouranadi | 5 | barisal
23 | hizla | 5 | barisal
24 | mehendiganj | 5 | barisal
25 | muladi | 5 | barisal
26 | babuganj | 5 | barisal
27 | bakerganj | 5 | barisal
38 | barisal-s | 5 | barisal
29 | uzirpur | 5 | barisal
31 | jhalokathi-s | 6 | jhalokathi
32 | kathalia | 6 | jhalokathi
33 | nalchity | 6 | jhalokathi
34 | rajapur | 6 | jhalokathi
48 | kabir hat | 7 | noakhali
50 | sonaimuri | 7 | noakhali
51 | noakhali-s | 7 | noakhali
41 | subarna char | 7 | noakhali
85 | chatkhil | 7 | noakhali
86 | begumganj | 7 | noakhali
87 | companiganj | 7 | noakhali
88 | hatiya | 7 | noakhali
89 | senbag | 7 | noakhali
63 | feni-s | 8 | feni
42 | daganbhuiyan | 8 | feni
43 | chhagalniya | 8 | feni
49 | sonagazi | 8 | feni
65 | porshuram | 8 | feni
71 | fulgazi | 8 | feni
55 | laxmipur-s | 9 | laxmipur
44 | komol nagar | 9 | laxmipur
45 | ramgati | 9 | laxmipur
46 | ramganj | 9 | laxmipur
47 | raipur | 9 | laxmipur
52 | chandina | 10 | comilla
53 | daudkandi | 10 | comilla
54 | debidwar | 10 | comilla
72 | barura | 10 | comilla
81 | homna | 10 | comilla
91 | monohorganj | 10 | comilla
92 | brahmanpara | 10 | comilla
93 | burichong | 10 | comilla
94 | chouddagram | 10 | comilla
95 | comilla-s | 10 | comilla
96 | laksham | 10 | comilla
97 | nangalkot | 10 | comilla
101 | comilla-s daksin | 10 | comilla
107 | muradnagar | 10 | comilla
108 | meghna | 10 | comilla
99 | titas | 10 | comilla
64 | sitakunda | 11 | chittagong
73 | anwara | 11 | chittagong
66 | raojan | 11 | chittagong
67 | rangunia | 11 | chittagong
68 | mirsharai | 11 | chittagong
69 | hathazari | 11 | chittagong
70 | fatikchari | 11 | chittagong
56 | sandwip | 11 | chittagong
57 | lohagara | 11 | chittagong
58 | satkania | 11 | chittagong
59 | patiya | 11 | chittagong
60 | chandanish | 11 | chittagong
61 | boalkhali | 11 | chittagong
62 | banskhali | 11 | chittagong
74 | shahrasti | 12 | chandpur
82 | matlab (uttar) | 12 | chandpur
77 | chandpur-s | 12 | chandpur
78 | faridganj | 12 | chandpur
79 | haimchar | 12 | chandpur
80 | haziganj | 12 | chandpur
90 | kachua | 12 | chandpur
84 | matlab (dakshin) | 12 | chandpur
100 | cox's bazar-s | 13 | cox's bazar
125 | pekua | 13 | cox's bazar
126 | moheskhali | 13 | cox's bazar
129 | ramu | 13 | cox's bazar
130 | ukhiya | 13 | cox's bazar
135 | teknaf | 13 | cox's bazar
123 | chakoria | 13 | cox's bazar
75 | kutubdia | 13 | cox's bazar
76 | ashuganj | 14 | b.baria
102 | akhaura | 14 | b.baria
103 | bancharampur | 14 | b.baria
104 | b.baria-s | 14 | b.baria
105 | kasba | 14 | b.baria
106 | nabinagar | 14 | b.baria
83 | nasirnagar | 14 | b.baria
98 | sarail | 14 | b.baria
487 | BijoyNagar | 14 | b.baria
109 | bandarban-s | 15 | bandarban
127 | ruma | 15 | bandarban
118 | rowangchari | 15 | bandarban
119 | thanchi | 15 | bandarban
120 | lama | 15 | bandarban
121 | naikhyongchari | 15 | bandarban
122 | alikadam | 15 | bandarban
116 | manikchari | 16 | khagrachari
117 | laxmichari | 16 | khagrachari
124 | matiranga | 16 | khagrachari
110 | khagrachari-s | 16 | khagrachari
111 | mahalchari | 16 | khagrachari
112 | dighinala | 16 | khagrachari
113 | panchari | 16 | khagrachari
114 | ramgarh | 16 | khagrachari
115 | rajosthali | 17 | rangamati
136 | juraichari | 17 | rangamati
137 | langadu | 17 | rangamati
138 | barkal | 17 | rangamati
139 | kaukhali | 17 | rangamati
128 | belaichari | 17 | rangamati
131 | rangamati-s | 17 | rangamati
132 | baghaichari | 17 | rangamati
133 | kaptai | 17 | rangamati
134 | nanniarchar | 17 | rangamati
140 | ghatail | 18 | tangail
156 | dhanbari | 18 | tangail
142 | shakhipur | 18 | tangail
143 | mirzapur | 18 | tangail
144 | tangail-s | 18 | tangail
145 | madhupur | 18 | tangail
146 | kalihati | 18 | tangail
147 | gopalpur | 18 | tangail
148 | nagarpur | 18 | tangail
149 | bhuapur | 18 | tangail
150 | basail | 18 | tangail
239 | delduar | 18 | tangail
210 | itna | 19 | kishoreganj
201 | hossainpur | 19 | kishoreganj
165 | karimganj | 19 | kishoreganj
158 | nikli | 19 | kishoreganj
195 | austagram | 19 | kishoreganj
196 | bajitpur | 19 | kishoreganj
197 | bhairab | 19 | kishoreganj
151 | mithamoin | 19 | kishoreganj
152 | tarail | 19 | kishoreganj
153 | pakundia | 19 | kishoreganj
154 | kuliarchar | 19 | kishoreganj
155 | katiadi | 19 | kishoreganj
141 | kishoreganj-s | 19 | kishoreganj
157 | araihazar | 20 | narayanganj
198 | narayanganj-s | 20 | narayanganj
160 | rupganj | 20 | narayanganj
161 | bandar | 20 | narayanganj
162 | sonargaon | 20 | narayanganj
171 | kapasia | 21 | gazipur
172 | kaliganj | 21 | gazipur
173 | kaliakoir | 21 | gazipur
174 | gazipur-s | 21 | gazipur
159 | sreepur | 21 | gazipur
181 | haluaghat | 22 | mymensingh
182 | muktagacha | 22 | mymensingh
183 | trishal | 22 | mymensingh
184 | dhobaura | 22 | mymensingh
190 | fulbaria | 22 | mymensingh
163 | nandail | 22 | mymensingh
188 | gaffargaon | 22 | mymensingh
208 | mymensingh-s | 22 | mymensingh
216 | phulpur | 22 | mymensingh
217 | gouripur | 22 | mymensingh
218 | bhaluka | 22 | mymensingh
214 | ishwarganj | 22 | mymensingh
164 | shibpur | 23 | narshingdi
166 | palash | 23 | narshingdi
167 | narshingdi-s | 23 | narshingdi
168 | raipura | 23 | narshingdi
169 | belabo | 23 | narshingdi
179 | monohardi | 23 | narshingdi
170 | dohar | 24 | dhaka
175 | tejgaon circle | 24 | dhaka
176 | savar | 24 | dhaka
177 | nawabganj | 24 | dhaka
178 | keraniganj | 24 | dhaka
215 | dhamrai | 24 | dhaka
189 | kalmakanda | 25 | netrokona
180 | kendua | 25 | netrokona
185 | atpara | 25 | netrokona
186 | barhatta | 25 | netrokona
187 | durgapur | 25 | netrokona
191 | madan | 25 | netrokona
192 | mohanganj | 25 | netrokona
193 | netrakona-s | 25 | netrokona
194 | purbadhala | 25 | netrokona
199 | khaliajuri | 25 | netrokona
200 | nakla | 26 | sherpur
209 | jhenaigati | 26 | sherpur
211 | nalitabari | 26 | sherpur
212 | sherpur-s | 26 | sherpur
213 | sreebordi | 26 | sherpur
202 | dewanganj | 27 | jamalpur
203 | islampur | 27 | jamalpur
204 | jamalpur-s | 27 | jamalpur
205 | madarganj | 27 | jamalpur
206 | melendah | 27 | jamalpur
207 | sarishabari | 27 | jamalpur
219 | bakshiganj | 27 | jamalpur
220 | muksudpur | 28 | gopalganj
230 | kotwalipara | 28 | gopalganj
241 | gopalganj-s | 28 | gopalganj
232 | tungipara | 28 | gopalganj
245 | kasiani | 28 | gopalganj
221 | baliakandi | 29 | rajbari
222 | goalanda | 29 | rajbari
223 | pangsha | 29 | rajbari
224 | rajbari-s | 29 | rajbari
225 | kalukhali | 29 | rajbari
226 | kalkini | 30 | madaripur
227 | madaripur-s | 30 | madaripur
228 | rajoir | 30 | madaripur
231 | shibchar | 30 | madaripur
229 | saltha | 31 | faridpur
253 | nagarkanda | 31 | faridpur
254 | alfadanga | 31 | faridpur
255 | bhanga | 31 | faridpur
256 | boalmari | 31 | faridpur
257 | charbhadrasan | 31 | faridpur
258 | faridpur-s | 31 | faridpur
261 | sadarpur | 31 | faridpur
262 | madhukhali | 31 | faridpur
233 | bhedarganj | 32 | shariatpur
234 | damuddya | 32 | shariatpur
235 | goshairhat | 32 | shariatpur
236 | naria | 32 | shariatpur
237 | shariatpur-s | 32 | shariatpur
238 | janjira | 32 | shariatpur
240 | gazaria | 33 | munshiganj
246 | sreenagar | 33 | munshiganj
247 | tongibari | 33 | munshiganj
243 | lauhajong | 33 | munshiganj
244 | munshiganj-s | 33 | munshiganj
250 | sirajdikhan | 33 | munshiganj
251 | saturia | 34 | manikganj
252 | shivalaya | 34 | manikganj
248 | daulatpur | 34 | manikganj
249 | harirampur | 34 | manikganj
259 | singair | 34 | manikganj
260 | ghior | 34 | manikganj
242 | manikganj-s | 34 | manikganj
263 | dacope | 35 | khulna
264 | batiaghata | 35 | khulna
274 | dumuria | 35 | khulna
275 | koira | 35 | khulna
276 | paikgacha | 35 | khulna
277 | phultala | 35 | khulna
278 | terokhada | 35 | khulna
279 | rupsa | 35 | khulna
270 | dighalia | 35 | khulna
283 | moheshpur | 36 | jhenaidah
299 | kotchandpur | 36 | jhenaidah
265 | shailkupa | 36 | jhenaidah
307 | harinakunda | 36 | jhenaidah
308 | jhenaidah-s | 36 | jhenaidah
309 | kaliganj | 36 | jhenaidah
266 | narail-s | 37 | narail
267 | lohagara | 37 | narail
268 | kalia | 37 | narail
269 | salikha | 38 | magura
271 | magura-s | 38 | magura
272 | mohammadpur | 38 | magura
273 | sreepur | 38 | magura
285 | kaliganj | 39 | satkhira
286 | debhata | 39 | satkhira
292 | shyamnagar | 39 | satkhira
312 | tala | 39 | satkhira
280 | assasuni | 39 | satkhira
281 | kalaroa | 39 | satkhira
282 | satkhira-s | 39 | satkhira
293 | mirpur | 40 | kushtia
291 | kumarkhali | 40 | kushtia
288 | bheramara | 40 | kushtia
289 | daulatpur | 40 | kushtia
284 | khoksha | 40 | kushtia
297 | kushtia-s | 40 | kushtia
287 | abhoynagar | 41 | jessore
300 | bagherpara | 41 | jessore
301 | chowgacha | 41 | jessore
302 | jhikargacha | 41 | jessore
303 | keshabpur | 41 | jessore
304 | jessore-s | 41 | jessore
305 | monirampur | 41 | jessore
306 | sarsha | 41 | jessore
290 | damurhuda | 42 | chuadanga
294 | chuadanga-s | 42 | chuadanga
295 | jibannagar | 42 | chuadanga
311 | alamdanga | 42 | chuadanga
298 | mujib nagar | 43 | meherpur
310 | meherpur-s | 43 | meherpur
296 | gangni | 43 | meherpur
313 | mongla | 44 | bagerhat
314 | chitalmari | 44 | bagerhat
315 | sharankhola | 44 | bagerhat
316 | rampal | 44 | bagerhat
317 | mollahat | 44 | bagerhat
318 | kachua | 44 | bagerhat
319 | fakirhat | 44 | bagerhat
320 | bagerhat-s | 44 | bagerhat
321 | morrelganj | 44 | bagerhat
322 | mohadevpur | 45 | naogaon
332 | niamatpur | 45 | naogaon
324 | shapahar | 45 | naogaon
325 | raninagar | 45 | naogaon
326 | porsha | 45 | naogaon
327 | patnitala | 45 | naogaon
328 | dhamoirhat | 45 | naogaon
329 | naogaon-s | 45 | naogaon
336 | atrai | 45 | naogaon
367 | manda | 45 | naogaon
376 | badalgachi | 45 | naogaon
345 | singra | 46 | natore
330 | baraigram | 46 | natore
333 | gurudaspur | 46 | natore
334 | lalpur | 46 | natore
335 | natore-s | 46 | natore
323 | bagatipara | 46 | natore
331 | gomostapur | 47 | c. nawabganj
337 | bholahat | 47 | c. nawabganj
339 | nachol | 47 | c. nawabganj
340 | nawabganj-s | 47 | c. nawabganj
341 | shibganj | 47 | c. nawabganj
338 | godagari | 48 | rajshahi
368 | mohanpur | 48 | rajshahi
370 | puthia | 48 | rajshahi
371 | tanore | 48 | rajshahi
360 | bagha | 48 | rajshahi
358 | paba | 48 | rajshahi
364 | bagmara | 48 | rajshahi
365 | charghat | 48 | rajshahi
366 | durgapur | 48 | rajshahi
369 | faridpur | 49 | pabna
374 | ishwardi | 49 | pabna
383 | bhangura | 49 | pabna
384 | sujanagar | 49 | pabna
385 | santhia | 49 | pabna
387 | pabna-s | 49 | pabna
342 | atghoria | 49 | pabna
343 | bera | 49 | pabna
344 | chatmohar | 49 | pabna
346 | joypurhat-s | 50 | joypurhat
359 | akkelpur | 50 | joypurhat
361 | khetlal | 50 | joypurhat
362 | panchbibi | 50 | joypurhat
363 | kalai | 50 | joypurhat
372 | shajahanpur | 51 | bogra
347 | adamdighi | 51 | bogra
348 | bogra-s | 51 | bogra
349 | dhunot | 51 | bogra
350 | dhupchancia | 51 | bogra
351 | gabtali | 51 | bogra
352 | kahaloo | 51 | bogra
353 | nandigram | 51 | bogra
354 | sariakandi | 51 | bogra
355 | sherpur | 51 | bogra
356 | shibganj | 51 | bogra
357 | sonatala | 51 | bogra
373 | tarash | 52 | serajganj
375 | ullapara | 52 | serajganj
386 | kamarkhand | 52 | serajganj
377 | serajganj-s | 52 | serajganj
378 | shahzadpur | 52 | serajganj
379 | raiganj | 52 | serajganj
380 | kazipur | 52 | serajganj
381 | chowhali | 52 | serajganj
382 | belkuchi | 52 | serajganj
388 | pirgacha | 53 | rangpur
394 | rangpur-s | 53 | rangpur
395 | pirganj | 53 | rangpur
396 | mithapukur | 53 | rangpur
403 | kaunia | 53 | rangpur
424 | gangachara | 53 | rangpur
398 | taraganj | 53 | rangpur
434 | badarganj | 53 | rangpur
389 | patgram | 54 | lalmonirhat
390 | lalmonirhat-s | 54 | lalmonirhat
391 | kaliganj | 54 | lalmonirhat
392 | hatibandha | 54 | lalmonirhat
393 | aditmari | 54 | lalmonirhat
397 | dimla | 55 | nilphamari
399 | domar | 55 | nilphamari
400 | jaldhaka | 55 | nilphamari
401 | kishoreganj | 55 | nilphamari
402 | nilphamari-s | 55 | nilphamari
410 | sayedpur | 55 | nilphamari
406 | rajibpur | 56 | kurigram
407 | chilmari | 56 | kurigram
408 | fulbari | 56 | kurigram
409 | kurigram-s | 56 | kurigram
404 | bhurungamari | 56 | kurigram
430 | nageswari | 56 | kurigram
437 | rowmari | 56 | kurigram
444 | rajarhat | 56 | kurigram
445 | ulipur | 56 | kurigram
405 | thakurgaon-s | 57 | thakurgaon
425 | haripur | 57 | thakurgaon
426 | pirganj | 57 | thakurgaon
427 | ranisankail | 57 | thakurgaon
411 | baliadangi | 57 | thakurgaon
412 | birol | 58 | dinajpur
413 | bochaganj | 58 | dinajpur
414 | chirirbandar | 58 | dinajpur
415 | fulbari | 58 | dinajpur
416 | ghoraghat | 58 | dinajpur
417 | hakimpur | 58 | dinajpur
418 | kaharol | 58 | dinajpur
419 | khanshama | 58 | dinajpur
420 | dinajpur-s | 58 | dinajpur
421 | nawabganj | 58 | dinajpur
423 | birampur | 58 | dinajpur
435 | parbatipur | 58 | dinajpur
436 | birganj | 58 | dinajpur
431 | debiganj | 59 | panchagarh
432 | panchagarh-s | 59 | panchagarh
433 | tetulia | 59 | panchagarh
422 | boda | 59 | panchagarh
429 | atwari | 59 | panchagarh
438 | palashbari | 60 | gaibandha
439 | sundarganj | 60 | gaibandha
440 | sadullapur | 60 | gaibandha
441 | gobindaganj | 60 | gaibandha
442 | gaibandha-s | 60 | gaibandha
443 | fulchari | 60 | gaibandha
428 | saghata | 60 | gaibandha
454 | jointiapur | 61 | sylhet
455 | gowainghat | 61 | sylhet
459 | biswanath | 61 | sylhet
460 | beanibazar | 61 | sylhet
461 | balaganj | 61 | sylhet
446 | companiganj | 61 | sylhet
447 | kanaighat | 61 | sylhet
450 | dakshin surma | 61 | sylhet
451 | zakiganj | 61 | sylhet
452 | sylhet-s | 61 | sylhet
463 | golapganj | 61 | sylhet
457 | fenchuganj | 61 | sylhet
474 | sreemangal | 62 | moulvibazar
453 | moulvibazar-s | 62 | moulvibazar
448 | kulaura | 62 | moulvibazar
449 | kamalganj | 62 | moulvibazar
456 | rajnagar | 62 | moulvibazar
481 | juri | 62 | moulvibazar
482 | barlekha | 62 | moulvibazar
475 | nabiganj | 63 | habiganj
476 | madhabpur | 63 | habiganj
477 | lakhai | 63 | habiganj
478 | habiganj-s | 63 | habiganj
479 | chunarughat | 63 | habiganj
480 | bahubal | 63 | habiganj
458 | baniachong | 63 | habiganj
472 | azmiriganj | 63 | habiganj
473 | chatak | 64 | sunamganj
464 | biswamvarpur | 64 | sunamganj
465 | tahirpur | 64 | sunamganj
466 | sunamganj-s | 64 | sunamganj
467 | sulla | 64 | sunamganj
468 | jamalganj | 64 | sunamganj
469 | jagannathpur | 64 | sunamganj
470 | doarabazar | 64 | sunamganj
471 | dharmapasha | 64 | sunamganj
462 | dakhin sunamganj | 64 | sunamganj
483 | derai | 64 | sunamganj