## Lists (hidden)
RoadType | PavementType
UZR | BC
UNR | CC
VR-A | RCC
VR-B

## SchemeList
Serial | District Name | District Code/ID | Upazila Name | Upazila Code/ID | Project ID | Package No | Scheme Name | Road ID | Length of Scheme(Km) - Road | Length of Scheme(m) - Bridge/Culverts | Building Quantity | Estimated Amount(LAC) | Contractor Name | Contract Amount(LAC) | Date of Contract (DD/MM/YYYY) | Date of commencement (DD/MM/YYYY) | Date of Completion (DD/MM/YYYY) | Physical Progress(%) | Financial Progress (Amount) (LAC) | Financial Progress(%) | Date of Progress Update (DD/MM/YYYY) | Remarks
1 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/GAI-S/UNR/ 18-19/W-06 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | 132243029 | 3.654 | 6 |  | 304.3582 | M/S Basundhara, Kurigram | 304.3 | 2019-05-05 | 2019-05-11 | 2020-04-21 | 60 | 102.98 | 33.8416 | 2020-07-31
2 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/SAD/UNR/ 20-21/W-136 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | 132243029 | 0.43 |  |  | 42.3891 | [5 empty] | 0 |  | 0 | 2020-07-31 | Estimate Approved on 13-8-20
3 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-09 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure under khorda Rasulpur-Chandiapur Road at Ch.710.0m. Under Shdullapur, District Gaibandha. | 132823001 | 2 | 6.2 |  | 186.3288 | Md.Khademul Islam Jewel, Gaibandha | 186.1307 | 2019-05-05 | 2019-05-11 | 2020-03-17 | 75 | 125.875 | 67.6272 | 2020-07-31 | XEN Issued letter to Contractor regarding Time Extension.
4 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-10 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.2000m-4000m. including 6Nos (0.625x0.600) m U-Drain on Khorda Rasulpur-Chandiapur Road at Ch: 2920m,2953m,3089m,3393m, 3582m & 3743m and 1x2.00mx2.00 m RCC Box Culvert at Ch: 2645m under khorda Rasulpur-Chandiapur Road under Shdullapur, District Gaibandha. | 132823001 |  |  |  | 175.2451 |  | 175.1996 |  |  |  | 0 | 142.975 | 0 | 2020-07-31 | package holded
5 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-12 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | 132823002 | 2 | 0.6 |  | 87.7973 | M/S SAJIN TRADERS JV | 83.4074 | 2019-05-08 | 2019-05-14 | 2020-03-21 | 100 | 79.1856 | 81.6069 | 2020-07-31 | Work Completed
6 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAG/UNR/20-21/W-135 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure and Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | 132823017 | 1 | 3.6 |  | 267.7326 | Md. Mahomudun Nobi, Pirganj, Rangpur |  | 2019-04-07 | 2019-04-13 | 2020-03-08 | 100 |  | 94.9383 | 2020-07-31 | Final Bill Paid
7 | Gaibandha | 60 | Saghata | 428 | 826 | PRO/GAI/SAD/UNR/19-20/W- 71 | Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha. | 132883015 | 2.86 |  |  | 191.6517 |  | 162.9039 |  |  |  | 0 |  | 0 | 2020-07-31 | Estimate Approved on 13-8-20
8 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/19-20/W- 68 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | 132823004 | 2 | 14.3 |  | 97.5263 |  | 81.2647 | 2020-05-18 | 2020-05-28 | 2021-05-28 | 20 | 13.168 | 0 | 2020-07-31
9 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/19-20/W- 72 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | 132823009 | 1 | 1 |  | 110.4923 | Md.Shoeb Hossain Mona, Gaibandha | 90.9552 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 20 | 9.7658 | 16.2038 | 2020-07-31
10 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/GAI-S/VR/18-19/W-07 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | 132823015 | 1 | 5.3 |  | 230.3237 | Md.Shoeb Hossain Mona, Gaibandha | 230.2791 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 20 | 127.3 | 10.7369 | 2020-07-31