## লালমনিরহাট 24-12-2020
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 24/12/2020 | jvjgwbinvU nvwZevÜv | Name of Work : mprovement of Pathonbari Utar Parulia Kadors House Road Ch.00-1600 Road ID-152335026 | • ISG • Sub-base • WBM | ISG = 200mm AS = 150mm WBM = 150mm Proportion = 50:50 | mo‡Ki WBM Gi KvR mgvß †`Lv hvq¦ 2wU ¯’v‡b ( †PB‡bR: 500wg. I 600wg.) Sub grade ch©šÍ layer mg~n cixÿv Kiv nq¦ ISG, Base Course Gi thickness h_vµ‡g 200,215wg.wg. AS Gi thickness h_vµ‡g 152,150wg.wg.Ges WBM h_vµ‡g 155, 160 wg.wg. cvIqv hvq¦ WBM Ges AS layer -G DCP Test K‡i CBR cvIqv †Mj h_vµ‡g WBM Gi CBR b~b¨Zg 80% Gi ¯’‡j 36.6% Ges AS layer -Gi b~b¨Zg CBR 30% Gi ¯’‡j 31.9% cvIqv hvq¦ | • m¤ú~Y© WBM loose KiZ: over size Khoa †f‡½ Specifioation Abyhvqx size K‡i Compaction I CBR wbwðZ Kivi Rb¨ wb‡`©k cÖ`vb Kiv n‡q‡Q¦ Ges ÎæwU ms‡kvab bv nIqv ch©šÍ wej cÖ`v‡b wb‡la Kiv n‡q‡Q¦ • wbe©vnx cÖ‡KŠkjx‡K G msµvšÍ cÎ cÖ`vb Kiv n‡q‡Q¦
Completion Date : 10.12.2020
Physical Progress : 70 %
Name of Project : RDRIIP-2

## কুড়িগ্রাম 24-12-2020 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 29.06.2020
Physical Progress : 60%
Name of Project : RDRIIP-2

## Rangpur.29-10-20
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 29/10/2020Bs | iscyyi I cxiMvQv | Name of Work : Improvement of Mirapara Govt. Primary School Connecting Road (Ch: 00-1425m). (School Code-105050804) . | ISG AS WBM | ISG : 200mm AS : 150mm WBM : 150mm CBR (WBM) : 80% CBR (AS) : 30% CBR (ISG) : 8% AS Proportion (Khoa : Sand) = 50:50 | CBR Test done by DCP, AIV at Lab ISG : 240mm AS : 150mm WBM : 160mm CBR (WBM) : 66% CBR (AS) : 31.90% CBR (ISG) : 10.5% AIV : 28% AS Proportion (Khoa : Sand) = 52:48 | WBM Compaction Kg _vKvq cybivq Top Surface loose KiZ: Compaction K‡i 80% CBR Avb‡Z n‡e¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 18-03-2020
Physical Progress : 70%
Name of Project : RDRIIP-2

## Gaibandha 23.01.2021
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 2021-01-23 | উপজেলাঃ সাদুল্লাপুর, জেলাঃ গাইবান্ধা | Name of Work : RDRIIP-2/W-VRA-243 A.Improvement of Enaetpur bazar - Moshbandhi bazar Road Ch.2480-3480m. ID N0-132824060. under Sadullapur Upazila. Dist Gaibandha. | ISG, AS, WBM, | ISG-200mm AS-150mm WBM-150mm | KvRwU WBM ch©šÍ mgvß †`Lv hvq¦ †PB‡bR 2510 wg. -G Sand, AS, WBM Gi cyiæZ¡ cvIqv †Mj h_vÎ‡g 220 wg.wg., 150 wg.wg., 160 wg.wg.¦ AS Gi Proporfion 52:48 (Agreegate:Sand) cvIqv †Mj¦ AS Ges WBM-G DCP †U‡ó CBR cvIqv †Mj 34% I 80.7%¦ GKBfv‡e †PB‡bR 3450 wg. G Sand, AS, WBM Gi cyiæZ¡ cvIqv †Mj 280 wg.wg., 150 wg.wg., 155 wg.wg. AS Gi Proporfion 47:53 (Agreegate:Sand) Ges DCP †U‡ó AS I WBM Gi CBR cvIqv †Mj h_vµ‡g 31% I 82%¦ Shoulder-G gvwUi KvR Amgvß ‡`Lv hvq¦ | • `ªæZ Shoulder-Gi gvwUi KvR mgvß K‡i Carpeting mgvß Kivi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 31.05.21
Physical Progress : 75%
Name of Project : RDRIIP-2

## Rangpur 23.01.2021
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 24/01/2021 | Dc‡Rjv t e`iMÄ †Rjvt iscyi | Name of Work : Improvement of Kaligonj hat-Tochar More RHD Road Ch. 500-1175m Road ID No- 185034062 RDRIIP-2/W-VRA-214 | BC Seal Coat | BC :25mm SC : 7mm | KvRwU mgvß †`Lv hvq¦ †PB‡bR 750wg. Ges 850wg. G Kv‡c©wUs I Seal Coat Gi thickness cixÿv Kiv n‡jv Ges h_vµ‡g 33 wg.wg. I 35 wg.wg. cvIqv hvq¦ | • Shoulder G ch©všÍ gvwUi KvR bv _vKvq `ªæZ chv©ß gvwUi KvR Kivi Rb¨ ejv n‡jv¦
Completion Date :
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur 23.01.2021 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 24/01/2021 | Dc‡Rjv t e`iMÄ †Rjvt iscyi | Name of Work : Improvement of Kaligonj hat-Tochar More RHD Road Ch. 500-1175m Road ID No- 185034062 RDRIIP-2/W-VRA-214 | BC Seal Coat | BC :25mm SC : 7mm | KvRwU mgvß †`Lv hvq¦ †PB‡bR 750wg. Ges 850wg. G Kv‡c©wUs I Seal Coat Gi thickness cixÿv Kiv n‡jv Ges h_vµ‡g 33 wg.wg. I 35 wg.wg. cvIqv hvq¦ | • Shoulder G ch©všÍ gvwUi KvR bv _vKvq `ªæZ chv©ß gvwUi KvR Kivi Rb¨ ejv n‡jv¦
Completion Date :
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur 03.03.2021 (3)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 27/02/2021 | iscyi, KvDwbqv | Name of Work : Improvement of the Road from Burirhat Road to Tepamodhupur-Pawtana GC Road via H/O Kashem Chairman Ch.56-905m ID No. 185425157 . | PSG AS WBM BC, SC | BC-25mm SC-7mm | KvRwU 100% mgvß †PB‡bR 150m I 550m G Seal coat mn Carpeting cixÿv Kiv nq Ges c~iæZ¡ h_vµ‡g 36mm I 35mm cvIqv †Mj Dfq †ÿ‡µ Cake form K‡i‡Q¦ Shoulder G negative Slope †`Lv hvq¦ | • Negative Slope Acmvi‡bi Rb¨ ejv n‡q‡Q¦
Completion Date : 14.07.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## Gaibandha 04.03.2021 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 26/2/2021 | Dc‡Rjv : mv`yjøvcyi ‡Rjv : MvBevÜv | Name of Work : RDRIIP-2/W-VRB-157 A. Improvement of Sadullapur Madarganj Road - Sadullapur Dhaperhat Road Ch. 00-1400.00m under Sadullapur upazila Dist Gaibandha. Road ID. 132825028. | ISG, AS, WBM, Carpeting Seal Coat | A. ISG-200mm AS-150mm B. WBM, BC+Seal Coat | moKwU‡Z AS layer Gi KvR Pjgvb †`Lv hvq 2wU ¯’v‡b †PB‡bR 1200m I 1300m G AS Gi thickness I Proportion cixÿv Kiv nh¦ Thickness h_vµ‡g 160m I 165m cvIqv ‡Mj¦ Proportion h_vµ‡g 55:45, 57:43 (Khoa:Sand) cIqv ‡Mj¦ ch©vß Compaction nqwb g‡g© cÖZxqgvb n‡jv¦ Kv‡Ri AMÖMwZ gš’i¦ | • AS layer h_vh_fv‡e Compaction KiZ: Kv‡Ri AMÖMwZ Z¡ivwš^Z Kivi Rb¨ ejv n‡q‡Q¦
Completion Date : 25-04-2020
Physical Progress : 25%
Name of Project : RDRIIP-2

## Gaibandha 23.01.2021 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 2021-01-23 | উপজেলাঃ সাদুল্লাপুর, জেলাঃ গাইবান্ধা | Name of Work : RDRIIP-2/W-VRA-243 A.Improvement of Enaetpur bazar - Moshbandhi bazar Road Ch.2480-3480m. ID N0-132824060. under Sadullapur Upazila. Dist Gaibandha. | ISG, AS, WBM, | ISG-200mm AS-150mm WBM-150mm | KvRwU WBM ch©šÍ mgvß †`Lv hvq¦ †PB‡bR 2510 wg. -G Sand, AS, WBM Gi cyiæZ¡ cvIqv †Mj h_vÎ‡g 220 wg.wg., 150 wg.wg., 160 wg.wg.¦ AS Gi Proporfion 52:48 (Agreegate:Sand) cvIqv †Mj¦ AS Ges WBM-G DCP †U‡ó CBR cvIqv †Mj 34% I 80.7%¦ GKBfv‡e †PB‡bR 3450 wg. G Sand, AS, WBM Gi cyiæZ¡ cvIqv †Mj 280 wg.wg., 150 wg.wg., 155 wg.wg. AS Gi Proporfion 47:53 (Agreegate:Sand) Ges DCP †U‡ó AS I WBM Gi CBR cvIqv †Mj h_vµ‡g 31% I 82%¦ Shoulder-G gvwUi KvR Amgvß ‡`Lv hvq¦ | • `ªæZ Shoulder-Gi gvwUi KvR mgvß K‡i Carpeting mgvß Kivi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 31.05.21
Physical Progress : 75%
Name of Project : RDRIIP-2

## Rangpur 23.01.2021 (3)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 24/01/2021 | Dc‡Rjv t e`iMÄ †Rjvt iscyi | Name of Work : Improvement of Kaligonj hat-Tochar More RHD Road Ch. 500-1175m Road ID No- 185034062 RDRIIP-2/W-VRA-214 | BC Seal Coat | BC :25mm SC : 7mm | KvRwU mgvß †`Lv hvq¦ †PB‡bR 750wg. Ges 850wg. G Kv‡c©wUs I Seal Coat Gi thickness cixÿv Kiv n‡jv Ges h_vµ‡g 33 wg.wg. I 35 wg.wg. cvIqv hvq¦ | • Shoulder G ch©všÍ gvwUi KvR bv _vKvq `ªæZ chv©ß gvwUi KvR Kivi Rb¨ ejv n‡jv¦
Completion Date :
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur 05.05.2021 (4)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 2021-05-04 | iscyi, m`i | Name of Work : A Improvement of Jalkor More-Amashu Pachimpara Shasan Road Ch.00-750m ID No-185495347 | AS WBM BC, SC | 25mm Carpeting, 7mm seal coat | KvRwU 100% mgvß ‡`Lv hvq 25mm Carpeting Ges 7mm seal coat aiv wQj¦ Carpeting Gi c~iæZ¡ †PB‡bR 350m, 650m G cvIqv †Mj h_vµ‡g 34mm, 33mm, | - | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 30.12.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## কুড়িগ্রাম 26-06-2021 (4)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 27/06/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | WBM | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z WBM Gi KvR mgvß ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G WBM -Gi CBR cvIqv ‡Mj 78%¦ | • AvenvIqv AbyK‚‡j Avm‡j Kv‡c©wUs KvR Ki‡Z n‡e¦ | 2 | 25/12/2020 | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | 2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦
|  |  | Completion Date : 29.06.2020 | [9 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020 | [7 empty] | Completion Date : 29.06.2020
|  |  | Physical Progress : 75% | [9 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60% | [7 empty] | Physical Progress : 60%
|  |  | Name of Project : RDRIIP-2 | [9 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2 | [7 empty] | Name of Project : RDRIIP-2

## Rangpur.26-09-2021 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 25/09/2021 | iscyi, m`i | Name of Work : (A) Improvement of Mohadebpur H/O Abul Kalam-Abul Khayer Factory Road Ch. 00-1233m Road ID No- 185495344 (B) Improvement Debipur H/O Lutfor-Mosque of Mintu Member Road Ch. 00-769m Road ID No- 185495345 [Rangpur-S] Package No: RDRIIP-2/W-VRB-184 | BC, WBM | BC :32mm, WBM : 150mm | KvRwU mgvß †`Lv hvq¦ 850m. G WBM Gi thickness cixÿv Kiv n‡j 165 m I †PB‡bR 220m Ges 850m G BC Gi thickness cixÿv Kiv n‡jv Ges h_vµ‡g 35mm I 35 mmcvIqv hvq¦ Shoulder I Slope -G ch©vß gvwUi KvR nqwb¦ | • `ªæZ Shoulder I Slope-G ch©vß gvwUi KvR Ki‡Z ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 26.06.2021
Physical Progress : 100%
Name of Project : RDRIIP-2
2 | 26/09/2021 | iscyi, wgVvcyKzi | Name of Work : Improvement of Ship Dayul Para Bazar -Emadpur Adibashi School Noorpur Road Ch. 000-1000m Road ID No- 185584050 MITHAPUKUR, Package No: RDRIIP-2/W-VRA-212 | BC | BC :32mm, | KvRwU mgvß †`Lv hvq¦ †PB‡bR 300m I 700m G BC Gi thickness cixÿv Kiv n‡jv Ges h_vµ‡g 32 mm I 34mm cvIqv ‡Mj¦ Shoulder-G ch©vß KvR nqwb¦ | • Shoulder -G ch©vß gvwUi KvR e¨wZZ PzovšÍ wej cÖ`vb bv Kivi Rb¨ ejv n‡jv¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 15.11.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## Kurigram-26-11-20211
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb-†Lvqvi mvBR/WBM Gi Thickness BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | ২৫-১১-২০২১ | কুড়িগ্রাম জেলা, রাজারহাট উপজেলা | Name of Work : Improvement of Chakirpashar UP office- Nakkatihat Road (ch. 1250m-2800m) Road ID: 149773005) | RDRIIP-2 | BC, SC, WBM, Sub-base, ISG | BC=25 mm, SC=7mm, WBM=150mm, Sub-base=150mm, ISG=200mm | KvRwU 100% mgvß ‡`Lv hvq 25mm Carpeting I 7mm seal coat Gi †ÿ‡Î †PB‡bR 1300m I 2250m G cvIqv †Mj h_vµ‡g 32mm I 33mm¦ |  | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 5/15/2020
Physical Progress : 100%
Name of Project : RDRIIP-2
2 | ২৫-১১-২০২১ | কুড়িগ্রাম জেলা, রাজারহাট উপজেলা | Name of Work : Improvement of Chakirpashar UP office- Milerpar Bazar Road (ch. 1000m-2257m) Road ID: 149773009) | RDRIIP-2 | BC, SC, WBM, Sub-base, ISG | BC=25 mm, SC=7mm, WBM=150mm, Sub-base=150mm, ISG=200mm | KvRwU 100% mgvß ‡`Lv hvq 25mm Carpeting I 7mm seal coat Gi †ÿ‡Î †PB‡bR 1250m, 1400m I 2150m G thickness cixÿv K‡i h_vµ‡g 34mm, 32mm I 33mm cvIqv †Mj¦ Shoulder G gvwUi Kv‡R Negative Slope i‡q‡Q¦ | • Shoulder Gi gvwUi KvR h_vh_ fv‡e KiZ: mwVK Slope Maintain Kivi Rb¨ ejv nBj¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 6/29/2020
Physical Progress : 100%
Name of Project : RDRIIP-2
3 | ২৫-১১-২০২১ | কুড়িগ্রাম জেলা, রাজারহাট উপজেলা | Name of Work : Improvemen of Nazimkhan Khadabag UZR at Sonalurkuti to Dangrarhat via Kalirhat Road (Ch. 00m-1951m) (Road ID: 149774023) | RDRIIP-2 | WBM, Sub-base, ISG | WBM=150mm, Sub-base=150mm, ISG=200mm | moKwU‡Z WBM Gi KvR mgvß †`Lv hvq¦ †PB‡bR 250m I 400m Thickness h_vµ‡g 150mm I 142mm cvIqv ‡Mj¦ | • Carpeting KvR Kivi c~‡e© WBM Gi Thickness ms‡kvab Kivi Rb¨ ejv n‡q‡Q¦
Completion Date :10/10/2021
Physical Progress : 65%
Name of Project : RDRIIP-2
4 | ২৫-১১-২০২১ | কুড়িগ্রাম জেলা, নাগেশ্বরী উপজেলা | Name of Work : Improvement of Vitor bondh Bazar Chowmohoni-Hatibandha Hafiza Marasa Road (Ch. 00m-420m) (Road ID: 149614047) | RDRIIP-2 | WBM, Sub-base, ISG | WBM=150mm, Sub-base=150mm, ISG=200mm | moKwU‡Z WBM Gi KvR mgvß †`Lv hvq¦ †PB‡bR 150m I 250m Thickness h_vµ‡g 152mm I 154mm cvIqv ‡Mj¦ iv¯Ívq Negative Slope we`¨gvb¦ | • Negative Slope Acmvib Ki‡Z ejv n‡q‡Q¦
|  |  | Completion Date : 5/20/2020 | [5 empty] | wbw`©ó mg‡q mgvß | nu¨v
Physical Progress : 70%
Name of Project : RDRIIP-2

## Rangpur-17-11-20211 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb-†Lvqvi mvBR/WBM Gi Thickness BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 24/11/2021 | iscyi, MsMvPov | Name of Work : Periodic Maintenance work of Gangachara Upazila Complex Internal Road (Ch. 100 -770m), Road ID - 185275136, Package No: RDRIIP-2/W-MAI-011 | RDRIIP-2 | WBM & BC | BC=25 mm, SC=7mm 75mmWBM | KvRwU 100% mgvß ‡`Lv hvq¦ 25mm Carpeting I 7mm seal coat Gi †ÿ‡Î †PB‡bR 350m, 450m I 600m G thickness cixÿv K‡i h_vµ‡g 35mm, 32mm I 34mm cvIqv †Mj¦ †PB‡bR 300m-420m G End edging ‡mvRv †bB¦ | • End edging ‡mvRv K‡i cyb:¯’vc‡bi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 11.03.2021
Physical Progress : 100%
Name of Project : RDRIIP-2

## Lalmonirhat-22-01-2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 22-01-2022 | Dc‡Rjv t nvwZevÜv, †Rjv t jvjgwbinvU | NAME OF WORK: Improvement of Ghundi Bazar-Purbo Dawabari Ghat Road at (Ch.00-1000m) [Road ID No:-152335365] Under Hatibandha Upazila District:-Lalmonirhat, | WBM Sub-Base ISG | WBM -150mm Sub-Base -150mm ISG-200mm | KvRwU Pjgvb †`Lv hvq¦†PB‡bR 300m, 650m I 900m G WBM Gi thickness cixÿv K‡i h_vµ‡g 155mm, 158mm I 153mm cvIqv †Mj¦ †PB‡bR 300m, 650m I 900m G Sub-Base Gi thickness cixÿv K‡i h_vµ‡g 160mm, 158mm I 155mm cvIqv †Mj Ges †Lvqv evwji AbycvZ h_vµ‡g 50t50, 52t48, I 52t48 cvIqv †Mj¦ †PB‡bR 300m, 650m I 900m G ISG Gi thickness cixÿv K‡i h_vµ‡g 210mm, 208mm I 215mm cvIqv †Mj¦ wVKv`vi Kvwc©wUs Kv‡Ri cÖ¯‘wZ wb‡”Qb¦ | • Shoulder G ch©vß gvwUi KvR m¤úbœ KiZ: `ªæZ Kv‡c©wUs Gi KvR m¤úbœ Ki‡Z ejv n‡jv¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 24-10-2021
Physical Progress : 75%
Name of Project : RDRIIP-2
5 | 2021-03-01 | উপজেলাঃ গোবিন্দগন্জ জেলাঃ গাইবান্ধা | Excavation of Rashiknagar -Chiargaon Khal | Khal Excavation Reference Bed Block Tree Plantation | Khal Excavation(00-5300m)- Top Width-12.5m Bottom Width-4m Slope-1:1.5 |  |  | wbw`©ó mg‡q mgvß | nu¨v
Completion Date 30-04-2021
Physical Progress : 70%
Name of Project :SSWRDP-2
6 | 2021-03-01 | উপজেলাঃ গাইবান্ধা সদর জেলাঃ গাইবান্ধা | e-APP/LGED/Gai/GOBM/19-20/W-72 Rehabilitation of Gaibandha - Laxmipur Road Ch.10000m-10300m. Road ID No. 132242001. under Gaibandha Sadar upazila. Dist. Gaibandha. | RCC Road | Hard bed prepartion. Thickness: 8 inch; Strength: 30MPA |  |  | wbw`©ó mg‡q mgvß | nu¨v
Completion Date 25-09-2020
Physical Progress : 100%
Name of Project :GOBM

## Kurigram-24-01-22
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb-†Lvqvi mvBR/WBM Gi Thickness BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 24/01/2022 | KzwoMÖvg †Rjv, ivRvinvU Dc‡Rjv | Name of Work : Improvement of Chakirpasha UP office - Nakkatihat road (ch. 1250m-2800m) (Road ID: 149773005) | BC,SC,WBM, Sub-base, ISG | BC=25 mm, SC=7mm, WBM=150mm, Sub-base=150mm, ISG=200mm | †PB‡bR 1620m I 2460m G BC I SC Gi thickness GK‡Î h_vµ‡g 33mm I 32mm Ges WBM Gi thickness h_vµ‡g 150 mm I 152mm cvIqv hvq¦ |  | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 28/11/2021
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur-26-02-2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 23-02-2022 | iscyi,cxiMÄ | Name of Work : A Improvement of Choto Falia Joarpur - Nanfar Bill Kadirabad Pacca road Connecting Road Ch.00-1310mID No-185765119 | WBM | 250mm ISG, 150mm AS, 150 WBM | KvRwU Pjgvb ‡`Lv hvq¦ 150mm WBM Gi cyiæZ¡ †PB‡bR 30m, 267m, 706m, 1102m G cvIqv †Mj h_vµ‡g 155mm, 160mm, 160mm I 155mm. †PB‡bR 30m I 706m G ISG c~iæZ¡ cvIqv †Mj 260mm I 265mm. AS G cvIqv †Mj 160mm I 155mm Ges AS Gi Proportion cvIqv †Mj evjy:‡Lvqv= 55:45 I 50:50. | • Shoulder G gvwUi KvRmn `ªæZ KvR m¤úbœ Kivi Rb¨ ejv n‡jv¦
Package No. RDRIIP-2/W-VRB-229
Completion Date : 07.06.2022
Physical Progress : 60%
Name of Project : RDRIIP-2
2 | 23-02-2022 | iscyi, wgVvcyKzi | Name of Work : Improvement of Mithapukur Collage - Neterbazar (Dabra) via Tulshipur GPS Road (Ch. 3320-4615m). ID No- 185583010. | WBM, Sub-Base, BG & BC | 150mm WBM, 150mm Sub Base, 250mm ISG, 25mm BC & 7mm Seal Coat | কাজটি 100% সমাপ্ত দেখা যায়। Seat coat সহ Carpeting এর পুরুত্ব চেইনেজ 3645mm, 4090mm, 4570mm, এ পাওয়া গেল যথাক্রমে 35mm, 34mm, 33mm
Package No.RDRIIP-2/W-UNR-082
Completion Date : 11.06.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur-24-02-2022 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 23-02-2022 | iscyi,cxiMÄ | Name of Work : A Improvement of Choto Falia Joarpur - Nanfar Bill Kadirabad Pacca road Connecting Road Ch.00-1310mID No-185765119 | WBM | 250mm ISG, 150mm AS, 150 WBM | KvRwU Pjgvb ‡`Lv hvq¦ 150mm WBM Gi cyiæZ¡ †PB‡bR 30m, 267m, 706m, 1102m G cvIqv †Mj h_vµ‡g 155mm, 160mm, 160mm I 155mm. †PB‡bR 30m I 706m G ISG c~iæZ¡ cvIqv †Mj 260mm I 265mm. AS G cvIqv †Mj 160mm I 155mm Ges AS Gi Proportion cvIqv †Mj evjy:‡Lvqv= 55:45 I 50:50. | • Shoulder G gvwUi KvRmn `ªæZ KvR m¤úbœ Kivi Rb¨ ejv n‡jv¦
Package No. RDRIIP-2/W-VRB-229
Completion Date : 07.06.2022
Physical Progress : 60%
Name of Project : RDRIIP-2
2 | 23-02-2022 | iscyi, wgVvcyKzi | Name of Work : Improvement of Mithapukur Collage - Neterbazar (Dabra) via Tulshipur GPS Road (Ch. 3320-4615m). ID No- 185583010. | WBM, Sub-Base, BG & BC | 150mm WBM, 150mm Sub Base, 250mm ISG, 25mm BC & 7mm Seal Coat | কাজটি 100% সমাপ্ত দেখা যায়। Seat coat সহ Carpeting এর পুরুত্ব চেইনেজ 3645mm, 4090mm, 4570mm, এ পাওয়া গেল যথাক্রমে 35mm, 34mm, 33mm
Package No.RDRIIP-2/W-UNR-082
Completion Date : 11.06.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## 20-21 অর্থ বছরের সমাপ্তকৃত স্কী
wUg-20 KZ©„K 2020-21 A_©eQ‡i mgvßK…Z ¯‹x‡gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvg BZ¨vw` mn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨v mg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/†Lvqvi mvBR BZ¨vw`) |  |  | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | µwU ms‡kva‡b mycvwikgvjv/ M„nxZ e¨e¯’vw` I gšÍe¨ | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | µwU ms‡kva‡b mycvwikgvjv/ M„nxZ e¨e¯’vw` I gšÍe¨
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 9 | 10
1 | 31-03-2022 | jvjgwbinvU, m`i | Name of Work : Improvement of Milon Bazar-Tista Riverghat Road (Ch. 00-1850m). [Road ID:152554087] | BC, Seal coat, Palisading | 25mm, 07mm |  | n¨vu (wbw`©ó mg‡q mgvß n‡q‡Q) |  |  | n¨vu
Completion Date : 06.08.2020
Physical Progress : 100%
Name of Project : RDRIIP-2
2 | 28-03-2022 | iscyi, cxiMvQv | Name of Work :Improvement of Pirgacha UZHQ - Chowdarani GC via Jamirzan Road (Ch. 1262-4800m), ID no-185732007.Package No:RDRIIP-2/ W-UZR-37 | ISG, AS, WBM, BC, Seal Coat | ISG-250mm AS-150mm WBM-150mm BC-25mm Seal Coat- 7mm | KvRwU 100% mgvß †`Lv hvq¦ †PB‡bR 2000m, 3350m, 4500m G BC+Seal Coat Gi c~iæZ¡ h_vµ‡g 35mm, 38mm, 39mm cvIqv ‡Mj¦ iv¯Ívi cÖk¯ÍZv mwVK cvIqv †Mj¦ | n¨vu |  |  | n¨vu
Completion Date : 25-09-2020
Physical Progress : 100%
Name of Project : RDRIIP-2
Note on C10: Author: vQv

## লালমনিরহাট..31.03.2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
wefvM : iscyi †Rjv : jvjgwbinvU
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | µwU ms‡kva‡b mycvwikgvjv/ M„nxZ e¨e¯’vw` I gšÍe¨
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 9 | 10
1 | 31.03.2022 | Sadar | Name of Work : Improvement of Milon Bazar-Tista Riverghat Road (Ch. 00-1850m). [Road ID:152554087] |  |  |  |  | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 06.08.2020
Physical Progress : 100%
Name of Project : RDRIIP-2

## Rangpur.03.28.2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw`
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 8
1 | 28-03-2022 | iscyi/ cxiMvQv | Name of Work :Improvement of Pirgacha UZHQ - Chowdarani GC via Jamirzan Road (Ch. 1262-4800m), ID no-185732007.Package No:RDRIIP-2/ W-UZR-37 | Edging | 125mm | KvRwU 100% mgvß †`Lv hvq¦ †PB‡bR 2000m, 3350m G BC Gi c~iæZ¡ h_vµ‡g 35mm, 38mm cvIqv ‡Mj¦ iv¯Ívi cÖk¯’Zv mwVK cvIqv †Mj¦
|  |  | Completion Date : 25-09-2020 | BC | 32mm
Physical Progress : 100%
Name of Project : RDRIIP-2
Note on C6: Author: vQv

## 20-21 অর্থ বছরের সমাপ্তকৃত (2)
wUg-20 KZ©„K 2020-21 A_©eQ‡i mgvßK…Z ¯‹x‡gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvg BZ¨vw` mn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨v mg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/†Lvqvi mvBR BZ¨vw`) |  |  | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | µwU ms‡kva‡b mycvwikgvjv/ M„nxZ e¨e¯’vw` I gšÍe¨ | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv) | µwU ms‡kva‡b mycvwikgvjv/ M„nxZ e¨e¯’vw` I gšÍe¨
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 9 | 10
1 | 28-03-2022 | iscyi, cxiMvQv | Name of Work :Improvement of Pirgacha UZHQ - Chowdarani GC via Jamirzan Road (Ch. 1262-4800m), ID no-185732007.Package No:RDRIIP-2/ W-UZR-37 | ISG, AS, WBM, BC, Seal Coat | ISG-250mm AS-150mm WBM-150mm BC-25mm Seal Coat- 7mm | KvRwU 100% mgvß †`Lv hvq¦ †PB‡bR 2000m, 3350m, 4500m G BC+Seal Coat Gi c~iæZ¡ h_vµ‡g 35mm, 38mm, 39mm cvIqv ‡Mj¦ iv¯Ívi cÖk¯ÍZv mwVK cvIqv †Mj¦ | n¨vu |  |  | n¨vu
Completion Date : 25-09-2020
Physical Progress : 100%
Name of Project : RDRIIP-2
Note on C6: Author: vQv

## রংপুর.12.06.2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b (‡g/2022 gv‡mi)
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw`
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | 29-05-2022 | iscyi/ m`i | Name of Work :mprovement Palichara GC to Rangpur Badarganj R & H Road via Kasimbazar Road (Ch. 6100-7072m) [Road ID No-185492022] (Package No.RDRIIP-2/W-UZR-041) | ISG AS WBM Bc+Sc | 25mm BC & 7mm Seal Coat | KvRwU 100% mgvß †`Lv hvq, 25mm Carpeting Ges 7mm Seal GK‡Î cyiæZ¡ †PB‡bR 6200m, 6500m, 7000m, 7050m G cvIqv †Mj h_vµ‡g 35mm, 34mm, 34mm I 32mm.
Completion Date : 07-03-2022
Physical Progress : 100%
Name of Project : RDRIIP-2
2 | 29-05-2022 | iscyi/ ZvivMÄ | Name of Work :Improvement of Tetultola GC to Alampur UP Road (Ch.00-1500m) Road ID No.185923016 (Package No.RDRIIP-2/W-UNR-212 | ISG AS WBM Bc+Sc | WBM | KvRwU Pjgvb i‡q‡Q¦ eZ©gvb AMÖMwZ 70%¦ 150mm WBM Gi cyiæZ¡ †PB‡bR 35m, 270m, 923m, 1306m G cvIqv †Mj h_vµ‡g 160mm, 162mm, 162mm I 160mm. | • Aewkó KvR `ªæZ mgvwßi Rb¨ ejv n‡q‡Q¦
Completion Date : 07-03-2022
Physical Progress : 70%
Name of Project : RDRIIP-2
Note on C6: Author: vQv
Note on C10: Author: vQv

## কুড়িগ্রাম 03-08-2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©K„Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/ Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb-‡Lvqvi mvBR/WBM Gi Thickness BZ¨vw`) |  |  | ÎæwU ms‡kva‡bi mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw`
[5 empty] | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | 17/07/2022 | KywoMÖvg, ivRvinvU | Kv‡Ri bvgt Improvement of Road from Kanarmore- Chhararpar Sabuj Shathy Govt. Primary School Connecting road from Ch.00m-1000m [School Code: 107070703 ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvixi bvgt wbev©nx cÖ‡KŠkjxt †gvt gvmy`yi ingvb Dc‡Rjv cÖ‡KŠkjxt †gvt †mv‡nj ivbv Dc-mnKvix cÖ‡KŠkjxt †gvt Avãyj Lv‡jK Kvh© mnKvixt GKivgyj nK ivbv | RDRIIP-2 | ISG, Sub-Base, WBM | ISG= 200mm, Sub-Base= 150mm, WBM= 150mm

## কুড়িগ্রাম 10-08-2022
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©K„Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/ Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb-‡Lvqvi mvBR/WBM Gi Thickness BZ¨vw`) |  |  | ÎæwU ms‡kva‡bi mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw`
[5 empty] | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | 17/07/2022 | KywoMÖvg, ivRvinvU | Kv‡Ri bvgt Kvbvi†gvo-Pvivicvo meyR mv_x miKvix cÖv_wgK we`¨vjq ms†hvM moK (†PB-00wgt-1000wgt) [¯‹yj †KvW bs-107070703] Kv‡Ri AMÖMwZ : 70%¦ ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvixi bvgt wbev©nx cÖ‡KŠkjxt †gvt gvmy`yi ingvb Dc‡Rjv cÖ‡KŠkjxt †gvt †mv‡nj ivbv Dc-mnKvix cÖ‡KŠkjxt †gvt Avãyj Lv‡jK Kvh© mnKvixt GKivgyj nK ivbv | RDRIIP-2 | ISG, Sub-Base, WBM | ISG= 200mm, Sub-Base= 150mm, WBM= 150mm | KvRwU WBM ch©šÍ mgvß †`Lv hvq 2wU †PB‡b‡R cixÿv‡šÍ cÖvß djvdj: (At ch. 40m, ISG=210mm, Sub-base=160mm & proportion of brick chips and sand 52:48, WBM=155mm), (At ch. 4800m, ISG=220mm, Sub-base=165mm & proportion of brick chips and sand 50:50, WBM=160mm), | • ‡¯úwmwd‡Kkb Abyhvqx KvRwU `ªæZ mgvß Kivi Rb¨ ejv n‡q‡Q¦

## Rangpur 13.07.2022 (4)
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 2022-11-08 | iscyi/KvDwbqv | Kv‡Ri bvg t Improvement of Sarai UP (Zahir) - Eakotar Bazar via Udoy Narayon Machari Pry. School Road (Ch. 1375-2375m.). ID No- 185423012. | RDRIIP-2 | BC, Seal Coat | BC=25mm Seal Coat=7mm | KvRwU 100% mgvß †`Lv hvq, †PB‡bR 1470m, 2550m G Kv‡c©wUs I Seal coat Gi cyiæZ¡ cixÿv K‡i cvIqv †Mj h_vµ‡g 35mm, 35mm. bgybvmg~n Cake form K‡i‡Q¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t †gvt †iRvDj nK
Dc‡Rjv cÖ‡KŠkjx t †gvt Avmv`y¾vgvb †Rwg
Dc-mnKvix cÖ‡KŠkjx t ‡gvt dvBRyj Bmjvg
Kvh© mnKvix t ‡gvt Avãyj KzÏym

## গাইবান্ধা 28-11-2022
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 |  | MvBevÜv †Mvwe›`MÄ | Kv‡Ri bvg t RDRIIP-2/W-VRB-270 Improvement Matherpur - Dinajpur road at firm via Sautalpara Road (Ch. 440-1500m) ID No. 132305101 under Gobindagonj Upazila District Gaibandha | RDRIIP-2 | ISG, Sub-base, WBM, BC Palisading | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat Palisading-77m | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 500m I 1400m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 210mm, Sub-base : 155mm (Agg50 : Sand50), WBM : 160mm, DBC : 35mm I ISG : 220, Sub-base : 155mm (Agg.52 : Sand48), WBM : 150mm, BC+SC=37mm : 36mm¦ mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t মোঃ ছাবিউল ইসলাম
Dc‡Rjv cÖ‡KŠkjx t মোঃ আব্দুল লতিফ
Dc-mnKvix cÖ‡KŠkjx t খালেদ আহমেদ চৌধুরী
Kvh© mnKvix t ওয়াজেদ আলী মন্ডল
2 |  | MvBevÜv †Mvwe›`MÄ | Kv‡Ri bvg t RDRIIP-2/W-VRB-269 Improvement Kogaria - Jhirai Road (Ch. 00-950m) ID No. 132305036 under Gobindagonj Upazila District Gaibandha.Total cost of Salvage Materials Tk. 205462.00 | RDRIIP-2 | ISG, Sub-base, WBM, BC, SC | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat U drain-3nos | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 250m I 800m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 215mm, Sub-base : 155mm (Agg50 : Sand50), WBM : 153mm, BC+SC : 35mm I ISG : 208, Sub-base : 157mm (Agg52 : Sand48), WBM : 150mm, BC+SC : 40mm¦ mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t মোঃ ছাবিউল ইসলাম
Dc‡Rjv cÖ‡KŠkjx t মোঃ আব্দুল লতিফ
Dc-mnKvix cÖ‡KŠkjx t খালেদ আহমেদ চৌধুরী
Kvh© mnKvix t ওয়াজেদ আলী মন্ডল

## গাইবান্ধা 20-02-2023
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 2023-11-01 | গাইবান্ধা পলাশবাড়ী | Kv‡Ri bvg t RDRIIP-2/W-UZR-054 Improvement of Komorpur GC- Marirhat GC Road via sahindaha Road ( Ch. 4580-7500m) under Upazila : Palashbari, Dist. Gaibandha Road ID No-132672009 | RDRIIP-2 | ISG,AS,WBM, Carpeting seal coat | ISG-250mm AS-150mm WBM-150mm SC+BC- 32mm 2 nos RCC Culvert, 8 nos U-drain | KvRwU 100% mgvß †`Lv hvq¦ ‡PB‡bR 4600m, 6000m, 7105m G Kv‡c©wUs seal I coat Gi cyiæZ¡ cvIqv †Mj h_vµ‡g 35mm, 35mm, 40mm mo‡Ki cÖk¯ÍZv 3.70m Gi ¯’‡j 3.89m cvIqv †Mj¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t মোঃ ছাবিউল ইসলাম
Dc‡Rjv cÖ‡KŠkjx t মোঃ শাহারিয়ার
Dc-mnKvix cÖ‡KŠkjx t মোঃহেলালুর রহমান
Kvh© mnKvix t দেলোয়ার হোসেন

## কুড়িগ্রাম. 20-02-2023
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 2023-12-01 | KywoMÖvg, wPjgvix | Kv‡Ri bvg t kwi‡di nvU - Kvwkg evRvi †bqvi igbv BDwc mo‡K 1255 wgt †PB‡b‡R nwi‡li `viv Lv‡ji Dci 64.00 wgt `xN© Aviwmwm MvW©vi eªxR wbg©vb [†ivW AvBwW bs-149093001], AMÖMwZ : 60% | RDRIIP-2 | Rod binding for Slab casting | 64m lenght RCC Girder Bridge | weªRwUi KvR Pjgvb †`Lv hvq 1wU ¯ú¨v‡bi Girder Gi rod fabrication Pjgvb wQj¦ Stone chips gvbm¤§Z †`Lv hvq¦ Girder Gi j¨vc‡jš’ Kg †`Lv hvq¦ Bearing pad Gi †Pó wi‡cvU© cvIqv hvqwb¦ | • i‡Wi j¨vc‡jš’ Carrection Gi Rb¨ Ges Bearing Pad Gi Test report wbwðZ n‡q MvW©vi XvjvB‡qi Rb¨ ejv n‡jv¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t †gvt gvmy`yi ingvb
Dc‡Rjv cÖ‡KŠkjx t ‡gvt wd‡ivRyyi ingvb
Dc-mnKvix cÖ‡KŠkjx t ‡gvt AvZvDi ingvb
Kvh© mnKvix t †gvt bvRgyj Bmjvg
2 | 13/1/2023 | KywoMÖvg, Dwjcyi | Kv‡Ri bvg t _vbvnvU BDwc - bvMivKzovnvU moK Dbœqb KvR (†PB-970wgt-1892wgt) [†ivW AvBwW bs-149943014] AMÖMwZ : 100% | RDRIIP-2 | ISG, Sub-Base, WBM, BC, SC | ISG= 200mm, Sub-Base= 150mm, WBM= 150mm, BC=25mm, SC= 7mm | KvRwU mgvß †`Lv hvq¦ †PB‡bR 1200m, 1690m, 1840m-G Carpeting+Seal coat -Gi cyiæZ¡ cixÿv K‡i cvIqv †Mj h_vµ‡g 32mm, 32mm, 33mm Shoulder G gvwUi KvR Ach©vß †`Lv hvq¦ | • `ªæZ Shoulder G ch©vß gvwUi KvR Kivi Rb¨ ejv n‡jv¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t †gvt gvmy`yi ingvb
Dc‡Rjv cÖ‡KŠkjx t ‡K‡KGg mv‡`Kzj Avjg
Dc-mnKvix cÖ‡KŠkjx t †gvt bRiæj Bmjvg
Kvh© mnKvix t †gvt gÄyi nvmvb (ivbv)
3 | 13/1/2023 | KywoMÖvg, Dwjcyi | Kv‡Ri bvg t Dwjcyi eRiv moK (Avgevox ¯‹zj) - AviGÛGBR moK eª¨vK †gvo evjvevox BDwc fvqv †Pqvig¨vb evox moK Dbœqb KvR (†PB-00wgt-1140wgt Ges 1640wgt - 1975wgt) [†ivW AvBwW bs-149944119] AMÖMwZ : 100% | RDRIIP-2 | ISG, Sub-Base, WBM, BC, SC | ISG= 200mm, Sub-Base= 150mm, WBM= 150mm, BC=25mm, SC= 7mm | KvRwU 100% mgvß †`Lv hvq¦ †PB‡bR 20m, 600m, 850m G BC+SCGi cyiæZ¡ cixÿv K‡i cvIqv †Mj h_vµ‡g 40mm, 35mm, 33mm Shoulder G gvwUi KvR Ach©vß †`Lv hvq¦ | • `ªæZ Shoulder G ch©vß gvwUi KvR Kivi Rb¨ ejv n‡jv¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t †gvt gvmy`yi ingvb
Dc‡Rjv cÖ‡KŠkjx t ‡K‡KGg mv‡`Kzj Avjg
Dc-mnKvix cÖ‡KŠkjx t ‡gvt AvKivg †nv‡mb
Kvh© mnKvix t †gvt gÄyi nvmvb (ivbv)

## রংপুর 26-12-2022
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 26-12-2022 | iscyi/MsMvPov | Kv‡Ri bvg t | RDRIIP-2 |  |  | weªR wbg©vY KvRwU Pjgvb ‡`Lv hvq¦ Pjgvb cvB‡ji Kv‡Ri MS rod fabfication, Bentonite Slury, Chamber etc cixÿv K‡i wWRvB‡bi mv‡_ wgj cvIqv †Mj¦ | • AMÖMwZ Z¡ivwš^Z Kivi Rb¨ ejv n‡jv¦
Construction of 40.00m Long RCC Variable depth Girder Bridge on Burirhat GC- Kakina RHD Road (Gangachara Part) at ch.5030m. Road ID No-185272012 Package No. RDRIIP-2/W-BRI-051
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t ‡gvnv¤§` kvnRvnvb Avjx
Dc‡Rjv cÖ‡KŠkjx t ‡gvt gwR`yj Bmjvg
Dc-mnKvix cÖ‡KŠkjx t ‡gvt mv‡R`yi ingvb
Kvh© mnKvix t kÖx mgi Kzgvi
2 | 26-12-2022 | iscyi/MsMvPov | Kv‡Ri bvg t | RDRIIP-2 |  |  | 3¯ú¨vb wewkó wcGwm MvW©vi weª‡Ri 2wU ¯ú¨v‡bi MvW©vi Ges 1wU ¯ú¨v‡bi ¯øvc ch©šÍ m¤úbœ †`Lv hvq¦ MvW©vi mg~‡ni Finished Surface fvj ‡`Lv †Mj¦ weª‡Ri wWRvBb, msµvšÍ wKQz cwieZ©b Kiv n‡q‡Q hv wWRvBb BDwbU KZ…©K cÖ`Ë wWRvBb Abyhvqx m¤úbœ Kiv n‡q‡Q¦ | • Kv‡Ri AMÖMwZ Z¡ivwš^Zmn `ªæZ G‡cÖvP mo‡Ki KvR m¤úbœ Kivi Rb¨ ejv n‡jv¦
Construction of 96.10m Long PSC Girder Bridge on Monirampur Bangla Para More-Ozir para via Boyratipara Road at ch. 150m. ID no.- 185274040 Package No. RDRIIP-2/W-BRI-031
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t ‡gvnv¤§` kvnRvnvb Avjx
Dc‡Rjv cÖ‡KŠkjx t ‡gvt gwR`yj Bmjvg
Dc-mnKvix cÖ‡KŠkjx t ‡gvt mv‡R`yi ingvb
Kvh© mnKvix t ‡gvt jv‡qK wgqv
* Kjvg 1 †_‡K 7 ch©šÍ Z_¨ c~iY K‡i †cÖi‡Yi Rb¨ Aby‡iva Kiv n‡jv¦

## লালমনিরহাট-27-12-2022
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 27-12-2022 | KvjxMÄ jvjgwbinvU | Kv‡Ri bvg t Improvement of Votmari UP-Kaligonjhat via Shatipara Road (Ch.1000m-2444m), [Road ID No-152393020], Under Kaliganj Upazila, District: Lalmonirhat. (Package No: RDRIIP-2/W-UNR-205), (Tender ID No.618969). | RDRIIP-2 | Sand Filling, SBBC, S@SBC,BC, SC, Palisading, U-Drain | Sand Filling=250mm, SBBC=150mm. S@SBC=150mm25mmBC, 7mmSC, Palisading=80m, U-Drain=6.0mx0.600mx0.600m | KvRwU Sub-base, lays I wKQz As‡k WBM Pjgvb i‡q‡Q¦ †PB‡bR 1900m. AS check K‡i thickness 160mm Sand thickness 301mm Ges A:S=55:45 cvIqv †Mj¦ Road width cvIqv †Mj 3.1m. †PB‡bR 1020m-G WBM cixÿv K‡i cvIqv †Mj 180mm. DCP Test K‡i cvIqv †Mj 42 Gi ¯’‡j 25 blow/150mm ¦ AviI Compaction cÖ‡qvRb¦ | • AS Ges WBM As‡k h_vh_ Compaction Ki‡Z ejv n‡jv¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t †gvt gÄyi Kv‡`i Bmjvg
Dc‡Rjv cÖ‡KŠkjx t Avey ˆZqe †gvt kvgmy¾vgvb, ‡gvt mvbwR` ivbv,
Dc-mnKvix cÖ‡KŠkjx t ‡gvt gvneyevi ingvb, †gvt AvBbyj nK (mv‡f©qvi)
Kvh© mnKvix t ‡gvt wmivRyj Bmjvg

## গাইবান্ধা 22-11-2022 (3)
20 cwi`k©b wUg -Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | ‡Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi bvg Ges ev¯Íevq‡b RwoZ Kg©KZ©v/Kg©PvixM‡bi bvg | cÖK‡íi bvg | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv |  |  | ÎæwU ms‡kva‡bi Rb¨ mycvwikgvjv/ M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
[5 empty] | Item | Design/ Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | 25-11-2022 | MvBevÜv †Mvwe›`MÄ | Kv‡Ri bvg t RDRIIP-2/W-VRB-270 Improvement Matherpur - Dinajpur road at firm via Sautalpara Road (Ch. 440-1500m) ID No. 132305101 under Gobindagonj Upazila District Gaibandha | RDRIIP-2 | ISG, Sub-base, WBM, BC Palisading | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat Palisading-77m | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 500m I 1400m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 210mm, Sub-base : 155mm (Agg50 : Sand50), WBM : 160mm, DBC : 35mm I ISG : 220, Sub-base : 155mm (Agg.52 : Sand48), WBM : 150mm, BC+SC=37mm : 36mm¦ mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t মোঃ ছাবিউল ইসলাম
Dc‡Rjv cÖ‡KŠkjx t মোঃ আব্দুল লতিফ
Dc-mnKvix cÖ‡KŠkjx t খালেদ আহমেদ চৌধুরী
Kvh© mnKvix t ওয়াজেদ আলী মন্ডল
2 | 25-11-2022 | MvBevÜv †Mvwe›`MÄ | Kv‡Ri bvg t RDRIIP-2/W-VRB-269 Improvement Kogaria - Jhirai Road (Ch. 00-950m) ID No. 132305036 under Gobindagonj Upazila District Gaibandha.Total cost of Salvage Materials Tk. 205462.00 | RDRIIP-2 | ISG, Sub-base, WBM, BC, SC | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat U drain-3nos | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 250m I 800m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 215mm, Sub-base : 155mm (Agg50 : Sand50), WBM : 153mm, BC+SC : 35mm I ISG : 208, Sub-base : 157mm (Agg52 : Sand48), WBM : 150mm, BC+SC : 40mm¦ mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
ev¯Íevq‡b wbhy³ Kg©KZ©v/Kg©Pvix t
wbe©vnx cÖ‡KŠkjx t মোঃ ছাবিউল ইসলাম
Dc‡Rjv cÖ‡KŠkjx t মোঃ আব্দুল লতিফ
Dc-mnKvix cÖ‡KŠkjx t খালেদ আহমেদ চৌধুরী
Kvh© mnKvix t ওয়াজেদ আলী মন্ডল

## মাঠ পর্যায়ে উন্নয়ন কাজ (2)
gvV ch©v‡qi Dbœqbg~jK KvR cwi`k©b cÖwZ‡e`b (Aewkó)
cwi`k©bKvix Kg©KZ©vi bvg I c`ex : †gvt mvLvIqvZ †nv‡mb, cÖKí cwiPvjK, Avt iwk` wgqv, Dc-cÖKí cwiPvjK, †gvt iv‡k`yj nvmvb, mnKvix cÖ‡KŠkjx¦
cwi`k©‡bi ZvwiL t
µwgK bs | cwi`k©b GjvKv (†Rjv/Dc‡Rjv) | cwi`k©bK…Z ¯‹x‡gi weeiY [¯‹x‡gi bvg, cÖK‡íi bvg, c¨v‡KR bs, mgvwßi Rb¨ wbav©wiZ ZvwiL, eZ©gvb AMÖMwZ] | KvR ev¯Íevq‡b mswkøó Kg©KZ©v/Kg©PvixM‡Yi bvg [wbe©vnx cÖ‡KŠkjx/Dc‡Rjv cÖ‡KŠkjx/Dc-mnKvix cÖ‡KŠkjx/Kvh©mnKvix] | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx: [†hgb-iv¯Ív/weªR/wewìs‡qi wewfbœ K‡¤úv‡b‡›Ui w_K‡bm/wdwbwms/wbg©vY mvgwMÖi ¸bMZ gvb BZ¨vw`] |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv/M„nxZ e¨e¯’vw` I gšÍe¨ (KvRwU m‡šÍvlRbK/ÎæwUc~Y©) | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design/ Specification | Field Observation
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10
1 | MvBevÜv/†Mvwe›`MÄ | Name of Work : RDRIIP-2/W-VRB-269 Improvement Kogaria - Jhirai Road (Ch. 00-950m) ID No. 132305036 under Gobindagonj Upazila District Gaibandha.Total cost of Salvage Materials Tk. 205462.00 | wbe©vnx cÖ‡KŠkjx t †gvt QvweDj Bmjvg, Dc‡Rjv cÖ‡KŠkjx t †gvt Avãyj jwZd, Dc-mnKvix cÖ‡KŠkjx t Lv‡j` Avn‡g` †PŠayix, Kvh© mnKvix t Iqv‡R` Avjx gÛj | ISG, Sub-base, WBM, BC Palisading | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat Palisading-77m | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 250m I 800m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 215mm, Sub-base : 155mm (Agg. : Sand=50:50), WBM : 153mm, BC+SC : 35mm I ISG : 208, Sub-base : 157mm (Agg.:Sand=52:48), WBM : 150mm, BC+SC : 40mm¦ mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
Completion Date : 12-06-2022
Physical Progress : 100%
Name of Project : RDRIIP-2
2 | MvBevÜv/†Mvwe›`MÄ | Name of Work :RDRIIP-2/W-VRB-270 Improvement Matherpur - Dinajpur road at firm via Sautalpara Road (Ch. 440-1500m) ID No. 132305101 under Gobindagonj Upazila District Gaibandha | wbe©vnx cÖ‡KŠkjx t †gvt QvweDj Bmjvg, Dc‡Rjv cÖ‡KŠkjx t †gvt Avãyj jwZd, Dc-mnKvix cÖ‡KŠkjx t Lv‡j` Avn‡g` †PŠayix, Kvh© mnKvix t Iqv‡R` Avjx gÛj | ISG, Sub-base, WBM, BC Palisading | ISG-200mm Subbase-150mm WBM-150mm Carpeting- 25mm+7mm seal coat Palisading-77m | KvRwU 100% mgvß †`Lv hvq¦ U-drain Gi msL¨v mwVK cvIqv hvq¦ ‡PB‡bR 500m I 1400m G layer mg~‡ni cyiæZ¡ cixÿv Kiv nq Ges h_vµ‡g ISG : 210mm, Sub-base : 155mm (Agg50 : Sand50), WBM : 160mm, BC+SC=35mm I ISG : 220, Sub-base : 155mm (Agg.52 : Sand48), WBM : 150mm, BC+SC=37mm mo‡Ki cÖk¯ÍZv I ˆ`N¨© mwVK cvIqv †Mj¦
Completion Date : 12-06-2022
Physical Progress : 100%
Name of Project :RDRIIP-2