## 20 পরির্দশন টিম প্রতিবেদন
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b ÒQKÓ
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 2020-05-09 | KzwoMÖvg, bv‡Mk^ix | Name of Work : Rahabilitation of Bhitorbond GC- Komorpur RHD road from Ch.00m -3300m Road ID : 149612003. | DC | 40mm | ‡PB‡bR 750wg. Ges 850wg., 2 wU ¯’v‡b Kv‡c©wUs cixÿv K‡i cyiæZ¡ mwVK cvIqv ‡Mj¦ | mo‡Ki ‡mvìv‡i cÖ`Ë gvwUi Kv‡Ri Compaction h_vh_ bv _vKvq Zv K¯ú¨vKkb Ki‡Z ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 14.08.2020
Physical Progress : 95%
Name of Project : NOBIDEP
2 | 2020-05-09 | jvjgwbinvU, jvjgwbinU m`i | Name of Work : Rahabilitation of Barobarihat GC- Rajarhat Upazila H/Q via Sindurmoti road from Ch.00m -7810m Road ID : 152552004 | DC | 40mm | Kv‡c©wUs KvR Pjgvb ‡`Lv hvq, ‡PB‡bR 2150wg. Ges 2250 wg., 2wU ¯’v‡b thickness cixÿv K‡i mwVK cvIqv ‡Mj¦ | cwi`k©b Kvjxb cÖPzi e„wócvZ wQj¦ Kv‡c©wUs Kv‡Ri Dchy³ AvenvIqv bv _vKvq KvR eÜ ivLvi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 22.10.2020
Physical Progress : 85%
Name of Project : NOBIDEP
3 | 2020-05-09 | MvBevÜv, ‡Mvwe›`MÄ | Name of Work : Union Parishad (Random Inspection) | Ñ | Ñ | Foundation-G Sandfilling MS rod fabrication Gi KvR PjwQj, Brick chips gRy` wQj¦ | MS rod 60 grade e¨envi Ki‡Z ‡`Lv hvq wKš‘ Specification-G 40 grade aiv n‡q‡Q Specification Abyhvqx 40 grade MS rod e¨env‡ii Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 30.06.2021
Physical Progress : 20 %
Name of Project : GoB Maint
4 | 2020-05-09 | KzwoMÖvg, f‚iæ½vgvix | f‚iæ½vgvix Dc‡Rjv Awdm e¨e¯’vcbv | Ñ | Ñ | Ñ | • Dc‡Rjv cÖ‡KŠkjx‡K cvIqv hvqwb¦ • †Kvb SAE cvIqv hvqwb¦ • Movement Register cvIqv hvqwb¦ • cwi`k©b Register/Book cvIqv hvqwb¦ • nvwRiv LvZvq `ßi cÖav‡bi cÖwZ¯^vÿi †bB¦ • bZzb Dc‡Rjv Kg‡cø· fe‡bi Qv‡`i ‡¯øvc mwVK bv _vKvq Ges g~jfe‡bi Qv‡`i †j‡fj n‡Z wPjv‡KvVvi Qv‡`i †j‡fj bxPz nIqvq e„wó‡Z Qv‡`i cvwb cÖej †e‡M wmwo †e‡q cÖ‡Z¨K †d¬v‡i XzK‡Q¦ mgm¨vwU `ªæZ mgvav‡bi Rb¨ mswkøó‡`i‡K Aby‡iva Kiv n‡jv¦ Awdm e¨ve¯’vcbv `„e©j e‡j cÖZxqgvb n‡jv hv Dbœq‡bi Rb¨ wewfbœ civgk© cÖ`vb Kiv nq¦ | wbw`©ó mg‡q mgvß | nu¨v

## লালমনিরহাট 24-12-2020
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 23/12/2020 | jvjgwbinvU Avw`Zgvix | Name of Work : Construction of 2 Storied Market with 4 Storied Foundation in Saptibarihat. | • Sand Filling in floor. • Brick work. |  | 1st Floor Ges Ground floor Gi Slab casting m¤úbœ Kiv n‡q‡Q¦ Floor -G Sand Gi cwie‡Z© evjygvwU e¨envi Kiv n‡q‡Q¦ PL ch©šÍ Brick work Kiv n‡q‡Q¦ Brick work Gi 2 layer BU wb¤œgv‡bi¦ | • Floor Gi mg~`q evjygvwU Acmvib K‡i Specifioation Abyhvqx 1.2 GdGg Gi evjy fivU Ges PL ch©šÍ m¤úvw`Z 2 layer wb¤œgv‡bi Brick work Acmvi‡bi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date :27-07-2021
Physical Progress : 65%
Name of Project : CRMIDP
2 | 23/12/2020 | jvjgwbinvU Avw`Zgvix | Avw`Zgvix Dc‡Rjv Awdm e¨e¯’vcbv |  |  |  | • Dc‡Rjv cÖ‡KŠkjxi `ß‡ii Awdm e¨e¯’vcbvi wewfbœ wel‡qi g‡a¨ cÖ‡qvRbxq †iwR÷vimg~n, K¨vk ewn I Pjgvb Kv‡Ri bw_ cixÿv wbixÿv Kiv nq ¦ • Dc‡Rjvq Dc‡Rjv cÖ‡KŠkjxmn 14 Rb Kg©KZ©v/Kg©Pvix c`vqb i‡q‡Q, hv‡`i mevB‡K Dcw¯’Z cvIqv hvq¦ • cÖ‡qvRbxq †iwR÷vi mg~‡ni g‡a¨ Movement register, Stock register, Dead Stock register cvIqv hvqwb¦ Receive register update bvB¦ WvK dvBj wbqwgZ †`Lv nq bv¦ • Equipment register h_fv‡e e¨eüZ n‡”Q bv, Asset register e¨envi Kiv nq bv¦ • Dc‡Rjv cÖ‡KŠkjxi iæ‡g cwi”QbœZvi Afve i‡q‡Q¦ mvwe©K Awdm e¨e¯’vcbv m‡šÍvlRbK bq¦ Citizen charter ¯’vcbv Kiv nqwb¦ • nvwRiv LvZvq `ßi/Dc‡Rjv cÖ‡KŠkjxi Aby-¯^vÿi bv _vKvq, cÖwZw`b Aby-¯^vÿi Kivi civgk© cÖ`vb Kiv n‡q‡Q¦ • Pjgvb Kv‡Ri bw_ cixÿv‡šÍ †`Lv hvq bw_i cÎvs‡ki cÎvsKb (c„ôv bs) Kiv nqwb¦ • cÖ‡qvRbxq mKj †iwR÷vi h_vh_fv‡e e¨env‡ii Rb¨ ejv n‡jv¦ Awdm e¨e¯’vcbvi cÖ‡qvRbxq mKj welq¸wj Av‡jvPbv c~e©K myôzfv‡e cÖwZcvj‡bi Rb¨ ejv n‡q‡Q¦
3 | 23/12/2020 | jvjgwbinvU Avw`Zgvix | Avw`Zgvix Dc‡Rjvq Dc‡Rjv Kg‡cø· |  |  | Avw`Zgvix Dc‡Rjvq bewbwg©Z Dc‡Rjv Kg‡cø‡·i njiæg (†d¬v‡i UvBj‡mi KvR Pjgvb) cvwi`k©b Kiv nq¦ †`Lv hvq njiæ‡gi `iRvq Door Seal ivLv nqwb Bnv‡Z e„wói cvwb njiæ‡gi Af¨šÍ‡i Lye mn‡RB XzK‡Z cvi‡e¦ Interior work -G Floor level-G Wooden batten wVK †d¬v‡ii Dc‡iB cÖ`vb Kiv n‡q‡Q hv mn‡RB cvwbi ms¯ú‡k© G‡m bó nIqvi m¤¢vebv i‡q‡Q¦ G Qvov eviv›`vq Floor tiles Gi Slope out side-G bv n‡q inside-G n‡q‡Q, d‡j e„wói cvwb mn‡RB njiæ‡gi †fZ‡i cÖ‡ek Ki‡e¦ | ÎæwUmg~n wWRvBb msµvšÍ nIqvq cÖKí cvwiPvjK g‡nv`‡qi mv‡_ Av‡jvPbvc~e©K cÖ‡qvRbxq e¨e¯’v MÖn‡Yi Rb¨ ejv n‡q‡Q¦
4 | 24/12/2020 | jvjgwbinvU cvUMÖvg | Name of Work : Rehabililation of Bunimare R&H-Awliarhat GC road. | DC | 40mm | KvRwU m`¨ mgvß n‡q‡Q †`Lv hvq¦ Dense Carpeting -Gi thickness cixÿv K‡i 48mm cvIqv ‡Mj¦ Carpeting Gi bg~bv msMÖn KiZ: j¨ve‡iUix‡Z weUywgb extraction Test K‡i weUzwg‡bi cwigvb 4.4% (Specitication 4.5-5.5% by weight) cvIqv †Mj¦ mo‡Ki Surface Ges Shoulder fv‡jv Ae¯’vq †`Lv †Mj¦ | cieZ©x‡Z weUzwgb Content mwVK ivLvi Rb¨ AwaK mZK© _vKvi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 30.11.2020
Physical Progress : 100%
Name of Project : GOBM
5 | 24/12/2020 | jvjgwbinvU nvwZevÜv | Name of Work :Rehabililation of 30m Long PSC Girder Bridge on Barokhata GC- Hatibandha GC Road at Ch.2800m. | MS rod febrication in Slab |  | weª‡Ri Slab casting -Gi Rb¨ MS rod febrication Kiv n‡q‡Q¦ cixÿv‡šÍ Design Abyhvqx mwVK cvIqv †Mj¦ wKš‘ Centering Kv‡R e¨eüZ Props mg~n Ach©vß cÖZxqgvb nq¦ | • ch©vß msL¨K Bulla Post cÖ`vb KiZ: XvjvB‡qi Rb¨ civgk© cÖ`vb Kiv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 06.12.2020
Physical Progress :80 %
Name of Project : FDDRIRP:
6 | 24/12/2020 | jvjgwbinvU nvwZevÜv | Name of Work : mprovement of Pathonbari Utar Parulia Kadors House Road Ch.00-1600 Road ID-152335026 | • ISG • Sub-base • WBM | ISG = 200mm AS = 150mm WBM = 150mm Proportion = 50:50 | mo‡Ki WBM Gi KvR mgvß †`Lv hvq¦ 2wU ¯’v‡b ( †PB‡bR: 500wg. I 600wg.) Sub grade ch©šÍ layer mg~n cixÿv Kiv nq¦ ISG, Base Course Gi thickness h_vµ‡g 200,215wg.wg. AS Gi thickness h_vµ‡g 152,150wg.wg.Ges WBM h_vµ‡g 155, 160 wg.wg. cvIqv hvq¦ WBM Ges AS layer -G DCP Test K‡i CBR cvIqv †Mj h_vµ‡g WBM Gi CBR b~b¨Zg 80% Gi ¯’‡j 36.6% Ges AS layer -Gi b~b¨Zg CBR 30% Gi ¯’‡j 31.9% cvIqv hvq¦ | • m¤ú~Y© WBM loose KiZ: over size Khoa †f‡½ Specifioation Abyhvqx size K‡i Compaction I CBR wbwðZ Kivi Rb¨ wb‡`©k cÖ`vb Kiv n‡q‡Q¦ Ges ÎæwU ms‡kvab bv nIqv ch©šÍ wej cÖ`v‡b wb‡la Kiv n‡q‡Q¦ • wbe©vnx cÖ‡KŠkjx‡K G msµvšÍ cÎ cÖ`vb Kiv n‡q‡Q¦
Completion Date : 10.12.2020
Physical Progress : 70 %
Name of Project : RDRIIP-2

## কুড়িগ্রাম 24-12-2020 (2)
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Nazimkhan GC-Khedabag R&H via Rajarhat road from Ch.8690m-16260m ID No:149772001; | • Earth work •WMM |  | mo‡Ki Shoulder I Side slope -G gvwUi KvR Ges Widening KvR Pjgvb †`Lv hvq¦ Benching I Side slope cwi¯‹vi bv K‡i hÎZÎ gvwUi KvR Kiv n‡”Q †Kvbiæc Compaction Kiv n‡”Q bv¦ Pavement Gi Widening Portion -G WMM aiv _vK‡jI Specification Abyhvqx Zvi gradation wVK †bB Ges 2w`b hveZ †e‡W WMM materials Compaction bv K‡i †d‡j ivLv n‡q‡Q¦ d‡j Specification Abyhvqx OMC bó n‡”Q¦ Specification Abyhvqx 20mm down graded Brickchips 75% _vKv evÂbxq n‡jI ‡e‡W weQv‡bv WMM Gi g‡a¨ †Kvb 20mm down graded Brickchips cvIqv hvqwb Ges Mix Plant -G I †Kvb 20mm down graded Brickchips †`Lv hvqwb¦ Mechanical Mixing Plant -G cÖ‡qvRbxq hš¿cvwZ †`Lv hvqwb¦ Dcw¯’Z wVKv`v‡ii cÖwZwbwa‡K 20mm down graded Brickchips Gi wel‡q ejv n‡j wZwb welqwU Rv‡bb bv g‡g© AewnZ K‡ib¦ | • Side slope cwi¯‹vi K‡i Benching KiZ: gvwUi KvR layer by layer Compaction Ki‡Z ejv n‡q‡Q¦ • Specification Abyhvqx graded materials Øviv WMM Ki‡Z ejv n‡q‡Q¦ • Specification ewn:f‚Z WMM Acmvib c~e©K ms‡kvab Ki‡Z ejv n‡q‡Q¦ • WMM Mixing -Gi Rb¨ cÖ‡qvRbxq mKj hš¿cvwZ mvB‡U Avbvi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 20.04.2021
Physical Progress : 35%
Name of Project : RCIP
2 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Improvement of Chakirpashar UP office at at Vatitari-Kurigram R&H via Singimari GPS road from Ch.00m-1810m ID No:149773006; | ISG Sub-base | ISG = 200mm AS = 150mm Proportion = 50:50 | moKwU‡Z Sub-base Gi KvR m¤úbœ Kiv n‡q‡Q ‡`Lv hvq¦ ISG I AS Gi cyiæZ¡ I Proportion cixÿv Kiv n‡jv¦ †PB‡bR 600wg. I 700wg. G AS -Gi cyiæZ¡ h_vµ‡g 155wg.wg. I 170wg.wg. Ges ISG G Sand Gi cyiæZ¡ cvIqv ‡Mj 200 I 205wg.wg. ¦ Aggregate, Sand Proportion h_vµ‡g 55: 45 I 44: 56¦ DCP Test-G Sub-base-Gi CBR cvIqv ‡Mj b~b¨Zg 30% Gi ¯’‡j 24.4%¦ | • AS Gi layer loose KiZ: cybivq Compaction K‡i CBR 30% Avb‡Z n‡e¦ • Shoulder G gvwUi Kv‡Ri Compaction wbwðZ Ki‡Z n‡e¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 29.06.2020
Physical Progress : 60%
Name of Project : RDRIIP-2
3 | 25/12/2020 | KzwoMÖvg ivRvinvU | Name of Work : Periodic Maintenance of Baddyer Bazar-Kathal bari UP road from Ch.990m-2850m ID No:149774007; | DC | 25mm | Dense Carpeting KvR Pjgvb †`Lv hvq¦ BPC, 60/70 grade -G weUzwgb mvB‡U cvIqv hvq¦ 4wU Pzjvq weUzwg‡bi ZvcgvÎv cixÿv K‡i cvIqv ‡Mj 125,167,177,150 wWwMÖ †m: ch©vß Premixed metarials Stackyard - G †`Lv hvq¦ †PB‡bR 275 wg. Ges 400 wg. G Kv‡c©wUs-Gi cyiæZ¡ cvIqv ‡Mj, 30 wg.wg. Ges 31 wg.wg. Kv‡c©wUs -Gi cyiæZ¡ mwVK _vK‡jI Surface-Gi wdwbwks m‡šÍvlRbK n‡”Q bv¦ | • weUzwg‡bi ZvcgvÎv mwVK ivLvi Rb¨ Riæwi wb‡`©k †`Iqv n‡jv¦ • Top Surface finishing Gi Rb¨ fine aggregate Gi cwigvb e„w× KiZ: h_vh_ ZvcgvÎv eRvq _vK‡Z Compaction Ki‡Z ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 10.01.2021
Physical Progress : 45 %
Name of Project :GOBM
4 | 25/12/2020 | KzwoMÖvg m`i | Name of Work : Rehabilitation of Dharla Bridge Approach-Jatrapur GC road from Ch.00m-6881m ID No:1499522001; | DC Protective work with Block | 40mm | mo‡Ki Pavement Gi KvR mgvß †`Lv hvq¦ †mvìvimn Side Slope -G Protection work(Block placing) Gi KvR mvgvb¨ evKx †`Lv hvq¦ Dense Carpeting-Gi cyiæZ¡ cixÿv K‡i 40 wg.wg.-Gi ¯’‡j 50 wg.wg. cvIqv ‡Mj¦ Shoulder -G †b‡MwUf †¯øvc we`¨gvb¦ | • `ªæZ Protective work mn mg~`q KvR mgvß Kivi Rb¨ ejv n‡q‡Q¦ • Negative Slope ms‡kva‡bi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 13.08.2020
Physical Progress : 90 %
Name of Project : NOBIDEP
5 | 25/12/2020 | KzwoMÖvg m`i | Name of Work : Construction of 90m long PC Girder Bridge on Dharla Bridge Approach-Jatrapur GC road at Ch.2350m ID No:1499522001; |  |  | 2 wU wcqvi Cap ,4wU K‡i 12 wU wcwm MvW©v‡ii KvRmn Ab¨vb¨ KvR Amgvß i‡q‡Q ¦ cÖKí ¯’‡j Rbej, gvjvgvj I Kvh©µg †Zgb cwijwÿZ nqwb¦Kv‡Ri MwZ AZ¨šÍ gš’i¦ | • Kv‡Ri AMÖMwZ Z¡ivwš^Z Kivi Rb¨ †Rvi ZvwM` cÖ`vb Kiv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 13.08.2020
Physical Progress : 45%
Name of Project : CIBRR

## Rangpur.29-10-20
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 29/10/2020Bs | iscyyi I cxiMvQv | Name of Work : Construction of 54.00m Long RCC Girder Bridge on Pirgacha UZHQ - Pawtanahat GC Road Ch. 6+046km under Pirgacha Upazila, Dist: Rangpur. Road ID No : 185732002. | _ | _ | wKQz msL¨K Block Crack ‡`Lv hvq¦ g~j weª‡Ri KvR mgvß¦ G‡cÖv‡Pi cÖ‡UKkb KvR Pjgvb †`Lv hvq¦ cyivZb weª‡Ri Pier I wisevua Ges Artificial Island Gi gvwU AcmviY Kiv nqwb¦ | • Cracked Block ¸‡jv Acmvib Ki‡Z ejv n‡q‡Q ¦ • weª‡Ri wb‡P existing bridge Gi Pier Gi Ask we‡kl I Pile Gi KvR PjvKvjxb Artificial Island Gi gvwU AcmviY KiZ: ch©vß Water way wbwð‡Zi Rb¨ ejv n‡q‡Q¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 20-06-2020
Physical Progress : 90%
Name of Project : CLBUURP
2 | 29/10/2020Bs | iscyyi I cxiMvQv | Name of Work : Improvement of Mirapara Govt. Primary School Connecting Road (Ch: 00-1425m). (School Code-105050804) . | ISG AS WBM | ISG : 200mm AS : 150mm WBM : 150mm CBR (WBM) : 80% CBR (AS) : 30% CBR (ISG) : 8% AS Proportion (Khoa : Sand) = 50:50 | CBR Test done by DCP, AIV at Lab ISG : 240mm AS : 150mm WBM : 160mm CBR (WBM) : 66% CBR (AS) : 31.90% CBR (ISG) : 10.5% AIV : 28% AS Proportion (Khoa : Sand) = 52:48 | WBM Compaction Kg _vKvq cybivq Top Surface loose KiZ: Compaction K‡i 80% CBR Avb‡Z n‡e¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 18-03-2020
Physical Progress : 70%
Name of Project : RDRIIP-2
3 | 29/10/2020Bs | iscyyi I cxiMvQv | GSIDP, mvgvwRK AeKvVv‡gv †bKgvgy` Rv‡g gmwR` | Tiles | aiv wQj 14×10.3 =144.2 et wgt | 24m×12m =288 et wgt (cÖvvq) cvIqv wM‡q‡Q¦ | Kv‡Ri gvb m‡šÍvlRbK | wbw`©ó mg‡q mgvß | nu¨v
Completion Date :
Physical Progress : 100%
Name of Project : GSIDP
4 | 29/10/2020Bs | iscyyi I cxiMvQv | cxiMvQv Dc‡Rjv Awdm e¨e¯’vcbv |  |  |  | • Dc‡Rjv cÖ‡KŠkjxi `ß‡ii Awdm e¨e¯’vcbvi wewfbœ wel‡qi g‡a¨ cÖ‡qvRbxq †iwR÷vimg~n, K¨vk ewn I Pjgvb Kv‡Ri bw_ cixÿv wbixÿv Kiv nq ¦ • Dc‡Rjvq Dc‡Rjv cÖ‡KŠkjxmn (At`vt) 14 Rb Kg©KZ©v/Kg©Pvix c`vqb i‡q‡Q, hv‡`i mevB‡K Dcw¯’Z cvIqv hvq¦ • cÖ‡qvRbxq cÖvq mKj †iwR÷viB e¨eüZ n‡”Q Ges nvjbvMv` i‡q‡Q¦ Asst ‡iwR÷vi Ges Stock ‡iwR÷vi GK‡Î e¨eüZ n‡”Q, hv wfbœ K‡i e¨env‡ii Rb¨ civgk© cÖ`vb Kiv n‡jv¦ • nvwRiv LvZvq `ßi/Dc‡Rjv cÖ‡KŠkjxi Aby-¯^vÿi bv _vKvq, cÖwZw`b Aby-¯^vÿi Kivi civgk© cÖ`vb Kiv n‡q‡Q¦ • Pjgvb Kv‡Ri bw_ cixÿv‡šÍ †`Lv hvq bw_i cÎvs‡ki cÎvsKb (c„ôv bs) Kiv nqwb¦ • Dc‡Rjv cÖ‡KŠkjxi Kvh©vjq KZ©„K e¨eüZ Awdm Kÿmg~‡ni g‡a¨ wnmve kvLv e¨wZZ meMy‡jvB cwi”Qbœ i‡q‡Q¦ wnmve kvLvi KÿwU A‡MvQv‡jv I Acwi¯‹vi _vKvq Zv my›`i I cwi”Qbœfv‡e ¸wQ‡q ivLvi civgk© ‡`Iqv n‡q‡Q¦ • Dc‡Rjv cwil‡`i fe‡bi Qv` I Kvwb©‡k AvMvQv I gqjv _vKvq Zv `ªæZ cwi¯‹v‡ii cÖ‡qvRbxq e¨e¯’v MÖn‡Yi civgk© cÖ`vb Kiv nq¦ | wbw`©ó mg‡q mgvß | nu¨v

## Gaibandha.10-11-20
20 cwi`k©b wUg-Gi cwi`k©b cÖwZ‡e`b
µwgK bs | cwi`k©‡bi ZvwiL | †Rjv I Dc‡Rjv | cwi`k©bK…Z ¯‹x‡gi weeiY (mgvwßi Rb¨ wba©vwiZ ZvwiL, eZ©gvb AMÖMwZ Ges cÖK‡íi bvgmn) | cwi`k©bK…Z ¯‹xgmg~‡ni cwijwÿZ ÎæwU/mgm¨vmg~‡ni eY©bv (cÖ‡hvR¨ †ÿ‡Î my¯úó †¯úwmwd‡Kkb Abyhvqx; †hgb- BC/WBM/WMM/Sub-Base/ISG Gi Thickness/ †Lvqvi mvBR BZ¨vw`) |  |  | ÎæwU ms‡kvab/mgm¨vmg~n mgvav‡bi Rb¨ mycvwikgvjv Ges M„nxZ e¨e¯’vw` | ¯‹xgwU wbw`©ó mg‡q mgvß bv n‡j mgq ea©b h_vh_ KZ©„cÿ n‡Z MÖnY Kiv n‡q‡Q wKbv? (nu¨v/bv) | Frequency Abyhvqx Lab test m¤úv`b Kiv n‡q‡Q wKbv? (nu¨v/bv)
|  |  |  | Item | Design Specification | Field Observation
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 10/11/2020Bs | MvBevÜv m`i | Name of Work : Gaibandha-Laxmipur Road from Ch.00m-5750m. | Dense Carpeting | 25mm | 2wU †PB‡b‡R thickness cixÿv Kiv nq 28mm Ges 26mm cvIqv hvq , Dfq †ÿ‡ÎB Cake form n‡q‡Q¦ BPC, ERL. 60/67 grade Bitumen e¨envi Ki‡Z †`Lv hvq¦ weUzwg‡bi ZvcgvÎv PviwU Pzjvq 142°c , 110°c , 116°c, 139°c cvIqv hvq¦ Mixing tempereture 126°c cvIqv hvq¦ msM„nxZ bg~bv Lab test K‡i Bitumen Content 5.2% (Specificaton : 5-5.5%) cvIqv †Mj¦ Stack yard -G ch©vß Premixed materials Ges weUzwgb ‡`Lv hvq ¦ | • Specificaton Abyhvqx temperature wbqš¿¿‡b AviI mZK© _vKvi Rb¨ ejv n‡q‡Q¦ • mo‡Ki †mvìv‡i ch©vß gvwUi KvR Kiv nqwb¦ `ªæZ †mvìv‡i cÖ‡qvRbxq gvwUi KvR Kivi Rb¨ civgk© ‡`Iqv n‡jv¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 22/10/2020
Physical Progress : 50%
Name of Project : GOBM
2 | 10/11/2020Bs | MvBevÜv m`i | Name of Work : Gaibandha-Laxmipur Road from Ch.5750m-10300m & 10300m-11762m. | Dense Carpeting | 25mm | • wKQz wKQz Chainage -G Patch repair KvR Kiv n‡q‡Q¦ • ch©vß Premixed materials Ges weUzwgb ‡`Lv †Mj ¦ | cÖv°jb Abyhvqx †mvìv‡i ch©vß gvwUi KvR m¤úbœ K‡i Kv‡c©wUs KvR Ki‡Z ejv n‡jv¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 22/10/2020
Physical Progress : 20%
Name of Project : GOBM
3 | 10/11/2020Bs | MvBevÜv m`i | Name of Work : Construction of Extension of Upazila Complex Bhaban and Hall Room. | Upazila Complex Bhaban Hall Room |  | njiæ‡gi Base Casting Pjgvb wQj¦ Extension fe‡bi Base Gi GgGm iW Fabrication Ki‡Z †`Lv hvq¦ | SS eªv‡Ûi MS iW mvB‡U cvIqv hvq Ges D³ MS i‡Wi m‡šÍvlRbK Test report cvIqv hvq¦ gradation Abyhvqx 1/2 BwÂ downgraded stone chips ch©vß bv †`Iqvq, Zv ch©vß cwigvb cÖ`v‡bi wb‡`©k †`Iqv nq¦ F3 Footing -Gi Rvwj‡Z short direcfion -G 1wU iW Kg evauvq Zv ms‡kvab Ki‡Z wb‡`©k †`Iqv nq¦ | wbw`©ó mg‡q mgvß | nu¨v
Completion Date : 29/10/2021
Physical Progress : 20%
Name of Project : Construction of Extension of Upazila Complex Bhaban.
4 | 10/11/2020Bs | MvBevÜv m`i | MvBevÜv m`iv Dc‡Rjv Awdm e¨e¯’vcbv |  |  |  | • Dc‡Rjv cÖ‡KŠkjxi `ß‡ii Awdm e¨e¯’vcbvi wewfbœ wel‡qi g‡a¨ cÖ‡qvRbxq †iwR÷vimg~n, K¨vk ewn I Pjgvb Kv‡Ri bw_ cixÿv wbixÿv Kiv nq ¦ • Dc‡Rjvq Dc‡Rjv cÖ‡KŠkjxmn 16 Rb Kg©KZ©v/Kg©Pvix c`vqb i‡q‡Q, hv‡`i mevB‡K Dcw¯’Z cvIqv hvq¦ wnmve iÿK, Awdm mnKvix I Dc‡Rjv mnKvix cÖ‡KŠkjxi c` k~b¨ i‡q‡Q¦ • Movement Register & Visitor's Register/Book e¨wZZ cÖ‡qvRbxq cÖvq mKj †iwR÷viB e¨eüZ n‡”Q Ges nvjbvMv` i‡q‡Q¦ Citizen charter †`Lv hvqwb¦ • nvwRiv LvZvq `ßi/Dc‡Rjv cÖ‡KŠkjxi Aby-¯^vÿi bv _vKvq, cÖwZw`b Aby-¯^vÿi Kivi civgk© cÖ`vb Kiv n‡q‡Q¦ • Movement Register e¨env‡ii Rb¨ †Rvi ZvwM` cÖ`vb Kiv n‡q‡Q¦ • Visitor's Register/Book ‡Lvjv Ges `ªæZ Citizen charter cÖKvk¨ ¯’v‡b Uvbv‡bvi Rb¨ cigk© cÖ`vb Kiv n‡jv¦ | wbw`©ó mg‡q mgvß | nu¨v