## Page-1
cÖKí ev¯Íevqb cÖwZ‡e`b
[5 empty] | cÖwZ‡e`bKvj t | Ryb/2020Bs
1¦ cÖK‡íi bvg | t | wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí
2¦ Aby‡gv`b ch©vq | t | g~j: GK‡bK KZ…©K 28-11-2017 Bs Zvwi‡L Aby‡gvw`Z¦
1g ms‡kvab: ¯’vbxq miKvi gš¿Yvjq KZ©„K 7/11/2019 Aby‡gvw`Z
3¦ ms¯’v I gš¿Yvj‡qi bvg | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦ ¯’vbxq miKvi wefvM¦ ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq¦
4¦ cÖK‡íi D‡Ïk¨ | t | K) wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY moK Dbœq‡bi gva¨‡g K…wl/ AK…wl A_©bxwZi mÂvjb ¦
L) MÖvgxY RbM‡bi Rb¨ MÖvg, evRvi, ¯^v¯’¨‡K›`ª, wkÿv-cÖwZôvb I Ab¨vb¨ †mev`vbKvix cÖwZôv‡b hvZvqvZ myweav e„w×i gva¨‡g RxebhvÎvi gv‡bvbœqb¦
M) ¯^í I `xN©‡gqv‡` Kg©ms¯’vb m„wó¦
|  |  | g~j | 1g ms‡kvwaZ
5¦ ev¯ÍevqbKvj | t | K) KvR Avi‡¤¢i ZvwiL t RyjvB 2017 |  | RyjvB/2017
|  | L) cÖKí mgvwßi ZvwiL t Ryb 2020 |  | Ryb/2021
|  |  | g~j | 1g ms‡kvwaZ
6¦ cÖv°wjZ e¨q (j¶ UvKvq) | t | †gvU t | 44620 | 48610
|  | UvKv (wRIwe) t | 44620 | 48610
|  | cÖKí mvnvh¨ t | 0
|  | cÖKí mvnv‡h¨i t | 0
(UvKvsk)
7¦ cÖKí mvnv‡h¨i Drm | t | evsjv‡`k miKvi (wRIwe)

## ST_Schm (hidden)
STATUS OF SCHEMES / CONTRACTS IN RRMIMP-2
FINANCIAL YEAR: 2004-2005
#REF!
Sl.No. | Name of Project / Name of | ADP Provision and | No. of Schemes/ | Carried Over | Total | Work Plan Target |  | Scheme | Achivement |  |  |  |  | Physicial | Fund Spent | Remarks
| Development Assistant | Fund Release | Contracts New | Contracts/Excess |  | Last Date for | Last date for | Prepared | Schemes | Tender | Tender | Going on | Schemes | Progress
| Partner's | (GOB+RPA) | Schemes/ | Programme |  | awarding | Commencement |  | Preparation | Called | Evaluation |  | Completed
|  |  | Contract | of Previous |  | Contract |  |  | under |  | under
|  |  |  | year |  |  |  |  | Process |  | Process
|  |  | (No) | (No) | No |  |  |  |  | (No) |  | New+Carried Over |  |  | (GOB+RPA)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Rural Development Project; | 22020 | - | -
| Infrastructure Development : 26 | 6975
(15,520.00+6,500.00)
(0.00+0.00)
|  |  | Prepared by: | ______________ | [6 empty] | _____________________
|  |  |  | (Md. Eaar Uddin) | [6 empty] | (Md. Torab Ali Khan)
|  |  |  | Accounts Officer | [6 empty] | Project Director
|  |  |  | RDP-26, LGED | [6 empty] | RDP-26, LGED

## Page-2
8¦ e¨q (j¶ UvKvq) t
| †gvU | UvKv | cÖKí mvnvh¨ |  | ïé | FY cwi‡kva | gšÍe¨
|  |  | †gvU | UvKvsk (AviwcG)
Dc‡hvR‡bi gva¨‡g Kvh©µg wefv‡Mi ¯§viK bs-20.06.0000.605.14.067.2020/33 ZvwiL: 19 †g 2020‡Z eivÏK…Z 2000.00jÿ UvKv A_© wefvM †_‡K Qvo Kiv nq bvB¦
K) 2019-20Bs A_© erm‡ii GwWwc/AviGwWwc eivÏ¦ | 9000 | 9000 | 0 | 0 | 0
L) 2019-20Bs A_© erm‡ii t Ryb/2020Bs ch©šÍ Aegyw³¦ | 6975 | 6975 | 0 | 0 | 0
M) 2019-20Bs A_© erm‡ii t Ryb/2020Bs ch©šÍ e¨q¦ | 6973.71 | 6973.71 | 0 | 0 | 0
N) cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q | 14219.63 | 14219.63 | 0 | 0 | 0
9¦ cÖKí mvnv‡h¨I UvKvsk e¨q, `vex I cÖvwß (j¶ UvKvq) t cÖ‡hvR¨ bq
PjwZ A_© erm‡ii cÖwZ‡e`bKvj ch©šÍ t
welq | PjwZ A_© erm‡ii |  | µgcywÄf~Z
1¦ e¨q t | 0 |  | 0
2¦ `vexK…Z t | 0 |  | 0
3¦ cÖvwß t | 0 |  | 0

## Page 3
10¦ cÖavb cÖavb As‡Mi j¶¨gvÎv I AMÖMwZ t
GwcÖj/2016Bs¦
As‡Mi bvg |  | wWwcwc Abymv‡i j¶¨gvÎv |  |  |  | c~e©eZ©x erm‡ii Ryb/19 ch©šÍ µgcywÄZ AMÖMwZ |  |  | PjwZ 19-20 A_© erm‡ii j¶¨gvÎv (cwigvb I wWwcwcÕi %) |  |  |  | PjwZ 19-20 A_© erm‡ii cÖwZ‡e`bKvj ch©šÍ AMÖMwZ (cwigvb I eiv‡Ïi %) |  | cÖKí cwiPvjK/ Kg©KZ©v KZ…©K cÖKí GjvKv cwi`k©‡bi ZvwiL | gšÍe¨
|  | ev¯Íe |  | Avw_©K | J­u­VV h¡Ù¹h | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K (j¶ UvKvq) wWwcwc Abymv‡i | J­u­VV h¡Ù¹h | ev¯Íe | Avw_©K (j¶ UvKvq) |  |  | fªhÑha£Ñ j¡p | †g 08
1 |  | 2 |  | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
1¦ ivR¯^ e¨q t
K) Kg©KZ©v‡`i †eZb (4500) |  | 3 Rb |  | 100 |  | 38 Rb | 2 Rb | 17.24 | 36 Rb gvm |  | 17 |  | 36 Rb gvm | 16.5 |  |  | 421.2667 | 54.1667 | #VALUE! | 0.5 | <> Weight of each item |  |  | = | Est. cost of each respective item
[8 empty] | 17.24% |  |  | 17%
L) Kg©Pvix‡`i †eZb (4600) |  | 1 Rb |  | 32 |  | 4 Rb gvm | - | 0.9 | 12 Rb gvm |  | 2.85 |  | 12Rb gvm | 2.84 |  |  | 421.2667 | 54.1667 | #VALUE! | #VALUE! |  |  |  |  | Total cost of all physical item (s)
8.906%
M) fvZvw` (4700) |  | 14 Rb |  | 122 |  | 40 Rb gvm | - | 16.65 | 48 Rb gvm |  | 16 |  | 48 Rb gvm | 15.65 |  |  | 421.2667 | 54.1667 | #VALUE! | #VALUE!
[8 empty] | 13.65% |  |  | 13.11%
N.1) mieivn I †mev (4800) |  | ‡_vK |  | 237 |  | - | - | 76.61 | ‡_vK |  | 53.95 |  |  | 53.57 |  |  | 421.2667 | 54.1667 | #VALUE! | 15.04 | <> Physical percentage of total Project |  |  | = | Weight of each item x % of item.
[8 empty] | 32.32% |  |  | 22.76%
2) nvqvwis PvR© (AvDU‡mvwm©s ÷vd (4893) |  | 10 | Rb | 200 |  | - | - | 49.08 | 120 Rb gvm |  | 38.95 |  | 120 Rb gvm | 38.91
[8 empty] | 24.54% |  |  | 19.48%
O) †givgZ i¶Yv‡e¶Y I cybe©vmb (4900) |  | ‡_vK |  | 31 |  | - | - | 8.69 | ‡_vK |  | 11.25 |  |  | 11.24 |  |  | 421.2667 | 54.1667 | #VALUE! | 11.25
[8 empty] | 28.03% |  |  | 36.29% |  |  |  | 26/06/2020 n‡Z 27/06/2020 ZvwiL cÖKí GjvKv cwi`©kb K‡ib¦ | [6 empty] | 78.5
P) ‡_vK eivÏ (6681) |  | ‡_vK |  |  |  | - | - | - | ‡_vK |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | 0
‡gvU ivR¯^ e¨q |  |  |  | 722 |  | - | - | 169.17 |  |  | 140 |  |  | 138.71
2¦ g~jab e¨qt
K) m¤ú` msMÖn / µq (6800) | [21 empty] | 11205 | 92290816
1) hvbevnb (Rxc Mvox) |  | 1 |  | 90 |  | - | - | 90
100%
2) hvbevnb (wcKAvc f¨vb) |  | 2 |  | 100 |  | - | - | 100
100%
3) hvbevnb (†ivW †ivjvi) |  | 3 |  | 300 |  | - | - | 270
90%
4) †gvUi mvB‡Kj |  | 10 |  | 16.79 |  | - | - | 16.79
100%
5) wbg©vY hš¿cvwZ |  | ‡_vK |  | 80 |  | - | - |  | ‡_vK |  | 45.6 |  |  | 45.6
[11 empty] | 57% |  |  | 100% | [7 empty] | 25409 | 227267608
6) Awdm hš¿cvwZ |  | ‡_vK |  | 15.5 |  | - | - | 13.46 | ‡_vK |  | 0 | [10 empty] | #VALUE! | #VALUE!
[8 empty] | 86.84% |  |  | 0% | [10 empty] | 0
Dc †gvU= |  |  |  | 602.29 |  | - | - | 490.25 |  |  | 45.6 |  |  | 45.6
f~wg AwaMÖnY |  | ‡_vK |  | 30 | [6 empty] | 0
0%
Dc †gvU= |  |  |  | 30
L) wbg©vY I c~Z©KvR (7000)
1) Dc‡Rjv moK Dbœqb |  | 35.66 | wKtwgt | 3031.1 |  | 23 | 3 | 1616 | 12.66 |  | 1044.4 |  | 8.39 | 1044.4 | [7 empty] | 85
[6 empty] | 64.5% | 6.73% | 53.31% | 35.5% |  | 34.46% |  |  | 100% |  |  | 0 | 0 |  | -0.65544
2) BDwbqb moK Dbœqb |  | 45.21 | wKtwgt | 3390.75 |  | 11.05 | 1.05 | 881.5 | 15 |  | 1150 |  | 10.75 | 1150 | [7 empty] | 75
[6 empty] | 24.44% | 2.1% | 26% | 33.18% |  | 33.92% |  |  | 100%
3) MÖvg moK Dbœqb |  | 150.23 | wKtwgt | 11267.25 |  | 26 | 60 | 1736 | 25 |  | 1400 |  | 14 | 1400 | [7 empty] | 75
[6 empty] | 17.31% | 4.62% | 15.41% | 16.64% |  | 12.43% |  |  | 100%
52 (3)
4) Dc‡Rjv mo‡K eªxR/Kvjfv©U wbg©vY |  | 313.06 | wgUvi | 2504.48 |  |  |  |  | 100 |  | 920 |  | 30wgt | 920 | [7 empty] | 8
[9 empty] | 31.94% |  | 36.73%
5) BDwbqb mo‡K eªxR/Kvjfv©U wbg©vY |  | 242 | wgUvi | 1694 |  |  |  |  | 83.33 |  | 0 | [10 empty] | 7
[9 empty] | 34.43% |  | 0%
6) MÖvg mo‡K eªxR/Kvjfv©U wbg©vY |  | 483.5 | wgUvi | 3142.75 |  |  |  |  | 166.67 |  | 0
[9 empty] | 34.47% |  | 0%
7) Dc‡Rjv moK †givgZ |  | 20.54 | wKtwgt | 718.94 |  | 10 | bvB | 500 | 6 |  | 200 |  | 6 | 200 | 26/06/2020ZvwiL †_‡K 27/06/2020 ZvwiL ch©šÍ cÖKí GjvKv cwi`k©b K‡ib¦ | [5 empty] | 35.0019 | 35.0019
[8 empty] | 69.55% | 29.21% |  | 27.82% |  |  | 100%
8) BDwbqb moK †givgZ |  | 25.22 | wKtwgt | 882.84 |  | 8 |  | 500 | 8 |  | 300 |  | 3 | 300
[8 empty] | 56.64% | 31.72% |  | 33.98% |  |  | 100% | [7 empty] | 463.4
9) MÖvg moK ‡givgZ |  | 37.93 | wKtwgt | 1137.75 |  |  |  |  | 20 |  | 500 |  | 12 | 500
[8 empty] | 0% | 52.73% |  | 43.95% |  |  | 100%
10) Awdm feb m¤úªmvib |  | 1 | wU | 300 |  |  |  |  | 0 |  | 0
[9 empty] | 0% |  | 0%
11) moK cÖk¯ÍKiY |  | 20.41 | wKtwgt | 816.4 |  | 10 |  | 353 | 7 |  | 300 |  | 4 | 300
[8 empty] | 43.24% | 34.3% |  | 36.75% |  |  | 100%
12) Aviwmwm moK (mvegviwRej) |  | 71.01 | wKtwgt | 9586.35 |  | 11 |  | 1000 | 15 |  | 625 |  | 11 | 625
[8 empty] | 10.43% | 21.12% |  | 6.52% |  |  | 100%
13) ¯‹zj ms‡hvM moK (Dc‡Rjv,BDwbqb I MªvgxY moK) |  | 106 | wKtwgt | 7632 |  |  |  |  | 37.33 |  | 200 |  |  | 200
[9 empty] | 35.22% |  | 2.621% |  |  | 100%
14) nvU/evRvi |  | 9 | wU | 360 |  |  |  |  | 3 |  | 150 |  | 2wU | 150
[9 empty] | 33.33% |  | 41.67% |  |  | 100%
Dc †gvU= |  |  |  | 46464.61 |  |  |  | 6586.5 | 0 |  | 6789.4 |  |  | 6789.4
15) wmwU f¨vU |  | ‡_vK |  | 1 |  |  |  |  | 0 |  | -
M) wdwRK¨vj Kw›Ub‡RÝx (7980) |  | - |  | 400 |  |  |  |  | - |  | 0
N) cÖvBm Kw›Ub‡RÝx (7980) |  | - |  | 390.1 |  |  |  |  | - |  | 0
Dc †gvU= |  |  |  | 791.1 | #DIV/0! | [5 empty] | 6835 |  |  | 6835
‡gvU = |  | 1560.77 |  | 48610 | #DIV/0! |  |  | 7245.92 | 498.99 |  | 6975 | 0 |  | 6973.71 |  | 8.58 | #REF! | #REF! |  | #REF!
[6 empty] | 25% | 5% | 14.91% | 31.97% |  | 14.35% | #DIV/0! | 100% | 99.98% | [7 empty] | 1.29
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z †fŠZ AMÖMwZ (%) | t | 70% | [19 empty] | 2 | 64.81 | -62.81
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z Avw_©K AMÖMwZ (%) | t | 35% | [19 empty] | 1764 | 4514.4 | -2750.4
11¦ we`¨gvb mgm¨v | t | Lvj/wej/b`x _vKvq ‡cÖv‡UKvUf IqvK© Gi Kvi‡b wWwcwc †Z wbavwiZ e¨‡qi ‡P‡q AwaK e¨q n‡”Q¦ | [19 empty] | 1766 | 4579.21 | -2813.21
12¦ mycvwik | t | [12 empty] | (mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí
62, cwðg AvMviMvuI, GjwRBwW, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210
52 (4)
|  |  | ivR¯^ e¨q = | 722 |  |  |  |  | ivR¯^ e¨q = |  | 101.05 |  | ivR¯^ e¨q = | 99.8
|  |  | g~jab e¨q = | [5 empty] | g~jab e¨q = |  |  |  | g~jab e¨q =
|  |  | m¤ú` msMÖn = | 602.29 |  |  |  |  | m¤ú` msMÖn = |  | 45.6 |  | m¤ú` msMÖn = | 45.6
|  |  | wbg©vY I c~Z© KvR = | 46464.61 |  |  |  |  | wbg©vY I c~Z© KvR = |  | 4664.4 |  | wbg©vY I c~Z© KvR = | 5289.4
|  |  | Kw›Ub‡RwÝ = | 791.1 |  |  |  |  | Kw›Ub‡RwÝ = |  | 0 |  | Kw›Ub‡RwÝ = | 0
|  |  |  | 47858 | [6 empty] | 4710 |  |  | 5335
|  |  | me©‡gvU = | 48580 |  |  |  |  | me©‡gvU = |  | 4811.05 |  | me©‡gvU = | 5434.8
63.72
1.12
1.7577
0.027585

## Org-Prog
evwl©K Dbœqb Kg©m~Px (2019-2020)
K) gš¿Yvjq / wefvM |  | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq / ¯’vbxq miKvi wefvM
L) ms¯’vi bvg |  | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
M) cÖwZ‡e`b Kvj (gvm) |  | t | Ryb/2020Bs
(j¶ UvKvq)
µwgK bs | †KvW I cÖK‡íi bvg (cÖKí e¨q I ev¯ÍevqbKvj) | Aby‡gv`‡bi ch©vq | GwWwcÕi c„ôv bs I µwgK bs | PjwZ (2019-20) A_© erm‡ii evwl©K Dbœqb Kg©m~Px‡Z eivÏ |  |  |  | Aegyw³ |  |  |  | e¨q |  |  |  | cÖKí mvnv‡h¨i UvKvsk |  | AMÖMwZ (%) |  |  |  | cÖKí mvnv‡h¨i Drm | gšÍe¨
[18 empty] | †fŠZ |  | Avw_©K
|  |  |  | †gvU | UvKv | cÖKí mvnvh¨ |  | †gvU | UvKv | cÖKí mvnvh¨ |  | †gvU | UvKv | cÖKí mvnvh¨ |  | `vexK…Z | cÖvwß | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK) | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK)
[6 empty] | †gvU | UvKvsk |  |  | †gvU | UvKvsk |  |  | †gvU | UvKvsk
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 21 | 22 | 17 | 18 | 19 | 20 | 23 | 24
Dc‡hvR‡bi gva¨‡g Kvh©µg wefv‡Mi ¯§viK bs-20.06.0000.605.14.067.2020/33 ZvwiL: 19 †g 2020‡Z eivÏK…Z 2000.00jÿ UvKv A_© wefvM †_‡K Qvo Kiv nq bvB¦
52 | wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí¦ cÖKí e¨qt 48610.00 j¶ UvKv ev¯ÍevqbKvjt RyjvB/2017 - Ryb/2021 | Aby‡gvw`Z | c„ôv bs- 98 I 99, µwgK-52 | 9000 | 9000 | 0 | 0 | 6975 | 6975 | 0 | 0 | 6973.71 | 6973.71 | 0 | 0 | 0 | 0 | 25% | 25% | 25% | 25% | wRIwe
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí
62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210

## IMED-05 (Part-A)
Progress Report of On-going Development Projects/Operational Plan( Format 05/2009)
Reporting Period: |  | 2020-06-01 | [11 empty] | (All financial figures in Lakh Tk)
Part-A: Monthly Report
Ministry |  | : | Local Government, Rural Development & Cooperatives
Division |  | : | Local Government Division
Organization |  | : | Local Government Engineering Department (LGED)
1 | Name of the Project /Operational Plan : |  |  |  | Sirajgonj District of Important Rural Infrastructure Development Project
2 | Objectives of the Project/Operational : Plan (in Brief) |  |  |  | • Overall improvement of the transportation network to facilitate production and marketing of agricultural and non- agricultural products and socio-economic development of the project area. • To remove physical bottlenecks and reduce costs of rural transportation and marketing. • Create both short term and long term employment opportunities.
3 | Location of the Project/Operational Plan : |  |  |  | Division |  | District |  | Upazila
[5 empty] | Rajshahi |  | Sirajgonj |  | Sadar, Shajhadpur, Belkuchi, Ullapara, Tarash, Kamarkhando, Kazipur, Raiganj Chouhali (9 Upazilas)
4 | Project Approval Status & Cost :
| DPP/TPP | Date of approval |  |  | Implementation period |  |  | Total Cost |  |  | GOB |  | Project Aid (RPA)
| i. Original | 2017-05-16 |  |  | July'17 - June'20 |  |  | 44620 |  |  | 44620 |  | -
| ii. 1st Revised | 2018-07-11 |  |  | July'17 - June'21 |  |  | 48610 |  |  | 48610 |  | -
5 | Progress of Fund Release:
| Quarter-wise | Date of | [7 empty] | Amount Released |  | Date of issue of Cheque from CAO (in case of Autonomous body)
|  | Proposal Sending to Ministry/Division |  |  | Issue of order by Ministry |  | Issue of order from Finance Division
| 1 | 2 |  |  | 3 |  | 4 |  |  | 5 |  | 6
| 1st quarter | - |  |  | - |  | - |  |  | 1750
| 2nd quarter | - |  |  | - |  | - |  |  | 1750
| 3rd quarter | - |  |  | - |  | - |  |  | 1750
| 4th quarter | - |  |  | - |  | - |  |  | 1725
| RPA authorization | - |  |  | - |  | - |  |  | -
| Total | [8 empty] | 6975
6 | Target and Achievement of the main Components of the Project :
| Name of Important Components (With quantity) | Cost as per DPP/TPP | Achievement upto last June/19 |  |  | Revised Target of current year |  |  | Progress uptoJune/20 (the reporting month of current year) |  |  | Unspent /unfinished balance against DPP targets
|  |  | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical
|  |  | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component)
|  |  | b) Taka |  |  | b) Taka |  |  | b) Taka |  |  | b) Taka
| 1 | 2 | 3 |  | 4 | 5 |  | 6 | 7 |  | 8 | 9 |  | 10
1) Revenue :
| a) Pay of Officers | 100 | a) | 17.24 | 2 | a) | 17 | 0 | a) | 16.5 | 0 | a) | 66.26 | 66.26%
|  |  | b) | 17.24 | 16.42% | b) |  | 17% | b) | 16.5 | 0% | b)
| b) Pay of Establishment | 32 | a) | 0.9 | - | a) | 2.85 | 0 | a) |  | 12Rb gvm | a) | 28.26 | 88.31%
|  |  | b) | 0.9 | 0% | b) |  | 8.906% | b) | 2.84 | 0% | b)
| c) Allowances | 122 | a) | 16.65 | - | a) | 16 | 0 | a) | 15.65 | 48 Rb gvm | a) | 89.7 | 73.52%
|  |  | b) | 16.65 | 13.55% | b) |  | 13.11% | b) | 15.65 | 0% | b)
| d) Supplies and Services | 237 | a) | 76.61 | - | a) | 53.95 | LS | a) | 53.57 | 0 | a) | 106.82 | 45.07%
|  |  | b) | 76.61 | 8.08% | b) |  | 0% | b) | 53.57 | 3891% | b)
| e) Highering charge (Outsorcing) | 200 | a) | 49.08 | - | a) | 38.95 | 0 | a) | 38.91 | 120 Rb gvm | a) | 112.01 | 56.01%
|  |  | b) | 49.08 | - | b) |  |  | b) | 38.91 | 120 Rb gvm | b)
| f) Repair, Maintenance and Rehabilitation | 31 | a) | 8.69 | - | a) | 11.25 | LS | a) | 11.24 | 0 | a) | 11.07 | 35.71%
|  |  | b) | 8.69 | 100% | b) |  | 36.29% | b) | 11.24 | 0% | b)
2) Capital :
| a) Jeep | 90 | a) | 90 | - | a) | 0 |  | a) | 0 | 0 | a) | 90 | 100%
|  |  | b) |  | 0 | b) |  |  | b) | 0 | 0% | b)
| b) Pick-up | 100 | a) | 100 | - | a) | 0 |  | a) | 0 | 0 | a) | 100 | 100%
|  |  | b) |  | 0 | b) |  |  | b) | 0 | 0% | b)
| c) Road Roller | 300 | a) | 270 | - | a) | 0 |  | a) | 0 | 0 | a) | 300 | 100%
|  |  | b) |  | 0 | b) |  |  | b) | 0 | 0% | b)
| d) Motorcycle | 16.79 | a) | 16.79 | - | a) | 0 |  | a) | 0 | 0 | a) | 0 | 0%
|  |  | b) | 16.79 | 0 | b) |  |  | b) | 0 | 0% | b)
| e) Construction Equipment | 80 | a) |  | - | a) | 45.6 |  | a) |  | 0 | a) | 80 | 100%
|  |  | b) |  | 0 | b) |  |  | b) |  | 0% | b)
| f) Office Equipment | 15.5 | a) | 13.46 | - | a) | 0 |  | a) | 0 | 0 | a) | 2.04 | 13.16%
|  |  | b) | 13.46 | 0 | b) |  |  | b) | 0 | 0% | b)
| g) Acquisition of Assets | 30 | a) |  | - | a) | 0 | LS | a) |  | 0 | a) | 30 | 100%
|  |  | b) | 0 | 0% | b) |  | 0% | b) | 0 | 0% | b)
b) Civil Works :
| 1) Construction of Upazila Road | 3031.1 | a) | 1616 | 3.00km | a) | 1044.4 | 12.66 | a) | 1044.4 | 8.39 | a) | 370.7 | 12.23%
|  |  | b) | 1616 | 6.73% | b) |  | 35.5% | b) | 1044.4 | 0% | b)
| 2) Construction of Union Road | 3390.75 | a) | 881.5 | 1.05km | a) | 1150 | 15 | a) | 1150 | 10.75 | a) | 1359.25 | 40.09%
|  |  | b) | 881.5 | 2.1% | b) |  | 33.18% | b) | 1150 | 0% | b)
| 3) Construction of Village Road | 11267.25 | a) | 1736 | 6.00km | a) | 1400 | 25 | a) | 1400 | 14 | a) | 8131.25 | 72.17%
|  |  | b) | 1736 | 4.615% | b) |  | 16.64% | b) | 1400 | 0% | b)
| 4) Construction of Bridge on Upazila Road | 2504.48 | a) |  | 0% | a) | 920 | 100 | a) |  | 30wgt | a) | 1584.48 | 63.27%
|  |  | b) | 0 | 0% | b) |  | 31.94% | b) | 920 | 0% | b)
| 5) Construction of Bridge on Union Road | 1694 | a) |  | 0 | a) | 0 | 83.33 | a) |  | 0 | a) | 1694 | 100%
|  |  | b) | 0 | 0% | b) |  | 34.43% | b) | 0 | 0% | b)
| 6) Construction of Bridge on Village Road | 3142.75 | a) |  | 0 | a) | 0 | 166.67 | a) |  | 0 | a) | 3142.75 | 100%
|  |  | b) | 0 | 0% | b) |  | 34.47% | b) | 0 | 0% | b)
| 7) Repair of Upazila Road | 718.94 | a) | 500 | 0% | a) | 200 | 6 | a) | 200 | 6 | a) | 18.94 | 2.634%
|  |  | b) | 500 | 0% | b) |  | 29.21% | b) | 200 | 300% | b)
| 8) Repair of Union Road | 882.84 | a) | 500 | 0% | a) | 300 | 8 | a) | 300 | 3 | a) | 82.84 | 9.383%
|  |  | b) | 500 | 2.1% | b) |  | 31.72% | b) | 300 | 0% | b)
| 9) Repair of Village Road | 1137.75 | a) |  | 0% | a) | 500 | 20 | a) |  | 0 | a) | 1137.75 | 100%
|  |  | b) |  | 4.615% | b) |  | 52.73% | b) |  | 0% | b)
| 10) Widening | 816.4 | a) | 353 | 0% | a) | 300 | 0 | a) |  | 0 | a) | 463.4 | 56.76%
|  |  | b) | 353 | 0% | b) |  | 0% | b) |  | 0% | b)
| 11) RCC Road (Sub-Mersible) | 9586.35 | a) | 1000 | 0 | a) | 625 | 15 | a) | 625 | 11 | a) | 7961.35 | 83.05%
|  |  | b) | 1000 | 0% | b) |  | 21.12% | b) | 625 | 0% | b)
| 12) School Connecting Road | 7632 | a) |  | 0 | a) | 200 | 37.33 | a) |  | 2wU | a) | 7482 | 98.03%
|  |  | b) | 0 | 0% | b) |  | 33.33% | b) | 150 | 0% | b)
| 13) Office Building | 300 | a) |  | 0 | a) | 0 | 0 | a) |  | 0 | a) | 300 | 100%
|  |  | b) | 0 | 0% | b) |  | 0% | b) | 0 | 0% | b)
| 14) Groth center/Village Hat | 360 | a) |  | 0 | a) | 150 | 3 | a) |  | 2wU | a) | 360 | 100%
|  | 0 | b) | 0 | 0% | b) |  | 33.33% | b) | 0 | 0% | b)
| CD Vat | 1 | a) |  | 0% | a) |  |  | a) |  | 0 | a) | 1 | 100%
|  |  | b) |  | 0% | b) |  |  | b) |  | 0% | b)
| Physical Contingency | 400 | a) |  | 0% | a) | 0 |  | a) |  | 0 | a) | 400 | 100% | 0.73845 | 12714.03
|  |  | b) | 0 | 0% | b) |  | 0 | b) | 0 | 0% | b)
| Price Contingency | 390.1 | a) |  | 0% | a) | 0 |  | a) |  | 0 | a) | 390.1 | 100%
|  |  | b) | 0 | 0% | b) |  | 0 | b) | 0 | 0% | b)
| Grand Total : | 48610 | 7245.92 |  |  | 6975 |  |  | 6973.71 |  | 99.98% | 35895.97 |  | 73.84% | 41636.29 | 43141.89
41636.29
7 | Progress of Procurement in current FY: 2019-20
[7 empty] | Goods |  | Works |  | Services |  | Total
| a) Work Orders (WO) issued in last year or before | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| i) Number of WOs. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| ii) Expenditure in current FY | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| b) Work Orders (WO) issued during the reporting period, 2019-20. | [7 empty] | 0 |  | 0 |  | 0
| i) Number of WOs. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| ii) Expenditure in current FY. | [5 empty] | 460 |  | 5360 |  | 0 |  | 5820
| c) WOs to be issued during the rest of the period of the FY. 2019-20 | [5 empty] | 90 |  | 1400 |  | 21.77 |  | 1511.77
| d) Total expenditure for procurement up to reporting month, 2019-20 (a ii + b ii). | [5 empty] | 460 |  | 5360 |  | 0 |  | 5820
| e) Total budget/allocation for procurement, 2019-20. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| f) Cumulative expenditure upto last year. | [5 empty] | 460 |  | 5360 |  | 0 |  | 5820
| g) Total allocation as per DPP/TPP. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| h) Unspent amount as per DPP/TPP. | [13 empty] | -6975 | Balance
8 | Particulars of reimbursement claim and receipts :
| Initial advance Receipt with date | Upto 30/06/2019 | [6 empty] | During 2019-20
|  | Expenditure |  |  |  | Reimbursement in claimed |  |  | Expenditure |  |  |  | Reimbursement
|  | Direct payment |  | Payment from project account |  |  |  |  | Direct payment |  | Payment from project account
| 1 | 2 |  | 3 |  | 4 |  |  | 5 |  | 6 |  | 7
Sushanto Kumar Paul
Project Director
Phone No: 8144210.

## Status Rpt
Scheme Status Report
Sirajgonj District of Important Rural Infrastructure Development Project
Local Government Engineering Department (LGED)
Financial Year : 2019-2020
Reporting Period : | 2020-06-01
(Taka in Lakh)
Name of the project (name of Development Assistance partner) | (ADP Provision) & Total Fund Released (GOB + RPA) (Tk.) | No. of Scheme / Contracts |  |  | Work Plan Target |  | Achievement | [5 empty] | Physical Progress (%) | Total Fund Spent (GOB + RPA) | Remarks
|  | New Schemes/ Contracts (No.) | Carried Over Contracts/ Excess Programmes of Previous Year (No.) | Total (No.) | Last Date for Awarding Contract | Work Plan Target (No.) | Schemes Prepared (No.) | Schemes Preparation under process (No.) | Tender Called (No.) | Tender Evaluation under process (No.) | Works going on (No.) | Schemes Completed (No.)
Improvement of Important Rural Infrastructure of Sirajgonj District Project | 6975 | 137Nos. | 0 | 38 Nos. | - | 100 | 20 | 5 | - | 13 | 50 | - | 100% | 6973.71
6975
(6975+0)
6975
Sushanto Kumar Paul
Project Director
Phone No: 8144210.

## Purchase
µq msµvšÍ Z_¨vejx t 2019-20 A_© eQ‡ii AMÖMwZ (Ryb/2020ch©šÍ)
(j¶ UvKvq)
µwgK bs | cÖK‡íi bvg | cb¨ |  |  |  |  | c~Z© |  |  |  |  | †mev |  |  |  |  | K) wmwW f¨vUmn µqLv‡Z †gvU eivÏ (2019-20) L) wmwW f¨vU | K) wmwW f¨vUmn µqLv‡Z †gvU e¨q L) wmwW f¨vU | µqLv‡Z Ae¨wqZ eivÏ (2019-20) | †gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
|  | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v
|  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
52 | wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí¦ | 137wU | 5820 | - | 5062.5 | 196wU | 137wU | 5820 | 59wU | 6789.4 | 59wU | 2wU | 5820 | - | 0 | 59wU |  |  | 1646.54 | 6975 | 53.34%
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí
62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210

## Modified_form
2019-2020 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq GwWwcf~³ ev¯Íevqbvaxb cÖKímg~‡ni AMÖMwZi ch©v‡jvPbv QK-1
gv‡mi bvgt Ryb/2020
ms¯’v t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
(j¶ UvKvq)
µt bs | cÖK‡íi bvg (†gqv`Kvj) | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ e¨q | Aby‡gvw`Z wWwcwc/AviwWwcwcÕi Procurement Plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2019-2020 evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄf~Z c~bf©iY e¨q ( Ryb /19 ch©šÍ) L) †gvU cybf©iY e¨q (19-20 GwWwc) M) †gvU cybf©iY `vex †ck (19-20 AviGwWwc) N) †gvU cybf©iY cvwß (19-20 GwWwc) | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/ AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | AvM÷, 19 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Erm
[6 empty] | 2019-2020 GwWwc eivÏ | 2019-2020 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`k cÖ`vb, Avw_©K I †fŠZ j¶¨gvÎv AwR©Z bv nIqvi KviY (19-20 GwWwc)
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q/AMÖMwZ (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ (19-20 GwWwc) |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q (19-20 GwWwc)
|  | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | j¶¨gvÎv (%) | AMÖMwZ (%) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) |  |  | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | % | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | eQi/gvm
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
52
| wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí¦ ev¯ÍevqbKvj t 01-07-2017 nB‡Z 30-06-2021 ch©šÍ | 48610 | 7245.92 | 651/43235.40 | Õ0/0.00 | 6975 | 0 | 6975 | 0 | 6973.71 |  |  | (200/6750.00) | (163/6750.00) | (11/5000.00) | 159/6498.93 |  | N/A | 14219.63 |  | 34110.00 (70.17%)
29.25%
|  | 48610 | 7245.92 | 10/581.50 | (0/0.00) | 6975 | 0 | 6975 | 0 | 6973.71 | 25% | 30% | 4/500 | 4/230 | (0/0.00) | 4/500 |  | N/A | 14219.63 | 70% | 34110.00 (70.17%) | 12 gvm | wRIwe
|  | (-) | (-) | 640/42503.90 | (0/0.00) | (-) | (-) | (-) | (-) | (-) |  |  | (200/6750.00) | (163/6750.00) | (11/5000.00) | (112/3187.58) |  | N/A | (-) |  | (-)
|  | (-) | (-) | 1/150.00 | (0/0.00) | (-) | (-) | (-) | (-) | (-) |  |  | (2/80.00) | (2/80.00) | (0/0.00) | (2/42.50) |  | N/A | (-) |  | (-)
me©‡gvU |  | 48610 | - | 651/43235.40 | - | 6975 | 0 | 6975 | 0 | 6973.71 | 25% | 30% | (200/6750.00) | (163/6750.00) | (11/5000.00) | (112/3187.58) |  |  | 14219.63 | 70% | 34110.00 (70.17%) | 1 eQi 9 gvm | wRIwe
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ †Rjvi ¸iæZ¡c~Y© MÖvgxY AeKvVv‡gv Dbœqb cÖKí
[19 empty] | 62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦ |  |  |  |  | (mykvšÍ Kzgvi cvj)
[19 empty] | ‡dvb b¤^it 8144210 |  |  |  |  | cÖKí cwiPvjK
‡dvb-8144210

## Sheet1
1) Dc‡Rjv moK Dbœqb | 59.5 | wKtwgt | 4760 | 2.5 | 44.85
2) BDwbqb moK Dbœqb | 178.51 | wKtwgt | 11603.15
3) MÖvg moK Dbœqb | 345.1 | wKtwgt | 22431.5 | 1.7 | 25.15
4) Dc‡Rjv mo‡K exR wbg©vY | 254.5 | wgUvi | 1527 | 14.91 | 16.5
5) BDwbqb mo‡K exR wbg©vY | 315.6 | wgUvi | 1893.6 | 6.5 | 40
6) MÖvg mo‡K exR wbg©vY | 543 | wgUvi | 3258 |  | 3
7) NvUjv | 7 | wU | 105 |  | 500
8) nvU/evRvi | 12 | wU | 180
9) ‡RwV | 5 | wU | 75
10) moK ‡givgZ I eÿYv‡eÿY | 78 | wKtwgt | 1560 | 164 | 1200
11) moK wbivcËv | ‡_vK |  | 400 | 82 | 575
|  |  | 47793.25 | 216 | 770
|  |  |  | 487.61 | 3174.5