## Page-1
cÖKí ev¯Íevqb cÖwZ‡e`b
[6 empty] | cÖwZ‡e`bKvj t | Ryb/2020Bs
1¦ cÖK‡íi bvg | t | wkeMÄ †cŠimfvi †fŠZ AeKvVv‡gv Dbœqb cÖKí¦ (‡Rjv-e¸ov)
2¦ Aby‡gv`b ch©vq | t | K) g~jt wWwcwc-03/11/2018Bs Zvwi‡L gvbbxq cwiKíbv gš¿x KZ…©K Aby‡gvw`Z¦
1g ms‡kvab: wWwcwc-13/05/2020Bs Zvwi‡L gvbbxq cwiKíbv gš¿x KZ…©K Aby‡gvw`Z¦
L) FY Pzw³ ¯^v¶i - cÖ‡hvR¨ b‡n¦
M) FY Kvh©vKwiZv - cÖ‡hvR¨ b‡n¦
N) Dc‡`óv dvg© - cÖ‡hvR¨ b‡n¦
3¦ ms¯’v I gš¿Yvj‡qi bvg | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦ ¯’vbxq miKvi wefvM¦ ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq¦
4¦ cÖK‡íi D‡Ïk¨ | t | ‡gŠwjK bvMwiK Pvwn`v wgUv‡bvi D‡Ï‡k¨ Acwinvh© AeKvVv‡gv wbg©v‡Yi gva¨‡g †cŠimfvi cwi‡ek Dbœqb;
¯^í I `xN© †gqv`x Kg©ms¯’v‡bi my‡hvM m„wói gva¨‡g `vwi`ª `~ixKiY¦
5¦ ev¯ÍevqbKvj | t
|  | g~j |  | 1g ms‡kvwaZ
K) KvR Avi‡¤¢i ZvwiL | t | AvM÷ 2018Bs |  | AvM÷ 2018Bs
Ryb 2018
L) cÖKí mgvwßi ZvwiL | t | wW‡m¤^i 2020Bs |  | Ryb 2021Bs
wWwcwc
6¦ cÖv°wjZ e¨q (j¶ UvKvq) | t | †gvU | t | g~j: 4498.00 jÿ | 1g ms‡kvwaZ: 4997.00jÿ
|  | UvKv | t | g~j: 4498.00 jÿ | 1g ms‡kvwaZ: 4997.00jÿ
|  | cÖKí mvnvh¨ | t | -
|  | cÖKí mvnv‡h¨i | t | -
(UvKvsk)
7¦ cÖKí mvnv‡h¨i Drm | t | evsjv‡`k miKvi (wRIwe)

## Page-2
8¦ e¨q (j¶ UvKvq) t
| †gvU | UvKv | cÖKí mvnvh¨ |  | ïé | FY cwi‡kva | gšÍe¨
|  |  | †gvU | UvKvsk (AviwcG)
K) 2019-20Bs A_© erm‡ii GwWwc eivÏ | 2200 | 2200 | 0 | 0 | 0 | 0 | Dc‡hvR‡bi gva¨‡g Kvh©µg wefv‡Mi ¯§viK bs-20.06.0000.605.14.067.2020/33 ZvwiL: 10 Ryb 2020‡Z eivÏK…Z 700.00jÿ UvKv A_© wefvM †_‡K Qvo Kiv nq bvB¦
L) 2019-20Bs A_© erm‡ii t Ryb/2020Bs ch©šÍ Aegyw³¦ | 1500 | 1500 | 0 | 0 | 0 | 0
M) 2019-20Bs A_© erm‡ii t Ryb/2020Bs ch©šÍ e¨q¦ | 1499.85 | 1499.85 | 0 | 0 | 0 | 0
N) cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q | 2499.85 | 2499.85 | 0 | 0 | 0 | 0
9¦ cÖKí mvnv‡h¨i UvKvsk e¨q, `vex I cÖvwß (j¶ UvKvq) t cÖ‡hvR¨ bq¦
PjwZ A_© erm‡ii cÖwZ‡e`bKvj ch©šÍ t
welq | PjwZ A_© erm‡ii |  | µgcywÄf~Z
1¦ e¨q t | 0 |  | 0
2¦ `vexK…Z t | 0 |  | 0
3¦ cÖvwß t | 0 |  | 0

## Page-3
10¦ cÖavb cÖavb As‡Mi j¶¨gvÎv I AMÖMwZ t
As‡Mi bvg | wWwcwc Abymv‡i j¶¨gvÎv |  |  | c~e©eZ©x erm‡ii Ryb/19 ch©šÍ µgcywÄZ AMÖMwZ |  |  | PjwZ 2019-20 A_© erm‡ii j¶¨gvÎv (cwigvb I wWwcwcÕi %) |  |  |  | PjwZ 2019-20 A_© erm‡ii RyjvB/2019 ch©šÍ AMÖMwZ (cwigvb I eiv‡Ïi %) |  |  | cÖKí cwiPvjK/Kg©KZ©v KZ…©K cÖKí GjvKv cwi`k©‡bi ZvwiL | gšÍe¨
| ev¯Íe | Avw_©K | J­u­VV h¡Ù¹h | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K (j¶ UvKvq) wWwcwc Abymv‡i | J­u­VV h¡Ù¹h | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K (j¶ UvKvq) |  |  | fªhÑha£Ñ j¡p | †g 08 |  |  |  |  | Kg©KZ©v‡`i †eZb (4b) |  | Kg©Pvixi †eZb (4b) |  | Kg©KZ©v/ Kg©Pvixi |  | mieivn I †mev (4800) | ‡givgZ i¶bv‡e¶Y I c~b©evmb (4800) |  |  | 4 Kjvg Gi nvd 8bs Kjv‡g | 4 Kjvg Gi nvd 8bs Kjv‡g
1 | 2 | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 |  | 9 | 10 | 11 | [10 empty] | fvZvw` (8b) |  | 4800 | 4900 | 8+4 | 9+5
1¦ ivR¯^ | [21 empty] | 0.7972 |  | 0.40485 |  | 1.2392 |  | 0.52799 | 4.735
mieivn I †mev (4800) | [20 empty] | 2
M¨vm/R¦vjvbx | ‡_vK | 2 | [6 empty] | 0
‡c‡Uªvj I jyweª‡KÈ | ‡_vK | 2 | [6 empty] | 0
K) ‡ókbvix, mxj I ó¨v¤ú | ‡_vK | 2 |  |  |  | 1 | ‡_vK |  | 1 |  |  |  | 2 |  |  | 421.2667 | 54.1667 | #VALUE! |  | -1 | 2.58 | 6 | gvm | 6 |  | 6 |  | 6 | 0 | 0 | 3 | 0 | 0.5
|  |  | 0.00044464 | [5 empty] | 50% | [12 empty] | 4.7832 |  | 2.4291 |  | 7.4353 |  | 0.68728 | 4.735 | 0% | 0% | 0 | 0
cÖPvi I weÁvcb | ‡_vK | 1 | [6 empty] | 1
KÝvj‡UwÝ | ‡_vK | 35 |  |  |  | 2 | ‡_vK |  | 18 |  |  |  | 17.85
51.43%
mve-m‡qj Bb‡fwó‡Kkb | msL¨v | 2 | [6 empty] | 1 |  |  |  | 1
mv‡f© | msL¨v | 3 | [6 empty] | 1 |  |  |  | 1
m¤§vbxfvZv/wd/cvwikÖwgK | ‡_vK | 1
Kw¤úDUvi mvgMÖx | ‡_vK | 2 | [6 empty] | 1 |  |  |  | 1
‡givgZ, msiÿY I cybe©vmb t
‡gvUi hvbevnb | ‡_vK | 2
Ab¨vb¨ | ‡_vK | 1 | 0 | [5 empty] | 0.58 |  |  |  | 0.58 |  |  | 421.2667 | 54.1667 | #VALUE! |  | 0 |  | 5.2 |  | 2.626 | Kg©KZ©vi ‡evbvm | 1.5944 |  | 5.2014
|  |  | 0.00022232 | [18 empty] | 9.9832 |  | 5.0551 | Kg©Pvixi ‡evbvm= | 0.8097 | 2 C` ‡evbvm | 0.4752 |  | 0 | 0.58 | 0 | 0
‡gvU ivR¯^ |  | 53 |  |  |  | 3 |  |  | 23.58 |  |  |  | 23.43
2¦ g~jab | [20 empty] | 1.58 |  | #VALUE! |  | #VALUE! | [6 empty] | #VALUE! | #VALUE!
m¤ú` msMÖn (6800)
Kw¤úDUvi (2wU) I d‡UvKwcqvi (1wU) | ‡_vK | 4 | 0 |  |  | 4 | [9 empty] | 11195.9191 | 1585.9659 | #VALUE! | 0 | 0 | [7 empty] | 706252 |  | 0 | 4 | 0 | 2
0%
109(3)
wbg©vY I c~Z© (7000) t |  |  | 0.00088928 | [24 empty] | 124878 |  | 0% | 0% | 0 | 0
MvW©vi weªR wbg©vY | 63 | 565 |  |  |  |  | 72 |  | 650 |  | 1 wU |  | 650 |  |  | 11195.9191 | 1585.9659 | #VALUE! | 0 | 0 |  | #REF! | [7 empty] | #VALUE! | 650 | 0 | 0
|  |  | 0.12561 |  |  |  | 114.3% |  | 115% |  |  |  | 100% | [16 empty] | 0% | 0% | 0 | 0
moK wbg©vY | 15.91 | 1089.89 | 0 | 8 |  | 800 | 7.91 |  | 251.42 |  | 7 |  | 251.42 |  |  | 11195.9191 | 1585.9659 | #VALUE! | 0 | 0 |  | 650 | [7 empty] | 15 | 1051.42 | 4 | 400
|  |  | 0.24231 |  |  |  | 49.72% |  | 23.07% |  |  |  | 100% | [16 empty] | 0% | 0% | 0 | 0
‡Wªb wbg©vY | 11596 | 2255.53 | 0 | 2000 |  | 193 | 8000 |  | 281 |  | 5000 |  | 281 |  |  | 11195.9191 | 1585.9659 | #VALUE! | 0 | 0 |  | 251.42 | [7 empty] | 7000 | 474 | 1000 | 96.5
|  |  | 0.50145 |  |  |  | 68.99% |  | 12.46% |  |  |  | 100% | [16 empty] | 0% | 0% | 0 | 0
w÷ªU jvBU | 1400 | 22.15 |  |  |  |  | 1400 wU |  | 22 |  |  |  | 22
100%
wmwm eøK/c¨vjvmvBwWs | 2334 | 350.19 |  |  |  |  | 1500wg: |  | 200 |  | 500 |  | 200
[13 empty] | 100% | [8 empty] | 5004
‡cŠi AwW‡Uvwiqvg ms¯‹vi | 19.5 | 52.48 |  |  |  |  | 19.50 eM© wg: |  | 52 |  |  |  | 52
100%
Wv÷web wbg©vY | 405 | 45.69
e½eÜz m„wZ g~¨ivj wbg©vY | 1 | 20 |  |  |  |  | 1wU |  | 20 |  | 1wU |  | 20
100%
cÖvBm Kw›Ub‡RÝx | ‡_vK | 20 | 0 | [12 empty] | 11195.9191 | 1585.9659 | #VALUE! | 0 | 0 |  | 281 | [7 empty] | 0 | 0 | 0 | 0
|  |  | 0.0044464 | [18 empty] | 0 | [7 empty] | 0% | 0% | 0 | 0
wdwRK¨vj Kw›Ub‡RÝx |  | 20.07
†gvU |  | 4498 | 0.87537 |  | 0 | 1000 |  |  | 1500 |  |  |  | 1499.85 |  |  | #REF! | #REF! |  |  | #REF! | 1182.42 | 78.83% | [8 empty] | #REF! | #REF! | #REF!
|  |  |  | 0% |  | 22.23% | 0% | 0 | 33.35% | 0% |  | 0 | 99.99% | [7 empty] | 1182.42 | [9 empty] | #REF! | #VALUE! | #VALUE!
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z †fŠZ AMÖMwZ t | 83% | [19 empty] | 1185
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z Avw_©K AMÖMwZ t | 62%
11¦ we`¨gvb mgm¨v t | [20 empty] | 0.15
12¦ mycvwik t
109(4)
2499.85
24-12-2011Bs nB‡Z
29-12-2011BsZvwiL ch©š—
cÖKí cwiPvjK cÖK‡íi
ev¯—evqbvaxb cvebv, wmivRMÄ I
bv‡Uvi ‡Rjvi DbœqYg~jK KvR ¦
cwi`k©b 'K‡ib

## ST_Schm (hidden)
STATUS OF SCHEMES / CONTRACTS IN RRMIMP-2
FINANCIAL YEAR: 2004-2005
#REF!
Sl.No. | Name of Project / Name of | ADP Provision and | No. of Schemes/ | Carried Over | Total | Work Plan Target |  | Scheme | Achivement |  |  |  |  | Physicial | Fund Spent | Remarks
| Development Assistant | Fund Release | Contracts New | Contracts/Excess |  | Last Date for | Last date for | Prepared | Schemes | Tender | Tender | Going on | Schemes | Progress
| Partner's | (GOB+RPA) | Schemes/ | Programme |  | awarding | Commencement |  | Preparation | Called | Evaluation |  | Completed
|  |  | Contract | of Previous |  | Contract |  |  | under |  | under
|  |  |  | year |  |  |  |  | Process |  | Process
|  |  | (No) | (No) | No |  |  |  |  | (No) |  | New+Carried Over |  |  | (GOB+RPA)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Rural Development Project; | 22020 | - | -
| Infrastructure Development : 26 | #REF!
(15,520.00+6,500.00)
(0.00+0.00)
|  |  | Prepared by: | ______________ | [6 empty] | _____________________
|  |  |  | (Md. Eaar Uddin) | [6 empty] | (Md. Torab Ali Khan)
|  |  |  | Accounts Officer | [6 empty] | Project Director
|  |  |  | RDP-26, LGED | [6 empty] | RDP-26, LGED

## Org-Prog
evwl©K Dbœqb Kg©m~Px (2019-20)
K) gš¿Yvjq / wefvM |  | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq / ¯’vbxq miKvi wefvM
L) ms¯’vi bvg |  | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
M) cÖwZ‡e`b Kvj (gvm) |  | t | Ryb/2020Bs
(j¶ UvKvq)
µwgK bs | †KvW I cÖK‡íi bvg (cÖKí e¨q I ev¯ÍevqbKvj) | Aby‡gv`‡bi ch©vq | GwWwcÕi c„ôv bs I µwgK bs | PjwZ (2019-20) A_© erm‡ii evwl©K Dbœqb Kg©m~Px‡Z eivÏ |  |  |  | Aegyw³ |  |  |  | e¨q |  |  |  | cÖKí mvnv‡h¨i UvKvsk |  | AMÖMwZ (%) |  |  |  | cÖKí mvnv‡h¨i Drm | gšÍe¨
[18 empty] | †fŠZ |  | Avw_©K
|  |  |  | †gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | †gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | †gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | `vexK…Z | cÖvwß | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK) | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK)
[6 empty] | †gvU | UvKvsk |  |  | †gvU | UvKvsk |  |  | †gvU | UvKvsk
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 21 | 22 | 17 | 18 | 19 | 20 | 23 | 24
| †KvW t 224260100 cÖKí t wkeMÄ †cŠimfvi †fŠZ AeKvVv‡gv Dbœqb kxl©K cÖKí¦ (e¨q t 4498.00 j¶ UvKv, ev¯Íevqb Kvj t AvM÷ 2018 n‡Z wW‡m¤^i 2020) | Aby‡gvw`Z | c„ôv-360-361 µwgK-109 | 2200 | 2200 | 0 | 0 | 1500 | 1500 | 0 | 0 | 1499.85 | 1499.85 | 0 | 0 | 0 | 0 | 25% | 25% | 25% | 25% | wRIwe | KvR Pjgvb
109 |  |  |  |  | ( -) |  |  |  | ( -) |  |  |  | ( -) | [9 empty] | Dc‡hvR‡bi gva¨‡g Kvh©µg wefv‡Mi ¯§viK bs-20.06.0000.605.14.067.2020/33 ZvwiL: 10 Ryb 2020‡Z eivÏK…Z 700.00jÿ UvKv A_© wefvM †_‡K Qvo Kiv nq bvB¦

## IMED-05 (Part-A)
Progress Report of On-going Development Projects/Operational Plan( Format 05/2010)
Reporting Period: |  | 2020-06-01 | [11 empty] | (All financial figures in Lakh Tk)
Part-A: Monthly Report
Ministry |  | : | Local Government, Rural Development & Cooperatives
Division |  | : | Local Government Division
Organization |  | : | Local Government Engineering Department (LGED)
1 | Name of the Project /Operational Plan : |  |  |  | Shibganj Pourashava Physical Infrastructure Development Project
2 | Objectives of the Project/ |  |  |  | (a) Develop urban physical infrastructure to meet civic needs.
| Operational : Plan (in Brief) |  |  |  | (b) Improve Environment: and
(c) Create employment opportunities.
3 | Location of the Project/Operational Plan : |  |  |  | Shibganj Pourashava (Bogura)
4 | Project Approval Status & Cost :
| DPP/TPP | Date of approval |  |  | Implementation period |  |  | Total Cost |  |  | GOB |  | Project Aid (RPA)
| i. Original | 2018-03-11 |  |  | August'2018-December '2020 |  |  | 4498 |  |  | 4498
5 | Progress of Fund Release:
| Quarter-wise | Date of | [7 empty] | Amount Released |  | Date of issue of Cheque from CAO (in case of Autonomous body)
|  | Proposal Sending to Ministry/Division |  |  | Issue of order by Ministry |  | Issue of order from Finance Division
| 1 | 2 |  |  | 3 |  | 4 |  |  | 5 |  | 6
| 1th quarter | [8 empty] | 375
| 2nd quarter | [8 empty] | 375
| 3rd quarter | [8 empty] | 375
| 4th quarter | [8 empty] | 375
| Total | [8 empty] | 1500
6 | Target and Achievement of the main Components of the Project :
| Name of Important Components (With quantity) | Cost as per DPP/TPP | Achievement upto last June/19 |  |  | Target of current year |  |  | Progress uptoJune/20 (the reporting month of current year) |  |  | Unspent /unfinished balance against DPP targets
|  |  | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical
|  |  | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component)
|  |  | b) Taka |  |  | b) Taka |  |  | b) Taka |  |  | b) Taka
| 1 | 2 | 3 |  | 4 | 5 |  | 6 | 7 |  | 8 | 9 |  | 10
Supply and service
| Gas / fuel | 2 | a) |  |  | a) | 0 |  | a) | 0 |  | a) | 2 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Petrol and lubricant | 2 | a) |  |  | a) | 0 |  | a) | 0 |  | a) | 2 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Stationery, seal and stamp | 2 | a) | 1 |  | a) | 1 |  | a) | 2 |  | a) | 0 | 0%
|  |  | b) |  |  | b) |  |  | b) | 2 |  | b)
| Promotion and Advertising | 1 | a) |  |  | a) | 1 |  | a) | 0 |  | a) | 1 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Consultancy | 35 | a) | 2 |  | a) | 18 |  | a) | 17.85 |  | a) | 17.15 | 49%
|  |  | b) |  |  | b) | 18 |  | b) | 17.85 |  | b)
| Sub-cell Investigation | 2 | a) |  |  | a) | 1 |  | a) | 1 |  | a) | 1 | 50%
|  |  | b) |  |  | b) |  |  | b) | 1 |  | b)
| Survey | 3 | a) |  |  | a) | 1 |  | a) | 1 |  | a) | 2 | 66.67%
|  |  | b) |  |  | b) |  |  | b) | 1 |  | b)
| Honorary Allowance / Fee | 1 | a) |  |  | a) |  |  | a) | 0 |  | a) | 1 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Computer accessories | 2 | a) |  |  | a) | 1 |  | a) | 1 |  | a) | 1 | 50%
|  |  | b) |  |  | b) | 1 |  | b) | 1 |  | b)
| Repair, conservation and rehabilitation |  | a) |  |  | a) |  |  | a) | 0 |  | a) | 0 | #DIV/0!
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Motor vehicles | 2 | a) |  |  | a) |  |  | a) | 0 |  | a) | 2 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Other | 1 | a) |  |  | a) | 0.58 |  | a) | 0.58 |  | a) | 0.42 | 42%
|  |  | b) |  |  | b) | 0.58 |  | b) | 0.58 |  | b)
| Asset Collecting |  | a) |  |  | a) |  |  | a) |  |  | a) | 0
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Computer (2) and photocopier (1) | 4 | a) | 4 |  | a) | 0 |  | a) | 0 |  | a) | 4 | 100%
|  |  | b) |  |  | b) | 0 |  | b) | 0 |  | b)
Construction and Works
| Construction of the Girder Bridge | 565 | a) |  |  | a) | 650 |  | a) | 650 |  | a) | -85 | -15.04%
|  |  | b) |  |  | b) | 650 |  | b) | 650 |  | b)
| Construction of Road | 1089.89 | a) | 800 |  | a) | 251.42 |  | a) | 251.42 | 7 | a) | 838.47 | 76.93%
|  |  | b) |  |  | b) | 251.42 |  | b) | 251.42 | 7 | b)
| Construction of the drain | 2255.53 | a) | 193 |  | a) | 281 |  | a) | 281 | 5000 | a) | 1974.53 | 87.54%
|  |  | b) |  |  | b) | 281 |  | b) | 281 | 5000 | b)
| Street lights | 22.15 | a) |  |  | a) | 22 |  | a) | 22 |  | a) | 0.15 | 0.6772%
|  |  | b) |  |  | b) | 22 |  | b) | 22 |  | b)
| CC Block / Palsiding | 350.19 | a) |  |  | a) | 200 |  | a) | 200 |  | a) | 150.19 | 42.89%
|  |  | b) |  |  | b) | 200 |  | b) | 200 |  | b)
| Municipal Auditorium Reforms | 52.48 | a) |  |  | a) | 52 |  | a) | 52 |  | a) | 0.48 | 0.9146%
|  |  | b) |  |  | b) | 52 |  | b) | 52 |  | b)
| Dustbin construction | 45.69 | a) |  |  | a) | 0 |  | a) |  |  | a) | 45.69 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Construction of Bangabandhu Memorial Mural | 20 | a) |  |  | a) | 20 |  | a) | 20 |  | a) | 0 | 0%
|  |  | b) |  |  | b) |  |  | b) | 20 |  | b)
| Physical Contingency | 20 | a) |  |  | a) |  |  | a) |  |  | a) | 20 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Price Contingency | 20.07 | a) |  |  | a) |  |  | a) |  |  | a) | 20.07 | 100%
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
| Grand Total : | 4498 |  | 1000 | 22.23% |  | 1500 | 0% | 1499.85 |  | 0% | 1998.15 |  | 44.42%
7 | Progress of Procurement in current FY:
[7 empty] | Goods |  | Works |  | Services |  | Total |  | 43 | 1056 | 1099
| a) Work Orders (WO) issued in last year or before | [13 empty] | 42 |  | 571 | 613
| i) Number of WOs. | [5 empty] | 0 |  | - |  | 0 |  | - |  |  |  |  | 0
| ii) Expenditure in current FY | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 82.07 |  | 10642.68 | 10724.75
| b) Work Orders (WO) issued during the reporting period, 2018-19. | [13 empty] | 6 |  | 65 | 71
| i) Number of WOs. | [5 empty] | - | [5 empty] | 0 |  |  |  |  | 0
| ii) Expenditure in current FY. | [5 empty] | 0 |  |  |  | 0 |  | 0 |  | 5 |  | #REF! | #REF!
| c) WOs to be issued during the rest of the period of the FY. | [16 empty] | 0
| d) Total expenditure for procurement up to reporting month, 2018-19 (a ii + b ii). | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 87.07 |  | #REF! | #REF!
| e) Total budget/allocation for procurement, 2018-19. | [7 empty] | 0 |  | 0 |  | 0 |  | 5 |  | 9853.83 | 9858.83
| f) Cumulative expenditure upto last year. | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 87.07 |  | #REF! | #REF!
| g) Total allocation as per DPP/TPP. | [5 empty] | 0 |  | 4498 |  | 0 |  | 4498 |  | 228.2 |  | 41255.35 | 41483.55
| h) Unspent amount as per DPP/TPP. | [5 empty] | 0 |  | 4498 |  | 0 |  | 4498 |  | 141.13 |  | #REF! | #REF!
Sushanto Kumar Paul
Project Director
Phone No: 8144210.

## Purchase
µq msµvšÍ Z_¨vejx t 2019-20 A_© eQ‡ii AMÖMwZ (Ryb/2019Bs ch©šÍ)
(j¶ UvKvq)
µwgK bs | cÖK‡íi bvg | gvjvgvj |  |  |  |  | c~Z© |  |  |  |  | †mev |  |  |  |  | K) wmwW f¨vUmn µqLv‡Z †gvU eivÏ (2019-20) L) wmwW f¨vU | K) wmwW f¨vUmn µqLv‡Z †gvU e¨q L) wmwW f¨vU | µqLv‡Z Ae¨wqZ eivÏ (19-20) | †gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
|  | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/2019Bs mgqKv‡j cÖ`vbK„Z |  | RyjvB/2019Bs n‡Z Ryb/20 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/2019Bs mgqKv‡j cÖ`vbK„Z |  | RyjvB/2019Bs n‡Z Ryb/20 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/2019Bs mgqKv‡j cÖ`vbK„Z |  | RyjvB/2019Bs n‡Z Ryb/20 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v
|  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
109 | †KvW t 224260100 cÖKí t wkeMÄ †cŠimfvi †fŠZ AeKvVv‡gv Dbœqb kxl©K cÖKí¦
|  | 18wU | 1000 | 26 | 2384 | - | 18 | 1000 | 26 | 2384 | 10 |  | 10 | - | - | 29wU | - | 0 | - | 2200 | 99.7%
[17 empty] | ( - ) | ( - )
mykvšÍ Kzgvi cvj
cÖKí cwiPvjK
wkeMÄ †cŠimfvi †fŠZ AeKvVv‡g Dbœqb cÖKí¦
‡dvb b¤^i t 8144210
[8 empty] | 95.5 |  | 2.98
[8 empty] | 1650 |  | 1.39
[8 empty] | 105 |  | 5.06
[8 empty] | 2047 |  | 4.82
[8 empty] | 106 |  | 0.72
[8 empty] | 211 |  | 14.97
40
98
[8 empty] | 4352.5 |  | 5963.22 | 5948.25
5.25
4357.75

## Modified_form
2019-2020 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq GwWwcf~³ ev¯Íevqbvaxb cÖKímg~‡ni AMÖMwZi ch©v‡jvPbv QK-1
gv‡mi bvg t Ryb/2020Bs
ms¯’v t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
(j¶ UvKvq)
µt bs | cÖK‡íi bvg (†gqv`Kvj) | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ e¨q | Aby‡gvw`Z wWwcwc/AviwWwcwcÕi Procurement Plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2019-2020A_©eQ‡ii evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄf~Z c~bf©iY e¨q ( RyjvB /19 ch©šÍ) L) †gvU cybf©iY e¨q (2019-20 GwWwc) M) †gvU cybf©iY `vex †ck(2019-20 GwWwc) N) †gvU cybf©iY cvwß (2019-20 GwWwc) | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/ AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | A‡±vei/2019 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Erm
[6 empty] | 2019-2020 GwWwc eivÏ | 2019-20 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`k cÖ`vb, Avw_©K I †fŠZ j¶¨gvÎv AwR©Z bv nIqvi KviY (2019-20 GwWwc)
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ (2019-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv (2019-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q/AMÖMwZ (2018-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ (2019-20 GwWwc) |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨q (2019-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q (2019-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q (2019-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q (2019-20 GwWwc)
|  | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | j¶¨gvÎv (%) | AMÖMwZ (%) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) |  |  | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | % | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | eQi/gvm
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
101
| cÖKí t wkeMÄ †cŠimfvi †fŠZ AeKvVv‡gv Dbœqb kxl©K cÖKí¦ ev¯Íevqb Kvj t AvM÷ 2018 n‡Z wW‡m¤^i 2020 ch©šÍ¦ | g~j: 4498.00 jÿ | 1000 | 0 | 0/0.00 | 2200 | 0 | 1500 | 1475 | 1499.85 | 0% |  |  | 0 | 0 | 1499.85 |  | N/A | 2499.85 |  | 1998 |  |  | 26793.3
|  | g~j: 4498.00 jÿ | 1000 | 0 | 0/0.00 | 2200 | 0 | 1500 | 1475 | 1499.85 | 0% | 0% |  | 0 | 0 | 1499.85 | - | N/A | 2499.85 | 0% | 1998 | 6 gvm | wRIwe |  | 42500 | 28238.03 | 150.5%
28229.06
|  | (0) | (0) | 0 | 0/0.00 | (0/0) | (0/0) | (0/0) | (0/0) | (0/0) |  |  |  | 0 | 0 | - |  | N/A | (0/0) |  | (0/0) |  |  |  | 14270.94
|  | (0) | (0) | 0 | (0/0) | (0/0) | (0/0) | (0/0) | (0/0) | (0/0) |  |  | - | - | 26/2384 | - |  | N/A | (0/0) |  | (0/0)
me©‡gvU |  | g~j: 4498.00 jÿ |  | 0 |  | 2200 | 0 | 1500 | 1475 | 1499.85 |  | 0% |  |  | 26/2384 |  |  |  | 2499.85 |  | 1998 |  |  |  | 42.58
57.42
mykvšÍ Kzgvi cvj
cÖKí cwiPvjK
wkeMÄ †cŠimfvi †fŠZ AeKvVv‡g Dbœqb kxl©K cÖKí¦
‡dvb b¤^i t 8144210
100
[21 empty] | 27369.63 | #VALUE!
#VALUE!
[14 empty] | 79939.93 | 60885.86 | 19054.07
[7 empty] | GwWwc eivÏ | 9000 | ch©v‡jvPbvaxb Avw_©K e¨q | 0 |  |  |  |  | #VALUE! | 0.31295 |  |  | µgcywÄZ Avw_©K e¨q | 2499.85 | AeivÏK„Z UvKv | 1000 |  | 87.84
[7 empty] | Aegyw³ | 4000 | [10 empty] | cÖKí e¨q | 79939.93 | cÖKí e¨q | 79939.93 |  | 12.16
[7 empty] | % | 44.4444 | % | #REF! | [8 empty] | % | 3.1272 | % | 1.2509 |  | 100

## Status Rpt (2)
Scheme Status Report
Shibganj Pourashava Physical Infrastructure Development Project
Local Government Engineering Department (LGED)
Financial Year : 2019-20
Reporting upto: | 2020-06-25
(Taka in Lakh)
Name of the project (name of Development Assistance partner) | (ADP Provision) & Total Fund Released (GOB + RPA) (Tk.) | No. of Scheme / Contracts |  |  | Work Plan Target |  | Achievement | [5 empty] | Physical Progress (%) | Total Fund Spent (GOB + RPA) | Remarks
|  | New Schemes/ Contracts | Carried Over Contracts/ Excess Programmes of Previous Year (No.) | Total (No.) | Last Date for Awarding Contract | Last Date for Commen-cement | Schemes Prepared (No.) | Schemes Preparation under process (No.) | Tender Called (No.) | Tender Evalation under process (No.) | Works going on (No.) | Schemes Completed (No.)
Shibganj Pourashava Physical Infrastructure Development Project. | 1500 | [10 empty] | - | 83% | - | -
| 1500 | 0 | 5 | 5 | 2019-07-10 | 14/11/2019 | 18 | 31 | 18 | 0 | 5 | 21 |  | ( - )
( - )
Project Director
Shibganj Pourashava Physical Infrastructure Development Project.