## Page-1
cÖKí ev¯Íevqb cÖwZ‡e`b
[6 empty] | cÖwZ‡e`bKvj Ryb/2020Bs | uu
1¦ cÖK‡íi bvg | t | wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí
2¦ Aby‡gv`b ch©vq | t | g~j: ¯’vbxq miKvi gš¿Yvjq KZ…©K 05/03/2017 ZvwiL Aby‡gvw`Z¦
1g ms‡kvwaZ: ¯’vbxq miKvi gš¿Yvjq KZ…©K 07/11/2018 Aby‡gvw`Z¦
2q ms‡kvwaZ: ¯’vbxq miKvi gš¿Yvjq KZ…©K 24/02/2020 Aby‡gvw`Z¦
3¦ ms¯’v I gš¿Yvj‡qi bvg | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦ ¯’vbxq miKvi wefvM¦ ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq¦
4¦ cÖK‡íi D‡Ïk¨ | t | K) wmivRMÄ ‡Rjvi ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b Kivmn wewfbœ Dbœqb KvR m¤úv`b Kiv¦
L) ‡cŠi GjvKvq LvjLbb Ges evRvi, ¯^v¯’¨‡K›`ª, wkÿv-cÖwZôvb I Ab¨vb¨ †mev`vbKvix cÖwZôv‡b hvZvqvZ myweav e„w×i gva¨‡g cwi‡ek I RxebhvÎvi gv‡bvbœqb¦
M) we‡bv`‡bi myweavi m„wó Kiv¦
N) ¯^í I `xN©‡gqv‡` Kg©ms¯’vb m„wó¦
|  |  | g~j | 1g ms‡kvwaZ | 2q ms‡kvwaZ
5¦ ev¯ÍevqbKvj | t | K) KvR Avi‡¤¢i ZvwiL t Rvbyqvix 2017 |  | Rvbyqvix 2017 | Rvbyqvix 2017
|  | L) cÖKí mgvwßi ZvwiL t Ryb 2019 |  | Ryb 2020 | Ryb 2021
|  |  | g~j | 1g ms‡kvwaZ | 2q ms‡kvwaZ
6¦ cÖv°wjZ e¨q (j¶ UvKvq) | t | †gvU t | 2253 | 2580 | 2580
|  | UvKv (wRIwe) t | 2253 | 2580 | 2580
|  | cÖKí mvnvh¨ t | 0
|  | cÖKí mvnv‡h¨i t | 0
(UvKvsk)
7¦ cÖKí mvnv‡h¨i Drm | t | evsjv‡`k miKvi (wRIwe)

## ST_Schm (hidden)
STATUS OF SCHEMES / CONTRACTS IN RRMIMP-2
FINANCIAL YEAR: 2004-2005
#REF!
Sl.No. | Name of Project / Name of | ADP Provision and | No. of Schemes/ | Carried Over | Total | Work Plan Target |  | Scheme | Achivement |  |  |  |  | Physicial | Fund Spent | Remarks
| Development Assistant | Fund Release | Contracts New | Contracts/Excess |  | Last Date for | Last date for | Prepared | Schemes | Tender | Tender | Going on | Schemes | Progress
| Partner's | (GOB+RPA) | Schemes/ | Programme |  | awarding | Commencement |  | Preparation | Called | Evaluation |  | Completed
|  |  | Contract | of Previous |  | Contract |  |  | under |  | under
|  |  |  | year |  |  |  |  | Process |  | Process
|  |  | (No) | (No) | No |  |  |  |  | (No) |  | New+Carried Over |  |  | (GOB+RPA)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Rural Development Project; | 22020 | - | -
| Infrastructure Development : 26 | 580
(15,520.00+6,500.00)
(0.00+0.00)
|  |  | Prepared by: | ______________ | [6 empty] | _____________________
|  |  |  | (Md. Eaar Uddin) | [6 empty] | (Md. Torab Ali Khan)
|  |  |  | Accounts Officer | [6 empty] | Project Director
|  |  |  | RDP-26, LGED | [6 empty] | RDP-26, LGED

## Page-2
8¦ e¨q (j¶ UvKvq) t
| †gvU | UvKv | cÖKí mvnvh¨ |  | ïé | FY cwi‡kva | gšÍe¨
|  |  | †gvU | UvKvsk (AviwcG)
K) 2019-20Bs A_© erm‡ii GwWwc/AviGwWwc eivÏ¦ | 580 | 580 | 0 | 0 | 0
L) 2019-20Bs A_© erm‡ii t uu ch©šÍ Aegyw³¦ | 580 | 580 | 0 | 0 | 0
M) 2019-20Bs A_© erm‡ii t uu ch©šÍ e¨q¦ | 580 | 580 | 0 | 0 | 0
N) cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q | 1680 | 1680 | 0 | 0 | 0
9¦ cÖKí mvnv‡h¨I UvKvsk e¨q, `vex I cÖvwß (j¶ UvKvq) t
PjwZ A_© erm‡ii cÖwZ‡e`bKvj ch©šÍ t
welq | PjwZ A_© erm‡ii |  | µgcywÄf~Z
1¦ e¨q t | - |  | -
2¦ `vexK…Z t | - |  | 0
3¦ cÖvwß t | - |  | -

## Page 3
10¦ cÖavb cÖavb As‡Mi j¶¨gvÎv I AMÖMwZ t
GwcÖj/2016Bs¦
As‡Mi bvg |  | wWwcwc Abymv‡i j¶¨gvÎv |  |  |  | c~e©eZ©x erm‡ii Ryb/19 ch©šÍ µgcywÄZ AMÖMwZ |  |  | PjwZ 19-20 A_© erm‡ii j¶¨gvÎv (cwigvb I wWwcwcÕi %) |  |  |  | PjwZ 19-20 A_© erm‡ii cÖwZ‡e`bKvj ch©šÍ AMÖMwZ (cwigvb I eiv‡Ïi %) |  | cÖKí cwiPvjK/ Kg©KZ©v KZ…©K cÖKí GjvKv cwi`k©‡bi ZvwiL | gšÍe¨
|  | ev¯Íe |  | Avw_©K | J­u­VV h¡Ù¹h | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K | ev¯Íe | J­u­VV h¡Ù¹h | Avw_©K (j¶ UvKvq) wWwcwc Abymv‡i | J­u­VV h¡Ù¹h | ev¯Íe | Avw_©K (j¶ UvKvq) |  |  | fªhÑha£Ñ j¡p | †g 08
1 |  | 2 |  | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 | 9 | 10 | 11
1¦ ivR¯^ e¨q t
K) Kg©KZ©v‡`i †eZb (4500) |  | 0 |  | 0 |  | - |  |  | 0 |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | 0 | <> Weight of each item |  |  | = | Est. cost of each respective item
L) Kg©Pvix‡`i †eZb (4600) |  | 0 |  | 0 |  | - |  |  | 0 |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | #VALUE! |  |  |  |  | Total cost of all physical item (s)
0%
M) fvZvw` (4700) |  | 0 |  | 0 |  | - |  |  | 0 |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | #VALUE!
0%
N.1) mieivn I †mev (4800) |  | ‡_vK |  | 35 |  | - |  | 4 | ‡_vK |  | 2 |  |  | 2 |  |  | 421.2667 | 54.1667 | #VALUE! | -13 | <> Physical percentage of total Project |  |  | = | Weight of each item x % of item.
[9 empty] | LS |  | 5.714% |  |  | 100%
2) civgk©K |  |  |  | 0 |  |  |  | 14 |  |  | 15 |  |  | 15
[11 empty] | 0% |  |  | 100%
O) †givgZ i¶Yv‡e¶Y I cybe©vmb (4900) |  | ‡_vK |  | 0 |  | - |  |  | 0 |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | 0
0%
P) ‡_vK eivÏ (6681) |  | ‡_vK |  |  |  | - |  |  | 0 |  | 0 | [5 empty] | 421.2667 | 54.1667 | #VALUE! | 0
‡gvU ivR¯^ e¨q |  |  |  | 35 |  |  |  | 18 |  |  | 17 |  |  | 17
2¦ g~jab e¨qt
wbg©vY I c~Z©KvR (7000)
1) Lvj cybtLbb |  | 4.2 | wKtwgt | 500 |  | 4.2 | 1.5 | 500 | 0 |  | 0 | [10 empty] | 119.0476
[6 empty] | 100% | #VALUE! | 100% | 0% |  | 0% | [5 empty] | 0 | 0 |  | 0
2) Lv‡ji †¯øvc cÖ‡UKkb |  | 0.7 | wKtwgt | 195 |  | 0.7 | 1 | 195 |  |  | 0 | [10 empty] | 278.5714
[6 empty] | 100% | #VALUE! | 100% | 0% |  | 0%
3) moK wbg©vY |  | 1 | wKtwgt | 100 |  | 1 | 1 | 100 | [13 empty] | 100
[6 empty] | 100% | #VALUE! | 100% | 0% |  | 0%
4) IqvKI‡q wbg©vY |  | 3 | wKtwgt | 240 |  | 1 | 0 | 80 | 2 |  | 130 |  | 1.5 | 130 | [7 empty] | 80
[7 empty] | #VALUE! |  | 66.67% |  | 54.17% |  | 75% | 100%
5) Aviwmwm †Wªb wbg©vY |  | 1 | wKtwgt | 90 |  | 0.5 | 0 | 40 | 0.5 |  | 30 |  | 0.35 | 30 | [7 empty] | 90
[7 empty] | #VALUE! | 44.44% | 50% |  | 50% |  | 70% | 100%
6) NvUjv/wmwo wbg©vY |  | 4 | wU | 65 |  | 2 | 2 | 27 | 2 |  | 38 |  | 1 | 38
[7 empty] | #VALUE! | 50% | 50% |  | 58.46% |  | 50% | 100%
7) eªxR/Kvjfv©U wbg©vY |  | 80 | wgt | 1012 |  | ‡_vK | 0 | 0 | 80 |  | 320 |  |  | 320 | [7 empty] | 2510
[7 empty] | #VALUE! | 0% | 100% |  | 31.62% | [10 empty] | 9528
8) moK evwZ ¯’vcb I evMvb wbg©vY |  | 4 | wKtwgt | 50 |  | 3 | 4 | 30 | 1 |  | 0
[7 empty] | #VALUE! | 40% | 25% |  | 0%
83
105 (3)
9) ivBW wbg©vY |  | 5 | wU | 158 |  | 80% | 0 | 110 | 20% |  | 45 |  | 18% | 45
[7 empty] | #VALUE! | 69.62% | 4% |  | 28.48% |  |  | 100%
10) j¨vÛ‡¯‹wcs |  | 1 | wU | 50 |  |  | 0 |  | 1 |  | 0
[7 empty] | #VALUE! |  | 100% |  | 0%
11) MY‡kŠPvMvi |  | 2 | wU | 30 |  |  | 0 |  | 2 |  | 0
[7 empty] | #VALUE! |  | 100% |  | 0%
12) e„ÿ‡ivcb |  | 0 | ‡_vK | 20 |  |  | 0 |  | ‡_vK |  | 0
[7 empty] | 0% |  | 0% |  | 0%
Dc †gvU= |  |  |  | 2510 |  |  | 0 |  | 0
M) wdwRK¨vj Kw›Ub‡RÝx (7980) |  | - |  | 20 |  |  | - | 0 | - |  | 0
N) cÖvBm Kw›Ub‡RÝx (7980) |  | - |  | 15 |  |  | - | 0 | - |  | 0
Dc †gvU= |  |  |  | 35 | #DIV/0! |  |  | 1082 |  |  | 563 |  |  | 563
‡gvU = |  | 105.9 |  | 2580 | #DIV/0! | 60% | #VALUE! | 1100 | 88.7 |  | 580 | 0 | 30% | 580 |  | 8.58 | #REF! | #REF! |  | #REF!
[7 empty] | #VALUE! | 42.64% | 83.76% |  | 22.48% | #DIV/0! |  | 100% | [7 empty] | 0
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z †fŠZ AMÖMwZ (%) | t | 95% | [19 empty] | 2 | 2 | 0
cÖwZ‡e`b Kvj ch©šÍ µgcywÄf~Z Avw_©K AMÖMwZ (%) | t | 65.12% | [19 empty] | 1764 | 160 | 1604
11¦ we`¨gvb mgm¨v | t | [20 empty] | 1766 | 162 | 1604
12¦ mycvwik | t | [12 empty] | (mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí
62, cwðg AvMviMvuI, GjwRBwW, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210
105 (4)
|  |  | ivR¯^ e¨q = | 35 |  |  |  |  | ivR¯^ e¨q = |  | 2 |  | ivR¯^ e¨q = | 2
|  |  | g~jab e¨q = | [5 empty] | g~jab e¨q = |  |  |  | g~jab e¨q =
|  |  | m¤ú` msMÖn = | #VALUE! |  |  |  |  | m¤ú` msMÖn = |  | #VALUE! |  | m¤ú` msMÖn = | #VALUE!
|  |  | wbg©vY I c~Z© KvR = | 2510 |  |  |  |  | wbg©vY I c~Z© KvR = |  | 563 |  | wbg©vY I c~Z© KvR = | 198
|  |  | Kw›Ub‡RwÝ = | 35 |  |  |  |  | Kw›Ub‡RwÝ = |  | 0 |  | Kw›Ub‡RwÝ = | 0
|  |  |  | #VALUE! | [6 empty] | #VALUE! |  |  | #VALUE!
|  |  | me©‡gvU = | #VALUE! |  |  |  |  | me©‡gvU = |  | #VALUE! |  | me©‡gvU = | #VALUE!
63.72
1.12
1.7577
0.027585

## Org-Prog
evwl©K Dbœqb Kg©m~Px (2019-20)
K) gš¿Yvjq / wefvM |  | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq / ¯’vbxq miKvi wefvM
L) ms¯’vi bvg |  | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
M) cÖwZ‡e`b Kvj (gvm) |  | t | cÖwZ‡e`bKvj Ryb/2020Bs
(j¶ UvKvq)
µwgK bs | †KvW I cÖK‡íi bvg (cÖKí e¨q I ev¯ÍevqbKvj) | Aby‡gv`‡bi ch©vq | GwWwcÕi c„ôv bs I µwgK bs | PjwZ (2019-20) A_© erm‡ii evwl©K Dbœqb Kg©m~Px‡Z eivÏ |  |  |  | Aegyw³ |  |  |  | e¨q |  |  |  | cÖKí mvnv‡h¨i UvKvsk |  | AMÖMwZ (%) |  |  |  | cÖKí mvnv‡h¨i Drm | gšÍe¨
[18 empty] | †fŠZ |  | Avw_©K
|  |  |  | †gvU | UvKv | cÖKí mvnvh¨ |  | †gvU | UvKv | cÖKí mvnvh¨ |  | †gvU | UvKv | cÖKí mvnvh¨ |  | `vexK…Z | cÖvwß | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK) | j¶¨gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK)
[6 empty] | †gvU | UvKvsk |  |  | †gvU | UvKvsk |  |  | †gvU | UvKvsk
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 21 | 22 | 17 | 18 | 19 | 20 | 23 | 24
97 | wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí¦ cÖKí e¨qt 2580.00 j¶ UvKv ev¯ÍevqbKvjt Rvbyqvix/2017 - Ryb/2020 | Aby‡gvw`Z | c„ôv bs- 360 I 361, µwgK-97 | 580 | 580 | 0 | 0 | 580 | 580 | 0 | 0 | 580 | 580 | 0 | 0 | 0 | 0 | 25% | 25% | 25% | 25% | wRIwe
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí
62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210

## IMED-05 (Part-A)
Progress Report of On-going Development Projects/Operational Plan( Format 05/2009)
Reporting Period: |  | 2020-06-01 | [11 empty] | (All financial figures in Lakh Tk)
Part-A: Monthly Report
Ministry |  | : | Local Government, Rural Development & Cooperatives
Division |  | : | Local Government Division
Organization |  | : | Local Government Engineering Department (LGED)
1 | Name of the Project /Operational Plan : |  |  |  | Sirajgonj Paurashava Katakhal Improvement and Surrounding area Beautification Project
2 | Objectives of the Project/Operational : Plan (in Brief) |  |  |  | • Overall improvement of the transportation network to facilitate production and marketing of agricultural and non- agricultural products and socio-economic development of the project area. • To remove physical bottlenecks and reduce costs of rural transportation and marketing. • Create both short term and long term employment opportunities.
3 | Location of the Project/Operational Plan : |  |  |  | Division |  | District |  | Upazila
[5 empty] | Rajshahi |  | Sirajgonj |  | Sirajgonj Paurashava
4 | Project Approval Status & Cost :
| DPP/TPP | Date of approval |  |  | Implementation period |  |  | Total Cost |  |  | GOB |  | Project Aid (RPA)
| i. Original | 2017-05-16 |  |  | January'17 - June'19 |  |  | 2253 |  |  | 2253 |  | -
| ii. 1st Revised | 2018-07-11 |  |  | January'17 - June'20 |  |  | 2580 |  |  | 2580 |  | -
5 | Progress of Fund Release: |  |  | Fund Release Not Yet.
(Taka in Lakh)
| Quarter-wise | Date of | [7 empty] | Amount Released |  | Date of issue of Cheque from CAO (in case of Autonomous body)
|  | Proposal Sending to Ministry/Division |  |  | Issue of order by Ministry |  | Issue of order from Finance Division
| 1 | 2 |  |  | 3 |  | 4 |  |  | 5 |  | 6
| 1st quarter | - |  |  | - |  | - |  |  | 0
| 2nd quarter | - |  |  | - |  | - |  |  | 0
| 3rd quarter | - |  |  | - |  | - |  |  | 0
| 4th quarter | - |  |  | - |  | - |  |  | 0
| RPA authorization | - |  |  | - |  | - |  |  | 0
| Total | [8 empty] | 580
6 | Target and Achievement of the main Components of the Project :
| Name of Important Components (With quantity) | Cost as per DPP/TPP | Achievement upto last June/19 |  |  | Revised Target of current year (2019-2020) |  |  | Progress uptoJune/20 (the reporting month of current year) |  |  | Unspent /unfinished balance against DPP targets
|  |  | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical
|  |  | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component) | a) Total |  | (% of the component)
|  |  | b) Taka |  |  | b) Taka |  |  | b) Taka |  |  | b) Taka
| 1 | 2 | 3 |  | 4 | 5 |  | 6 | 7 |  | 8 | 9 |  | 10
1) Revenue :
| a) Pay of Officers | 0 | a) |  |  | a) |  | 0 | a) |  |  | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 | 0% | b) | 0 | 0% | b)
| b) Pay of Establishment | 0 | a) |  |  | a) |  | 0 | a) |  |  | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 | 0% | b) | 0 | 0% | b)
| c) Allowances | 0 | a) |  |  | a) |  | 0 | a) |  |  | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 | 0% | b) | 0 | 0% | b)
| d) Supplies and Services | 35 | a) | 18 |  | a) | 17 | 2 | a) | 17 |  | a) | 17 | 48.57%
|  |  | b) | 18 | - | b) | 0 | 0% | b) |  | 1500% | b) | 17
| e) Repair, Maintenance and Rehabilitation | 0 | a) |  |  | a) |  | 0 | a) |  |  | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 | 0% | b) |  | 0% | b)
| f) Middle Evaluation | 0 | a) |  |  | a) |  | 0 | a) |  |  | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 | 0% | b) | 0 | 0% | b)
2) Capital :
| 1) Re-excavation of Khal | 500 | a) | 500 | 1.50km | a) | 0 | 0 | a) | 0 | 0 | a) | 0 | 0%
|  |  | b) |  | 1.50km | b) | 0 | 0% | b) | 0 | 0% | b) | 0
| 2) Khal slope potection | 195 | a) | 195 | 0 | a) | 0 | 0 | a) | 0 | 0 | a) | 0 | 0%
|  |  | b) | 195 | 0 | b) | 0 |  | b) | 0 | 0% | b) | 0
| 3) Construction of Roads | 100 | a) | 100 | 0 | a) | 0 | 0 | a) | 0 | 0 | a) | 0 | 0%
|  |  | b) | 0 | - | b) | 0 |  | b) | 0 | 0% | b) | 0
| 4) Construction of walkway | 240 | a) | 80 |  | a) | 130 | 2 | a) | 130 | 1.5 | a) | 30 | 12.5%
|  |  | b) | 80 | - | b) | 0 | 0% | b) | 130 | 75% | b) | 30
| 5) Construction of RCC Drain | 90 | a) | 40 |  | a) | 30 | 0.5 | a) | 30 | 0.35 | a) | 20 | 22.22%
|  |  | b) | 40 | - | b) |  | 66.67% | b) | 30 | 75% | b) | 20
| 6) Construction of Bridge/Culvert | 1012 | a) | 100 | LS | a) | 320 | 100% | a) | 320 | 0 | a) | 592 | 58.5%
|  |  | b) | 100 | LS | b) |  | 100% | b) | 320 | 0% | b) | 592
| 7) Construction of RCC Ghatla | 65 | a) | 27 | 2m | a) | 38 | 2 | a) | 38 | 0 | a) | 0 | 0%
|  |  | b) | 27 | 2m | b) |  | 2 | b) | 38 | 50% | b) | 0
| 8) Street Lighting & Garden Light | 50 | a) | 30 | LS | a) | 0 | LS | a) | 0 | 0 | a) | 20 | 40%
|  |  | b) | 30 | LS | b) |  | LS | b) | 0 | 0% | b) | 20
| 9) Construction of Rides. | 158 | a) | 110 | - | a) | 45 | 0.2 | a) | 45 | 0.18 | a) | 3 | 1.899%
|  |  | b) | 110 |  | b) | 0 | 4% | b) | 45 | 0% | b) | 3
| 10) Landscaping | 50 | a) |  | LS | a) | 0 | 9% | a) | 0 | 0 | a) | 50 | 100% | 488
|  |  | b) |  | LS | b) |  | LS | b) | 0 | 0% | b) | 50
| 11) Public Toilets | 30 | a) |  | 0 | a) | 0 | LS | a) | 0 | 0 | a) | 30 | 100%
|  | 0 | b) |  | LS | b) |  | LS | b) | 0 | 0% | b) | 30
| 12) Tree Plantation | 20 | a) |  | - | a) | 0 | 1 | a) | 0 | 0 | a) | 20 | 100%
|  |  | b) |  |  | b) |  | 1 | b) | 0 | 0% | b) | 20
| Physical Contingency | 20 | a) |  |  | a) | 0 | 0 | a) |  |  | a) | 20 | 100%
|  |  | b) | 0 | - | b) | 0 | 0 | b) | 0 | 0 | b) | 20
| Price Contingency | 15 | a) |  |  | a) | 0 | - | a) |  |  | a) | 15 | 100%
|  |  | b) | 0 | - | b) | 0 | 0 | b) | 0 | 0 | b) | 15
| Grand Total : | 2580 | 1200 |  |  | 580 |  |  | 580 |  | 0% | 817 |  | 31.67% | 2000 | 2017
2000
7 | Progress of Procurement in current FY: 2019-20
[7 empty] | Goods |  | Works |  | Services |  | Total
| a) Work Orders (WO) issued in last year or before | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| i) Number of WOs. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| ii) Expenditure in current FY | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| b) Work Orders (WO) issued during the reporting period, 2019-20. | [7 empty] | 0 |  | 0 |  | 0
| i) Number of WOs. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| ii) Expenditure in current FY. | [5 empty] | 0 |  | 580 |  | 0 |  | 580
| c) WOs to be issued during the rest of the period of the FY. 2019-20 | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| d) Total expenditure for procurement up to reporting month, 2019-20 (a ii + b ii). | [5 empty] | 0 |  | 580 |  | 0 |  | 580
| e) Total budget/allocation for procurement, 2019-20. | [5 empty] | 0 |  |  |  | 0 |  | 0
| f) Cumulative expenditure upto last year. | [5 empty] | 0 |  | 580 |  | 0 |  | 580
| g) Total allocation as per DPP/TPP. | [5 empty] | 0 |  | 0 |  | 0 |  | 0
| h) Unspent amount as per DPP/TPP. | [5 empty] | 0 |  |  |  | 0 |  |  |  | -580 | Balance
8 | Particulars of reimbursement claim and receipts :
| Initial advance Receipt with date | Upto 30/06/2019 | [6 empty] | During 2019-20
|  | Expenditure |  |  |  | Reimbursement in claimed |  |  | Expenditure |  |  |  | Reimbursement
|  | Direct payment |  | Payment from project account |  |  |  |  | Direct payment |  | Payment from project account
| 1 | 2 |  | 3 |  | 4 |  |  | 5 |  | 6 |  | 7
Sushanto Kumar Paul
Project Director
Phone No: 8144210.

## Status Rpt
Scheme Status Report
Katakhal Improvement and surrounding area Beautyfication Project
Local Government Engineering Department (LGED)
Financial Year : 2019-2020
Reporting Period : |  | 2020-06-01
(Taka in Lakh)
Name of the project (name of Development Assistance partner) | (RADP Provision) & Total Fund Released (GOB + RPA) (Tk.) | No. of Scheme / Contracts |  |  | Work Plan Target |  | Achievement | [5 empty] | Physical Progress (%) | Total Fund Spent (GOB + RPA) | Remarks
|  | New Schemes/ Contracts (No.) | Carried Over Contracts/ Excess Programmes of Previous Year (No.) | Total (No.) | Last Date for Awarding Contract | Work Plan Target (No.) | Schemes Prepared (No.) | Schemes Preparation under process (No.) | Tender Called (No.) | Tender Evaluation under process (No.) | Works going on (No.) | Schemes Completed (No.)
Katakhal Improvement and surrounding area Beautyfication Project | 580 | 8 (Nos.) | 7 | 8 (Nos.) |  | 0 | - | - | 8 | - | 11 | - | 95% | 580
580
(580+0)
0
Sushanto Kumar Paul
Project Director
Phone No: 8144210.

## Purchase
µq msµvšÍ Z_¨vejx t 2019-20 A_© eQ‡ii AMÖMwZ (Ryb/2020 ch©šÍ)
(j¶ UvKvq)
µwgK bs | cÖK‡íi bvg | gvjvgvj |  |  |  |  | c~Z© |  |  |  |  | †mev |  |  |  |  | K) wmwW f¨vUmn µqLv‡Z †gvU eivÏ (2019-20) L) wmwW f¨vU | K) wmwW f¨vUmn µqLv‡Z †gvU e¨q L) wmwW f¨vU | µqLv‡Z Ae¨wqZ eivÏ (2019-20) | †gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
|  | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvwi/2020 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvwi/2020 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_© eQ‡i ev c~‡e© cÖ`vbK…Z |  | RyjvB/19-Ryb/20 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvwi/2020 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v
|  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2018-19 A_© eQ‡ii cÖK…Z e¨q | Kvh©v‡`‡ki msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
97 | wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí¦ | 10wU | 690 | - | - | - | 10wU | 690 | 4 | 1000 | - | - | 0 | - | - | - |  |  | - | 580 | 99.95%
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí
62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦
‡dvb b¤^it 8144210

## Modified_form
2019-2020 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq GwWwcf~³ ev¯Íevqbvaxb cÖKímg~‡ni AMÖMwZi ch©v‡jvPbv QK-1
gv‡mi bvg t Ryb/2020
ms¯’v t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
(j¶ UvKvq)
µt bs | cÖK‡íi bvg (†gqv`Kvj) | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ e¨q | Aby‡gvw`Z wWwcwc/AviwWwcwcÕi Procurement Plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2019 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2019-2020 evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄf~Z c~bf©iY e¨q ( Ryb /19 ch©šÍ) L) †gvU cybf©iY e¨q (19-20 GwWwc) M) †gvU cybf©iY `vex †ck (19-20 AviGwWwc) N) †gvU cybf©iY cvwß (19-20 GwWwc) | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/ AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | AvM÷/19 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Erm
[6 empty] | 2019-2020 GwWwc eivÏ | 2019-2020 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`k cÖ`vb, Avw_©K I †fŠZ j¶¨gvÎv AwR©Z bv nIqvi KviY (19-20 GwWwc)
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q/AMÖMwZ (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ (19-20 GwWwc) |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ †UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q (19-20 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q (19-20 GwWwc)
|  | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvs‡k) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | j¶¨gvÎv (%) | AMÖMwZ (%) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) | ‡gvU (cY¨) (c~Z©) (†mev) |  |  | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | % | ‡gvU (%) wRIwe(%) cÖKí mvnvh¨(%) UvKvsk (%) | eQi/gvm
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
97
| wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí¦ ev¯ÍevqbKvj t 01-01-2017 nB‡Z 30-06-2020 ch©šÍ | 2580 | 1100 | 14/2210 | Õ0/0.00 | 1480 | 0 | 0 | 580 | 580 | 25% | 25% | 5/698.00 | 0 | 0 | (0/0.00) | - | N/A | 1680(65.00%) |  | 900.00 (34.88%)
|  | 2580 | 1100 | 0/0.00 | (0/0.00) | 1480 | 0 | 0 | 580 | 580 | 25% | 25% | 5/698 | 0 | (0/0.00) | (0/0.00) |  | N/A | 1680(65.00%) | 95% | 900.00 (34.88%) | 1eQi †gqv` e„w×mn 2q ms‡kvab cÖwµqvaxb | wRIwe
|  | (-) | (-) | 12/2195.00 | (0/0.00) | (-) | (-) | (-) | (-) | (-) |  |  | (4/912.00) | 0 | (0/0.00) | (0/0.00) |  | N/A | (-) |  | (-)
|  | (-) | (-) | 2/15.00 | (0/0.00) | (-) | (-) | (-) | (-) | (-) |  |  | (1/7.00) | 0 | (0/0.00) | (0/0.00) |  | N/A | (-) |  | (-)
me©‡gvU |  | 2580 | - | 14/2210 | - | 1480 | 0 | 0 | 580 | 580 | 25% | 25% | 5/698.00 | 0 | (0/0.00) | (0/0.00) |  |  | 1680(65.00%) | 95% | 900.00 (34.88%) | 1 eQi 9 gvm | wRIwe
(mykvšÍ Kzgvi cvj)
cÖKí cwiPvjK
wmivRMÄ ‡cŠimfv KvUvLvj I cvk^©eZ©x ¯’v‡bi †mŠ›`h© ea©b cÖKí
[19 empty] | 62, cwðg AvMviMvuI, †j‡fj-6, †k‡ievsjv bMi XvKv¦ |  |  |  |  | (mykvšÍ Kzgvi cvj)
[19 empty] | ‡dvb b¤^it 8144210 |  |  |  |  | cÖKí cwiPvjK
‡dvb-8144210

## Sheet1
1) Dc‡Rjv moK Dbœqb | 59.5 | wKtwgt | 4760
2) BDwbqb moK Dbœqb | 178.51 | wKtwgt | 11603.15
3) MÖvg moK Dbœqb | 345.1 | wKtwgt | 22431.5
4) Dc‡Rjv mo‡K exR wbg©vY | 254.5 | wgUvi | 1527
5) BDwbqb mo‡K exR wbg©vY | 315.6 | wgUvi | 1893.6
6) MÖvg mo‡K exR wbg©vY | 543 | wgUvi | 3258
7) NvUjv | 7 | wU | 105
8) nvU/evRvi | 12 | wU | 180
9) ‡RwV | 5 | wU | 75
10) moK ‡givgZ I eÿYv‡eÿY | 78 | wKtwgt | 1560
11) moK wbivcËv | ‡_vK |  | 400
47793.25