## DPP Bandarban scheme list
Proposed Roads & Structures
Name of The Project : Rural Infrastructure Development Project: Chittagong Hill Tracts- 2nd Phase
District : Bandarban
Sl No | Upazila | Name of the Road and proposed chainage | ID No | Nature of works | Total Road length |  |  | Already completed length |  |  | Unit Cost |  |  | Proposed Length |  |  | Estimated Cost (Tk.in Lakh) | Remaining length to be developed |  |  | Remarks
[5 empty] | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) |  | Road (Km) | Bridge (m) | Culverts (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road.(Ch.2950-7060m) | 403143002 | BC | 10.12 | 111.6 | 51.81 | 2.95 | 71.6 | 51.81 | 105 | 6.5 | 4.5 | 4.11 | 0 | 0 | 431.55 | 3.06 | 40 | 0
2 |  | Holudia-Vaggakul-Tankbati Road.(Ch.00-3350m) | 403143005 | BC | 27.15 | 108 | 207.85 | 6.15 | 90 | 194.35 | 105 | 6.5 | 4.5 | 3.35 | 48 | 0 | 663.75 | 17.65 | -30 | 13.5
Sadar Sub-Total (UNR) | [13 empty] | 7.46 | 48 | 0 | 1095.3 | 20.71 | 10 | 13.5
3 | Lama | Lama muk-Selertua road Ch.00-3300m | 403513007 | HBB | 8.72 | 140 | 28.8 | 0 | 13 | 0 | 84 | 6.5 | 4.5 | 3.3 | 0 | 22.85 | 380.025 | 5.42 | 127 | 5.95
4 |  | Shelertua-Rupashi Para Road Ch.00-1650m | 403513010 | HBB | 5.1 | 126.1 | 28.5 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 1.65 | 30 | 21.7 | 431.25 | 3.45 | 96.1 | 6.8
Lama Sub-Total (UNR) | [13 empty] | 4.95 | 30 | 44.55 | 811.275 | 8.87 | 223.1 | 12.75
5 | Ruma | Thana HQ (Ruma Mukh)-Gallanga UP office Road(Ch.00-1230m) | 403913003 | BC | 22 | 604.4 | 197 | 0 | 12.4 | 21.8 | 105 | 6.5 | 4.5 | 1.23 | 152 | 40 | 1297.15 | 20.77 | 440 | 135.2 | Not a Single Bridge
Ruma Sub-Total (UNR) | [13 empty] | 1.23 | 152 | 40 | 1297.15 | 20.77 | 440 | 135.2
6 | Thanchi | Thanchi-Balipara road.(Ch.1000-6200m) | 403952001 | BC | 12.17 | 450 | 12.5 | 1 | 31.95 | 6.5 | 135 | 6.5 | 4.5 | 5.2 | 76 | 0 | 1196 | 5.97 | 342.05 | 6
Thanchi Sub-Total (UZR) | [13 empty] | 5.2 | 76 | 0 | 1196 | 5.97 | 342.05 | 6
7 | Alikadam | Alikadam Bazar- Naikhongchari Border via Rombow road. (Ch.00-2880m) | 403042002 | BC | 2.88 | 94 | 15 | 0 | 14 | 5 | 135 | 6.5 | 4.5 | 2.88 | 80 | 10 | 953.8 | 0 | 0 | 0
Alikadam Sub-Total (UZR) | [13 empty] | 2.88 | 80 | 10 | 953.8 | 0 | 0 | 0
8 | Alikadam | Alikadam-Dochori Road (ch.00-2000m) | 403043004 | BC | 14 | 56 | 41 | 9.5 | 56 | 41 | 105 | 6.5 | 4.5 | 2 | 0 | 0 | 210 | 2.5 | 0 | 0
9 |  | Sonaichori R&H-Varirmukh Road.(Ch.821-1571m) | 403043005 | BC | 3 | 0 | 9 | 0.821 | 0 | 9 | 105 | 6.5 | 4.5 | 0.75 | 0 | 1 | 83.25 | 1.429 | 0 | -1
10 |  | Chikkan para (cioni para) road (Ch.1441-2191m) | 403043006 | BC | 3 | 24 | 9 | 1.44 | 24 | 4 | 105 | 6.5 | 4.5 | 0.75 | 0 | 1 | 83.25 | 0.81 | 0 | 4
11 |  | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 00-2600m) | 403043007 | BC | 2.6 | 70 | 11 | 0 | 0 | 9 | 105 | 6.5 | 4.5 | 2.6 | 70 | 2 | 737 | 0 | 0 | 0
Alikadam Sub-Total (UNR) | [13 empty] | 6.1 | 70 | 4 | 1113.5 | 4.739 | 0 | 3
12 | Rowangchari | Taracha up - Meufapara(Ruma Road - Tarasa UP Office Road) road.(Ch.4200-6500m) | 403893007 | HBB | 8.5 | 119 | 66.85 | 4.2 | 74 | 22.7 | 84 | 6.5 | 4.5 | 2.3 | 0 | 27 | 314.7 | 2 | 45 | 17.15
13 |  | Kalaghata to Taracha UP office road(Ch.00-3000m) | 403893004 | BC | 8.25 | 237 | 57.05 | 5 | 12 | 47.15 | 105 | 6.5 | 4.5 | 3 | 50 | 0 | 640 | 0.25 | 175 | 9.9
Rowangchari Sub-Total (UNR) | [13 empty] | 5.3 | 50 | 27 | 954.7 | 2.25 | 220 | 27.05
14 | Naikhonchari | Naikhongchari - Lemouchari road.(Ch.00-4000m) | 403733001 | BC | 10.4 | 0 | 24 | 0 | 0 | 9 | 105 | 6.5 | 4.5 | 4 | 0 | 0 | 420 | 6.4 | 0 | 15
15 |  | Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road.(Ch.00-3000m) | 403733002 | BC | 19 | 54 | 28 | 9 | 54 | 28 | 105 | 6.5 | 4.5 | 3 | 30 | 0 | 510 | 7 | -30 | 0
16 |  | North Ghumdum - Tumbru Bazar road.(Ch.1000-4000m) | 403733003 | BC | 7.78 | 77.5 | 36.4 | 1 | 14.5 | 16.4 | 105 | 6.5 | 4.5 | 3 | 20 | 0 | 445 | 3.78 | 43 | 20
17 |  | Dochori - Ali Kadam road.(Ch.00-3000m) | 403733004 | BC | 32 | 517 | 35.3 | 9 | 134 | 16.3 | 105 | 6.5 | 4.5 | 3 | 0 | 0 | 315 | 20 | 383 | 19
18 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600-9060m | 403733008 | HBB | 9 | 237 | 30.9 | 1.65 | 12 | 30.9 | 84 | 6.5 | 4.5 | 7.2414 | 220 | 0 | 2038.2776 | 0.1086 | 5 | 0 | At Ch.1650m Required-105m Bridge
Naikhongchari Sub-Total (UNR) | [13 empty] | 20.2414 | 270 | 0 | 3728.2776
|  | Total UZR | [11 empty] | 8.08 | 156 | 10 | 2149.8
|  | Total UNR | [11 empty] | 45.2814 | 620 | 115.55 | 9000.2026
Grand Total (UZR+UNR) | [13 empty] | 53.3614 | 776 | 125.55 | 11150.0026
[18 empty] | Road | Bridge | Culvet
[13 empty] | Road UZR cost |  |  |  |  | 1090.8 | 1014 | 45
3232.95
[13 empty] | Road UNR cost |  |  |  |  | 1217.2776 | 4030 | 519.975
[18 empty] | 5541.0276 | 5044 | 564.975 | 11150.0026

## DPP Khagrachari scheme list
Proposed Roads & Structure
Name of the Porject: Rural Intrastructure Development Project: Chittagong Hill Tracts-2nd Phase
District: Khagrachari
Sl. No. | Upazila | Name of the Road and Proposed Chainage | ID No | Nature of Works | Total Road Length |  |  | Already Completed Length |  |  | Unit Cost |  |  | Proposed Length |  |  | Estimated Cost (Tk. in Lakh) | Remaining Length to be development
[5 empty] | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) |  | Road (km) | Bridge (m) | Culvert (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Bhaibonchara GC-Gumti GC via Chota Bari Para Road (Sadar Part) (Ch: 00-7000m). | 446492001 | BC | 7 | 150 | 0 | 0 | 150 | 0 | 135 | 6.5 | 4.5 | 7 | 0 | 0 | 945 | 0 | 0 | 0
2 | Sadar | Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road (Sadar Part) (Ch: 00-2940m). | 446492002 | BC | 16 | 31.1 | 0 | 0 | 11.1 | 0 | 135 | 6.5 | 4.5 | 2.94 | 20 | 0 | 526.9 | 13.06 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 9.94 | 20 | 0 | 1471.9
3 | Sadar | Golabari Union H/Q (Upper Perachara)-Pora Bazar via Bhuachari & Cristian Para Road (Ch: 4100-7040m). | 446493001 | BC | 11 | 102.36 | 0 | 4.1 | 102.36 | 0 | 105 | 6.5 | 4.5 | 2.9 | 0 | 0 | 304.5 | 4 | 0 | 0
4 | Sadar | Bichitola Bazar-Khagrachari Sadar HQ (Battali) Road (Ch: 1130-3130m). | 446493002 | BC | 8 | 88.7 | 0 | 1.13 | 78.7 | 0 | 105 | 6.5 | 4.5 | 2 | 10 | 0 | 275 | 4.87 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 4.9 | 10 | 0 | 579.5
5 | Matiranga | BGumti GC-Bhibonchara GC Road. (Matiranga Part) (Ch: 00-2500m). | 446702002 | BC | 8.19 | 45 | 0 | 0 | 0 | 0 | 135 | 6.5 | 4.5 | 2.5 | 45 | 0 | 630 | 5.69 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 2.5 | 45 | 0 | 630
6 | Matiranga | Belchari Union H/Q-Ajuddah Bazar Road (Ch: 6480-7980m). | 446703004 | BC | 15 | 77.7 | 0 | 6.48 | 0 | 0 | 105 | 6.5 | 4.5 | 1.5 | 40 | 0 | 417.5 | 7.02 | 37.7 | 0
7 | Matiranga | Gumti UP Office-Bhibonchara GC via Tailafang & Gakulmani BDR Camp Road (Ch: 00-1500m). | 446703010 | BC | 8.57 | 10 | 0 | 0 | 0 | 0 | 105 | 6.5 | 4.5 | 1.5 | 0 | 0 | 157.5 | 7.07 | 10 | 0
8 | Matiranga | Gumti Bazar-Ramsharia Bazar Road (Ch: 4280-7280m). | 446703006 | BC | 7.28 | 0 | 0 | 4.28 | 0 | 0 | 105 | 6.5 | 4.5 | 3 | 0 | 0 | 315 | 0 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 6 | 40 | 0 | 890
9 | Panchari | Panchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) (Ch: 3291-7292m). | 446772001 | BC | 15 | 138 | 54.07 | 3.29 | 102.07 | 39.7 | 135 | 6.5 | 4.5 | 4 | 0 | 15 | 607.5 | 7.71 | 35.93 | -0.63
10 | Panchari | Panchari GC-Bhaibonchara GC via Shantipur Road (Panchari Part) (Ch: 11058-12280m). | 446772003 | BC | 12.28 | 202 | 151.7 | 11.058 | 152 | 149.7 | 135 | 6.5 | 4.5 | 1.17 | 50 | 2 | 491.95 | 0.052 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 5.17 | 50 | 17 | 1099.45
11 | Panchari | Logong Union H/Q-Tanakkya Para Bazar Road (Panchari Part) (Ch.8500-12500m). | 446773001 | BC | 19 | 96 | 11 | 8.5 | 54 | 11 | 105 | 6.5 | 4.5 | 5 | 20 | 0 | 655 | 5.5 | 22 | 0
|  | Sub: Total (UNR) | [11 empty] | 5 | 20 | 0 | 655
12 | Mohalchari | Mahalchari GC-Maischari GC Road (Ch: 4118-6347m). | 446652001 | BC | 10.98 | 110.9 | 51.25 | 8.754 | 80.9 | 54.25 | 135 | 6.5 | 4.5 | 2.228 | 30 | 10 | 540.78 | -0.002 | 0 | -13
13 | Mohalchari | Maischari GC (Juramyachari)-Longadu GC Road (Mahalchari Part) (Ch: 2525-2950m & Ch: 3029-4817m). | 446652002 | BC | 15.5 | 139.5 | 20.6 | 2.604 | 100.5 | 20.6 | 135 | 6.5 | 4.5 | 2.2142 | 39 | 8 | 588.417 | 10.6818 | 0 | -8
14 | Mohalchari | Mahalchari GC (Singinala)-Khagrachari Sadar Upazila H/Q Road (Mahalchari Part) (Ch: 574-5574m). | 446652005 | BC | 12.85 | 52.52 | 23.3 | 1.284 | 42.52 | 23.3 | 135 | 6.5 | 4.5 | 5 | 10 | 20 | 830 | 6.566 | 0 | -20
|  | Sub: Total (UZR) | [11 empty] | 9.4422 | 79 | 38 | 1959.197
15 | Mohalchari | Sindukchari Union H/Q-Tinduck Chari Bazar Road (Ch: 1520-3520m). | 446653002 | BC | 10.86 | 0 | 0 | 1.52 | 0 | 0 | 105 | 6.5 | 4.5 | 2 | 0 | 0 | 210 | 7.34 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 2 | 0 | 0 | 210
16 | Dighinala | Panchari-Langadu road. [Dighinala GC-Panchari GC Via Nunchari Road] (Dighinala Part) (Ch: 2320-4320m). | 446432001 | BC | 22.12 | 207.3 | 72.1 | 2.318 | 37.3 | 37.5 | 135 | 6.5 | 4.5 | 2 | 40 | 0 | 530 | 17.802 | 130 | 34.6
17 | Dighinala | Choto Merung Bazar R&H - Baghaichari Upazila HQ Road (Ch: 2600-4600m). | 446432003 | BC | 6.2 | 76.7 | 13.9 | 2.595 | 19.7 | 1.2 | 135 | 6.5 | 4.5 | 2 | 0 | 10 | 315 | 1.605 | 57 | 2.7
|  | Sub: Total (UZR) | [11 empty] | 4 | 40 | 10 | 845
18 | Dighinala | Babuchara Union HQ-Naraichari Bazar via Dhanpata Manorath Talukdar Para Road (Ch: 2685-4185m). | 446433003 | BC | 26.85 | 332.35 | 58.04 | 10.85 | 82.55 | 36.07 | 105 | 6.5 | 4.5 | 1.5 | 7 | 0 | 203 | 14.5 | 242.8 | 21.97
|  | Sub: Total (UNR) | [11 empty] | 1.5 | 7 | 0 | 203
19 | Ramghar | Sonaipul GC-Hayako GC via Khagrabill Road (Ramghar Part) (Ch: 13650-15000m). | 446802001 | BC | 15 | 22 | 22.7 | 13.65 | 22 | 22.7 | 135 | 6.5 | 4.5 | 1.35 | 0 | 0 | 182.25 | 0 | 0 | 0
20 | Ramghar | Khagrabill GC-Manikchari GC via Batnatali Bazar Road (Ramghar Part) (Ch: 2000-4650m). | 446802002 | BC | 7.8 | 13 | 21.05 | 2 | 13 | 21.05 | 135 | 6.5 | 4.5 | 2.65 | 0 | 0 | 357.75 | 3.15 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 4 | 0 | 0 | 540
21 | Ramghar | Patachara Union H/Q-Guimara GC Road via Parshuramghat (Ramgarh Part) (Ch: 2000-4500m). | 446803002 | HBB | 6.25 | 0 | 17.82 | 2 | 0 | 17.82 | 84 | 6.5 | 4.5 | 2.5 | 0 | 7 | 241.5 | 1.75 | 0 | -7
|  | Sub: Total (UNR) | [11 empty] | 2.5 | 0 | 7 | 241.5
22 | Manikchari | Manikchari Union H/Q (Mohamuni)-Hatimura Bazar Road via Gaidhan (Ch: 520-3020m) | 446673002 | HBB | 20.54 | 12.5 | 41.4 | 0.52 | 12.5 | 27.4 | 84 | 6.5 | 4.5 | 2.5 | 0 | 5 | 232.5 | 17.52 | 0 | 9
23 | Manikchari | Jogyachola Bazar-Batnatali Union H/Q Road via Chadurkhil Bazar (Ch: 1220-1600m & 3150-6150m). | 446673004 | HBB | 12.05 | 118.5 | 36.6 | 9.05 | 36.5 | 23.5 | 84 | 6.5 | 4.5 | 3 | 50 | 13.1 | 635.95 | 0 | 32 | 0
|  | Sub: Total (UNR) | [11 empty] | 5.5 | 50 | 18.1 | 868.45
|  | Total (UZR) | [11 empty] | 35.0522 | 234 | 65 | 6545.547
|  | Total (UNR) | [11 empty] | 27.4 | 127 | 25.1 | 3647.45
|  | Grand Total (UZR+UNR) | [11 empty] | 62.4522 | 361 | 90.1 | 10192.997
[17 empty] | Road | Bridge | Culvet
[12 empty] | Road UZR cost |  |  |  |  | 4732.047 | 1521 | 292.5
2037
[12 empty] | Road UNR cost |  |  |  |  | 672 | 825.5 | 112.95
[17 empty] | 7441.047 | 2346.5 | 405.45 | 10192.997

## DPP Rangamati Scheme list
Proposed Roads & Structures
Name of the Project: RIDP-CHT-II
District: Rangamati
SL No | Upazila | Name of the Road and proposed Chainage | ID No | Nature of Works | Total Road Length |  |  | Already Completed Length |  |  | Unit cost |  |  | Proposed Length |  |  | Estimated Cost (Tk. In lakh) | Remaining Length to be developed |  |  | Remarks
[5 empty] | Road (m) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (m) | Bridge (m) | Culvert (m) | Road (m) | Bridge (m) | Culvert (m) |  | Road (m) | Bridge (m) | Culvert (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km | 484212001 | BC | 30.43 | 640 | 16 | 1.8 | 15 | 2 | 135 | 6.5 | 4.5 | 1.5 | 120 | 3 | 996 | 27.13 | 505 | 11 | 2 Bridge Less then 100m
Sub total(UZR) |  |  |  |  | 30.43 | 640 | 16 | 1.8 | 15 | 2 | 135 | 6.5 | 4.5 | 1.5 | 120 | 3 | 996 | 27.13 | 505 | 11
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km | 484872004 | BC | 8 | 47 | 5 | 2.65 | 47 | 2 | 135 | 6.5 | 4.5 | 1.5 | 0 | 3 | 216 | 3.85 | 0 | 0
Sub total(UZR) |  |  |  |  | 8 | 47 | 5 | 2.65 | 47 | 2 | 135 | 6.5 | 4.5 | 1.5 | 0 | 3 | 216 | 3.85 | 0 | 0
3 | Langadu | Mainimukh -Forest office to Durchari Bazar road (Ch.3+500km - 8+500km)=5.00km | 484582004 | BC | 17.85 | 300 | 90 | 1.5 | 63 | 0 | 135 | 6.5 | 4.5 | 5 | 90 | 15 | 1327.5 | 11.35 | 147 | 75 | Bridge 3 Nos Less then 100.00m
Sub-Total (UZR) |  |  |  |  | 17.85 | 300 | 90 | 1.5 | 63 | 0 | 135 | 6.5 | 4.5 | 5 | 90 | 15 | 1327.5 | 11.35 | 147 | 75
4 | Baghaichari | Marishya bazar-Durchari bazar road (Ch: 9.00 to 10.50km)=1.5km & Bridge at Ch: 10.20km | 484072003 | BC | 10.5 | 198 | 100 | 9 | 100 | 90 | 135 | 6.5 | 4.5 | 1.5 | 120 | 5 | 1005 | 0 | 78 | 5 | Durchari Bridge 120.00m
5 | Baghaichari | Durchari bazar-Karallyachari bazar Road up to Supari Pata Chara (Ch.00-3.00km)=3.00km | 484072005 | BC | 25 | 200 | 95 | 0 | 0 | 5 | 135 | 6.5 | 4.5 | 3 | 55 | 5 | 785 | 22 | 145 | 85 | Bridge 4 Nos Less then 100.00m
Sub-Total (UZR) |  |  |  |  | 35.5 | 398 | 195 | 9 | 100 | 95 | 270 | 13 | 9 | 4.5 | 175 | 10 | 1790 | 22 | 223 | 90
6 | Belaichari | Belaichari -Farua bazar road (Ch.12+000 to 16+000km)=4.00km | 484292001 | BC | 44 | 1200 | 60 | 12 | 418 | 10 | 135 | 6.5 | 4.5 | 4 | 0 | 40 | 720 | 28 | 368 | 175
Sub-Total (UZR) |  |  |  |  | 44 | 1200 | 60 | 12 | 418 | 10 | 135 | 6.5 | 4.5 | 4 | 0 | 40 | 720 | 28 | 368 | 3050
7 | Jurachari | Jurachari H/Q-Shilchari G.C. road (Ch.1+000 to 6+500km)=5.00km & Bridge at Ch: 5+750km | 484472002 | BC | 13.43 | 204 | 60 | 1 | 15 | 8 | 135 | 6.5 | 4.5 | 5.5 | 120 | 10 | 1567.5 | 6.93 | 84 | 42 | Samira Bridge 120.00m Long
8 | Jurachari | 20.00m Long Bridge on Jurachari H/Q-Eraichari Ghat road at Ch: 1+690km | 484472001 | RCC | 4.15 | 200 | 10 | 4.15 | 180 | 10 | 135 | 6.5 | 4.5 | 0 | 20 | 0 | 130 | 0 | 20 | 0 | Bridge
Sub-Total (UZR) |  |  |  |  | 17.58 | 404 | 70 | 5.15 | 195 | 18 | 270 | 13 | 9 | 5.5 | 140 | 10 | 1697.5 | 6.93 | 104 | 42
9 | Kawkhali | Ghilachari - Panchari Road (Ch.3600 to 6600km)=3.00km | 484252003 | BC | 9.14 | 100 | 45 | 3.6 | 12 | 10 | 135 | 6.5 | 4.5 | 3 | 80 | 10 | 970 | 2.54 | 20 | 25 | 2Bridge
10 | Kawkhali | 20.00m Long Bridge on Kawkhali H/Q Sugarmill road (Ch.0+690km) | 484252001 | BC | 12 | 160 | 49 | 12 | 100 | 29 | 135 | 6.5 | 4.5 | 0 | 20 | 0 | 130 | 0 | 140 | 20 | Bridge
Sub-Total (UZR) |  |  |  |  | 21.14 | 260 | 94 | 15.6 | 112 | 39 | 270 | 13 | 9 | 3 | 100 | 10 | 1100 | 2.54 | 160 | 45
11 | Rajosthali | Rajasthali H/Q-Khansama para road (To words Bagmara GC) (Ch.2.650 to 4.650km)=2.00km | 484782001 | BC | 10.57 | 120 | 80 | 2.65 | 40 | 10 | 135 | 6.5 | 4.5 | 2 | 0 | 15 | 337.5 | 5.92 | 120 | 55
Sub-Total (UZR) |  |  |  |  | 10.57 | 120 | 80 | 2.65 | 40 | 10 | 135 | 6.5 | 4.5 | 2 | 0 | 15 | 337.5 | 5.92 | 120 | 55
12 | Kaptai | Baraghonia Market-Debotachari bazar viaTanchangapara road (Ch: 3+800-5+300km)=1.5km | 484363003 | BC | 8 | 60 | 6 | 3.8 | 60 | 6 | 105 | 6.5 | 4.5 | 1.5 | 0 | 3 | 171 | 2.7 | 0 | 0
Sub total(UNR) |  |  |  |  | 8 | 60 | 6 | 3.8 | 60 | 6 | 105 | 6.5 | 4.5 | 1.5 | 0 | 3 | 171 | 2.7 | 0 | 0
13 | Langadu | Kalapakuzza Union(Mahilla)-Mainimukh growth center road (Ch.0+000 to 4+000km)=4.00km & Bridge at Ch: 1+600km | 484583002 | HBB | 6.6 | 240 | 90 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 4 | 190 | 30 | 1706 | 2.6 | 50 | 60 | 2 Bridge. Hossain Pur Bridge 120.00m another is 70.00m
14 | Langadu | Bagachattar - C.O's Tila Road (Ch.0+000 to 2+000km)=2.00km | 484583005 | HBB | 5 | 500 | 150 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 0 | 10 | 213 | 3 | 500 | 140
Sub-Total (UNR) |  |  |  |  | 11.6 | 740 | 240 | 0 | 0 | 0 | 168 | 13 | 9 | 6 | 190 | 40 | 1919 | 5.6 | 550 | 200
15 | Baghaichari | Thana H/Q-Doser road(Ch: 1640 to 3640m)=2.00km | 484073004 | HBB | 15 | 100 | 60 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 30 | 10 | 408 | 13 | 70 | 803
Sub-Total (UNR) |  |  |  |  | 15 | 100 | 60 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 30 | 10 | 408 | 13 | 70 | 803
16 | Jurachari | Juraichari G.C.-Chalka para Via Lulang Chari road.(Ch: 00-2444m=2.44km) & (Ch: 3944-4944m=1.00km) =3.44km | 484473003 | HBB | 21.23 | 100 | 69 | 1.49 | 30 | 39 | 84 | 6.5 | 4.5 | 3.4405 | 50 | 15 | 681.4995 | 16.2995 | 50 | 15
Sub-Total (UNR) |  |  |  |  | 21.23 | 100 | 69 | 1.49 | 30 | 39 | 84 | 6.5 | 4.5 | 3.4405 | 50 | 15 | 681.4995 | 16.2995 | 50 | 15
17 | Naniarchar | R & H road - Karatchari via Golachari road (Ch.0+000 to 2+000km)=2.00km | 484753006 | HBB | 7.5 | 60 | 20 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 20 | 10 | 343 | 5.5 | 40 | 10
18 | Naniarchar | R&H road-West Dewan Para Ghat (Ch: 0+00-2km)=2.00km | 484753004 | HBB | 7.75 | 90 | 20 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 0 | 10 | 213 | 5.75 | 90 | 10
Sub-Total (UNR) |  |  |  |  | 15.25 | 150 | 40 | 0 | 0 | 0 | 168 | 13 | 9 | 4 | 20 | 20 | 556 | 11.25 | 130 | 20
Total (UZR) | [13 empty] | 27 | 625 | 106 | 8184.5
Total (UNR) | [13 empty] | 16.9405 | 290 | 88 | 3735.4995
Grand Total[(UZR)+(UNR)] | [13 empty] | 43.9405 | 915 | 194 | 11919.9995
[17 empty] | Road | Bridge | Culvet
[12 empty] | Road UZR cost |  |  |  |  | 3645 | 4062.5 | 477
157.5
[12 empty] | Road UNR cost |  |  |  |  | 1296.9995 | 1885 | 396
[17 empty] | 5099.4995 | 5947.5 | 873 | 11919.9995

## Rangamati (Maint)
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2015-2016
Reporting Month: August' 2020
[14 empty] | Reporting Date |  |  |  |  | 2026-07-28
District Name: Rangamati
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvet Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km |  | BC
Sub total Barkal:
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km |  | BC
Sub total Sadar:
Maintenance Work
1 | Sadar | Periodic Maintenance of Jhagrabil (R&H) - Kaptai (R&H) via Baradam Road . Ch. 2500-1550m) Effectiove length 2500m, ID No. 484252001 | RANG/SADAR/UZR/W23 | Maint | 2016-06-27 | 2.5 | 0 |  | Road 9: 10312574; Culvert 10: 0; Brigde 11: 0; Brigde 12: 10312574; Brigde 13: 0; Brigde 21: APP Approved (H/Q) | 1
Sub-Total Sadar : |  |  | 1 |  |  | 2.5 | 0 |  | 10312574 | 0 | 0 | 10312574 | 0 |  |  | 0 | 0 | 0% | 0%
1 | Kawkhali | Periodic Maintenance of Kawkhali HQ- Sugarmil Road ch. 10000-11000m, ID No. 484252001 | RANG/KAWK/UZR/W04 | Maint | 19-11-2015 | 1 | 0 |  | 12915546 | 0 | 0 | 12915546 | 0 | 2016-01-26 | 2017-02-24 | 11941512.7 | 2720000 | 40% |  | M/S SS Traders | WBM Gi KvR Pj‡Q¦ | 1
Sub-Total Kawkhali : |  |  | 1 |  |  | 1 | 0 |  | 12915546 | 0 | 0 | 12915546 | 0 |  |  | 11941512.7 | 2720000 | 40% | 0%
1 | Kaptai | Periodic Maintenance of Raikhali Barakolapara-Bangalhalia R&H ctg. Border via Bongnal road. At ch. 00-1000m, ID No. 484362003 | RANG/KAPTAI/UZR/W20 | Maint | 2016-05-03 | 1 | 0 |  | 3332804 | 0 | 0 | 3332804 | 18350 |  |  | 3000696.545 |  | 0% |  | M/S Marma Enterprise, Ruma, Bandarban | NOA Issued | 1
Sub-Total Kaptai : |  |  | 1 |  |  | 1 | 0 |  | 3332804 | 0 | 0 | 3332804 | 18350 |  |  | 3000696.545 | 0 | 0% | 0%
|  | Total Maintenance : | 3 |  |  | 4.5 | 0 |  | 26560924 | 0 | 0 | 26560924 | 18350 |  |  | 14942209.245 | 2720000 | 8.889% | 0%
[9 empty] | Brigde 13: Total Contract Package :; Brigde 16: 3 | 3

## Bandarban
Monthly Progress Report Under
Disaster Damage Rural Road Improvement Project: 3Hill Districts | [25 empty] | 64
Financial Year 2019-2020
Reporting Month: August' 2020
[16 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Bandarban
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) |  | Approved Length |  |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Pro/Work/ (Km) | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Pro/Work/ | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Lama | Improvement of Lama mukh to silartua Road.(HBB) (Ch.3+300km – 8+000km); Effective length=4700 m; ID No: 403513008 | BAN/LAMA/UNR/W03 | HBB | 2019-07-03 | 0 | 4.7 | 9 | 0 | 0 | Road 9: 52783684; Culvert 10: 6280068; Brigde 11: 0; Brigde 12: 59063752; Brigde 13: 0; Brigde 16: 61864174.398; Brigde 20: AC - UT JV | 1
2 |  | Improvement of Silartuah-Rupashipara. (HBB) Road. Ch: 1650m-6200m); Effective Length= 4550m. ID No. 403513011 | BAN /LAMA/UNR/W16 | HBB | 2019-05-11 | 0.43 | 4.55 | 11 |  | 28177733 | Road 9: 62737992; Culvert 10: 8905563; Brigde 11: 0; Brigde 12: 99821288; Brigde 16: 104534470.642; Brigde 20: M/S HASAN ENTERPRISE & M M TRADERS (JV) | 1
3 |  | Rehabilitation of Rajbari – Lama Rupashipara road (Ch. 0.00-3010.00 m), Effective length=3010.00m; ID No. 403515014 | BAN/LAMA/VILL./W25 | BC | 29/01/2020 | 0.98 | 3.01 | 12 |  | 9185334 | Road 9: 38808458; Culvert 10: 5341929; Brigde 12: 53335721; Brigde 13: 1152737; Brigde 16: 55470337.547; Brigde 20: Mohammed Eunus & Brothers (Pvt) Ltd. | 1
|  | Lama Sub-Total : | 3 |  |  | 1.41 | 12.26 | 32 | 0 | 37363067 | Road 9: 154330134; Culvert 10: 20527560; Brigde 11: 0; Brigde 12: 212220761; Brigde 13: 1152737; Brigde 16: 221868982.587; Brigde 17: 0 | 3
1 | Naikhonchari | Improvement of Tumbru GC - Kutupalong RHD Road. (Ch.4+000km – 6+000km); Effective length=1981 m; ID No: 403732009 | BAN/NAIK /UZR/W04 | BC | 25/03/19 | 0.24 | 1.981 | 12 | 0 | 3614488 | Road 9: 26622108; Culvert 10: 5680627; Brigde 11: 0; Brigde 12: 35917223; Brigde 16: 38343079.39; Brigde 20: M/S HASAN ENT & Emmu Con(Jv), | 1
2 |  | (i) Construction of 45.00m long RCC Girder Bridge On Tumbru GC Road. Ch: 1850m; (ii) Construction of 32.00m long PSC Girder Bridge On Tumbru GC Road. Ch: 1950m; ID No. 403732006 (iii) Construction of 32.00m long PSC Girder Bridge On Sonaichari UP- Panjakana Bazar RHD Road (N.Chhari Part) Road. Ch: 260m; (iv) Construction of 12.00m long RCC Girder Bridge On Sonaichari UP- Panjakana Bazar RHD Road (N.Chhari Part) Road. Ch: 310m; ID No. 403733014 | BAN/NAIKHONG/BRIDGE/W07 | Bridge | 22/07/19 |  |  |  | 121 |  | Brigde 11: 70089786; Brigde 12: 70089786; Brigde 16: 72010113; Brigde 20: NSUT- JV | 1
3 |  | Improvement of Chakdhala Bazar - Ashartali BGB Camp Road. (Ch.0+000km – 4+500km); Effective length= 4.425 m; ID No: 403733006 | BAN/NAIK /UNR/W08 | BC | 2019-07-08 |  | 4.425 |  |  |  | Road 9: 56882148; Brigde 12: 56882148; Brigde 13: 10193187; Brigde 16: 62282794.161; Brigde 20: Mr. U.T Mong, Maddayam Para, Bandarban. | 1
4 |  | i) Improvement of Sonaichari UP- Panjakana Bazar RHD Road (N.Chhari Part) (Ch.1+250km – 2+250km); Effective length= 0.956 m; ID No: 403733014 ii) Improvement of Tumbru GC - Kutupalong RHD Road (Ch.6+000km – 9+200km); Effective length= 3.176 m; ID No: 403732009 | BAN/NAIK/UNR.UZR/W09 | BC | 2019-07-08 |  | 4.13 |  |  |  | Road 9: 60600692; Culvert 10: 4021132; Brigde 12: 64621824; Brigde 16: 70918411.919; Brigde 20: Mr. U.T Mong, Maddayam Para, Bandarban. | 1
5 |  | Rehabilitation of Eidgor UP- Shapergara Bazar Via Kangarbill GPS & Kagojikhola Police Camp Road.(N.Chhari Part); Ch. 0.00-7500.00m ID No. 403733013 | BAN/NAIKHONG/UNR/W10 | Bc | 29/08/19 | 2.5 | 7.453 | 4 |  | 1331825 | Road 9: 118658367; Culvert 10: 2685971; Brigde 12: 122676163; Brigde 13: 14489504; Brigde 16: 128588550.63; Brigde 20: M/S Milton Traders & Mominul Hoque (JV) | 1
6 |  | Rehabilitation of Naikhongchari UZ HQ – Alikadam UZ HQ Road via Dochari UP Road. (Ch. 15050m-18350m). Effective Length: 3010.00m ID No: 403732007 | BAN/NAIK /UZR/W14 | Bc | 24/10/19 | 0 | 3.01 | 6 | 0 | 0 | Road 9: 56055999; Culvert 10: 3697990; Brigde 12: 59753989; Brigde 13: 3287787; Brigde 16: 54930931.982; Brigde 20: S. Ananta Bikash Tripura, Khagrachari, Sadar, Khagrachari | 1
7 |  | Improvement of Baischari UPC – Dochari UPC via Longgudhu mukh Bakkhali Road. (Ch. 7000m-12000m). Effective Length: 4832.00m ID No: 403733002 | BAN/NAIK /UNR/W15 | Bc | 24/10/19 | 0.115 | 4.832 | 6 | 0 | 891340 | Road 9: 94305029; Culvert 10: 3697990; Brigde 11: 0; Brigde 12: 98894359; Brigde 13: 2486032; Brigde 16: 93026749.798; Brigde 20: S. Ananta Bikash Tripura, Khagrachari, Sadar, Khagrachari | 1
8 |  | Rehabilitation of Kachubunia RHD – Reju amtali Bazar BGB Camp via mog ghat Bazar Road (Ch.0+000km – 1+700km); & (Ch.2+225km – 5+755km); Effective length=5158 m; ID No: 403733005 | BAN/NAIK /UNR/W05 | Bc | 2019-10-04 |  | 5.158 | 3 |  |  | Road 9: 64844474; Culvert 10: 2636569; Brigde 12: 67481043; Brigde 13: 10753845; Brigde 16: 69116372.01; Brigde 20: S. Ananta Bikash Tripura, Khagrachari, Sadar, Khagrachari | 1
9 |  | Rehabilitation of Tumbru GC - BTV Relay Center RHD via Pachimkul Road. (Ch.0+000km – 3+000km); Effective length=3000 m; ID No: 403732010 | BAN/NAIK /UZR/W06 | Bc | 2019-10-04 |  | 3 |  |  |  | Road 9: 37909162; Brigde 12: 37909162; Brigde 13: 6017005; Brigde 16: 40476971.09; Brigde 20: M/S Hasan Enterprise 7 Emu Construction JV | 1
10 |  | i) Construction of 33.00m long RCC Girder Bridge On Naikhongchari UZ HQ – Alikadam UZ HQ Road via Dochari UP Road. Ch: 18.50km ID No. 403732007 ii) Construction of 33.00m long RCC Girder Bridge On Naikhongchari UZ HQ – Alikadam UZ HQ Road via Dochari UP Road. Ch: 17.00km; ID No. 403732007 iii) Construction of 22.00m long RCC Girder Bridge On Naikhongchari UZ HQ – Alikadam UZ HQ Road via Dochari UP Road. Ch: 17.50km; ID No. 403732007 iv) Construction of 32.00m long PC Girder Bridge On Baischari UPC – Dochari UPC via Longgudhu mukh Bakkhali Road. Ch: 12.00km; ID No. 403733002 | BAN/NAIKHONG/BRIDGE/W17 | Bridge | 2019-06-11 |  |  |  | 120 |  | Brigde 11: 71138487; Brigde 12: 71138487; Brigde 16: 78192230.473; Brigde 20: M/S Emu Construction & Hasan Enterprise (JV) | 1
11 |  | i) Construction of 96.00m long RCC Girder Bridge with 32m via Duct On Baischari UPC – Dochari UPC via Longgudhu mukh Ch: 9.50km; ID No. 403733002 ii) Construction of 64.00m long RCC Girder Bridge On Baischari UPC – Dochari UPC via Longgudhu mukh Ch: 7.50km; ID No. 403733002 | BAN/NAIKHONG/BRIDGE/W19 | Bridge | 2019-01-12 |  |  |  | 160 |  | Brigde 11: 96023586; Brigde 12: 96023586; Brigde 16: 105467881.631; Brigde 20: M/S HASAN ENTERPRISE & U. T Mong ( jv). | 1
12 |  | Rehabilitation of Naikhongchari UZ HQ – Alikadam UZ HQ Road via Dochari UP road (Ch. 18350-233500m), Effective length=5000m; ID No. 403732007 | BAN/NAIKHONG/UZR/W23 | UZR | 19/01/20 | 0.42 | 5 | 24 |  | 12742995 | Road 9: 57663242; Culvert 10: 12170644; Brigde 12: 82576881; Brigde 16: 88343329.514; Brigde 20: M/S HASAN ENTERPRISE & U T MONG (JV) | 1
13 |  | Improvement of Baischari UPC – Dochari UPC via Longgudhu mukh Bakkhali Road road (Ch. 12000-170000.00m), Effective length=5000.00m; ID No. 403733002 | BAN/NAIKHONG/UNR/W24 | UNR | 19/01/20 |  |  |  |  | 11689746 | Road 9: 49154141; Culvert 10: 12170644; Brigde 12: 73014531; Brigde 16: 78782678.947; Brigde 20: M/S HASAN ENTERPRISE & U T MONG (JV) | 1
|  | Naikhonchari Sub-Total : | 13 |  |  | 2.855 | 38.989 | 31 | 401 | 5837653 | Road 9: 622695362; Culvert 10: 22420279; Brigde 11: 237251859; Brigde 12: 936979182; Brigde 13: 47227360; Brigde 16: 980480094.545; Brigde 17: 0 | 13
1 | Rowangchari | A) Improvement of Bangchari Road (Rowangchari – Bangchari) Road at (Ch. 00m-5740m). ID No: 403893001 B) Rehabilation of Rowangchari Bazar G.C Road at (Ch. 00m-965 m). ID No: 403892002 | BAN/ROWAN/UZR.UNR/W11 | BC | 25/09/19 |  | 6.7 |  |  |  | Road 9: 118179064; Culvert 10: 14423725; Brigde 12: 132602789; Brigde 16: 144000000; Brigde 20: Mohammed Eunus & Brothers (pvt) Ltd | 1
2 |  | A) Construction of 35.00m Long PC Girder Bridge on Bangchari Road. (Rowangchari – Bangchari) Road at ch.4942 m. Construction of 40.00m Long PC Girder Bridge on Bangchari Road. (Rowangchari – Bangchari) Road at ch.5580 m.ID No: 403893001 B) Construction of 90.00m PC Girder Bridge on Bangchari Road. (Rowangchari – Bangchari Road) at ch.265m. ID No: 403893001 | BAN//ROWAN/BRIDGE/W12 | Bridge | 25/09/19 |  |  |  | 165 |  | Brigde 11: 93071052; Brigde 12: 93071052; Brigde 16: 102775147.39; Brigde 20: S. Ananta Bikash Tripura, Khagrachari, Sadar, Khagrachari | 1
3 |  | Improvement of Rowangchari-Gheraw Road. (Ch. 3020m-7650m). ID No: 403893003 | BAN/ROWAN/UNR/W13 | BC | 2019-10-10 | 2.025 | 4.63 |  |  | 9019963 | Road 9: 59014386; Brigde 12: 68034349; Brigde 13: 9601085; Brigde 16: 65299910.3; Brigde 20: Mr. U. T Mong | 1
4 |  | Improvement of Bengchari Road (Rowangchari-Bengchari Road.); (Ch: 5740m-11200m); Effective Legth= 5460m. ID No. 403893001 | BAN/ROWAN/UNR/W18 | HBB | 2019-06-11 | 2.025 | 5.46 |  |  | 10084345 | Road 9: 112702495; Brigde 12: 122786840; Brigde 16: 128691303.328; Brigde 20: M/S Hasan Enterprise & M M Traders (JV) . | 1
5 |  | Rehabilitation of Kalaghata to Taracha UP Office Road. (Ch. 350.00-5120.00 m), Effective length=4770.00m; ID No. 403893004 | BAN/ROWAN/UNR/W30 | BC | 25/02/2020 | 2.5 | 4.77 | 7 |  | 10049974 | Road 9: 63153708; Culvert 10: 5105275; Brigde 12: 78308957; Brigde 13: 3041093; Brigde 16: 81769233.162; Brigde 20: M/S Emu Construction & Hasan Enterprise (JV) | 1
|  | Rowangchari Sub-Total : | 5 |  |  | 6.55 | 21.56 | 7 | 165 | 29154282 | 353049653 | 19529000 | 93071052 | 494803987 | 12642178 |  |  | 522535594.18 | 0 | 0 | 0 |  |  | 5
1 | Sadar | i) Improvement of Holudia-Vaggakul-Tankabati via Chimbuk RHD Road. (Ch.13670 - 16000m); Effective length=2330 m; ii) Improvement of Holudia-Vaggakul-Tankabati via Chimbuk RHD Road. (Ch.16000 - 18200m); Effective length=2200 m; iii) Improvement of Holudia-Vaggakul-Tankabati via Chimbuk RHD Road. (Ch.18200 - 20450m); Effective length=2250 m; ID No: 403143005 | BAN/SADR/UNR/W01 | BC | 2019-03-01 | 3.89 | 6.78 | 0 | 0 | 8718493 | Road 9: 62946655; Culvert 10: 0; Brigde 11: 0; Brigde 12: 71665148; Brigde 13: 12662876; Brigde 16: 78007501; Brigde 20: Mr. U. T Mong | 1
2 |  | i) Improvement of Swualok UP-Sultanpur Road. (Ch.00.00 - 2000m); Effective length=2000 m; ii) Improvement of Swualok UP-Sultanpur Road. (Ch.2000 - 4100m); Effective length=2100 m; | BAN/SADR/UNR/W02 | BC | 2019-04-01 | 2.3 | 4.1 | 0 | 0 | 6979976 | Road 9: 40108088; Culvert 10: 0; Brigde 11: 0; Brigde 12: 47088064; Brigde 13: 6726626; Brigde 16: 53035587; Brigde 20: Mr. U. T Mong | 1 | 1
3 |  | Improvement of Chemedolu para-Kuhalong UP road (Ch. 0.00-5000m), Effective length=5000m; ID No. 403143004 | BAN/SADAR/UNR/W20 | BC | 29/12/19 | 1.5 | 5 | 0 | 0 | 4823942 | Road 9: 69834006; Culvert 10: 0; Brigde 11: 0; Brigde 12: 74657948; Brigde 13: 10330087; Brigde 16: 78009279.48; Brigde 20: Mr. U. T Mong | 1
4 |  | Improvement of Chemedolu para-Kuhalong UP road (Ch. 5000-10000m), Effective length=5000m; ID No. 403143004 | BAN/SADAR/UNR/W21 | BC | 29/12/19 | 1.1 | 5 | 0 | 0 | 3481040 | Road 9: 64967027; Culvert 10: 0; Brigde 11: 0; Brigde 12: 68448067; Brigde 13: 11371870; Brigde 16: 71631458.433; Brigde 20: Mr. U. T Mong | 1
5 |  | Construction of 35.00m long PSC Girder Bridge On Bikirichara - Muslimpra Road. Ch: 401.00m; ID No. 403145028 | BAN/SADAR/BRIDGE/W29 | Bridge | 20/02/20 |  |  |  | 35 |  | Road 9: 23225802; Brigde 12: 23225802; Brigde 13: 11371870; Brigde 16: 24375479.199; Brigde 20: M/S Emu Construction & Hasan Enterprise (JV) M/S Emu Construction & Hasan | 1
6 |  | Rehabilitation of Chimbuk R & H Road to Hativanga Tripura Para Road (Ch. 0.00-755 m), Effective length = 755.00m; ID No. 403144055 | BAN/SADAR/VILL/W31 | BC | 18/03/2020 | 0.755 |  |  |  | 11178876 | Brigde 12: 11178876
7 |  | Improvement of K B Road – Kanapara Road at (Ch. 0.00-3000.00m), Effective length= 3000.00m; ID No. 403145008 | BAN/SADAR/VILL/W32 | BC | 25/03/2020 | 1.5 | 3 |  |  | 21711658 | Road 9: 52367836; Brigde 12: 74079494
8 |  | Improvement of K B Road – Bandarban University Connecting road. at (Ch. 0.00-2000.00m), Effective length= 2000.00m; ID No. 403144055 | BAN/SADAR/VILL/W33 | BC | 25/03/2020 | 1.7 | 2 |  |  | 27671034 | Road 9: 29826892; Brigde 12: 57497926
|  | Sub TotalSadar | 8 |  |  | 12.745 | 25.88 | 0 | 35 | 84565019 | Road 9: 343276306; Culvert 10: 0; Brigde 11: 0; Brigde 12: 427841325; Brigde 13: 52463329; Brigde 16: 305059305.112; Brigde 17: 0 | 5
1 | Alikadam | (i) Improvement of Babu para – up Nungkyomey house road (Ch. 0.00-600m), Effective length=600m; ID No. 403045018 (ii) Improvement of Noa Bazar – Marma para road (Noapara GPS road) via marma para Bonik Para road (Ch. 00.00-1320.00m), Effective length=1320.00m; ID No. 403044008 (iii) Improvement of Noa para – Roambow – Moncha para road (Ch. 00.00-1629.00m), Effective length=1629.00m; ID No. 403044005 (iv) Improvement of Bagan para Jamey Mosque via Monu Member House up to PIO Bridge road (Ch. 00.00-1320.00m),Effective length=1320.00m; ID No. 4030445013 (v) Improvement of Noa Para Centre Jamey Mosque Road – via Mohamad Sarber House up to Kasem Member House road (Ch. 00.00-800.00m), Effective length=800.00m; ID No. 403045012 | BAN/ALIKADAM/VILL/W22 | BC | 13/01/20 | 2.5 | 5.669 | 3.5 | 0 | 15326121 | Road 9: 45196647; Culvert 10: 1344565; Brigde 11: 0; Brigde 12: 61867333; Brigde 13: 3876632; Brigde 16: 57853843.214; Brigde 20: S. Ananta Bikash Tripura, Khagracha | 1
|  | Sub TotalAlikadam | 1 |  |  | 2.5 | 5.669 | 3.5 | 0 | 15326121 | Road 9: 45196647; Culvert 10: 1344565; Brigde 11: 0; Brigde 12: 61867333; Brigde 13: 3876632; Brigde 16: 57853843.214; Brigde 17: 0 | 1
1 |  | Rehabilitation of Ruma Battali Bazar R&H Road-Galanga UP Office Road. at (Ch.0.00m-6055.00m); Effective Length: 6055.00m. ID No: 403913004 | BAN/RUMA /UNR/W26 | BC | 2020-03-02 | 2.36 | 6.055 |  |  | 15681080 | Road 9: 84984755; Brigde 12: 100665835; Brigde 13: 14221452; Brigde 16: 110500644.325; Brigde 20: Mr. U.T Mong | 1
2 | Ruma | Rehabilitation of UZ HQ-Munnuam Bazar via Paindu UP office Road. at (Ch.0.00m-7540.00m); Effective Length: 7540.00m. ID No: 403913002 | BAN/RUMA /UNR/W27 | BC | 2020-03-02 | 2.36 | 7.54 |  |  | 11907008 | Road 9: 98200711; Brigde 12: 110107719; Brigde 13: 18802130; Brigde 16: 120391663.465; Brigde 20: M/S Emu Construction & Hasan Enterprise (JV) | 1
2 |  | Rehabilitation of UZ HQ-Munnuam Bazar via Paindu UP office Road. at (Ch.7540.00 m-13572.00m).; Effective Length: 6032.00m .ID No: 403913002 | BAN/RUMA /UNR/W28 | BC | 2020-03-02 | 1.78 | 6.032 |  |  | 24967005 | Road 9: 81498007; Brigde 12: 106465012; Brigde 13: 17635807; Brigde 16: 120292425.473; Brigde 20: M/S HASAN ENTERPRISE & U T MONG (JV) | 1
|  | Sub Total Ruma: | 3 |  |  | 6.5 | 19.627 | 0 | 0 | 52555093 | Road 9: 264683473; Culvert 10: 0; Brigde 11: 0; Brigde 12: 317238566; Brigde 13: 50659389; Brigde 16: 351184733.263; Brigde 17: 0 | 3
Grand Total Bandarban Dist: |  |  | 33 |  |  | 26.06 | 104.358 | 73.5 | 601 | 172246142 | Road 9: 1518548102; Culvert 10: 63821404; Brigde 11: 330322911; Brigde 12: 2450951154; Brigde 13: 117362236; Brigde 16: 2438982552.901; Brigde 17: 0 | 30

## Khagrachari
Monthly Progress Report Under
Disaster Damage Rural Road Improvement Project: 3Hill Districts
Financial Year 2019-2020
Reporting Month: August' 2020
[16 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Khagrachari
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  |  | Approved Estimated Cost (Taka) |  |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) |  | Culvert Length (m) | BridgeLength (m) | Road |  | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
District Name: Khagrachari
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) | Approved Length |  |  |  | Approved Estimated Cost (Taka) |  |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Pro/Work/ (Km) | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Pro/Work | Road | Culvert 11: Culvert; Brigde 12: Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Matiranga | Improvement of Matiranga Tannakkapara RHD (Palaspur)- Gumti GC Road.. (Ch.0+000km – 4+380km); Effective length=2600.00 m; ID No: 446702005 | KHAGRA/MATIRA/UZR/W01 | BC | 2019-04-03 |  | 2.6 |  |  |  | 22022925 |  |  | 22022925 | 6566548 | 30/5/19 | 2020-09-06 | 23013956.023 | 16970504 | 70% |  | M/S RIP ENTERPRISE, Narankhaiya, Sadar, Khagrachari. |  | 1
2 |  | Improvement of Gumti Union H/Q-Ramsira Bazar (R&H) Road. (Ch.3+000km – 7+800km); Effective length=4350.00 m; ID No: 446703006 | KHAGRA/MATIRA/UNR/W02 | BC | 2019-04-03 | 3.53 | 3.56 |  |  | 348516 | 35395083 |  |  | 35743599 | 9212707 | 27/5/19 | 2020-12-10 | 37352030.853 | 34760404 | 95% |  | M/S Selim & Brothers, Arambagh, Sadar, Khagrachari. |  | 1
0
3 |  | Improvement of Matiranga Tannakkapara RHD(Ajuddah more) – Ramgor Upazila HQ Road (Matiranga Part) (Ch.7980m – 9905m); Effective length= 1925.00 m; IDNo: 446702004 | KHAGRA/MATIRAN/UZR/W18 | BC | 2019-04-11 | 0.15 | 1.925 |  |  | 1945471 | 23359066 | Brigde 12: 25304537; Brigde 13: 261811; Brigde 16: 25289538.044; Brigde 20: Sikder Ent. & Kabi Ranjan (JV) | 1
4 |  | Construction of 45.00m long RCC Girder Bridge on Matiranga Tannakkapara RHD(Ajuddah more) – Ramgor Upazila HQ Road(Matiranga Part) at Ch . 9+905Km. ID No: 446702004 | KHAGRA/MATIRANGA/BRIDGE/W30 | Bridge | 22/07/2020 |  |  |  | 45 |  |  | Brigde 11: 21675891; Brigde 12: 21675891
5 |  | Construction of 42.00m long RCC Girder Bridge on Belchari Union HQ to Ajudda Bazar Road at Ch 12235.00m. (Matiranga Tannakkapara RHD(Ajuddah more) – Ramgor Upazila HQ Road (Matiranga Part) ID No: 446702004 | KHAGRA/MATIRANGA/BRIDGE/W32 | Bridge | 2020-04-08 |  |  |  | 42 |  |  | Brigde 11: 25954719; Brigde 12: 25954719
6 |  | Construction of 42.00m long RCC Girder Bridge on Gumti GC-Bhibonchara GC Road. at Ch 4100.0m; ID No: 446702002 | KHAGRA/MATIRANGA/BRIDGE/W33 | Bridge | 2020-04-08 |  |  |  | 42 |  |  | Brigde 11: 33085099; Brigde 12: 33085099
7 |  | Improvement of Gumti GC-Bhibonchara GC Road. (Matiranga Part) Road. (Matiranga Part) (Ch.4000.00m – 8280.00m); Effective length= 4280.00 m; IDNo: 446702002 | KHAGRA/MATIRA/UZR/W34 | HBB | 2020-04-08 |  | 4.28 |  |  |  | 43704101 | Brigde 12: 43704101
|  | Sub: Total: Matiranga | 7 |  |  | 3.68 | 12.365 | 0 | 129 | 2293987 | 124481175 | Culvert 10: 0; Brigde 11: 80715709; Brigde 12: 207490871; Brigde 13: 16041066; Brigde 16: 85655524.92; Brigde 17: 51730908 | 3
1 |  | Improvement of Sindukchari UP Office -Guimara GC via Nakrai para road. (Ch.1160m – 2058m & 6668-11400); Effective length=5400 m; ID No: 446633001 | KHAGRA/GUMARA/UNR/W05 | BC | 24/03/19 | 1.115 | 5.4 |  |  | 10190568 | 46581177 | Brigde 12: 56771745; Brigde 13: 13398041; Brigde 16: 62306831.774; Brigde 17: 1429; Brigde 18: 10%; Brigde 20: M/S Selim & Brothers | 1
2 | Guimara | Improvement of Sindukchari UP Office -Guimara GC via Nakrai para road. (Ch.2058m – 6668m); Effective length=4300 m; ID No: 446633001 | KHAGRA/GUMARA/UNR/W06 | BC | 24/03/19 | 0.324 | 4.3 |  |  | 2608866 | 45493998 | Brigde 12: 48102864; Brigde 16: 52672652.907; Brigde 20: M/S Selim & Brothers | 1
3 |  | Rehabilitation of Hapchari UP Office-Batnatali Union H/Q Road. [Jalia Para-Batnatali Road] (Ramgarh Part). (Ch.0+000km – 5+000km); Effective length=4968m; ID No: 446633003 | KHAGRA/GUMARA/UNR/W07 | BC | 24/03/19 | 0.125 | 4.968 |  |  | 854644 | 59322644 | Brigde 12: 60177288; Brigde 13: 12916492; Brigde 16: 65831086.709; Brigde 17: 47358647; Brigde 18: 70%; Brigde 20: M/S Selim & Brothers | 1
4 |  | (i) Construction of 50.00m long RCC Girder Bridge on Sindukchari UP Office -Guimara GC via Nakrai para Road. at ch.2128.00m. ID No: 446633001 (ii) Construction of 88.00m long RCC Girder Bridge on Sindukchari UP Office -Guimara GC via Nakrai para road. at Ch 8278.00m. ID No: 446633001 (iii) Construction of 90.00m long PC Girder Bridge on Sindukchari UP Office -Guimara GC via Nakrai para road. at Ch 3758.00m. ID No: 446633001 | KHAGRA/GUMARA/BRIDGE/W19 | Bridge | 2019-07-11 |  |  |  | 228 |  |  | Brigde 11: 150335749; Brigde 12: 150335749
5 |  | Construction of 40.00m long PSC Girder Bridge on Gumara (CTG, RHD) Road –Kukichara Road at Ch .0+010Km. ID No: 446634036 Package No. WD/DDRRIP-3HD/ | KHAGRA/GUIMARA/BRIDGE/W29 | Bridge | 16/06/20 |  |  |  | 40 |  |  | Brigde 11: 22966208; Brigde 12: 22966208
|  | Sub: Total: Guimarar | 5 |  |  | 1.564 | 14.668 | 0 | 268 | 13654078 | 151397819 | 0 | 173301957 | 338353854 | 26314533 | 0 | 0 | 180810571.39 | 47360076 | 0.1 | 0 | 0 | 0 | 3
1 | Sadar & Diginala | i) Improvement of Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road. (Sadar Part) (Ch.4+967km – 7+800km); Effective length= 2.833 m; ID No: 446492002 ii) Improvement of Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road. (Sadar Part) (Ch.7+800km – 10+650km); Effective length= 2.850 m; ID No: 446492002 iii) Improvement of Dighinala GC - Panchari GC Via Nunchri Road (Dighinala part) (Ch.5+320km – 9+320km); Effective length= 4.000 m; ID No: 446432001 | KHAGRA/SADAR.DHIGI/UZR/W11 | BC | 24/06/19 | 1.56 | 9.68 |  |  |  | 129245183 | Brigde 12: 129245183; Brigde 13: 14542982; Brigde 16: 147325971.27; Brigde 18: 20%; Brigde 20: S. Ananta Bikash Tripura. | 1
2 | Sadar & Ramghar | i) Improvement of Khagrabill GC-Manikchari GC via Batnatali Bazar Road by HBB. (Ramgarh Part) (Ch.5+750km – 7+200km) & (Ch.7+550km – 7+800km); Effective length= 1700 m; IDNo: 446802002 ii) Improvement of Kampara RHD-Khagrabill GC Road by HBB. (Ch.4+400km – 6+500km); Effective length= 2100 m; ID No: 446802004 iii) Improvement of Bichitola Bazar-Khagrachari Sadar HQ (Battali) Road by HBB. (Ch.3+330km – 5+520km); Effective length= 2190 m; ID No: 446493002. iv) Improvement of Bhaibonchara GC-Muslim Para Road by BC. (Ch.0+000km – 1+952km); Effective length= 1952 m; ID No: 446495019; | KHGRA/SADAR.RAMGHAR/UZR/W12 | HBB | 2019-01-07 | 1.56 | 7.942 | 4 |  |  | 67829136 | Culvert 10: 3240543; Brigde 12: 71069679; Brigde 13: 4418463; Brigde 16: 74623204.52; Brigde 17: 13537296; Brigde 18: 95%; Brigde 20: S. Ananta Bikash Tripura. | 1
3 | Sadar & Diginala | i) Construction of 40.00m long PSC Girder Bridge on Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road. (Sadar Part). at ch.10+950km; ID No: 446492002 ii) Construction of 69.06m long RCC Girder Bridge on Dighinala GC-Bhbonchara GC via BuddhaPara, Alimgrtila Road. at ch.6+10km. ID No: 446432002 iii) Construction of 45.00m long RCC Girder Bridge on Dighinala GC-Bhbonchara GC via BuddhaPara, Alimgrtila Road. at ch.6+250km. ID No: 446432002 | KHAGRA/SADAR.DIGINALA/BRIDGE/W28 | Bridge | 2020-02-06 |  |  |  | 154 |  |  | Brigde 11: 80625528; Brigde 12: 80625528; Brigde 18: 20%
|  | Sub: Total: Matringa & Panchari | 3 |  |  | 3.12 | 17.622 | 4 | 0 | 0 | 197074319 | Culvert 10: 3240543; Brigde 11: 0; Brigde 12: 280940390; Brigde 13: 18961445; Brigde 16: 221949175.79; Brigde 17: 13537296; Brigde 18: 1.15 | 2
1 |  | Construction of 96.00m long RCC Girder Bridge on Bichitola Bazar-Khagrachari Sadar HQ (Battali) Road. at ch.4+140km. ID No: 446493002 | KHAGRA/SADAR/BRIDGE/W13 | Bridge | 25/09/19 |  |  |  | 96 |  |  | Brigde 11: 58277160; Brigde 12: 58277160; Brigde 16: 63536288; Brigde 17: 2579694; Brigde 18: 15%; Brigde 20: S. Ananta Bikash Tripura. | 1
2 | Sadar | i) Improvement of Golabari Union H/Q (Upper Perachara)-Pora Bazar via Bhuachari & Cristian Para Road. (Ch.7+040km – 10+740km); Effective length=3700.00 m; ID No: 446493001 ii) Improvement of Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road. (Sadar Part) (Ch.10+650km – 13+250km); Effective length=2600.00 m; ID No: 446492002. | KHAGRA/SADAR/UZR.UNR/W14 | BC | 2019-03-10 | 0.501 | 6.3 |  |  | 5097044 | 62562162 | Brigde 12: 67659206; Brigde 16: 70993908.733; Brigde 18: 10%; Brigde 20: Mr Construction - Shamsul alam | 1
3 |  | Improvement of Kamalchari (A.P.B.N) – Pora Bazar (Ultachari Road (Ch.1000m – 3000m); Effective length= 2000 m; IDNo: 446494002 | KHAGRA/SADAR/VILL/W22 | BC | 2020-12-03 | 0.75 | 2 |  |  | 1011884 | 24488374 | Brigde 12: 25500258; Brigde 13: 4738406; Brigde 16: 22950232.785; Brigde 20: Mr. U T Mong | 1
|  | Sub: Total: Sadar | 3 |  |  | 2.81 | 8.3 | 0 | 96 | 6108928 | 87050536 | 0 | 58277160 | 151436624 | 4738406 | 0 | 0 | 157480429.518 | 2579694 | 0.25 |  |  |  | 3
1 | Mohalchari | i) Improvement of Mahalchari GC (Machine Para)- Khagrachari Sadar Upazila H/Q Road. (Mahalchari Part) (Ch.6+226km – 8+500km); Effective length=2242.00 m; ID No: 446652005 ii) Improvement of Maischari GC (Juramyachari) - Longadu GC Road. (Mahalchari Part) (Ch.4+692km – 7+400km); Effective length=2699.00 m; ID No: 446652002 | KHAGRA/MAHAL/UZR.UNR/W15 | HBB | 2019-03-10 | 1.274 | 4.94 | 25 |  | 12456600 | 57372672 | Culvert 10: 14126900; Brigde 12: 83956172; Brigde 16: 92267832.14; Brigde 20: SB-RE-JV | 1
2 |  | Rehabilitation of Kayang Ghat Union H/Q- Maischari GC Road. (Ch.0+000km – 2+700km); Effective length=2700 m; ID No: 446653004 | KHAGRA/MAHAL/UNR/W09 | BC | 2019-07-04 |  | 2.7 | 33 |  |  | 26815077 | Culvert 10: 21027730; Brigde 12: 47842807; Brigde 13: 7573325; Brigde 16: 52134733.052; Brigde 17: 36520754; Brigde 18: 65%; Brigde 20: M/S RIP ENTERPRISE, Narankhaiya, Sadar, Khagrachari. | 1
3 |  | Rehabilitation of Kayang Ghat Union H/Q- Maischari GC Road. (Ch.2+700km – 5+619km); Effective length=2919 m; ID No: 446653004 | KHAGRA/MAHAL/UNR/W10 | BC | 2019-07-04 | 0.28 | 2.919 | 41.6 |  | 609972 | 28587397 | Culvert 10: 20074850; Brigde 12: 49272219; Brigde 13: 8139784; Brigde 16: 53953114.856; Brigde 17: 28174826; Brigde 18: 65%; Brigde 20: M/S Selim & Brothers, Arambagh, Sadar, Khagrachari. | 1
|  | Sub: Total:Mohalchari | 3 |  |  | 1.554 | 10.559 | 99.6 | 0 | 13066572 | 112775146 | 55229480 | 0 | 181071198 | 15713109 | 0 | 0 | 198355680.048 | 64695580 | 0 |  |  |  | 3
1 | Ramghar | i) Construction of 66.06m long RCC Girder Bridge on Patachara RHD-Guimara GC Road via Parshuramghat. (Ramgarh Part) at Ch 5+00.00km. ID No: 446802005 ii) Construction of 78.00m long RCC Girder Bridge on Ramgarh – Jagunath Para road. at Ch 5+60.00m. ID No: 446804009 Package No. WD/DDRRIP-3HD/ | KHAGRA/RAMGHAR/BRIDGE/W25 | Bridge | 2020-02-06 | 1.834 |  |  | 144.06 |  |  | Brigde 11: 95295985; Brigde 12: 95295985
|  | Sub: Total:Ramghar | 1 |  |  | 1.834 | 0 | 0 | 144.06 | 0 | 0 | 0 | 95295985 | 95295985 | 0 | 0 | 0 | 0 | 0
1 | Panchari | (i) Improvement of Panchari-Langadu Road. [Panchari GC (College Gate) - Dighinala GC via Gonggaram Para Road.] (Panchari Part) (Ch.6265m – 16000m); Effective length= 9735 m; ID No: 446772001 | KHAGRA/PANCHARI//UZR/W08 | BC | 2020-01-01 | 5.92 | 15.86 | 16 |  | 43960944 | 118521230 | Culvert 10: 7602829; Brigde 12: 170085003; Brigde 13: 12731714; Brigde 16: 186573301.905; Brigde 20: SB-RE (JV) | 1
(ii) Improvement of Pujgang (bazar) RHD Chikonchari Road. (Ch.0.00m – 1000m); Effective length= 1000 m; IDNo: 446774004 (iii) Improvement of Monipur - Tarabonchara Road. (Ch.1680m – 4800.00m); Effective length= 3120 m; IDNo: 446774015 (iv) Improvement of Lotiban Para to Sundar Kabari para Road. (Ch.0.00m – 2000m); Effective length= 2000 m; IDNo: 446774041
2 |  | Improvement of Nalkata (R &H) – Suknachari Tarabon Road (Ch.1000m – 4000m); Effective length= 3000 m; IDNo: 446774042 | KHAGRA/PANCHARI/VILL/W23 | BC | 2020-12-03 | 0.9 | 3 |  |  | 4693884 | 33888769 | Brigde 12: 38582653; Brigde 16: 34724387.835; Brigde 20: Mr. U T Mong | 1
3 |  | Improvement of Pujgang - Karalyachari Road (Ch.1000m – 3000m); Effective length= 2000 m; IDNo: 446774014 | KHAGRA/PANCHARI/VILL/W24 | BC | 2020-12-03 | 0.85 | 2 |  |  | 8230169.11 | 22027886 | Brigde 12: 30258055.11; Brigde 13: 4833951; Brigde 16: 28955575.429; Brigde 20: S. Ananta Bikash Tripura. | 1
4 |  | (i) Improvement of Pilot Road from BGB batalion with main road connects. (Ch.0.00m – 1500.00m); Effective length= 1500 m; IDNo: 446775001 (ii) Rehabilation of Hasan Nagar BDR Camp Road. at Ch. 00m-1000m. ID No: 446775009 | KHAGRA/PANCHARI/ VILL./W20 | Road | 2019-10-12 | 1.5 | 2.5 |  |  | 13324371 | 17643000 | Brigde 12: 30967371; Brigde 13: 1848574
|  | Sub: Total:Panchari | 4 |  |  | 7.67 | 20.86 | 16 | 0 | 56884997.11 | 174437885 | Culvert 10: 7602829; Brigde 11: 0; Brigde 12: 269893082.11; Brigde 13: 17565665; Brigde 16: 250253265.169; Brigde 17: 0 | 3
1 | Diginala | (i) Improvement of Dighinala GC-Bhbonchara GC via BuddhaPara, Alimgrtila Road. (Ch.5+000km – 6+520km); Effective length= 1520 m; ID No: 446432002 (i) Improvement of Dighinala GC-Bhbonchara GC via BuddhaPara, Alimgrtila Road. (Ch.5+000km – 6+520km); Effective length= 1520 m; ID No: 446432002 (ii) Improvement of Dighinala GC-Bhbonchara GC via BuddhaPara, Alimgrtila Road. (Ch.6+520km – 8+550km); Effective length= 2030 m; ID No: 446432002 | KHAGRA/DIGINALA/UZR/W27 | HBB | 2020-02-06 |  | 3.55 | 8 |  |  | 62781797 | Culvert 10: 5719632; Brigde 12: 68501429
2 |  | Construction of 72.00m long RCC Girder Bridge on Dighinala GC - Panchari GC Via Nunchri Road (Dighinala part) at Ch . 11+803Km. ID No: 446432001 | KHAGRA/DIGINALA/BRIDGE/W31 | Bridge | 26/07/2020 |  |  |  | 72 |  |  | Brigde 11: 27688577; Brigde 12: 27688577
|  | Sub: Total:Diginala | 2 |  |  |  | 3.55 | 8 | 72 | 0 | 62781797 | Culvert 10: 5719632; Brigde 11: 27688577; Brigde 12: 96190006
1 | Manikchari | Rehabilitation of Batnatali Union H/Q-Hapchari Union H/Q (Jaliapara) Road (Manikchari Part). (Ch.0+00km – 4+750km); Effective length=2145.50 m; ID No: 446673006 | KHAGRA/MANIK/UNR/W03 | BC | 2019-04-03 | #VALUE! | 0.49 |  |  | 1505336 | 18977752 |  |  | 20483088 | 5557583 | 30/5/19 | 44049 | 21404827.639 | 16684115 | 80% |  | M/S Selim & Brothers |  | 1
2 |  | Rehabilitation of Batnatoli Union H/Q (Dinechori)-Hatimura Bazar via Mora Dolu Road(Ch.0+00km – 4+150km); Effective length=3528.50 m; ID No: 446673009 | KHAGRA/MANIK/UNR/W04 | BC | 2019-04-03 | #VALUE! | 0.312 |  |  | 3272007 | 35152000 | Brigde 12: 38424007; Brigde 13: 8395720; Brigde 16: 42055020.96; Brigde 17: 33001745; Brigde 18: 65%; Brigde 20: S. Ananta Bikash Tripura. | 1
3 |  | Rehabilitation of Manikchari Union H/Q-Hatimura Bazar Road. (Ch.0+000km – 5+000km); Effective length=4948.22 m; ID No: 446673007 | KHAGRA/MANIK/UNR/W16 | BC | 2019-06-10 | 1.91 | 4.95 | 27 |  | 14370334.17 | 67243508.83 | Culvert 10: 1062649; Brigde 12: 82676492; Brigde 13: 11367378; Brigde 16: 90206097.25; Brigde 17: 19894457; Brigde 18: 20%; Brigde 20: S. Ananta Bikash Tripura. | 1
4 |  | Rehabilitation of Manikchari GC-Garitana GC via Joggyachola Road. (Ch.5+500km – 8+715km); Effective length= 3146.60 m; IDNo: 446672002 | KHAGRA/MANIK//UZR/W17 | BC | 2019-09-10 | 0.602 | 3.146 | 3.5 |  | 5184052 | 37271419 | Culvert 10: 1980680.28; Brigde 12: 44436151.28; Brigde 13: 6612226; Brigde 16: 47484115.047; Brigde 20: Mr Construction - Shamsul alam | 1
5 |  | Improvement of Tintohori GC-Garitana GC via Paccatila GPS Road. (Ch.0+000km – 7+717km); Effective length= 7.633 m; ID No: 446673010 | KHAGRA/MANIK/UNR/W26 | HBB | 2020-02-06 |  | 7.633 | 20 |  |  | 115784417 | Culvert 10: 13331022; Brigde 12: 129115439; Brigde 13: 17814605
|  |  | 5 |  |  | 5.03 | 8.898 | 30.5 | 0 | 24331729.17 | 158644679.83 | 3043329.28 | 0 | 315135177.28 | 49747512 |  |  | 201150060.896 | 69580317 | 1.65 | 0 | 0 | 0 | 4
Grand Total Khagrachari Dist: |  |  | 33 |  |  | 27.262 | 93.272 | 150.1 | 637.06 | 116340291.28 | 1005861559.83 | Culvert 10: 69116181.28; Brigde 11: 407590811; Brigde 12: 1935807187.39; Brigde 13: 149081736; Brigde 16: 1295654707.731; Brigde 17: 249483871 | 21

## Rangamathi
Monthly Progress Report Under
Disaster Damage Rural Road Improvement Project: 3Hill Districts
Financial Year 2019-2020
Reporting Month: August' 2020
[16 empty] | Reporting Date |  |  |  |  | 2026-07-28
District Name: Rangamati
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  |  | Approved Estimated Cost (Taka) |  |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Pro/Work/ (Km) | Road Length (Km) | Culvet Length (m) | Bridge Length (m) | Pro/Work | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 |  | 9 |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km |  | BC
Sub total Barkal:
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km |  | BC
Sub total Sadar:
1 | Sadar | Improvement of Jibtali GC- Kaptai R & H via Kakartkal Road (Ch.0+000km – 3+200km); Effective length=3200 m;ID No: 484872001 | RANG/SADAR/UZR/W01 | BC | 2019-07-03 | 0.465 | 3.2 | 0 | 0 | 3403250.07 | 37635146 | Culvert 10: 0; Brigde 11: 0; Brigde 12: 41038396.07; Brigde 13: 8894672; Brigde 16: 42885755.09; Brigde 20: S. Ananta Bikash Tripura. | 1
2 |  | Construction of 96.00m Long PC Girder Bridge with 48.00m via duct on BDR Sector HQ to Awlad Azar via Jhagrabil Road at ch.1.24km ID No: 484874015 | RANG/SADAR/BRIDGE/W05 | Bridge | 23/09/19 |  |  |  | 96 |  |  | Brigde 11: 96101789; Brigde 12: 96101789; Brigde 16: 103392005.097; Brigde 20: S. Ananta Bikash Tripura –M/S Rangamati Traders (Jv) | 1
3 |  | Rehabilitation of Rangamati Upazila HQ-Kaptai R & H via Baradam road. (Ch.00m – 5000m); Effective length= 5000 m; ID No: 484872002 | RANG/SADAR /UZR/W10 | BC | 22/12/19 | 1.3 |  |  |  | 15082163 |  | Brigde 11: 86020096; Brigde 12: 101102259; Brigde 13: 1246408; Brigde 16: 101961963.458; Brigde 20: M/S Rangamati Traders -Mayadhan Chakma | 1
4 |  | Rehabilitation of Rangamati Upazila HQ-Kaptai R & H via Baradam road. (Ch.5000m – 10000m); Effective length= 3711 m; ID No: 484872002 | RANG/SADAR /UZR/W11 | BC | 22/12/19 | 1.79 |  |  |  | 34751774 |  | Brigde 11: 69005856; Brigde 12: 103757630; Brigde 13: 930512; Brigde 16: 102015338.65; Brigde 20: M/S Rangamati Traders -Mayadhan Chakma | 1
5 |  | Rehabilitation of Rangamati Upazila HQ-Kaptai R & H via Baradam road. (Ch.10000m – 18116m); Effective length= 5234 m; ID No: 484872002 | RANG/SADAR /UZR/W14 | BC | 2020-01-01 | 1.68 | 5.234 |  |  | 13157599 | 99695340 | Brigde 12: 112852939; Brigde 13: 1640986; Brigde 16: 111575363.206; Brigde 20: M/S Rangamati Traders- S. Ananta Bikash Tripura (JV) | 1
6 |  | Construction of 48.00m Long RCC Girder Bridge on Upazilla sadar -Tabalchari R & H Road at ch.5200m ID No: 484872002 | RANG/SADAR/BRIDGE/W16 | Bridge | 2020-12-02 |  |  |  | 48 |  |  | Brigde 11: 40858811; Brigde 12: 40858811; Brigde 16: 36420876.27; Brigde 20: M/S ST – HE Traders (JV) | 1
7 |  | Construction of Protection Work of XEN Rangamati Office Road & Boundary Wall,; | RANG/SADAR/ /PRO. WORK/W18 | Pro. Work | 2020-12-03 |  |  |  |  | 14138222.46 |  | Brigde 12: 14138222.46; Brigde 16: 13431311.33; Brigde 20: M/S RS TRADERS | 1
8 |  | Construction of 120.00m Long RCC Bridge on sadar Upazilla HQ-Kaptai R&H via Baradam Road at Ch. 6070m; ID No: 484872002 | RANG/SADAR/BRIDGE/W21 | Bridge | 2020-09-08 |  |  |  | 120 |  |  | Brigde 11: 56615806; Brigde 12: 56615806
9 |  | Construction of 96.00m Long RCC Bridge on sadar Upazilla HQ-Kaptai R&H via Baradam Road at Ch. 6490m; ID No: 484872002 | RANG/SADAR/BRIDGE/W22 | Bridge | 2020-09-08 |  |  |  | 96 |  |  | Brigde 11: 44609311; Brigde 12: 44609311
10 |  | Construction of 48.00m Long RCC Bridge on sadar Upazilla HQ-Kaptai R&H via Baradam Road at Ch. 10740m; ID No: 484872002 | RANG/SADAR/BRIDGE/W23 | Bridge | 2020-09-08 |  |  |  | 48 |  |  | Brigde 11: 24428192; Brigde 12: 24428192
11 |  | Construction of 115.00m Long RCC Bridge on Rangamati Upazila Sadar – Tabalchari R &H Road at Ch. 1083m; ID No: 484872003 | RANG/SADAR/BRIDGE/W24 | Bridge | 2020-09-08 |  |  |  | 115 |  |  | Brigde 11: 59329424; Brigde 12: 59329424
|  | Sub-Total Sadar : | 11 |  |  | 5.235 | 8.434 | 0 | 523 | 80533008.53 | 137330486 | Culvert 10: 0; Brigde 11: 476969285; Brigde 12: 694832779.53; Brigde 13: 12712578; Brigde 16: 511682613.101; Brigde 17: 0 | 7
1 | Longadu | Development of Mainimukh GC - Durchari Bazar (GC) road. (Longadu Part) (Ch.8+500km – 10+400km); Effective length=1900 m; ID No: 484582004 | RANG/LANGU/UZR/W02 | BC | 2019-07-03 | 0.14 | 2 | 0 | 0 | 248724 | 16577307 | Culvert 10: 0; Brigde 11: 0; Brigde 12: 16826031; Brigde 13: 0; Brigde 16: 16263958.632; Brigde 20: M/S RIP ENTERPRISE, Narankhaiya, Sadar, Khagrachari. | 1
2 |  | Rehabilitation of Longadu HQ – Mainy Mukh GC Road. (Ch.3085m – 5000m); Effective length= 2912m;ID No: 484582001 | RANG/LONGU /UZR/W17 | BC | 2020-12-02 | 0.9 | 2.912 |  |  | 14156706 | 38240114 | Brigde 12: 52396820; Brigde 13: 5564741; Brigde 16: 49932550.312; Brigde 20: Mahrum Traders – REPL MH (JV) | 1
3 |  | Development of Attrakchara UPC Islamabad R& H Road at the Shop of Jalil PC-Sonai Market via the H/O Barek Chowkider Road (Ch:1000-2000m), Effective Length = 987.00; ID No. 484585011 | RANG/LANGU/VILL/W19 | BC | 19/03/2020 | 0.085 | 0.987 | 4 |  | 462068 | 16541125 | Culvert 10: 2961111; Brigde 12: 19964304
|  | Sub-Total Longadu : | 3 |  |  | 1.125 | 5.899 | 4 | 0 | 14867498 | 71358546 | Culvert 10: 2961111; Brigde 11: 0; Brigde 12: 89187155; Brigde 13: 5564741; Brigde 14: 0; Brigde 15: 0; Brigde 16: 66196508.944 | 2
1 | Baghaichari | Development of Durchari Bazar GC-Karallyachari Bazar GC Road. (Ch.4+800km – 6+700km); Effective length=1.813 m; ID No: 484072005 | RANG/BAGHAI/UZR/W03 | BC | 20/03/19 | 0 | 1.813 | 12 | 0 | 0 | 20344422 | Culvert 10: 8435369; Brigde 11: 0; Brigde 12: 28779791; Brigde 13: 343472; Brigde 16: 29919825.87; Brigde 20: S. Ananta Bikash Tripura.; Brigde 21: Re-Cast | 1
2 |  | Rehabilitation of Marishya Bazar GC-Durchari Bazar GC road. (Ch.4500m – 10230m); Effective length= 5623 m; ID No: 484072003 | RANG/BAGHAI /UZR/W15 | BC | 2020-01-01 | 3.68 | 5.623 |  |  | 22120909 | 89270067 | Brigde 12: 111390976; Brigde 13: 15717977; Brigde 16: 104821736.053; Brigde 20: Mr. U.T Mong, | 1
|  | Sub-Total Baghaichari : | 2 |  |  |  | 1.813 | 12 |  |  |  | Brigde 12: 140170767; Brigde 13: 16061449; Brigde 16: 134741561.923 | 2
1 | Naniaerchar | Development of Road from R&H to West Dewanpara (Ch.2000m – 5500m); Effective length= 3500 m; ID No: 484753004 | RANG/NANIAR /UNR/W13 | BC | 18/12/19 | 0.284 | 3.5 | 8 |  | 12934085 | 59025338 | Culvert 10: 3298782; Brigde 12: 75258205; Brigde 16: 74208390.196; Brigde 20: M/S Rangamati Traders-Mayadhan Chakma (JV) | 1
|  | Sub-Total Naniyerchar : | 1 |  |  | 0.284 | 3.5 | 8 | 0 | 12934085 | 59025338 | Culvert 10: 3298782; Brigde 11: 0; Brigde 12: 75258205; Brigde 13: 0; Brigde 14: 0; Brigde 15: 0; Brigde 16: 74208390.196 | 1
1 | Rajosthali | Rehabilatiop of Bangalhalia R & H - Longadu R & H via Nailka Chari Road. (Ch.6+010km – 9+654km); Effective length= 3.644 m; ID No: 484783002 | RANG/RAJOS /UNR/W04 | BC | 28/03/19 | 0.59 | 3.64 | 8 | 0 | 2814155.37 | 60600355.16 | Culvert 10: 3936649.47; Brigde 11: 0; Brigde 12: 67351160; Brigde 13: 9204046; Brigde 16: 65883462.854; Brigde 20: S. Ananta Bikash Tripura. | 1
2 |  | Construction of 48.00m Long RCC Bridge on Rajasthali H/Q-Bagmara GC via Khansama para Road. at Ch. 9070m; ID No: 484782001 | RANG/RAJOSTHALI/BRIDGE/W25 | Bridge | 18/08/2020 |  |  |  | 48 |  |  | Brigde 11: 19916647; Brigde 12: 19916647
3 |  | Construction of 48.00m Long RCC Bridge on Rajasthali H/Q-Bagmara GC via Khansama para Road. at Ch. 9533m; ID No: 484782001 | RANG/RAJOSTHALI/BRIDGE/W26 | Bridge | 18/08/2020 |  |  |  | 48 |  |  | Brigde 11: 19989613; Brigde 12: 19989613
|  | Sub-Total Rajosthali : | 3 |  |  | 0.59 | 3.64 | 8 | 96 | 2814155.37 | 60600355.16 | Culvert 10: 3936649.47; Brigde 11: 39906260; Brigde 12: 107257420; Brigde 13: 9204046; Brigde 16: 65883462.854; Brigde 17: 0 | 1
1 | Kaptai | Construction of 57.00m RCC Girder bridge on Bangchari R& H road- Awlad Bazar GC road at ch.1.20km ID No: 484364020 | RANG/KAPTAI/BRIDGE/W06 | Bridge | 30/10/19 |  |  |  | 57 |  |  | Brigde 11: 25536297; Brigde 12: 25536297; Brigde 16: 24586471.779; Brigde 20: M/S Rangamati Traders | 1
|  | Sub-Total Kaptai : | 1 |  |  | 0 | 0 | 0 | 57 | 0 | 0 | Culvert 10: 0; Brigde 11: 25536297; Brigde 12: 25536297; Brigde 13: 0; Brigde 16: 24586471.779; Brigde 17: 0 | 1
1 |  | Rehabilitation of Chairy Bazar R & H-Laxmichari HQ via Barmachari (Kawkhali Part) Road. (Ch.00m – 3600m); Effective length= 3600 m; ID No: 484252005 | RANG/KAWKHA /UZR/W07 | BC | 2019-03-11 | 0.23 | 3.6 |  |  | 940413 | 49860513 | Brigde 12: 50800926; Brigde 13: 6639346; Brigde 16: 48846702.703; Brigde 20: Mr. U T Mong | 1
2 | Kawkhali | Rehabilitation of Chairy Bazar R & H-Laxmichari HQ via Barmachari (Kawkhali Part) Road. (Ch.3600m – 6800m); Effective length= 3154 m; ID No: 484252005 | RANG/KAWKHA /UZR/W08 | BC | 2019-03-11 | 0.403 | 3.154 |  |  | 9547531 | 47792836 | Brigde 12: 57340367; Brigde 13: 7974178; Brigde 16: 61925741.38; Brigde 20: Mr. U T Mong | 1
3 |  | Rehabilitation of Chairy Bazar R & H-Laxmichari HQ via Barmachari (Kawkhali Part) Road. (Ch.6800m – 10500m); Effective length= 3612 m; ID No: 484252005 | RANG/KAWKHA /UZR/W09 | BC | 2019-03-11 | 0.633 | 3.612 |  |  | 7359689 | 46129825 | Brigde 12: 53489514; Brigde 13: 8913608; Brigde 16: 49932550.312; Brigde 20: S. Ananta Bikash Tripura. | 1
4 |  | Rehabilitation of Kawkhali HQ-Laxmichari HQ via Barmachari Road under Kawkhali Upazila . (Ch.00m–4575m); Effective length= 4575 m; ID No: 484252004 | RANG/KAW/UZR/W12 | BC | 18/12/19 | 1.53 | 4.575 | 10 |  | 15315511 | 29858727 | Culvert 10: 5720483; Brigde 12: 50894721; Brigde 16: 46798380.951; Brigde 20: Mr. U T Mong | 1
5 |  | Improvement of Ghagra R & H – Duniya Karbari Para road via Army camp road at ch. 00-1000m.; ID No. 484255008 | RANG/KAW/VILL/W20 | BC | 2020-05-08 |  | 1 |  |  |  | 12476867 | Brigde 12: 12476867; Brigde 13: 685658
|  | Sub-Total Kawkhali : | 5 |  |  | 2.796 | 15.941 | 10 | 0 | 33163144 | 186118768 | Culvert 10: 5720483; Brigde 11: 0; Brigde 12: 225002395; Brigde 13: 24212790; Brigde 16: 207503375.346; Brigde 17: 0 | 4
Grand Total Rangamati Dist: |  |  | 26 |  |  | 10.03 | 39.227 | 42 | 676 | 144311890.9 | 514433493.16 | Culvert 10: 15917025.47; Brigde 11: 542411842; Brigde 12: 1357245018.53; Brigde 13: 67755604; Brigde 16: 1084802384.143; Brigde 17: 0 | 18

## Total
Monthly Progress Report Under
Disaster Damage Rural Road Improvement Project: 3Hill Districts
Financial Year 2019-2020
Reporting Month: August' 2020
[17 empty] | Reporting date: |  |  | 2026-07-28
|  |  | As per approved DPP | [8 empty] | Approved Estimated Cost | [6 empty] | Total Contract |  | Total Fund spent till date (Tk) | Total Physical Progress (%) | Total Financial Progress (%) | Remarks
Sl. No. | District | Nature of Work | Total Scheme Nos |  | DPP Length |  |  | Estimated Cost (Tk) |  |  |  | Total Package No. |  | Approved Length |  |  | Total Approved Cost (Tk) | Salvage Cost (Tk) | Package No. | Contract Amount (Taka)
|  |  |  | Pro/Work/ (Km) | Road (km) | Culvert (m) | Bridge (m) | Road | Culvert | Bridge | Total |  | Pro/Work/ (Km) | Road (km) | Culvert (m) | Bridge (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
1 | Bandarban | Dev/Bridge | 9 |  | 37.82 | 111.97 | 230 | 7528.95 | 605.5 | 1840 | 9974.45 | 33 |  | 104.358 | 73.5 |  | 2450951154 | 117362236
|  | Rehab | 9 | 49.01 | 83.29 | 111.97 | 230 | 6360.55 | 605.5 | 1840 | 8806.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2438982552.901
|  | Pro/Work | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1143.92 | 0 | 26.06 | 0 | 0 | 0 |  | 0
2 | Khagrachari | Dev/Bridge | 14 |  | 72.93 | 171.53 | 332 | 12433.26 | 760.66 | 2696 | 15889.92 | 33 | 27.262 | 93.272 | 0 | 0 | 1935807187.39 | 149081736 |  |  | 249483871
|  | Rehab | 10 | 61.81 | 81.85 | 171.53 | 332 | 7095.75 | 760.66 | 2696 | 10552.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1295654707.731
|  | Pro/Work | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1441.6 | 0 | 27.262 | 0 | 0 | 0 | 0 | 0
3 | Rangamati | Dev/Bridge | 11 |  | 17.02 | 93.5 | 397.5 | 3298.6 | 421.48 | 3180 | 6900.08 | 26 | 0 | 39.227 | 42 | 0 | 1357245018.53 | 67755604
|  | Rehab | 7 | 39.01 | 68.21 | 93.5 | 397.5 | 7414.9 | 421.48 | 3180 | 11016.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1084802384.143
|  | Pro/Work | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 909.15 | 0 | 10.03 | 0 | 0 | 0 | 0 | 0
Total 03 Districts |  |  | 60 | 149.83 | 361.12 | 754 | 1919 | 44132.01 | 3575.28 | 15432 | 66633.96 | 92 | 90.614 | 236.857 | 115.5 | 1914.06 | 5744003359.92 | 334199576 |  | 4819439644.775 | 249483871

## Summry
wZb cve©Z¨ †Rjvq `~‡h©v‡M ÿwZMÖ¯’ cjøx moK Dbœqb cÖK‡íi 18-08-2020 ZvwiL ch©šÍ †gvU Aby‡gvw`Z Z_¨vw`
‡gvU Aby‡gvw`Z ˆ`N©¨ (wKtwgt)
µt bs | ‡Rjv | wWwcwcf~³ Dc‡Rjv + BDwbqb iv¯Ívi ˆ`N©¨ (wKtwgt) | wWwcwcf‚³ moK cÖwZiÿvi ˆ`N©¨ (wKtwgt) | wWwcwcf~³ eªx‡Ri ˆ`N©¨ (wgt) | wWwcwcf‚³ KvjfvU© Gi ˆ`N©¨ (wgt) | Dc‡Rjv + BDwbqb iv¯Ívi ˆ`N©¨ (wKtwgt) |  |  |  | †gvU Aby‡gvw`Z g~j¨ (jÿ UvKvq) | c¨v‡KR msL¨v (wU) | Tender Approved msL¨v (wU) | Aby‡gvw`Z Pzw³g~j¨ (jÿ UvKvq)
[7 empty] | moK cÖwZiÿvi ˆ`N¨© | eªx‡Ri ˆ`N¨© | Kvjfv‡U©i ˆ`N©¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1¦ | ev›`ievb | 121 | 49.01 | 460 | 223.94 | 104.358 | 26.06 | 601 | 73.5 | 24509.5115 | 33 | 30 | 24389.8255
2¦ | LvMovQwo | 154.78 | 61.81 | 664 | 343.06 | 93.272 | 27.262 | 637.06 | 150.1 | 19358.0719 | 33 | 21 | 12956.5471
3¦ | iv½vgvwU | 85.23 | 39.01 | 795 | 187 | 39.227 | 10.03 | 676 | 42 | 13572.4502 | 26 | 18 | 10848.0238
me©‡gvU= |  | 361.01 | 149.83 | 1919 | 754 | 236.857 | 63.352 | 1914.06 | 265.6 | 57440.0336 | 92 | 69 | 48194.3964

## Sheet2 (hidden)
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2015-2016
Reporting Month: July' 2017
[14 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Bandarban
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Holudia-Vaggakul-Tankbati Road.(Ch.00-2000m), ID No.403143005 | BAN/SADR/UNR/W07 | BC | 21-01-06 | 2 | 0 |  | 22971805 | 0 | 0 | 22971805 | 7217924.56 | 2016-04-17 | 2017-05-14 | 17134949 | 15239564 | 100% | 88.94% | M/S Arpmilton (JV), Bandarban | Variation | 1
2 |  | Holudia-Vaggakul-Tankbati Road.(Ch.2000-3350m), ID No.403143005 | BAN/SADR/UNR/W08 | BC | 21-01-06 | 1.35 | 0 |  | 10735081.37 | 0 | 0 | 10735081.37 | 4040354 | 2016-04-17 | 2017-05-14 | 8271466.22 | 8271473 | 100% | 100% | M/S Milton Traders, Bandarban | Variation | 1
3 |  | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road. (Ch.2950-5500m), ID No.403143002 | BAN/SADR/UNR/W11 | BC | 28-02-06 | 2.55 | 0 |  | 19912233 | 0 | 0 | 19912233 | 5752819 | 2016-06-09 | 2017-07-16 | 16433913.837 | 7943105 | 70% | 0% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
4 |  | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road.(Ch.5500-7060m), ID No.403143002 | BAN/SADR/UNR/W12 | BC | 28-02-06 | 1.56 | 0 |  | 10029323 | 0 | 0 | 10029323 | 3479495 | 2016-06-30 | 2017-07-07 | 8499091.269 | 0 | 5% | 0% | M/S Emu Construction Chairman Market, Bandarban |  | 1
5 |  | Construction of 12.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 780.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W19 | Bridge | 2016-09-06 |  |  | 12 |  |  | 6070959 | 6070959 |  | 2017-01-08 | 2017-12-17 | 4798913.42 | 2975800 | 75% | 0 | Mr.UT Mong,Maddayum Para Bandarban |  | 1
6 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 1430.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W20 | Bridge | 2016-09-06 |  |  | 18 |  |  | 6785192 | 6785192 |  | 2017-01-08 | 2017-12-17 | 5278818.477 | 2658000 | 65% | 0 | M/S Milton Traders, Rowangchari |  | 1
7 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 3015.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W21 | Bridge | 2016-09-06 |  |  | 18 |  |  | 7181549 | 7181549 |  | 2017-01-08 | 2017-12-17 | 5558074.95 | 3269916 | 65% | 0 | M/S Milton Traders, Rowangchari |  | 1
Sadar Sub-Total : |  |  | 7 |  |  | 7.46 | 0 | 48 | 63648442.37 | 0 | 20037700 | 83686142.37 | 20490592.56 |  |  | 65975227.173 | 40357858 | 68.75% | 26.99%
1 | Thanchi | Thanchi-Balipara road. (Ch.00-1000m), ID No.403952001 | BAN/THAN/UZR/W02 | BC | 25-10-15 | 1 | 0 |  | 15630432 | 5528250 | 0 | 21158682 | 0 | 2016-02-15 | 2017-02-22 | 18436599.688 | 9885059 | 70% | 53.62% | M/S Milton Traders, Rowangchari | Box cutting Ges protection Gi KvR Pj‡Q | 1
2 |  | Thanchi-Balipara road. (Ch.1000-2000m), ID No.403952001 | BAN/THAN/UZR/W13 | BC | 28-02-15 | 1 | 0 |  | 10976788 | 0 | 0 | 10976788 | 0 | 2016-06-30 | 2017-07-07 | 9739608.14 | 4078464 | 70% | 41.88% | Mr.UT Mong,Maddayum Para Bandarban |  | 1
3 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 2467.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W24 | Bridge | 2017-02-01 |  |  | 20 | Brigde 11: 9870616; Brigde 12: 9870616; Brigde 16: 9869497.947; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
4 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 3623.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W25 | Bridge | 2017-02-01 |  |  | 20 | Brigde 11: 12644983; Brigde 12: 12644983; Brigde 16: 12644266.304; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
5 |  | Construction of 45.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 1958.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W26 | Bridge | 2017-02-01 |  |  | 45 | Brigde 11: 16636441; Brigde 12: 16636441; Brigde 16: 14972796.9; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
6 |  | Rehabilitation of Thanchi-Balipara road. (Ch.2+000-3+000m); ID No: 403952001 | WD/RIDPCHT-2/ BAN/ THANCHI/ UZR/W43 | BC | 2017-06-11 | 1 | 0 | 0 | Road 9: 17736535; Brigde 12: 17736535; Brigde 21: APP Apprpved Date: 05-07-17
Thanchi Sub-Total : |  |  | 6 |  |  | 3 | 0 | 85 | 44343755 | 5528250 | 39152040 | 89024045 | 0 |  |  | 65662768.979 | 13963523 | 11.67% | 8.936%
1 | Alikadam | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 00-1000m), ID No.403043007 | BAN/ALI/ UNR/W03 | BC | 15-11-15 | 1 | 0 | 0 | 8267241 | 1297011 | 0 | 9564252 | 1613216 | 2016-03-16 | 2017-03-17 | 8121080.587 | 8117349 | 100% | 99.95% | M/S Milton Traders, Rowangchari | 750m sub-base n‡q‡Q Ges WBM , 2 nos culvert Gi KvR Pj‡Q | 1
2 |  | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 1000-2600m), ID No.403043007 | BAN/ALI/ UNR/W10 | BC | 14-02-16 | 1.6 | 0 | 0 | 13307610 | 1987879 | 0 | 15295489 | 349138 | 2016-05-25 | 2017-06-02 | 13597665.717 | 13364051 | 100% | 98.28% | M/S Emmu Construction, Rowangchari, Bandarban |  | 1
3 |  | Improvement of Alikadam-Dochori Road (ch.00-2020m), ID No.403043004 | BAN/ALI/ UNR/W14 | BC | 21-03-2016 | 2.02 | 0 | 0 | 13037259 | 0 | 0 | 13037259 | 4614359 | 2016-07-25 | 2017-08-01 | 10729459.801 | 0 | 25% | 0% | M/S Prasanna kant Amu, Hospital raod, Bandarban |  | 1
4 |  | Construction of 81.00m long PSC Gider Bridge on Alikadam Bazar- Naikhongchari Border via Rombow road. Ch.1193m) ID No: 403042002 | BAN/ ALI / BRIDGE/W22 | Bridge | 2016-10-23 |  | 0 | 81 | 44255971 | 0 | 0 | 44255971 |  | 2017-03-29 | 2018-06-03 | 39677176.309 | 0 | 5% |  | M/S Noor Syndicate, Pachalish,Chittagong |  | 1
5 |  | Improvement of Alikadam Bazar- Naikhongchari Border via Rombow road. (Ch.00-2880m) ID No. 403042002 | WD/RIDPCHT-2/BAN/ALIKADAM/UZR/W39 | BC | 2017-06-08 | 2.88 | 0 | 0 | Road 9: 24720436; Brigde 12: 24720436; Brigde 13: 2507186; Brigde 21: APP Apprpved Date: 12-07-17
6 |  | Improvement of Sonaichori R&H-Varirmukh Road.(Ch.821-1571m) ID No. 403043005 | WD/RIDPCHT-2/BAN/ALIKADAM/ UNR/W40 | BC | 2017-06-08 | 0.75 | 1.6 | 0 | Road 9: 6323746; Culvert 10: 476351; Brigde 12: 6800097; Brigde 13: 482496; Brigde 21: APP Apprpved Date: 12-07-17
7 |  | Improvement of Chikkan para (cioni para) road (Ch.1441-2191m) ID No. 403043006 | WD/RIDPCHT-2/BAN/ALIKADAM/ UNR/W41 | BC | 2017-06-08 | 0.75 | 3.5 |  | Road 9: 4771148; Culvert 10: 1621901; Brigde 12: 6393049; Brigde 13: 269554; Brigde 21: APP Apprpved Date: 12-07-17
Alikadam Sub-Total : |  |  | 7 |  |  | 9 | 5.1 | 81 | 114683411 | 5383142 | 0 | 120066553 | 9835949 |  |  | 72125382.414 | 21481400 | 29.29% | 28.32%
1 | Rowangchari | Development of Kalaghata to Taracha UP office road at Ch.00-1000m, ID No.403893004 | BAN/ROW/UNR/W01 | BC | 25/10/2015 | 1 | 4.5 | 0 | 7665778 | 2161700 | 0 | 9827478 | 1119803 | 2016-02-16 | 2017-02-15 | 8044900.029 | 5335885 | 75% | 66.33% | M/S Milton Traders, Rowangchari | WBM ‡kl n‡q‡Q¦ | 1
2 |  | Development of Kalaghata to Taracha UP office road at Ch.1000-3000m, ID No. 403893004 | BAN/ROW/UNR/W15 | BC | 21-03-2016 | 2 | 6.4 | 0 | 22470615 | 1725180 | 0 | 24195795 | 4769663 | 2016-06-07 | 2017-07-23 | 19457598.284 | 12950245 | 75% | 66.56% | Mr.UT Mong,Maddayum Para Bandarban |  | 1
3 |  | Construction of 60.0m long RCC Girder Bridge on Kalaghata to Taracha UP office road at Ch.2885m, ID No: 403893004 | BAN/ROW/BRIDGE/W31 | Bridge | 2017-04-20 |  |  | 60 | Brigde 11: 26134485; Brigde 12: 26134485; Brigde 16: 23521036.5; Brigde 20: S. Ananta Bikash Tripura, Milonpur, Khagrachari | 1
Rowangchari Sub-Total : |  |  | 3 |  |  | 3 | 10.9 | 60 | 30136393 | 3886880 | 26134485 | 60157758 | 5889466 |  |  | 51023534.813 | 18286130 | 50% | 44.29%
1 | Naikhonchari | Naikhongchari - Lemouchari road.(Ch.00-1000m), ID No.403733001 | BAN/NAIK/UNR/W04 | BC | 2015-02-12 | 1 | 9 | 0 | 9088672 | 2982164 | 0 | 12070836 | 2401589 | 2016-03-07 | 2017-03-06 | 9658461.68 | 7382035 | 95% | 76.43% | M/S Milton Traders, Rowangchari | Variation | 1
2 |  | Naikhongchari - Lemouchari road.(Ch.1000-2500m), ID No.403733001 | BAN/NAIK/UNR/W05 | BC | 28-12-15 | 1.5 | 0 | 0 | 12914033 | 0 | 0 | 12914033 | 3535057 | 2016-03-10 | 2017-03-09 | 10509159.843 | 8818029 | 95% | 83.91% | M/S Emmu Construction , Bandarban |  | 1
3 |  | Naikhongchari - Lemouchari road.(Ch.2500-4000m), ID No.403733001 | BAN/NAIK/UNR/W06 | BC | 28-12-15 | 1.5 | 0 | 0 | 13616480 | 0 | 0 | 13616480 | 3520106 | 2016-03-10 | 2017-03-09 | 11062329.59 | 8280876 | 90% | 74.86% | M/S Emmu Construction , Bandarban |  | 1
4 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.2600-4100m, ID No.403733008 | BAN/NAIK/UNR/W09 | HBB | 28-01-16 | 1.5 | 0 | 0 | 11512651 | 0 | 0 | 11512651 | 0 | 2016-06-30 | 2017-07-07 | 9275721.942 | 0 | 10% | 0% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
5 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4100-5100m, ID No.403733008 | BAN/NAIK/UNR/W18 | HBB | 2016-04-27 | 1 | 4.5 | 0 | 8369888 | 1416240 | 0 | 9786128 | 0 |  |  | 9264612.157 | 0 | 0% |  | Mr. U.T Mong Madhyampara, Bandarban |  | 1
6 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W32 | Bridge | 2017-04-20 |  |  | 85 | Brigde 11: 30356111; Brigde 12: 30356111; Brigde 16: 27320499.9; Brigde 20: Mr. U.T Mong Madhyampara, Bandarban | 1
7 |  | Construction of 36.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.3780m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W33 | Bridge | 2017-04-20 |  |  | 36 | Brigde 11: 18179251; Brigde 12: 18179251; Brigde 21: Tender Receive Date: 30-05-17
8 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4970m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W34 | Bridge | 2016-04-24 |  |  | 85 | Brigde 11: 28151740; Brigde 12: 28151740; Brigde 21: APP Apprpved Date: 11-05-17
9 |  | Construction of 33.0m long RCC Girder Bridge on North Ghumdum - Tumbru Bazar road.Ch.2600m ID No: 403733003 | BAN/ NAIKHONG / BRIDGE/W35 | Bridge | 2016-04-24 |  |  | 33 | Brigde 11: 18085536; Brigde 12: 18085536; Brigde 21: APP Apprpved Date: 11-05-17
10 |  | Construction of 33.0m long RCC Girder Bridge on Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road. Ch.3000m ID No: 403733002 | BAN/ NAIKHONG / BRIDGE/W36 | Bridge | 2016-04-24 |  |  | 33 | Brigde 11: 18151717; Brigde 12: 18151717; Brigde 21: APP Apprpved Date: 11-05-17
11 |  | Improvement of Dochori - Ali Kadam road .(Ch.00-3000m); ID No: 403733004 | BAN/ NAIKHONG/ UNR/W37 | BC | 2017-04-25 | 3 | 0 | 0 | Road 9: 24633854; Brigde 12: 24633854; Brigde 21: Tender Receive Date: 20-06-17
12 |  | Improvement of Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road .(Ch.00-3180m); ID No: 403733002 | BAN/ NAIKHONG/ UNR/W38 | BC | 2017-04-25 | 3.18 | 0 | 0 | Road 9: 24755606; Brigde 12: 24755606; Brigde 21: Tender Receive Date: 20-06-17
13 |  | Construction of 33.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road). (Dochari UP office (Lemochari)-Powamohuri Bazar via Kalurghat, Painchari Bazar BGB camp & Dochari BGB Camp, Murong para BGB Camp Road) Ch.9800m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W42 | Bridge | 2017-06-08 | 0 | 0 | 33 | Brigde 11: 14373533; Brigde 12: 14373533; Brigde 21: APP Apprpved Date: 12-07-17
Naikhongchari Sub-Total : |  |  | 13 |  |  | 12.68 | 13.5 | 305 | 104891184 | 4398404 | 127297888 | 236587476 | 9456752 |  |  | 77090785.112 | 24480940 | 22.31% | 18.09%
1 | Ruma | Construction of 66.0m long RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.850m ID No.403913003 | BAN/RUMA/BRIDGE/W27 | Bridge | 2017-02-24 |  |  | 66 | Brigde 11: 24564086; Brigde 12: 24564086; Brigde 16: 25327853.157; Brigde 20: M/S Abser Construction, Bandarban | 1
2 |  | Construction of 68.0m long PSC & RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.850m ID No.403913003 | BAN/RUMA/BRIDGE/W28 | Bridge | 2017-03-14 |  |  | 68 | Brigde 11: 36527218; Brigde 12: 36527218; Brigde 16: 39841279.01; Brigde 20: Mohammed Eunus & Brothers (Pvt) Ltd, Chittagong. | 1
Ruma Sub-Total : |  |  | 2 |  |  |  |  | 134 | Road 9: 0; Culvert 10: 0; Brigde 11: 61091304; Brigde 12: 61091304; Brigde 13: 0; Brigde 16: 65169132.167
1 | Lama | Imrovement of Lama muk-Selertua road Ch.00-3300m ID No.403513008 (Old 3007) | BAN/LAMA/UNR/W16 | HBB | 2016-04-10 | 3.3 | 9 | 0 | 17474100.89 | 3072269.11 | 0 | 20546370 | 0 | 2016-08-28 | 2017-09-05 | 16031768.31 | 8786311 | 80% | 54.81% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
2 |  | Improvement of Shelertua-Rupashi Para Road Ch.00-1650m, ID No.403513011 (Old 3010) | BAN/LAMA/UNR/W17 | HBB | 2016-04-10 | 1.65 | 4.5 | 0 | 12367431.26 | 1524775.74 | 0 | 13892207 | 0 | 2016-06-30 | 2017-07-07 | 11075616.627 | 3355670 | 45% | 30.3% | M/S Abser Construction, Bandarban |  | 1
3 |  | Construction of 33.0m long RCC Girder Bridge on Shelertua-Rupashi Para Road at ch. 930m ID No: 403513010 | BAN/ LAMA/ BRIDGE/W29 | Bridge | 2017-04-11 |  |  | 33 | Brigde 11: 19899758; Brigde 12: 19899758; Brigde 16: 17909782.2; Brigde 20: Mr U T Mong, Madhyampara, Bandarban | 1
4 |  | Improvement of Polokhal Tetulia Moor-Quantum Cosmo College via Bodhechora public School Road. by HBB at (Ch.0+000 to 2+480km) ID No: 403515105 | BAN/LAMA/ V.Road/W44 | HBB | 2017-06-22 | 2.48 |  |  | Road 9: 15801353; Culvert 10: 1945321; Brigde 12: 17746674
5 |  | Improvement of Bodhe Chora Bamboorian Mor - Quantum Shabujan Pry School via Ground Olympian & Chompajhiri Para Mor Road by HBB at (Ch.0+000 to 2+500km) ID No: 403515106 | BAN/LAMA/ V.Road/W45 | HBB | 2017-06-22 | 2.5 |  |  | Road 9: 10827188; Brigde 12: 10827188
Lama Sub-Total : |  |  | 5 |  |  | 9.93 | 13.5 | 33 | 56470073.15 | 6542365.85 | 19899758 | 82912197 | 0 |  |  | 45017167.137 | 12141981 | 25% | 17.02%
Maintenance Work
1 | Sadar | Periodic Maintenance of Balaghata-Bagman Bazar Road start from B-ban Chandraghona. (Ch.5000-8000m) ID No: 403143003 | BAN/SADAR/ UNR/W23 | BC | 2016-11-27 | 3 |  |  | 10384827 |  |  | 10384827 |  | 2017-05-07 | 2018-03-15 | 9346344.3 | 6000000 | 75% |  | M/S marma enterprise, Mayd ampara, Bandarban |  | 1
2 |  | Khanshama-Bagmara road start B-Ban Rowangchari Road.(Ch.2500-7313m) ID No: 403142002 | BAN/SADAR/UZR/W30 | HBB | 2017-04-11 | 4.813 |  |  | Road 9: 10963617; Brigde 12: 10963617; Brigde 16: 9867255.3; Brigde 20: M/S Selim & Brothers, Baitus Sharaf Mosque Road, Arambag, Khagrachari. | 1
|  |  | 2 |  |  | 7.813 |  |  | Road 9: 21348444; Brigde 12: 21348444; Brigde 16: 19213599.6; Brigde 17: 6000000
|  | Total Maintenance : | 2 |  |  | 7.813 | 0 |  | 21348444 | 0 | 0 | 21348444 | 0 |  |  | 19213599.6 | 6000000 | 0% | 0%
Total Development : |  |  | 43 |  |  | 45.07 | 43 | 746 | 414173258.52 | 25739041.85 | 293613175 | 733525475.37 | 45672759.56 |  |  | 442063997.795 | 130711832 | 34.5% | 21.11%
Grand Total Bandarban Dist: |  |  | 45 |  |  | 52.883 | 43 | 746 | 435521702.52 | 25739041.85 | 293613175 | 754873919.37 | 45672759.56 |  |  | 461277597.395 | 136711832 | 34.5% | 21.11%
32
[13 empty] | Total Contract Package : |  |  | 32