## July-2020
Rural Access Road Improvement Project Under Sylhet Division (RARIP)
Progress Report (Physical & Financial)
District: Sunamgonj | [16 empty] | Duration: July-2020
SL.No | Upazila | PackageNo | Name of Scheme with Chainage & road ID No | Quantity |  | Estimated Cost (TK) |  |  | Cost of Salvage Material(TK) | Tender Recei. Date | Name of Contractor | Date of NOA Issued | Date of Contrat/Received | Contract/Variation Amount(Tk) | Work Commen. Date. | Phy Prog(%) | Date of Comple. as per Contract | Payment made (TK) |  |  | Financial Progress (%) | Remarks
|  |  |  | Road (km) | Structure (m) | Road | Structure | Total | [9 empty] | Road | Bridge/Culvert | Remaining Payment(TK)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | South Sunamgonj | LGED/RARIP/SUN/VR/18-19/W-31 | a) Damadurtupi-Ghuradumbur road (Ch.1650-2740m. Road ID No-690934007 | 1.09 | - | 11543983 |  | 11543983 | - | - | - | - | - | - | - | - | - |  | - |  | - | Evaluation Under process
|  |  | b) Jagannathpur road-Sichin South road [RHD(Sicni)-RHD(Minabazar)-Pagla UZR Road] (Ch.1000-2000m). Road ID No-690934020 | 1 | - |  | - | [8 empty] | - |  |  | - |  | -
Package Total = |  |  |  | 2.09 | — | 11543983 | — | 11543983 | — | — | — | — | — | 0 | — | — | — | 0 | — | 0 | — | —
2 | Chatak | LGED/RARIP/SUN/VR/18-19/W-32 | Moula (UZR)-Chowmuhoni Bazar Road via Rajapur road (Ch.1700-2700m). Road ID No-690234022 | 1 | 1.125 | 9228215 | 136823 | 9365038 | - | 5.11.18 | M/S Nurul Islam 01713-812992 | 4.12.18 | 01.01.19 | 8509132.67 | 14.1.19 | 35% | 31.12.19 | 2567000 | 700000 | 5942132.67 | 30.17% | -
3 | Chatak | LGED/RARIP/SUN/VR/18-19/W-33 | Jugal Nagar-Tuker Bazar road (Ch.00-1000m). Road ID NN0- 690235094 | 1 |  | 7207945 |  | 7207945 | 109771 | 21.1.19 | M/S Lucky Enter Prise | 13.03.19 | 10.04.19 | 7908016 | - | 65% | - | 4050000 | 0 | 3858016 | 51.21% | -
4 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-34 | Mojidpur (Pagla-Jagannathpur R&H)-Aralia road (Ch.00-1000m). Road ID No- 690474027 | 1 | - | 6585722 | - | 6585722 | - | - | Marina Contraction Associatio LTD. 01711385957 | 28.11.2019 | - | 7532568 | - | 10% | - | 0 | - | 7532568 | - | Tender validity period expired
5 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-35 | a) Rowail-Hilalpur road (Ch.2000-2670m). Road ID No-690474001 | 0.67 | - | 20045154 | - | 20045154 | - | 5.11.18 | JV of Belal Enterprise 01712-442893 | 14.1.19 | 07.02.19 | 19907548 | 20.2.20 | 60% | 20.02.20 | 6735000 | - | 13172548 | 33.83% | -
| Sadar |  | b) Sunamgonj-Chatak road to Alampur via Shahapur-Monoharpur Road (Ch.5750-6250m). Road ID No-690894067 | 0.5 |  |  | - | [8 empty] | 100% |  |  | -
| Sadar |  | C) Katair-Joynagar road to Kalaia Village road (Ch.00-1000m). Road ID No-690895034 | 1 |  |  | - | [8 empty] | 5% |  |  | -
Package Total = |  |  |  | 2.17 | — | 20045154 | — | 20045154 | — | — | — | — | — | 19907548 | — | 55% | — | 6735000 | — | 13172548 | 33.83% | —
6 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-36 | Amanipur-Nidhipur road (Ch.00-1000m). Road ID No- 690504004 | 1 | - | 8840492 | - | 8840492 | - | 5.11.18 | Md. Atiqur Rahman. 01712-521355 | 4.12.18 | 01.01.19 | 8810455 | 14.1.19 | 100% | 31.12.19 | 8785996 | 0 | 24459 | 99.72%
7 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-37 | a) Harinakandi-Ahcanpru road (Ch.00-1000m). Road ID No-690506035 | 1 | - | 15559515 | - | 15559515 | - | 5.11.18 | Aminul Islam Saim 01712-570420 | 14.1.19 | 07.02.19 | 15554733 | 21.2.19 | 100% | 20.02.20 | 8800000 | 0 | 6754733 | 56.57%
| Tahirpur |  | b) Baradol Uttar Up Office-Rajai road (Ch.1500-2250m & 2850-3100m). Road ID No-690924007 | 1 | - |  | - |  | - | [6 empty] | 5%
Package Total = |  |  |  | 2 | — | 15559515 | — | 15559515 | — | — | — | — | — | 15554733 | — | 52.5% | — | 8800000 | — | 6754733 | 0% | —
8 | Derai | LGED/RARIP/SUN/VR/18-19/W-38 | a) Negergaon Ferrighat-Nasni bazar road (Negergaon Ferryghat-Nachni bazar via Milon Bazar road) (Ch.5654-7100m). Road ID No-690294018 | 1.446 | - | 25721133 | - | 25721133 | - | - | - | - | - | - | - | - | - |  | - |  | - | Evaluation Under process
|  |  | b) Ditpur-Hossainpur via Pukidohar Kamribiz road (Ch.1000-2500m). Road ID No-690294018 | 1.5 | - |  | - | [8 empty] | - |  |  | - |  | -
Package Total = |  |  |  | 2.946 | — | 25721133 | — | 25721133 | — | — | — | — | — | 0 | — | — | — | 0 | — | 0 | — | —
9 | Derai | LGED/RARIP/SUN/VR/18-19/W-39 | Boalia Bazar-Tengrakhali road (Ch.1000-1950m). Road ID No-690294008 | 0.95 | - | 8868403 | - | 8868403 | - | - | Aminul Islam Saim 01712-570420 | 18.10.19 | - | 9754839 | - | 0% |  | 0 | - | 9754839 | 0%
10 | Biswamberpur | LGED/RARIP/SUN/VR/18-19/W-40 | a) Dhanpur-Bachurbari-Mothurkandi road(Dhanpur-Mothourkandi Bazar via Mujib bazar road) (Ch.1000-2000m. Road ID No-690184002 | 1 | - | 17388451 | - | 17388451 | - | 5.11.18 | M/S Aminul Haque &Co- 01711-026722 | 14.1.19 | 07.02.19 | 17367912 | 21.2.19 | 65% | 20.02.20 | 8712000 | - | 8655912 | 50.16%
|  |  | b) RHD Post Office-Mollikpur Kasmer Jungle Road (Ch.00-1000m). Road ID No-690184054 | 1 | - |  | - |  | - | - |  | - |  |  |  | 45% |  |  | -
Package Total = |  |  |  | 2 | — | 17388451 | — | 17388451 | — | — | — | — | — | 17367912 | — | 55% | — | 8712000 | — | 8655912 | 0% | —
11 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-41 | a) Haripadnagar Village Road (Ch.500-1500m). Road ID No-690335077 | 1 | - | 21735398 | - | 21735398 | - | 5.11.18 | M/S Aminul Haque & Co. 01711-026722 | 14.1.19 | 07.02.19 | 20352498 | 21.2.19 | 0% | 20.02.20 | 8326000 | - | 12026498 | 40.91% | -
|  |  | b) Manargaon-Putipushi Road (Ch.1000-2000m).Road ID No-690334061 | 1 |  |  | - |  | - | [6 empty] | 50% |  |  | - |  |  | -
|  |  | C) Dowarabazar-Banglabazar Road to Ustingergaon road (Ch.00-500m). Road ID No-690335074 | 0.5 |  |  | - |  | - | [6 empty] | 100% |  |  | - |  |  | -
Package Total = |  |  |  | 2.5 | — | 21735398 | — | 21735398 | — | — | — | — | — | 20352498 | — | 50% | — | 8326000 | — | 12026498 | 40.91% | —
12 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-42 | Norshingpur bazar-Notun Sirajpur Road (Ch.500-1500m). Road ID No-690335034 | 1 | - | 8778036 | - | 8778036 | - | 5.11.18 | M/S Nurul Islam 01713-812992 | 4.12.18 | 01.01.19 | 8768395 | 14.1.19 | 95% | 31.12.19 | 8100000 |  | 668395 | 92.38% | -
13 | Biswamberpur | LGED/RARIP/SUN/VR/18-19/W-43 | Mollikpur-DB College Road (Ch.00-1095m). Road ID No-690184041 | 1.095 | 2.74 | 11092489 | 231918 | 11324407 | - | 5.11.18 | M/S Akber Ali 01716-122058 | 4.12.18 | 01.01.19 | 11308919 | 14.1.19 | 95% | 31.12.19 | 10354000 |  | 954919 | 91.56% | -
14 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-44 | Dharmapash-Union Parishad-Kandapara via Radhanagor Rd (Ch.2200-3200m). Road ID No-690324002 | 1 | - | 10025005 | - | 10025005 | - | 5.11.18 | M/S Anwara Enterprise 01712-393624 | 4.12.18 | 01.01.19 | 10004558 | 14.1.19 | 60% | 31.12.19 | 5729000 |  | 4275558 | 57.26% | -
15 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-45 | a) Gastola Bazar-Siram Bazar (Barhatta) via Thanura Pasham road (Ch.1000-2000m). Road ID No-690324015 | 1 | - | 18902298 | - | 18902298 | - | - | Atiqur-Anwara(JV). 01712-393624 | 28.11.2019 | - | 20767198 | - | 0% | - | 0 | - | 20767198 | 0%
|  |  | b) Dharmapasha FRB-Singpur Road (Ch.00-1000m). Road ID No-690325025 (New 690324026). | 1 |  |  | - |  | - | - |  |  | - |  | - | 0% | - |  | -
Package Total = |  |  |  | 2 | — | 18902298 | — | 18902298 | — | — | — | — | — | 0 | — | 0% | — | 0 | — | 20767198 | — | —
16 | Sulla | LGED/RARIP/SUN/VR/18-19/W-46 | Kashipur to Chakua road (Ch.00-1000m). Road ID No-690864002 | 1 | - | 11479005 | - | 11479005 | - | - | - | - | - | 0 | - | - | - | 0 | - | 0 | - | Evaluation Under process
17 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-98 | a) Razapur-Gazaria ghat road (Ch.00-1000m). Road ID No-690324003 | 1 | - | 16532830 | - | 16532830 | - | 12.06.20 | Atiqur-Anwara(JV). 01712-393624 | 03.03.20 | 25.03.20 | 19738138 | 07.04.20 | 0% | - | 0 | — | 19738138 | 0%
|  |  | b) Paykurati Union Parishad-Jamalpur Rd (Ch.2350-3340). Road ID No-690324010 New-690323019 | 0.99 |  |  | - | [8 empty] | 0%
Package Total = |  |  |  | 1.99 | — | 16532830 | — | 16532830 | — | — | — | — | — | 0 | — | — | — | 0 | — | 19738138 | — | —
18 | South Sunamgonj | LGED/RARIP/SUN/VR/18-19/W-99 | Asampur Fery Ghat-Ashampur GPS road [RHD (Pagla)-Asampur Fery Ghat Road] (Ch.00-1500m). Road ID No-690934069 New 690934101 | 1.5 | - | 11624937 | - | 11624937 | - | 5.11.18 | M/S Sojib Construction | 4.12.18 | 01.01.19 | 11609991 | 14.1.19 | 65% | 31.12.19 | 4975000 |  | 6634991 | 42.85% | -
19 | Chatak | LGED/RARIP/SUN/VR/18-19/W-101 | Rukka Bazar-Rukka Madrasha road (Ch.1500-2500m). Road ID No-690235080 | 1 | 1.125 | 9240035 | 94962 | 9334997 | - | 5.11.18 | M/S Nurul Islam. 01713-812992 | 4.12.18 | 01.01.19 | 9306766 | 14.1.19 | 95% | 31.12.19 | 6779000 |  | 2527766 | 72.84% | -
20 | Chatak | LGED/RARIP/SUN/VR/18-19/W-102 | Noagaon-Senpur (Monir Gati) road (Ch.00-145m & Ch.485-1340m). Road ID No-690235036 | 1 | 1.125 | 7985261 | 101568 | 8086829 | - | 5.11.18 | M/S Lucky Enterprisej | 4.12.18 | 01.01.19 | 8073056 | 14.1.19 | 100% | 31.12.19 | 7600000 | - | 473056 | 94.14% | -
21 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-103 | Shibganj-Arunday Girls High School roa-to -Dustapur road (Ch.00-1000m). Road ID No-690475084 | 1 | - | 6913112 | - | 6913112 |  |  | Marina Contraction Associatio LTD. 01711385957 | 28.112 |  | 7768732 |  | 0% |  | 0 | - | 7768732 | 0%
22 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-104 | Gucchagram-Badarpur road (Ch.2500-3500m). Road ID No-690505007 | 1 | - | 8840492 | - | 8840492 | - | 5.11.18 | M/S Sojib Construction | 4.12.18 | 01.01.19 | 8828355 | 14.1.19 | 100% | 31.12.19 | 7932000 |  | 896355 | 89.85%
23 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-105 | Banglabazar-Haquenagar-Dhakin Chowdhuripara road (Ch.100-1100m). Road ID No-690335054 | 1 | - | 8777036 | - | 8777036 | - | 5.11.18 | M/S Aminul Haque & Co. 01711-026722 | 4.12.18 | 01.01.19 | 8022170 | 14.1.19 | 100% | 31.12.19 | 6400000 |  | 1622170 | 79.78%
24 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-106 | Paykurati-Barikandi Via Chakiacapur road (Ch.00-1000m). Road ID No-690324007 | 1 | - | 9172088 | - | 9172088 | - | 5.11.18 | M/S Baset Prokousholi, 01916-855289 | 4.12.18 | 01.01.19 | 9164721 | 14.1.19 | 100% | 31.12.19 | 9138081 |  | 26640 | 99.71% | -
25 | Sadar | LGED/RARIP/SUN/RHB/18-19/W-125 | a) Haluar Ghat-Ibrahimpur (Surma UPC) via Moinpur road (Ch.00-1200m). Road ID No-690893016 | 1.2 | - | 25241965 | - | 25241965 | - | 8.11.18 | M/S Akber Ali | 31.1.19 | 27.02.19 | 23498522 | 14.3.19 | 100% | 13.03.20 | 22216789 |  | 1281733 | 94.55% | -
|  |  | Buristhal-Abdullahpur road via Sreenathpur GPS (Mollapara UP) (Ch.00-2400m). Road ID No-690895095 | 2.4 | - |  | - |  | - | [6 empty] | 95% | [5 empty] | -
|  |  | Ampara-Khayergaon Bazar Pucca Road-Natun Godigaon road via Jharjaria (Ch.00-1700m). Road ID No-690893011 | 1.7 | - |  | - |  | - | [6 empty] | 95% | [5 empty] | -
Package Total = |  |  |  | 5.3 | — | 25241965 | — | 25241965 | — | — | — | — | — | 23498522 | — | 96.67% | — | 22216789 | — | 1281733 | 94.55% | —
26 | Derai | LGED/RARIP/SUN/RHB/18-19/W-126 | a) Rajanagar-Bangla Bazar road (Ch.00-2000m & 8930-9330m). Road ID No-690293004 | 2.4 | - | 8739411 | - | 8739411 |  | 8.11.18 | M/S Belal Enterprise. | 12.05.19 | 03.06.19 | 9533352.18 | 17.06.19 | 90% | 16.06.19 | 7061000 |  | 2472352.18 | 74.07% | -
|  |  | b) Tuk Derai to Kochua via Tajpur road (Ch.550-1550m). Road ID No-690294040 | 1 | - |  | - | [8 empty] | 95%
Package Total = |  |  |  | 3.4 | — | 8739411 | — | 8739411 | — | — | — | — | — | 9533352.18 | — | 92.5% | — | 7061000 | — | 2472352.18 | 74.07% | —
27 | Derai | LGED/RARIP/SUN/RHB/18-19/W-127 | Akilsha bazar Nagargaon Ferryghat via Kulange road (Ch.550-2419m). Road ID No-690294019 | 1.9 | - | 10798389 | - | 10798389 | - | 8.11.18 | M/S Padma Construction | 4.12.18 | 01.01.19 | 10572051 | 14.1.19 | 5% | 31.12.19 | 0 | - | 10572051 | 0% | -
28 | Biswamberpur | LGED/RARIP/SUN/RHB/18-19/W-128 | a) Karenter bazar-Dhanpur UP Office road (Ch.00-1204m). Road ID No-690183003 | 1.204 | - | 10351707 | - | 10351707 | - | 8.11.18 | M/S Aminul Haque & Co. Ukilpara, Sunamganj | 4.12.18 | 01.01.19 | 10345428 | 14.1.19 | 10% | 31.12.19 | 5040670 | - | 5304758 | 48.72% | -
| Biswamberpur |  | b) Chhaterkona-Anandabazar road (Ch.00-750m). Road ID No-690934012 | 0.75 | - |  | - |  | - | [6 empty] | 5% |  |  | - |  |  | -
| Dowarabazar |  | C) Baliura bazar Chowmuni road (Ch.00-700m). Road ID No-690334058 | 0.7 | - |  | - |  | - | [6 empty] | 100% |  |  | - |  |  | -
Package Total = |  |  |  | 2.654 | — | 10351707 | — | 10351707 | — | — | — | — | — | 10345428 | — | 38.33% | — | 5040670 | — | 5304758 | 48.72% | —
29 | Chatak | LGED/RARIP/SUN/RHB/18-19/W-129 | a) Kalaruka-Tajpur road (Ch.50-80, 1500-1575 & 2200-3100m). Road ID No-690233004 | 0.975 | - | 5210159 | - | 5210159 | - | - | - | - | - | - | - | - | - |  | - |  | - | Evaluation Under process
|  |  | b) Jalalpur (RHD)-Hasnabad bazar (RHD) road via Kamranji Village road (Ch.930-1533 & 1866-2266m). Road ID No-690233015 | 1 | - |  | - | [8 empty] | - |  |  | - |  | -
Package Total = |  |  |  | 1.975 | — | 5210159 | — | 5210159 | — | — | — | — | — | 0 | — | — | — | 0 | — | 0 | — | —
30 | Tahirpur | LGED/RARIP/SUN/RHB/18-19/W-130 | a) Badaghat GC-Bordal Uttar UP Office road (Ch.00-2650m). Road ID No-690923009 | 2.65 | - | 10766544 | - | 10766544 | - | 8.11.18 | M/S Amal kanti Chowdhury, Hassannagar, Sunamganj | 4.12.18 | 01.01.19 | 10433467 | 14.1.19 | 100% | 31.12.19 | 9918166 | - | 515301 | 95.06% | -
|  |  | b) Laorergar-Sharifganj Bazar Road (Ch.1700-2500m). Road ID No-690924061 | 0.8 | - |  | - |  | - | [6 empty] | 100% |  |  | - |  |  | -
Package Total = |  |  |  | 3.45 | — | 10766544 | — | 10766544 | — | — | — | — | — | 10433467 | — | 100% | — | 9918166 | — | 515301 | 95.06% | —
31 | Derai | LGED/RARIP/SUN/RHB/18-19/W-141 | Patharia-Banglabazar road (Ch.4550-5760m & 6200-7000m). Road ID No-690293001 | 2.1 | - | 8502453 | - | 8502453 | - | 8.11.18 | M/S Padma Construction & Supply Firm, | 4.12.18 | 01.01.19 | 8355111 | 14.1.19 | 0% | 31.12.19 | 0 | - | 8355111 | 0% | -
32 | Derai | LGED/RARIP/SUN/RHB/18-19/W-148 | a) Derai Bazar to Karimpur (Derai Bazar-Karimpur Via Tuk Derai) road (Ch.207-930m). Road ID No-690294031 | 0.723 | - | 7646780 | - | 7646780 | - | - | M/S Belal Enterprise. | 12.05.19 | 03.06.19 | 8139754.8 | 17.06.19 | 100% | 16.06.19 | 5836000 |  | 2303754.8 | 71.7% | -
| South Sunamganj |  | b) Pagla-Birgaon Road (Ch.8350-9200m). Road ID No-690933002 | 0.85 |  |  | - |  | - | - | [5 empty] | 100%
Package Total = |  |  |  | 1.573 | — | 7646780 | — | 7646780 | — | — | — | — | — | 8139754.8 | — | 100% | — | 5836000 | — | 2303754.8 | 71.7% | —
33 | Sadar | LGED/RARIP/SUN/UNR/18-19/W-03 | Haluar Ghat-Ibrahimpur (Surma UPC)-via Moinpur Road (Ch.1200-2351m). Road ID No-690893016 | 1.151 | 4.5 | 28028145 | - | 28028145 | - | 29.10.18 | M/S Milonkanti Dey 01712-020736 | 4.12.18 | 07.02.19 | 27633182 | 14.1.19 | 85% | 20.02.20 | 23532000 | 1151000 | 2950182 | 89.32% | -
| Dowarabazar |  | Banglabazar-Haquenagarbazar-Boglabazar road (Ch.6960-8960g). Road ID No-690333006 | 2 | - |  | - |  | - | [6 empty] | 100% | [5 empty] | -
Package Total = |  |  |  | 3.151 | 4.5 | 28028145 | — | 28028145 | — | — | — | — | — | 27633182 | — | 92.5% | — | 23532000 | 1151000 | 2950182 | 89.32% | —
34 | Derai | LGED/RARIP/SUN/UNRS/18-19/W-04 | Bangla Bazar-Alipur-Lepsia (Khaliajuri) road (Ch.5490-7690m). Road ID No-690293003 | 2.2 | - | 52450806 | - | 52450806 | - | - | - | - | - | - | - | - | - |  | - |  | - | Evaluation Under process
|  |  | Badolpur RHD-Shyamarchar via Gochia, Rajanagar, Chanarchar Bazar road (Ch.7525-9275 & 10925-11675m). Road ID No-690293008 New-690292007 | 2.5 |  |  | - | [8 empty] | - |  |  | - |  | -
Package Total = |  |  |  | 4.7 | — | 52450806 | — | 52450806 | — | — | — | — | — | 0 | — | — | — | 0 | — | 0 | — | —
35 | Jagannathpur | LGED/RARIP/SUN/UNR/18-19/W-05 | Shibganj-Raniganj road (Ch.1000-3250m). Road ID No-690473015 | 2.25 | - | 32836774 | - | 32836774 | - | 12.06.19 | MCAL&GI(JV) | 25.03.20 | 19.04.20 | 37664887 | 01.05.20 | 0% | 30.04.21 | 0 | - | 37664887 | 0%
|  |  | Enayetganj-Harinakandi via Gopalgonj road (Ch.5000-7500m). Road ID No-690473007, Salvage-776209/- | 2.5 |  |  | - |  | - | [6 empty] | 25% |  |  | - |  | -
Package Total = |  |  |  | 4.75 | — | 32836774 | — | 32836774 | — | — | — | — | — | 37664887 | — | — | — | 0 | — | 37664887 | 0 | —
36 | Biswamberpur | LGED/RARIP/SUN/UNR/ 18-19/W-14 | a) Dhakin Badaghat UP Office Basantapur Bazar Katakhali Bazar road (Ch.2000-4000m). Road ID No-690183004 | 2 | 10.25 | 26947599 | - | 26947599 | - | 29.10.18 | JV of Belal Enterprise 01712-442893 | 14.1.19 | 07.02.19 | 29338743 | 21.2.19 | 60% | 20.02.20 | 16732000 | - | 12606743 | 57.03% | -
| Chatak |  | b) Burarigaon-Alampur-Khaergaon Rd (Ch.2200-3200m). Road ID No-690233002 | 1 | - |  | - |  | - | [6 empty] | 85% |  |  | - |  |  | -
Package Total = |  |  |  | 3 | 10.25 | 26947599 | — | 26947599 | — | — | — | — | — | 29338743 | — | 72.5% | — | 16732000 | — | 12606743 | 0% | —
37 | Jamalgonj | LGED/RARIP/SUN/UNRS/18-19/W-15 | Sachna Bazar UP Office (Fazilpur) Ramnagar-Bazar Road (Ch.4150-5150m). Road ID No-690503001 | 1 | - | 49862471 | - | 49862471 | - | - | - | - | - | - | - |  | - | - | - |  | - | Re-Tender receive 01.09.19
| Sulla |  | Saskhai Bazar to Protappur Bazar (Ch.3000-5000m). (Submersible Road). Road ID No-690863004 | 2 | - |  | - |  | - | [9 empty] | - |  | -
| Dharmapash |  | Dharmapash-Badshagonj via Mohishakanda Bazar road (Ch.5400-7500m). Road ID No-690323001 | 2.1 | - |  | - |  | - | [9 empty] | - |  | -
Package Total = |  |  |  | 5.1 | - | 0 | — | 0 | — | — | — | — | — | 0 | — | 0% | — | 0 | — | 0 | 0% | —
38 | Jagannathpur | LGED/RARIP/SUN/MAR/18-19/W-157 | Improvement of Goprapur Bazer under Jagannthpur Upazila | 0 | 0 |  |  | 8161262 | [5 empty] | 0 |  |  |  | 0 |  |  |  | Re Tender
Improvement of kolkoli Bazer under Jagannthpur Upazila
Package Total = |  |  |  | 0 | 0 | 0 | — | 8161262 | — | — | — | — | — | 0 | — | 0% | — | 0 | — | 0 | 0% | —
39 | Jamalganj | LGED/RARIP/SUN/MAR/18-19/W-158 | Improvement of Ramnagar Bazer under Jamalganj Upazila | 0 | 0 |  |  | 2286642 | - | 12.11.19 | M/S Babuipurkayasto 01716072590 | 30.04.20 | 20.05.20 | 2508149 | 07.06.20 | 0% | 06.06.20 | 0 | - | 0 | 0% | Evaluation under process
Total |  |  |  | 77.294 | 20.865 | 508128762 | 565271 | 510980675 | 109771 | - | - | - | - | 386576011.65 | - | 63.1% | - | 205319702 | 1851000 | 218102496.65 | 53.11% | -