## Civil Works
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
[41 empty] | 100 | 2026-08-06
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks | Gap between Bank Per. Security and Completion date | DPP Length | DPP Cost | Total Contract days | daily target | Days spent till now |  | Targeted progress | Achived Progress | Gap Between achivement
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
6 | 2018-19 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/GAI-S/UNR/18-19/W-06 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | M/S Basundhara, Kurigram | 3600.00 4496.00 | 4150.00 7600.00 | 3.654 | 6 | 29444723.57 | 991093.47 | 30435817.04 | 29438902.5 | 991097.41 | 30429999.91 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 21-04-2020 31-12-2020 |  | 2020-12-31 | 65% | 10699800 | 2070100 | 12769900 | 1734520 | 335580 | 2070100 | 14840000 | 48.77% | WBM Complete. BC preparation ongoing | #VALUE! | 4 | 367.364 | #VALUE! | #VALUE! | 2650 | #VALUE! | #VALUE! | 65% | #VALUE!
136 | 2020-21 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/SAD/UNR/ 20-21/W-136 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 |  | 7627 | 8057 | 0.43 |  | 4238910 |  | 4238910 | [20 empty] | Evaluation on going
9 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-09 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure under khorda Rasulpur-Chandiapur Road at Ch.710.0m. Under Shdullapur, District Gaibandha. | Md.Khademul Islam Jewel, Gaibandha | 0 | 2000 | 2 | 6.2 | 16764810.71 | 1868067 | 18632877.71 | 17548454.17 | 1064613.71 | 18613067.88 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 17-03-2020 15-09-2020 |  | 2020-10-15 | 100% | 11273900 | 2138050 | 13411950 | 1797215 | 340834 | 2138049 | 15549999 | 83.54% | Work Completed | #VALUE! | 2 | 183.682 | #VALUE! | #VALUE! | 2650 | #VALUE! | #VALUE! | 100% | #VALUE!
10 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-69 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.2000m-4000m. including 6Nos (0.625x0.600) m U-Drain on Khorda Rasulpur-Chandiapur Road at Ch: 2920m,2953m,3089m,3393m, 3582m & 3743m and 1x2.00mx2.00 m RCC Box Culvert at Ch: 2645m under khorda Rasulpur-Chandiapur Road under Shdullapur, District Gaibandha. | [28 empty] | package holded | [8 empty] | 0% | 0%
10 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-10 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | M/S SAJIN TRADERS JV | 1235 | 3235 | 2 | 0.6 | 17379171 | 145336 | 17524507 | 17391992.65 | 127964.94 | 17519957.59 |  |  | 2019-04-18 | 2019-05-08 | 2019-05-14 | 2020-03-21 |  | 2020-04-19 | 100% | 9841196 | 2228152 | 12069348 | 1840948 | 387204 | 2228152 | 14297500 | 81.61% | Work Completed | 29 | 2 | 183.682 | 318 | 0.31447 | 2647 | 832.4% | 100% | 100% | 0%
135 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-70 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.0m-1250m. including Costruction of 2Nos (0.625x0.600) m U-Drain on Mohishbandhi-Mirpur Road at Ch: 52m & 946m Under Shdullapur, District Gaibandha. | [28 empty] | package holded | [8 empty] | 0% | 0%
12 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-12 | 132823017 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure and Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | Md. Mahomudun Nobi, Pirganj, Rangpur | 2627 | 3627 | 1 | 3.6 | 7673417 | 1106313 | 8779730 | 7289746.1 | 1050997.35 | 8340743.45 |  |  | 2019-03-21 | 2019-04-07 | 2019-04-13 | 2020-03-08 |  | 2020-03-31 | 100% | 5511343.59 | 1203622.41 | 6714966 | 1000461.77 | 203130.23 | 1203592 | 7918558 | 94.94% | Final Bill Paid | 23 | 1 | 91.841 | 336 | 0.29762 | 2678 | 797% | 100% | 100% | 0%
135 | 2020-21 | Gaibandha | Saghata | Union Road-BC | PRO/GAI/SAG/UNR/20-21/W-135 | 132883015 | Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha. |  | 3526 | 6386 | 2.86 |  | 26773265 |  | 26773265 | [20 empty] | NOA Issued |  | 2.85 | 261.7468 | [6 empty] | 0%
72 |  | Gaibandha | Fulchori | Union Road-BC |  | 132213003 | Erandabari U.P H/Q-Algarchar bazar | [30 empty] | 1.08 | 99.1883 | [6 empty] | 0%
7 |  | Gaibandha | Fulchori | Union Road-BC |  | 132213011 | Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S | [30 empty] | 2.5 | 229.6025 | [6 empty] | 0%
71 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 71 | 132823004 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | M/S Mafi Construction JV, Sadullapur, Gaibandha | 0 | 2000 | 2 | 14.3 | 16679589 | 2485578 | 19165167 | 14006744.15 | 2283645.85 | 16290390 |  |  | 2020-05-11 | 2020-05-18 | 2020-05-28 | 2021-05-28 |  | 2022-05-17 | 60% | 3119470 | 690265 | 3809735 | 565199 | 125066 | 690265 | 4500000 | 27.62% | WBM Complete |  | 2 | 183.682 | [6 empty] | 0%
68 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 68 | 132823009 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 1500 | 2500 | 1 | 1 | 9588269 | 164366 | 9752635 | 8126474.979 |  | 8126474.979 |  |  | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 |  | 2021-05-13 | 70% | 3099996 | 608400 | 3708396 | 508586 | 99814 | 608400 | 4316796 | 53.12% | WBM complete |  | 1 | 91.841 | [6 empty] | 0%
72 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 72 | 132823015 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 0 | 1000 | 1 | 5.3 | 9822898 | 1226329 | 11049227 | 9095523.665 |  | 9095523.665 |  |  | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 |  | 2021-05-13 | 20% | 707634 | 134472 | 842106 | 112999 | 21473 | 134472 | 976578 | 10.74% | Stopped work due water in both side of road |  | 1 | 91.841 | [6 empty] | 0%
14 |  | Gaibandha | Sadar | Village Road-BC |  | 132244025 | Jugir ghat-Badsharghat Road. | [30 empty] | 2.9 | 250.6215 | [6 empty] | 0%
114 |  | Gaibandha | Sadar | Village Road-BC |  | 132245056 | Salam bazar- Balayata bazar via Mouza malibari Edghah | [30 empty] | 2.5 | 216.053 | [6 empty] | 0%
115 |  | Gaibandha | Saghata | Village Road-BC |  | 132884061 | Trimohoni Khayaghat-Ullasonatola bazar Rd. | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
116 |  | Gaibandha | Saghata | Village Road-BC |  | 132884024 | Durgapur Sazahan Ali Govt. primary School - Pass Durgapur Govt. Primary School | [30 empty] | 2.2 | 190.1266 | [6 empty] | 0%
117 |  | Gaibandha | Saghata | Village Road-BC |  | 132884038 | Boliarber GPS - Kamalerpara- Falia Pucca road | [30 empty] | 2.38 | 205.6825 | [6 empty] | 0%
113 |  | Gaibandha | Sundargonj | Village Road-BC |  | 132914077 | Shaker Bazar-Wapda Embankment via Baraikandi road | [30 empty] | 4 | 345.6848 | [6 empty] | 0%
7 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI/GAI-S/VR/18-19/W-07 | 132244011 | Improvement of Bituminous Carpeting Road on Fulbari-Badiakhali hat Road At Ch0.00m-1623m. &2300m-3100m. including Costruction of 10 U- drain (0.600mx0.625m) Fulbari-Badiakhali hat Road atCh0.00m-1623m. &2300m-3100m. Under Gaibandha Sadar Upazila, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 2300 | 1623 3100 | 2.423 | 6 | 22031940.04 | 1000431.53 | 23032371.57 | 22027478.06 | 1000435.54 | 23027913.6 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 24-03-2020 30-12-2020 |  | 2020-12-31 | 95% | 11900400 | 2349800 | 14250200 | 1962327 | 387473 | 2349800 | 16600000 | 72.09% | BC Complete | #VALUE! | 3.5 | 302.4742 | #VALUE! | #VALUE! | 2650 | #VALUE! | #VALUE! | 95% | #VALUE!
8 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI /GAI-S/VR/18-19/W-08 | 132244021 | Improvement of Bituminous Carpeting Road on Ruper –Eslighat via Pramanik para Road at Ch.1500m-2980m including Costruction of 3 U- drain (0.600mX0.625m) at Ch.1280m,2300m,2640m. Under Gaibandha Sadar Upazila, District Gaibandha. | RSL Enterprise, gaibandha | 1500 | 2980 | 1.48 | 1.8 | 16529257.77 | 302110 | 16831367.77 | 16518512.1 | 302111.17 | 16820623.27 |  |  | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 |  | 2020-04-23 | 100% | 11472451 | 2253310 | 13725761 | 1904749 | 348561 | 2253310 | 15979071 | 95% | Final Bill Paid | 2 | 3 | 259.2636 | 352 | 0.28409 | 2650 | 752.8% | 100% | 100% | 0%
11 | 2018-19 | Gaibandha | Shadullapur | Village Road-BC | PRO/GAI/SAD/VR/18-19/W-11 | 132824014 | Improvement of Bituminous Road on Shdullapur Dhaperhat G.C road at Boxigonj Bazar toDhaperhat-Madarhat Road via Ambagan Road at Ch.0.00m-2480m. including Costruction of 11 Nos U-Drain 0.600mx0.625m at Ch.335m,720m,877m,1190m,1300m,1388m,1477m,1765m,1880m,1972m,&2226m. Under Shdullapur, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 | 2480 | 2.48 | 6.6 | 20485874 | 1361706 | 21847580 | 20563288.22 | 1361711.78 | 21925000 |  |  | 2019-04-18 | 2019-05-15 | 2019-05-21 | 02-05-2020 31-07-2020 |  | 2020-07-31 | 100% | 13273661 | 2504677 | 15778338 | 2107080 | 397597 | 2504677 | 18283015 | 83.39% | Work Complete | #VALUE! | 2.48 | 214.3246 | #VALUE! | #VALUE! | 2640 | #VALUE! | #VALUE! | 100% | #VALUE!
13 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-13 | 132885163 | Improvement of Bituminous Road on Gatia H/O Taibor Master-Chitholia H/O Mahatab Member Road at Ch.0.00m-800m. including Costruction of 4 Nos U-Drain 0.600mx0.625m at Ch20m,135m,290m,&700m Under Saghata, District Gaibandha. | Md. Jakir Hossain, Gaibandha | 0 | 800 | 0.8 | 2.4 | 7459743 | 304702 | 7764445 | 7086755.8 | 282523.35 | 7369279.15 |  |  | 2019-03-21 | 2019-04-15 | 2019-04-21 | 2020-04-06 |  | 2019-12-29 | 100% | 5007817 | 994738 | 6002555 | 839420 | 155318 | 994738 | 6997293 | 94.95% | Final Bill Paid | -99 | 0.8 | 69.137 | 357 | 0.28011 | 2670 | 747.9% | 100% | 100% | 0%
14 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-14 | 132884002 | Improvement of Bituminous Road on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Road at ch.600m-2930m. including Costruction of 10 Nos U-Drain 0.600mx0.625m at Ch.673m,735m,816m,925m,1387m,1760m,1920m,1987m,2150m,2493m.and Costruction of 3 Nos Slope Drain at Ch.1496m, 1745m, 2075m, and Costruction of 3 Nos (2.00mx2.00m) Cross Drainges Structure on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Roadat Ch.2395m,2590m, 2787m. Under Saghata, District Gaibandha. | M/S SAJIN TRADERS JV | 600 | 2930 | 2.33 | 22.5 | 18252469 | 3310465 | 21562934 | 20694775 | 853394.34 | 21548169.34 |  |  | 2019-04-18 | 2019-05-07 | 2019-05-13 | 2020-03-25 |  | 2020-04-23 | 100% | 11038037 | 2243231 | 13281268 | 1842848 | 400383 | 2243231 | 15524499 | 72.05% | Work Completed. | 29 | 2.85 | 246.3004 | 323 | 0.3096 | 2648 | 819.8% | 100% | 100% | 0%
114 | 2019-20 | Gaibandha | Sadar | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-114 | 132245158 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Salam bazar- Balata bazar via Mouja malibari Eidgah at ch. 00-2500m | 1.Mst. Mousi akter 2.Mst. Aduri | 0 | 2500 | 2.5 |  | 1331224.49 |  | 1331224.49 | 1281224.49 |  | 1281224.49 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% | 75200 |  | 75200 |  |  | 0 | 75200 | 5.869% | Work on going, | [8 empty] | 10%
115 | 2019-20 | Gaibandha | Shadullapur | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-115 | 132823009 132823008 132823001 132823004 132823006 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Naldanga G.C.-Ramzibon U.P. office. Road at ch. 00-780m. 2. Idilpur U.P. office-Dhaperhat U.P. office road at ch. 00-2000m. 3. Khorda Rasulpur-chandiapur roadat ch. 00-1020m. 4. Bhatgram U.P office-Jamalpur Bazar at ch.00-2000m. 5 Chandiapur bazar-Rahmatpur GC via Rasulpur bazar at ch.00-2000m. | 1. Mst. Jobeda Begum & Mst. Sahada Begum Begum 2 Mst.Rony begum & Shoprati 3. bimoti rani & Mst .Rahima Begum. 4. Dulali begum & Mst. Salaha Begum 5. Mst. Aysa Begum & Mst. Lili Begum | 0.00 0.00 0.00 0.00 0.00 | 780 2000 1020 2000 2000 | 7.8 |  | 3639329.09 |  | 3639329.09 | 3483329.08 |  | 3483329.08 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% | 198850 |  | 198850 |  |  | 0 | 198850 | 5.709% | Work on going, | [8 empty] | 10%
116 | 2019-20 | Gaibandha | Saghata | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-116 | 132885022 132885175 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Dighal Kandi- Digholkandi H/O Sonaullah Mirja at ch.00-2700m. 2. Chakili H/O Vikku sarker - Folia Bazar road at ch. 00-1900m. | 1.Mst. Fatema Begum & Mst.Rausan Ara 2. Rozina & Mst.salina | 0.00 0.00 | 2700 1900 | 4.6 |  | 2374181.13 |  | 2374181.13 | 2282181.12 |  | 2282181.12 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% | 128350 |  | 128350 |  |  | 0 | 128350 | 5.624% | Work on going, | [8 empty] | 10%
117 | 2019-20 | Gaibandha | Fulchori | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-117 | 132213003 132213011 132214050 132215025 132215037 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Erandabari U.P H/Q-Algarchar bazar at ch.1170-2250m. 2. Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S at ch.00-2500m. 3. Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram at ch.1170-2000m. 4. Pachim Khatiamary H/O Jalal Member-Gucha gram at ch.00-1000m. 5 Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary at ch.00-950m. | 1. Mst. Diljan Begum & Mst. Forida Begum 2. Mst. Rajina & Mst. Kulsum 3. Mst. Balia Khatun & Mst. Anna Khatun 4. Mst. Amena Begum & Mst. Azima Khatun 5. Mst. Foyzan & Mst. Rasheda Begum | 1170 0.00 1170 0.00 0.00 | 2250 2500 2000 1000 950 | 6.36 |  | 3210146.42 |  | 3210146.42 | 2929878.56 |  | 2929878.56 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% | 175350 |  | 175350 |  |  | 0 | 175350 | 5.985% | Work on going, | [8 empty] | 10%
28 |  | Gaibandha | Saghata | Village Road-HBB |  | 132885022 | Dighal Kandi- Digholkandi H/O Sonaullah Mirja | [30 empty] | 3.2 | 185.472 | [6 empty] | 0%
39 |  | Gaibandha | Fulchori | Village Road-HBB |  | 132214036 | Fulchari Kheyaghat-Tengrakandi Road | [30 empty] | 1.6 | 92.736 | [6 empty] | 0%
40 |  | Gaibandha | Fulchori | Village Road-HBB |  | 132214050 | Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram | [30 empty] | 0.83 | 48.1068 | [6 empty] | 0%
41 |  | Gaibandha | Fulchori | Village Road-HBB |  | 132215025 | Pachim Khatiamary H/O Jalal Member-Gucha gram | [30 empty] | 1 | 57.96 | [6 empty] | 0%
42 |  | Gaibandha | Fulchori | Village Road-HBB |  | 132215037 | Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary | [30 empty] | 0.95 | 55.062 | [6 empty] | 0%
43 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Ramdakua- Akotar Bazar | [30 empty] | 0.5 | 28.98 | [6 empty] | 0%
23 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Karent Bazar | [30 empty] | 0.5 | 28.98 | [6 empty] | 0%
81 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Mondoler hat | [30 empty] | 0.5 | 28.98 | [6 empty] | 0%
82 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Hazari hat | [30 empty] | 1 | 57.96 | [6 empty] | 0%
65 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar- Kagia Char Ahmed Nagar Bazar | [30 empty] | 1 | 57.96 | [6 empty] | 0%
66 |  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar-Vati Kapasia Nuton Asraon Bazar | [30 empty] | 1.41 | 81.7236 | [6 empty] | 0%
113 | 2019-20 | Gaibandha | Sundargonj | Maintenance-LCS | PRO/GAI/SUN/RMP/19-20/ MW-113 | 132915058 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Kapashia UP Office to Kashim Bazar- WAPDA Embankment via H/O Nesab Chairman (Kajir Char Ahammed Nagar Bazar) road, at Ch. 00-2300m. | 1.Mst. Momata Begum & Mst Ismat Ara Begum | 0 | 2300 | 2.3 |  | 1327224.49 |  | 1327224.49 | 1281224.49 |  | 1281224.49 |  |  |  | 2020-09-15 |  | 2022-09-14 |  |  | 10% | 75200 |  | 75200 |  |  | 0 | 75200 | 5.869% | Work on going,
104 |  | Gaibandha | Fulchori | Large Market |  |  | Purbo Fulchari Bazar | [31 empty] | 62.7 | [6 empty] | 0%
103 |  | Gaibandha | Fulchori | Large Market |  |  | Sannasirchar Bazar | [31 empty] | 62.7 | [6 empty] | 0%
112 |  | Gaibandha | Sundargonj | Large Market |  |  | Kashem Bazar | [31 empty] | 62.7 | [6 empty] | 0%
111 |  | Gaibandha | Sadar | Medium Market |  |  | Balua Hat | [31 empty] | 41.77 | [6 empty] | 0%
106 |  | Gaibandha | Sadar | Medium Market |  |  | Puraton Badiakhali Hat | [31 empty] | 41.77 | [6 empty] | 0%
89 |  | Gaibandha | Sadar | Medium Market |  |  | Lenga Bazar Hat | [31 empty] | 41.77 | [6 empty] | 0%
98 |  | Gaibandha | Saghata | Medium Market |  |  | Ullah Sonatola Bazar | [31 empty] | 41.77 | [6 empty] | 0%
130 |  | Gaibandha | Saghata | Medium Market |  |  | Bhangamore | [31 empty] | 41.77 | [6 empty] | 0%
110 |  | Gaibandha | Saghata | Medium Market |  |  | Falia Bottola Bazar | [31 empty] | 41.77 | [6 empty] | 0%
61 |  | Gaibandha | Saghata | Medium Market |  |  | Ullah Bazar | [31 empty] | 41.77 | [6 empty] | 0%
62 |  | Gaibandha | Saghata | Medium Market |  |  | Dhakin Digholkandi | [31 empty] | 41.77 | [6 empty] | 0%
87 |  | Gaibandha | Saghata | Medium Market |  |  | Nayabondar Bazar | [31 empty] | 41.77 | [6 empty] | 0%
122 |  | Gaibandha | Fulchori | Medium Market |  |  | Khatiamary Bazar | [31 empty] | 41.77 | [6 empty] | 0%
123 |  | Gaibandha | Fulchori | Medium Market |  |  | Taltola Bazar | [31 empty] | 41.77 | [6 empty] | 0%
124 |  | Gaibandha | Fulchori | Medium Market |  |  | Kayerhaat | [31 empty] | 41.77 | [6 empty] | 0%
16 |  | Gaibandha | Fulchori | Medium Market |  |  | Daluabari Haat | [31 empty] | 41.77 | [6 empty] | 0%
17 |  | Gaibandha | Fulchori | Medium Market |  |  | Jigabari Haat | [31 empty] | 41.77 | [6 empty] | 0%
74 |  | Gaibandha | Fulchori | Medium Market |  |  | Algharchar Bazar | [31 empty] | 41.77 | [6 empty] | 0%
137 |  | Gaibandha | Fulchori | Medium Market |  |  | Jhanjhor Bazar | [31 empty] | 41.77 | [6 empty] | 0%
138 |  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar | [31 empty] | 41.77 | [6 empty] | 0%
15 |  | Gaibandha | Shadullapur | Medium Market |  |  | Naldanga kachari Bazar | [31 empty] | 41.77 | [6 empty] | 0%
107 |  | Gaibandha | Sundargonj | Medium Market |  |  | Belka Bazar | [31 empty] | 41.77 | [6 empty] | 0%
108 |  | Gaibandha | Sundargonj | Medium Market |  |  | Charoker Hat | [31 empty] | 41.77 | [6 empty] | 0%
109 |  | Gaibandha | Sundargonj | Medium Market |  |  | Domer Hat | [31 empty] | 41.77 | [6 empty] | 0%
44 |  | Gaibandha | Sundargonj | Medium Market |  |  | Moyej Mear Hat | [31 empty] | 41.77 | [6 empty] | 0%
119 |  | Gaibandha | Sundargonj | Medium Market |  |  | Jamaler Hat | [31 empty] | 41.77 | [6 empty] | 0%
18 |  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar | [31 empty] | 41.77 | [6 empty] | 0%
19 |  | Gaibandha | Shadullapur | Medium Market |  |  | Kantanagar bazar | [31 empty] | 41.77 | [6 empty] | 0%
120 |  | Gaibandha | Saghata | Small Market |  |  | Futani Bazar | [31 empty] | 26.11 | [6 empty] | 0%
141 |  | Gaibandha | Fulchori | Small Market |  |  | Moshamari Bazar | [31 empty] | 26.11 | [6 empty] | 0%
140 |  | Gaibandha | Fulchori | Small Market |  |  | Katlamari Bazar | [31 empty] | 26.11 | [6 empty] | 0%
125 |  | Gaibandha | Sundargonj | Small Market |  |  | Shokher Hat | [31 empty] | 26.11 | [6 empty] | 0%
21 | 2018-19 | Kurigram | Chilmari | Union Road-BC | PRO/KUR/CHI/UNR/18-19/W-21 | 149093002 | Improvement of Bituminous Carpating Road On Thanahat up office – Balabarihat via Kajaldanga hat at Ch.2985m-3455m. Under Chilmari Upazila, District Kurigram. | Nakshi Mobile Palace,Krishnopur, Kurigram | 2985 | 3455 | 0.47 | 0 | 4159071 | 0 | 4159071 | 3951117.45 |  | 3951117.45 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-25 |  | 2020-05-14 | 100% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 75.44% | All Item Completed.Final Bill Sent to H/Q |  | 1.97 | 180.9268 | 273 | 0.3663 | 2627 | 962.3% | 100% | 100% | 0%
79 | 2019-20 | Kurigram | Chilmari | Rehabilitation-Union Road | PRO/KUR/CHIL/UNR/19-20/RW-79 | 149093002 | Rehabilitation of Thanahat Up Office to Balabarihat via Kazaldanga Hat Road at Ch: 00m-1040m including Construction of 1Nos 1x3.00mx2.50mm RCC. Box Culvert at Ch: 15m and 1Nos 1x0.625mx0.600mm U-Drain at Ch: 760m and 1Nos 1x2.50mx2.00m m RCC. Box Culvert at Ch: 820m under Upazila:Chilmari, District:Kurigram | Md.Abul Hossain, Shaheb Bazar,Groramara,Rajshahi. | 0 | 1040 | 1.04 | 7.5 | 4492492 | 1915132 | 6407624 | 3187498.28 | 1915132 | 5102630.28 |  |  | 2020-07-04 | 2020-04-21 | 2020-05-15 | 2021-02-14 |  | 2021-04-19 | 0% | [8 empty] | Work will start soon | [9 empty] | 0%
80 | 2019-20 | Kurigram | Nageswari | Union Road-BC | PRO/KUR/NAG/UNR/19-20/W-80 | 149613039 | Improvement of Ramkhana UP office to Sealkanda bazar Road at Ch: 1000m-2776m including Construction of 1Nos 1x2.00mx2.00m RCC. Box Culvert at Ch: 1727m and 4Nos 1x0.6250mx 0.625m m RCC. Box Culvert at Ch: 1080m,1390m,2022m & 2118.00m Under Upazila: Nageswari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 1000 | 2776 | 1.776 | 6.5 | 16305564 | 1149239 | 17454803 | 14035591.24 | 942642.23 | 14978233.472 |  |  | 2020-02-26 | 2020-03-15 | 2020-05-23 | 2021-05-22 |  | 2021-03-19 | 35% | [8 empty] | Sub-base complete |  | 3 | 275.523 | 433 | 0.23095 | 2335 | 539.3% | 100% | 35% | 65%
1 | 2019-20 | Kurigram | Sadar | Maintenance-Office | PRO/KUR/MAINT/19-20/W-1 |  | Maintenance work of LGED Office Building, Dist: Kurigram | M/S Afiya Traders, Krishnopur, Chorupara, Sadar, Kurigram | [6 empty] | 874612.86 |  |  | 874612.86 |  |  |  | 2019-11-11 | 2019-11-11 | 2019-11-28 |  |  | 100% |  |  | 753095 |  |  | 121517.86 | 874612.86 | 100% | Final bill paid
2 |  | Kurigram | Nageswari | Union Road-BC |  | 149613041 | Hasnabad UP Office - Newashi GC. | [30 empty] | 2 | 183.682 | [6 empty] | 0%
78 |  | Kurigram | Rajarhat | Union Road-BC |  | 149773010 | Burirhat-Gharialdanga UP office. | [30 empty] | 1.45 | 133.1695 | [6 empty] | 0%
20 | 2018-19 | Kurigram | Chilmari | Village Road-BC | PRO/KUR/CHI/VR/18-19/W-20 | 149095036 | Improvement of Bituminous Carpating Road on Kutigram Madrasha Pacca Rd – Kachkol CARE Bridge via Eblus Chairman house Road Ch. 00m-790m. & Link Road 0.00-230.0m. Under Chilmari Upazila, District Kurigram. | M/S. S. T Enterprise, Nageswari, Kurigram | 0 0 | 790 230 | 1.02 | 0 | 7735062 | 0 | 7735062 | 7348308.9 | 0 | 7348308.9 | 0 | 0 | 2019-05-05 | 2019-05-26 | 2019-06-03 | 25-02-2020 30-05-2021 |  | 19-05-2020 30-05-2020 | 65% | 2668854 | 0 | 2668854 | 0 | 0 | 0 | 2668854 | 36.32% | Sand filling , Sub-base & WBM completed. | #VALUE! | 1.45 | 125.3107 | #VALUE! | #VALUE! | 2629 | #VALUE! | #VALUE! | 65% | #VALUE!
22 | 2018-19 | Kurigram | Sadar | Village Road-BC | PRO/KUR/KUR-S/VR/18-19/W-22 | 149525128 | Improvement of Bituminous Carpating Road on Paramali Dr. Sahabuddin Tepoti to Rajarhat Ch.000-1930m & at Ch.1585 Link Road Ch.0.00-264.0m including Contruction of 04 Nos. (0.625mx0.600m) U-Drain on Paramali Dr. Sahabuddin Tepoti to Rajarhat Road at Ch.90m,730m,1250m & 1770m . Kurigram Sader Upzila,District Kurigram | Md. Mahmud Alam Liton, Fulbari Pourashova,Fulbari | 0 0 | 1930 264 | 2.19 | 2.5 | 16229100 | 514550.2 | 16743650.2 | 16241461.24 | 501008.14 | 16742469.38 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2021-05-27 | 65% | 9164025 | 0 | 9164025 | 0 | 0 | 0 | 9164025 | 54.74% | Ch. 0.00-2.190km sand filling Sub-base & WBM completed,3 Nos U-Drain completed. Turffing Work Running. [ Time Extension Under Process ] | 362 | 3 | 259.2636 | 366 | 0.27322 | 2625 | 717.2% | 100% | 65% | 35%
24 | 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BUR/VR/18-19/W-24 | 149064036 | Improvement of Bituminous Carpating Road on Milon Bazar – Baladfia Bazar (End point H/O Nasir Uddin) at Ch.00-2000.0m. including Contruction of 03 Nos. 0.625mx0.600m U-Drain at Ch.1003m, 1685m Under Bhurungamari Upazila, District Kurigram., | M/S. Hamid Traders, Hospitalpara, Kurigram Sadar, Kurigram | 0 | 2000 | 2 | 1.88 | 14468747 | 275159 | 14743906 | 13429170.35 | 260283.77 | 13689454.12 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2020-11-20 | 100% | 9370863 | 233117 | 9603980 | 0 | 0 | 0 | 9603980 | 70.16% | All Item Completed.Final Bill Sent to H/Q | 174 | 2 | 172.8424 | 366 | 0.27322 | 2625 | 717.2% | 100% | 100% | 0%
25 | 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KURI/NAW/VR/18-19/W-25 | 149615083 | Improvement of Bituminous Carpating Wabda Bazar – Berubari Abashon Road at Ch.00.0-1200.00m Under Nageswari Upazila, District Kurigram. ` | M/S. Fahim Traders, RK Road, Sadar Kurigram | 0 | 1200 | 1.2 | 0 | 9114248.72 | 0 | 9114248.72 | 8658536.55 | 0 | 8658536.55 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 |  | 2020-05-07 | 100% | 6573373 | 0 | 6573373 | 0 | 0 | 0 | 6573373 | 75.92% | All Item Completed.Final Bill Sent to H/Q | 70 | 2 | 172.8424 | 275 | 0.36364 | 2627 | 955.3% | 100% | 100% | 0%
26 | 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KURI/RJP/VR/18-19/W-26 | 149084053 | Improvement of Bituminous Carpating Road on By Tangalipara- Pakhiura road at Ch.0.00-2000.0m.Under Rajibpur Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 0 | 2000 | 2 | 0 | 15018035 | 0 | 15018035 | 14211257.3 |  | 14211257.3 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-07 | 2020-05-30 |  | 29-05-2020 28-02-2021 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | No work at site, XEN Issued letter to Contractor | #VALUE! | 2 | 172.8424 | 366 | 0.27322 | 2625 | 717.2% | 100% | 20% | 80%
27 | 2018-19 | Kurigram | Ulipur | Village Road-BC | PRO/KURI/ULP/VR/18-19/W-27 | 149944098 | Improvement of Bituminous Carpating Road on Ramramhat Mosque – Hatiar Mela WAPDA Embankment via Kokire para road at Ch.0.00-2080.0m including Contruction Of 2 Nos.0.600mx0.625m U-Drain at Ch.595, 786m. and Contruction Of 1 Nos.Cross Drainge Structure at Ch.1485.0m. Under Ulipur Upzila, District Kurigram. | Milu Nowroj Abu Bakar, College Road, Kurigram Sadar, Kurigram | 0 | 2080 | 2.08 | 4.2 | 17817664.39 | 1159563.14 | 18977227.53 | 15698506.57 | 1143205.21 | 16841711.78 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 28-05-2020 31-02-2021 | 55% | 8981947 | 0 | 8981947 | 0 | 0 | 0 | 8981947 | 53.33% | Contractor wil start reamining work soon.Sand filling & Sub-base Up to 1950m, WMB 1950m Running 3 Nos U-Drain/1.Nos Cross Drain Completed,Palisading work 400m Completed . [ Time Extension Under Process ] | #VALUE! | 3 | 259.2636 | 366 | 0.27322 | 2625 | 717.2% | 100% | 55% | 45%
28 | 2018-19 | Kurigram | Rajarhat | Village Road-BC | PRO/KURI/RAJ/VR/18-19/W-28 | 149775079 | Improvement of Bituminous Carpating Road on Mondir Mouja at H/O Nousher Ali- Khamar GPS Road at Ch.0.00m-2725.0m under Fulbari Upazila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2725 | 2.725 | 0 | 21122799.06 | 0 | 21122799.06 | 18424739.36 | 0 | 18424739.36 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 21-05-2020 21-11-2020 | 40% | 5779701 | 0 | 5779701 | 0 | 0 | 0 | 5779701 | 31.37% | WBM complete. [ Time Extension Under Process ] | #VALUE! | 3 | 259.2636 | 366 | 0.27322 | 2625 | 717.2% | 100% | 40% | 60%
39 | 2018-19 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/18-19/W-39 | 149185051 | Improvement of Bituminous Carpating Road On Bokultola Bazar-H/O Nobiul Road at Ch. 00m – 1070.00m including Construction of U-drain (600mm X 0.625mm) at Ch.131m. Under Fulbari Upazila, District Kurigram. | M/S. Milon Traders, Nilkhanto, Khalilgonj Bazar, Kurigram Sadar, Kurigram | 0 | 1070 | 1.07 | 0.6 | 8949548.12 | 100532 | 9050080.12 | 8502070.714 | 95505.4 | 8597576.114 | 0 | 0 | 2019-05-05 | 2019-05-30 | 2019-06-06 | 2020-02-28 |  | 2020-02-13 | 100% | 5143774 | 0 | 5143774 | 0 | 0 | 0 | 5143774 | 59.83% | All Item Completed. | -15 | 2 | 172.8424 | 274 | 0.36496 | 2625 | 958% | 100% | 100% | 0%
40 | 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KUR/NAG/VR/18-19/W-40 | 149614060 | Improvement of Bituminous Carpating Road on Kherbari More UZR-Boitulah More via Taleberhat Road at Ch.1000-4070m including Construction Of 9 Nos. 0.600mx0.625mU-Drain at.Ch.1400m, 1780m, 1940m, 2220m, 3300m, 2244m, 3550m, 3680m & 3840m,Under Nageswari Upazila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 1000 | 4070 | 3.07 | 5.4 | 24836379.47 | 1048387.17 | 25884766.64 | 21156136.31 | 890699.56 | 22046835.87 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 10-09-2020 31-03-2021 | 90% | 1057593 | 890699 | 1948292 | 0 | 0 | 0 | 1948292 | 8.837% | BC work complete [ Time Extension Procedure Under Process ] | #VALUE! | 3 | 259.2636 | 366 | 0.27322 | 2608 | 712.6% | 100% | 90% | 10%
41 | 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KUR/RAJI/VR/18-19/W-41 | 149084053 | Improvement of Bituminous Carpating Road on Tangalipara- Pakhiura road at Ch.2000-4000m.Under Rajibpur Upzila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 2000 | 4000 | 2 | 0 | 10723064 |  | 10723064 | 9828649 |  | 9828649 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 10-09-2020 31-03-2021 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contractor will start remaining work soon.Ch. 2.000-4.000km sand filling completed. AS Layer Running. [ Time Extension Procedure Under Process ] | #VALUE! | 2 | 172.8424 | 366 | 0.27322 | 2608 | 712.6% | 100% | 25% | 75%
42 | 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BHU/VR/18-19/W-42 | 149064003 | Improvement of Bituminous Carpating Road on R&H Trimohoni – Shingjhar Road at Ch.325.00-2685.00m. including Construction Of 1 Nos. (4x4.00x4.00) m Cross Drianges Structure at Ch 1702.00m. and Construction Of 1 Nos. (2.00x2.00) m Cross Drianges Structure and Construction Of 14 Nos.0.600mx0.625m U-Drain at Ch.636m,714m,935m,960m,1051m,1201m,1355m,1550m,2003m,2166m,2230m,2586m,2767m&3330m.Under Bhurungamari Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 325 | 2685 | 2.36 | 14.9 | 16522104 | 6439018 | 22961122 | 14962086.19 | 6239684.88 | 21201771.07 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 |  | 29-05-2020 28-02-2021 | 50% | 5749291 | 0 | 5749291 | 0 | 0 | 0 | 5749291 | 27.12% | Stopped work due water in both side of road | #VALUE! | 2.36 | 203.954 | 366 | 0.27322 | 2608 | 712.6% | 100% | 50% | 50%
43 | 2018-19 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/18-19/W-43 | 149775095 | Improvement of Bituminous Carpating Road on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.0.00m-2000.0m Under Rajarhat Upzila, District Kurigram. including Construction Of 2 nos. 0.600mx0.625m U-Drain on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.1667m, &1924m. under Rajarhat Upzila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2000 | 2 | 1.2 | 16290727 | 186745 | 16477472 | 14742059.38 | 168353.11 | 14910412.49 | 0 | 0 | 2019-05-27 | 2019-05-30 | 2019-06-06 | 2020-05-30 |  | 2020-05-28 | 100% | 7373958 | 0 | 7373958 | 0 | 0 | 0 | 7373958 | 49.46% | All Item has been Completed. Final bill sent to HQ | -2 | 2 | 172.8424 | 366 | 0.27322 | 2625 | 717.2% | 100% | 100% | 0%
23 | 2018-19 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/HBB/18-19/W-23 | 149064016 | Improvement of Bituminous Carpating Road on HBB from Pagla hat Bazar –Shangkose River Ghat at Ch.00-1390.0m. Under Bhurungamari Upazila, District Kurigram. | M/S. Akram Traders, Porchim Nageswari, Kurigram | 0 | 1390 | 1.39 | 0 | 7388648.15 | 0 | 7388648.15 | 7019215.6 | 0 | 7019215.6 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 |  | 2022-05-26 | 100% | 4290110 | 0 | 4290110 | 0 | 0 | 0 | 4290110 | 61.12% | All Item Completed.Final Bill Sent to H/Q | 819 | 1.4 | 81.144 | 275 | 0.36364 | 2627 | 955.3% | 100% | 100% | 0%
63 |  | Kurigram | Sadar | Village Road-BC |  | 149525029 | Kawnia Ghat-Kaggipara G.P. School | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
64 |  | Kurigram | Sadar | Village Road-BC |  | 149524014 | Nowbash BWDB Emb.-Nayerhat Emb. | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
133 |  | Kurigram | Sadar | Village Road-BC |  | 149525043 | Shop of Abul at BWDB Embank.-Velurbazar | [30 empty] | 1 | 86.4212 | [6 empty] | 0%
131 |  | Kurigram | Sadar | Village Road-BC |  | 149525031 | Char Boraibari Rd | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
3 |  | Kurigram | Fulbari | Village Road-BC |  | 149185057 | Boroloi Bazar-Amsa Bazar | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
81 | 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 81 | 149185050 | Improvement of Uttar Kashipur Shenpara – Kashem Bazar Via Ghugurhat Road at Ch: 00m-2500m including Construction of 3Nos 1x0.600mx0.600m m RCC. Box Culvert at at Ch: 90m,270m,1437m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2500 | 2.5 | 3 | 21253035 | 317903 | 21570938 | 18298929.65 | 317903 | 18616832.65 |  |  | 2020-03-19 | 2020-03-29 | 2020-05-15 | 2021-05-14 |  | 2021-03-21 | 25% | [8 empty] | Box Cutting Completed,Sand Filling Running. |  | 2.5 | 216.053 | [6 empty] | 0%
82 | 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 82 | 149185060 | Improvement of H/O Shajamal – Bokultola Bazar Via Abder Tale House Road at Ch: 00m-545.00m including Construction of 2Nos U-Drain at Ch: 124m,375m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 545 | 0.545 | 2 | 4620972 | 211935 | 4832907 | 4027967.48 | 211935 | 4239902.48 |  |  | 2020-02-26 | 2020-03-16 | 2020-05-02 | 2020-11-02 |  | 2020-09-06 | 20% | [8 empty] | Box Cutting Completed,Sand Filling under running, Palisading and u-drain complete |  | 2 | 172.8424 | 231 | 0.4329 | 2334 | 1010% | 100% | 20% | 80%
5 |  | Kurigram | Bhurungamari | Village Road-BC |  | 149064020 | Thanaghat-Shahebganj Border Road | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
33 |  | Kurigram | Nageswari | Village Road-BC |  | 149615081 | Baparitary-Horibolarkuti via H/O Nur Islam Master | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
34 |  | Kurigram | Nageswari | Village Road-BC |  | 149614028 | Sarker tari UZR to Chanderhat | [30 empty] | 2.5 | 216.053 | [6 empty] | 0%
35 |  | Kurigram | Nageswari | Village Road-BC |  | 149614012 | Sadar Beparirghat - Momingonj bazar | [30 empty] | 1.84 | 159.015 | [6 empty] | 0%
65 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W-65 | 149774012 | Improvement of Bituminus carpeting road Chandamari-Shyom Narayan at Biddyananda road at Ch: 1000m-2235m including 1 Nos(0.625X0.625)m U-Drain under Upazila: Rajarhat, District: Lalmonirhat. | M/S Khairul Enterprise | 1000 | 2235 | 1.235 | 1 | 6826143 | 101493 | 6927636 | 5907689.72 | 101493 | 6009182.72 |  |  | 2020-11-02 | 2020-02-17 | 2020-02-24 | 2020-08-23 |  | 2020-02-16 | 0% | [8 empty] | Date over, no work at all |  | 2 | 172.8424 | 188 | 0.53191 | 2362 | 1256% | 100% | 0% | 100%
66 | 2019-20 | Kurigram | Rajarhat | Rehabilitation-Village Road | PRO/KUR/RAJA/VR/19-20/RW-66 | 149774012 | Rehabilitation of Chandamari-Shyom Narayan at Biddyananda road at Ch:00m-1000m under Upazila: Rajarhat, District: Lalmonirhat. | M/S Khairul Enterprise | 0 | 1000 | 1 |  | 2479051 |  | 2479051 | 2030770.61 |  | 2030770.61 |  |  | 2020-11-02 | 2020-02-17 | 2020-02-24 | 2020-08-23 |  | 2020-02-16 | 0% | [8 empty] | Date over, no work at all |  |  |  | 188 | 0.53191 | 2362 | 1256% | 100% | 0% | 100%
46 |  | Kurigram | Rajarhat | Village Road-BC |  | 149774029 | Rajmallihat hat-Nazimkhan UP (Jorsarar hat) via Battalarhat. | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
105 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W- 105 | 149774008 | Improvement of Rajmallir hat-Shakoa GPS road Ch: 00 m-1985.00m including Construction of 2x3.00mx3.00m Rcc.Box Culvert and 2 Nos0.925x0.925m U-Drain at Ch: 00 m-1985.00m Under Upazila: Razarhat, District:Kurigram. | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 0 | 1985 | 1.985 | 9.8 | 17188824 | 2342534 | 19531358 | 16512938.6 | 0 | 16512938.6 |  |  | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 |  | 2021-04-05 | 0% | [8 empty] | Contractor mobilization on going |  | 2 | 172.8424 | [6 empty] | 0%
99 |  | Kurigram | Rajarhat | Village Road-BC |  | 149775058 | Ramratan Mouza - Chinai UP gat road | [30 empty] | 1 | 86.4212 | [6 empty] | 0%
104 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W- 104 | 149775066 | Improvement of WAPDA Emb.at Chaturvuj Mouza-Makli Mouja at Brahmmon para road Ch: 00m-2000m Under Upazila: Razarhat, District:Kurigram. | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 0 | 2000 | 2 |  | 18457590 |  | 18457590 | 15528767.62 | 0 | 15528767.62 |  |  | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 |  | 2021-04-05 | 0% | [8 empty] | Contractor mobilization on going |  | 2 | 172.8424 | [6 empty] | 0%
103 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W-103 | 149774067 | Improvement of Nazimkhan -Forkerhat at Boroghat Madrasha More-Bottalahat road Ch: 00m-1000m including Construction of 3Nos 1x0.6250mx 0.625m m U-Drain at Ch: 630m,840m &982m Under Upazila: Razarhat, District:Kurigram | Sheetal Construction,R.K Road,Khalilgong,Sadar, Kurigram | 0 | 1000 | 1 | 3 | 9000125 | 312627 | 9312752 | 7905979.71 | 0 | 7905979.71 |  |  | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 |  | 2021-04-05 | 0% | [8 empty] | Contractor mobilization on going |  | 1 | 86.4212 | [6 empty] | 0%
112 | 2019-20 | Kurigram | Ulipur | Maintenance-LCS | PRO/KUR/ULI/RMP/19-20/MW-112 | 149944076 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Mollahat-Panchim side of Mogholbacha UP simana road at Ulipur Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 4.000Km) |  |  |  | 4 |  | 1981199 |  | 1981199 | [20 empty] | Will be dropped |  | 3 | 259.2636 | [6 empty] | 0%
111 | 2019-20 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/ULI/RMP/19-20/MW-111 | 149525026 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Panchgachi Bazer-Nayani Para Sarak at Kurigram Sadar Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 1.650Km) | Beauti Begum / Santona Rani |  |  | 1.65 |  | 1114033 |  | 1114033 | 1114033 |  | 1114033 |  |  |  | 2020-07-27 | 2020-09-01 | 2022-08-31 |  |  | 8% | [8 empty] | Maintenance work running
32 |  | Kurigram | Ulipur | Village Road-BC |  | 149944136 | Bozra U.P. office-Babur hat | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
106 | 2019-20 | Kurigram | Rowmari | Village Road-BC | PRO/KUR/ROW/VR/19-20/W- 106 | 149795038 | Improvement of Shaydabad to Shiber Dhangi FCD road Ch: 1000m-2000m Under Upazila: Rowmari, District:Kurigram. | M/s K.M Abu Bakar, Collage Road,Kurigram Sadar,Kurigram | 1000 | 2000 | 1 |  | 7923918 |  | 7923918 | 6881841.14 |  | 6881841.14 |  |  | 2020-06-26 | 2020-07-20 | 2020-09-01 | 2021-02-28 |  | 2021-03-28 | 40% | [8 empty] | WBM Complete |  | 1 | 86.4212 | [6 empty] | 0%
38 |  | Kurigram | Rowmari | Village Road-BC |  | 149795077 | Saidabad Bazar- west side Pakhiura hat via Komorvangi GPS | [30 empty] | 2.2 | 190.1266 | [6 empty] | 0%
89 | 2019-20 | Kurigram | Rowmari | Village Road-BC | PRO/KUR/ROW/VR/19-20/W-89 | 149794017 | Improvement of Boalmari Modho Mosque –Changtapara Via Danguapara Road at Ch: 1000m-3000m Under Upazila:Rowmari, District:Kurigram | M/S Hamid Traders | 1000 | 3000 | 2 |  | 17170453 |  | 17170453 | 15980384.43 |  | 15980384.43 |  |  | 2020-02-26 | 2020-03-16 | 2020-05-23 | 2021-05-22 |  | 2021-05-14 | 30% | [8 empty] | Work stopped now,Sand filling running |  | 2 | 172.8424 | 432 | 0.23148 | 2334 | 540.3% | 100% | 30% | 70%
98 | 2019-20 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/VR/19-20/W- 98 | 149064029 | Improvement of Dhaldanga Bazar-Shilkhuri Kheya ghat road (HBB) Ch: 1200m-2250m including Construction of 1x2.00mx 2.00m RCC. Box Culvert on Ch: 1540m under Upazila:Bhurungamari, District:Kurigram. | M/S. Belal Construction,Horiswor Kaloea,Khalilgonj,Kurigram sadar,Kurigram. | 1200 | 2250 | 1.05 | 2.5 | 5160645 | 758362 | 5919007 | 5172960.88 |  | 5172960.88 |  |  | 2020-12-04 | 2020-04-21 | 2020-05-15 | 2021-09-14 |  | 2021-09-05 | 85% | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 57.99% | HBB completed. Turfing on going. |  | 1.05 | 60.858 | [6 empty] | 0%
130 | 2020-21 | Kurigram | Rajarhat | Village Road-BC | PRO/KURI/RAJA/VR/ 19-20/W-130 |  | Improvement of Bazar Gate of Nazimkhan Union- Dangghat Kali Mondir via Ratiram Pathanpara GPS Road. road Ch: 0.0m-1580m including Construction of 1Nos 0.625m x 0.625m U-Drain at Ch: 427 m Under Upazila: Rajarhat, District:Kurigram. |  | 0 | 1580 | 1.58 | 1 | 13888297 | 101493 | 13989790 | [20 empty] | Evaluation on going |  | 1.5 | 86.94 | [6 empty] | 0%
88 |  | Kurigram | Rajarhat | Large Market |  |  | Panga | [31 empty] | 62.7 | [6 empty] | 0%
85 |  | Kurigram | Chilmari | Large Market |  |  | Jorgach Hat | [31 empty] | 62.7 | [6 empty] | 0%
83 |  | Kurigram | Chilmari | Large Market |  |  | Thana Hat | [31 empty] | 62.7 | [6 empty] | 0%
84 |  | Kurigram | Chilmari | Large Market |  |  | Fakirar Hat | [31 empty] | 62.7 | [6 empty] | 0%
126 |  | Kurigram | Ulipur | Large Market |  |  | Sunamgonj Hat | [31 empty] | 62.7 | [6 empty] | 0%
|  | Kurigram | Ulipur | Large Market |  |  | Mollar Hat | [31 empty] | 62.7 | [6 empty] | 0%
|  | Kurigram | Rajibpur | Large Market |  |  | Rajibpur GC | [31 empty] | 62.7 | [6 empty] | 0%
110 | 2019-20 | Kurigram | Sadar | Large Market | PRO/KURI/SAD/LM/19-20/W-110 |  | Construction of Jatiner Hat Upazila: Sadar, District: Kurigram (03 nos LCS group) | (LCS-01) Shamoli Rani /Mst.Banecha Begum (LCS-02) Mst. Lubna Begum / Kalpona Begum (LCS-03) Arifa Khatun / Srimoti Sumi Muhonto | [6 empty] | 9805786 |  |  | 9805786 |  |  |  | 2020-06-30 |  | 2021-05-31 |  |  | 0% | 1600000 | 0 | 1600000 | 0 | 0 | 0 | 1600000 | 16.32% | Contact Signed. |  |  | 62.7 | [6 empty] | 0%
|  | Kurigram | Sadar | Large Market |  |  | Panchgachi Hat | [31 empty] | 62.7 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Burirhat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Sharisabari Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Chandamari Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Dangrar Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Chowrahat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Medium Market |  |  | Rajmallirhat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Chilmari | Medium Market |  |  | karai Barisal | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Chilmari | Medium Market |  |  | Kachkol hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Nageswari | Medium Market |  |  | Chilakhana Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Nageswari | Medium Market |  |  | Egaromatha Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Nageswari | Medium Market |  |  | Berubari Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Nageswari | Medium Market |  |  | Schooler Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Nageswari | Medium Market |  |  | Monigonj Bazar | [31 empty] | 41.77 | [6 empty] | 0%
61 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-61 |  | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Gouribala and Bimala Rani | [6 empty] | 2577497 |  |  | 2577497 |  |  |  | 2019-12-17 | 2019-12-29 | 2020-12-28 |  |  | 40% | 800000 | 0 | 800000 | 0 | 0 | 0 | 800000 | 31.04% | Male Toilet : ( Septic Tank & Soak Well) on going . Female : base On Going. |  |  | 41.77 | 377 | 0.26525 | 2424 | 643% | 100% | 40% | 60%
62 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-62 |  | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Sagorika Bala and Anju Begum | [6 empty] | 2579493 |  |  | 2579493 |  |  |  | 2019-12-17 | 2019-12-29 | 2020-12-28 |  |  | 60% | 800000 | 0 | 800000 | 0 | 0 | 0 | 800000 | 31.01% | 1 Nos Multipurpose Shed : Beam On Going. 1 Nos Multipurpose Shed : Column Completed. Internal CC Road On Goning. |  |  |  | 377 | 0.26525 | 2424 | 643% | 100% | 60% | 40%
87 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-87 |  | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Joymala begum and Beuty Begum | [6 empty] | 534466 |  |  | 534466 |  |  |  | 2020-01-12 | 2020-01-19 | 2020-07-18 |  |  | 90% | 200000 | 0 | 200000 | 0 | 0 | 0 | 200000 | 37.42% | Ground Raising : Earth Work On Going. |  |  |  | 188 | 0.53191 | 2398 | 1276% | 100% | 90% | 10%
122 | 2020-21 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/KUR_S/RMP/19-20/ MW-122 | 149525029 | i)Kawnia Ghat-Kaggipara G.P. School | Mst Rashada Bebum / Mst Shanila Begum | 1500 | 4500 | 3 |  | 1311672.96 |  | 1311672.96 | 1311672.96 |  | 1311672.96 |  |  |  | 2020-07-27 | 2020-09-01 | 2022-08-31 |  |  | 8% | [8 empty] | Maintenance work running
123 | 2020-21 | Kurigram | Rajarhat | Maintenance-LCS | PRO/KUR/RAJA/RMP/19-20/ MW-123 | 149775054 149774065 | i)Amtoli Bazar to Sakhoa GPS road. ii)Dino Bazar rail line to Amtail Bazar via Narayam Nember House. | i) Najma Begum / Sumi Begum ii) Anita Rani / Rasida Begum | 0 0 | 1800 1000 | 2.8 |  | 1587940.81 |  | 1587940.81 | 1587940.81 |  | 1587940.81 |  |  |  | 2020-08-09 | 2020-09-01 | 2022-08-31 |  |  | 8% | [8 empty] | Maintenance work running
124 | 2020-21 | Kurigram | Rajibpur | Maintenance-LCS | PRO/KUR/RAJIRMP/19-20/ MW-124 | 149084006 | i) Boraidangi Collage Road. | Mrs. Joynob / Mrs. Lutfa | 0 | 0.825 | 0.825 |  | 713992.18 |  | 713992.18 | 713992.18 |  | 713992.18 |  |  |  | 2020-10-01 | 2020-11-01 | 2022-10-31 |  |  | 5% | [8 empty] | Maintenance work running
|  | Kurigram | Rowmari | Medium Market |  |  | Saydabad Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rowmari | Medium Market |  |  | Lawbari hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rowmari | Medium Market |  |  | Baraikandhi Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Fulbari | Medium Market |  |  | Boroloi Bazar | [31 empty] | 41.77 | [6 empty] | 0%
155 | 2020-21 | Kurigram | Fulbari | Medium Market | PRO/KUR/FUL/MM/20-21/W- 155 |  | Construction of Shiberhat Bazar | [7 empty] | 4605783 | [20 empty] | Estimate approved in December-20 |  |  | 41.77 | [6 empty] | 0%
|  | Kurigram | Fulbari | Medium Market |  |  | Bokultala Bazar | [31 empty] | 41.77 | [6 empty] | 0%
156 | 2020-21 | Kurigram | Fulbari | Medium Market | PRO/KUR/FUL/MM/20-21/W- 156 |  | Construction of Ghogurhat Bazar | [7 empty] | 5652007 | [20 empty] | Estimate approved in December-20 |  |  | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Sardob RDRS Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Rajarhat Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Hazir Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Nayer Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Shimultala Wapda Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Sadar | Medium Market |  |  | Valur Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram |  | Medium Market |  |  | Char Boraibari Hat | [31 empty] | 41.77 | [6 empty] | 0%
153 | 2020-21 | Kurigram | Bhurungamari | Medium Market | PRO/KUR/BUR/MM/20-21/W-153 |  | Construction of Boldia Hat | [7 empty] | 5522607 | [20 empty] | Estimate approved on 22-11-20 |  |  | 41.77 | [6 empty] | 0%
|  | Kurigram | Bhurungamari | Medium Market |  |  | Choudhurir Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Small Market |  |  | Kalirhat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Small Market |  |  | Fulkhar Chakla | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Small Market |  |  | Amtola Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Small Market |  |  | Kalirhat Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Rajarhat | Small Market |  |  | Battalar Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Taleber Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Wapda Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Chander Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Shialkanda Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Daknirpat Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Nageswari | Small Market |  |  | Mina Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram |  | Small Market |  |  | New Annandapur Hat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Kurigram | Sadar | Small Market |  |  | masterer Hat | [31 empty] | 26.11 | [6 empty] | 0%
154 | 2020-21 | Kurigram | Bhurungamari | Small Market | PRO/KUR/BUR/SM/20-21/W-154 |  | Construction of Muktijoddha Hat | [7 empty] | 4051958 | [20 empty] | Estimate approved on 22-11-20 |  |  | 26.11 | [6 empty] | 0%
16 | 2018-19 | Rangpur | Kaunia | Union Road-BC | PRO/RAN/KAU/UNR/18-19/W-16 | 185423012 | Improvement of Bituminous Carpeting Road on Sarai Up office (Zahir) to Eakota Bazar Via Udaynarayon Machari Govt.Primary School at Ch.2375m-3055m. Under Kaunia Upazila, District Rangpur. | M/S. Nila Enterprise, Shalbon, Rangpur | 2375 | 3055 | 0.68 | 0 | 5430014.69 | 0 | 5430014.69 | 5158514.25 | 0 | 5158514.25 | 0 | 0 | 2019-03-19 | 2019-04-09 | 2019-04-16 | 2020-02-15 |  | 2020-03-24 | 50% | 2569188 | 0 | 2569188 | 0 | 0 | 0 | 2569188 | 49.8% | WBM complete | 38 | 1 | 91.841 | 312 | 0.32051 | 2676 | 857.7% | 100% | 50% | 50%
17 | 2018-19 | Rangpur | Gangachara | Union Road-BC | PRO/RAN/GAN/UNR/18-19/W-17 | 185273020 | Improvement of Bituminous Carpeting Road on Kolkando UP (Binbina Ferrighat)-Abuliahat Upto Kaliganj Upazila Border (Tusvander UP) Road at Ch 00-2350m. including Costruction of 3 U- drain at Ch 00-2350m Under Gangachara Upazila, District Rangpur. | M/S. Onto & Tahity (JV), Rangpur | 0 | 2350 | 2.35 | 4.8 | 19971756.68 | 1573720 | 21545476.68 | 18763031.63 | 1476418.6 | 20239450.23 | 0 | 0 | 2019-04-15 | 2019-04-30 | 2019-05-06 | 2020-05-05 | - | 2020-06-03 | 100% | 16366218 | 0 | 16366218 | 922375 | 0 | 922375 | 17288593 | 85.42% | BC Complete | 29 | 4.2 | 385.7322 | 371 | 0.26954 | 2655 | 715.6% | 100% | 100% | 0%
74 | 2019-20 | Rangpur | Kaunia | Union Road-BC | PRO/RAN/KAU/UNR/19-20/W-74 | 185423013 | Improvement of Bituminous carpeting Road on Sarai UP- Bhahishwler More bazar via Naira Pry.School Road at Ch: 1412m-3412m including Construction of 1Nos (0.625x0.625) m U-Drain at Ch: 1775m,2247m, 2537m,2590m & 3155m and 1Nos 3x4.50mx4.00 m RCC Box Culvert at Ch: 2127m and 1Nos 1x2.00mx2.00 m RCC Box Culvert at Ch: 2901m Under Upazila:Kaunia, District: Rangpur | KZ-AHC (JV) Kashimpur, Mithapukur, Rangpur | 1412 | 3412 | 2 | 22.5 | 18739034 | 6076156 | 24815190 | 16586327.95 | 5605135.56 | 22191463.51 |  |  | 2020-03-01 | 2020-03-25 | 2020-04-04 | 2021-04-03 |  | 2021-06-08 | 30% | 1691277 | 0 | 1691277 | 0 | 0 | 0 | 1691277 | 7.621% | WBM running |  | 2 | 183.682 | [6 empty] | 0%
|  | Rangpur | Kaunia | Village Road-BC |  | 185424016 | Haragach pucca road-Joybangla Bazar Rd. | [30 empty] | 0.84 | 72.5938 | [6 empty] | 0%
137 | 2020-21 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/20-21/W-137 | 185424058 | Improvement of Bituminous carpeting on Jummarpar R&H - Mirbag Gramen Bank More Bazar. Road at Ch:00m-1482m including Construction of 2Nos 0.625x0.625 m U-Drain at Ch:315m & 465m Under Kaunia Upazila , District: Rangpur. | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 0 | 1482 | 1.482 | 2 | 13006125 | 271764 | 13277889 | 11157613.26 | 261511.74 | 11419125 |  |  | 2020-10-07 | 2020-11-15 | 2020-11-21 | 2021-10-05 |  |  | 0% | [8 empty] | WO Issued, work will start |  | 2.35 | 203.0898 | [6 empty] | 0%
138 | 2020-21 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/20-21/W-138 | 185424060 | Improvement of Bituminous carpeting Road on Topical GC hat - Branter bazar via Gopidanga GPS. Road at Ch: 00m-2785m including Construction of 3Nos 0.625x0.625 m Drainage Structure at Ch:640m,1383m &1814m and 1Nos 1x1.500x1.50 m RCC Box Culvert at Ch: 551m and 1x2.00x2.00 m RCC Box Culvert at Ch: 128m 2x4.50x4.00 m RCC Box Culvert at Ch: 910m and 3x4.50x4.00 m RCC Box Culvert at Ch: 1607m Under Under Kaunia Upazila , District: Rangpur. | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 0 | 2785 | 2.785 | 32.8 | 23976518 | 9984639 | 33961157 | 18756306 | 9693337 | 28449643 |  |  | 2020-10-25 | 2020-11-15 | 2020-11-21 | 2022-04-04 |  |  | 0% | [8 empty] | WO Issued, work will start |  | 2.5 | 216.053 | [6 empty] | 0%
|  | Rangpur | Gangachara | Village Road-BC |  | 185275115 | Bagerhat to Sankordho Hafazia Madrasha | [30 empty] | 1 | 86.4212 | [6 empty] | 0%
|  | Rangpur | Gangachara | Village Road-BC |  | 185275107 | Balatary Chowpati - Joydeb Dolapara Road | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
|  | Rangpur | Gangachara | Village Road-HBB |  | 185275134 | Betgari Kachua UZR near Patakhowa more - Sudhuir Master's house road | [30 empty] | 1.72 | 99.6912 | [6 empty] | 0%
15 | 2018-19 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/18-19/W-15 | 185424019 | Improvement of Bituminous carpeting Road on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 00-1715m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | Md. Hafizur Rahman Burirhat, Rangpur. | 0 | 1715 | 1.715 | 0.6 | 13105734.48 | 106317 | 13212051.48 | 12748776.42 | 101028.9 | 12849805.32 |  |  | 2019-04-15 | 2019-04-30 | 2019-05-05 | 2020-03-22 | 2019-09-10 | 2020-04-20 | 100% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 99.04% | Final bill paid | 29 | 3 | 259.2636 | 327 | 0.30581 | 2655 | 811.9% | 100% | 100% | 0%
107 | 2019-20 | Rangpur | Kaunia | Medium Market | PRO/RAN/KAU/MM/19-20/W- 107 |  | Construction of Ekoter Hat Upazila:Kaunia, District: Rangpur, Under PROVATi3 Project. | Mst Sahida Khatun and Mst. Merina Begum (LCS-1)/Mst. Dolena and Mst. Sheuli Begum(LCS-2) | [6 empty] | 5032629 |  |  | 5032629 |  |  |  | 2020-07-21 |  | 2021-07-21 |  |  | 0% | [8 empty] | Training Complete |  |  | 41.77 | [6 empty] | 0%
108 | 2019-20 | Rangpur | Gangachara | Maintenance-LCS | PRO/RAN/GAN/RMP/19-20/MW-108 | 185275228 185275241 | (i) Rural road maintenance by LCS (Material & Wages) work on Char Nohali Bridger Bazar- Minar Bazar via Ashrayon Bazar (Bager hat) Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (ii) Rural road maintenance by LCS (Material & Wages) work on Kutub hat(konabari) - Khamer mohona GPS via uttor kishamot Gonesh GPS Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | Mst. Ayouli Begum & Mst. Anufa Begum (LCS-01) Mst. Monzila Begum & Mst. Rabeya Begum(LCS-02) |  |  | 9 |  | 3666856.72 |  | 3666856.72 | 1261167.96 |  | 1261167.96 |  |  |  | 2020-06-01 |  | 2022-05-31 |  |  | 20% | 216000 | 0 | 216000 | 0 | 0 | 0 | 216000 | 17.13% | Work on going ,Pkg#3 package already done from other project.
109 | 2019-20 | Rangpur | Kaunia | Maintenance-LCS | PRO/RAN/KAU/RMP/19-20/MW-109 | 185423013 | Rural road maintenance by LCS (Material & Wages) work on Sarai UP-Bhahishwler more Bazar via Naira Pry. School Sarak at Kaunia Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | Mst. Rabeya Khatun & Mst. Rugina Begum |  |  | 2.275 |  | 1326724.49 |  | 1326724.49 | 1326724.49 |  | 1326724.49 |  |  |  | 2020-06-01 |  | 2022-05-31 |  |  | 21% | 191250 | 0 | 191250 | 0 | 0 | 0 | 191250 | 14.42% | Work on going
|  | Rangpur | Kaunia | Medium Market |  |  | Bhaier Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Rangpur | Kaunia | Medium Market |  |  | Bhutsora(Mirbag)Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Rangpur | Kaunia | Medium Market |  |  | Haqueer hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Rangpur | Gangachara | Medium Market |  |  | Babubazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Rangpur | Gangachara | Medium Market |  |  | Abuliarhat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Rangpur | Gangachara | Small Market |  |  | Bagerhat | [31 empty] | 26.11 | [6 empty] | 0%
|  | Rangpur | Gangachara | Small Market |  |  | Ichli Bazar(SKS Bazar) | [31 empty] | 26.11 | [6 empty] | 0%
3 | 2019-20 | Rangpur | Gangachara | Maintenance-Office | PRO/RANG/MAINT/19-20/MW-3 |  | Repair & maintenance work of LGED office building, Dist: Rangpur | M/S Tahity Enterprise | [6 empty] | 2141640 |  |  | 1547911.47 |  |  | 2020-08-25 | 2020-09-09 | 2020-09-15 | 2021-01-14 |  | 2021-05-07 | 90% |  |  | 1070767 |  |  |  | 1070767 | 69.17%
44 | 2018-19 | Nilphamari | Dimla | Union Road-BC | PRO/NIL/DIM/UNR/18-19/W-44 | 173123002 | Improvement of Bituminous carpeting Road of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164 km Under Dimla Upazila,District Nilphamari including Construction of 1Nos (2.00x2.00)m Cross Drainges Structure .at Ch.2287m and Construction of 2 Nos 7.00m Long.0.625mx0.625m U-Drain on Ch.2785,4011.0m of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164.00km Under Dimla Upazila,District Nilphamari | M/S. Misuk Enterprise, Food Office Road, Nilphamari. | 2255 | 4164 | 1.909 | 3.25 | 16925909.68 | 1073862.5 | 17999772.18 | 16669437.91 | 1057539.337 | 17726977.247 |  |  | 2019-07-27 | 2019-08-07 | 2019-08-13 | 2020-08-12 |  | 2020-08-31 | 90% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 83.65% | BC Completed. Length and Contact amount decresed(length is 1.5 instead on 1.9km). | 19 | 1.5 | 137.7615 | 371 | 0.26954 | 2556 | 688.9% | 100% | 90% | 10%
119 | 2019-20 | Nilphamari | Dimla | Union Road-BC | PRO/NIL/DIM/UNR/19-20/W-119 | 173123014 | Improvement of Bituminous carpeting Road of Naotara U.P Office-Motirbazar Rd. Ch: 950m-3250m including Construction of 1Nos 1x1.50mx 1.50 m U-Drain at Ch. 1159m and 2Nos 1mX0.6250mX 0.60m m U-Drain at Ch. 1389m under Upazila: Dimla, Dist: Nilphamari | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 950 | 3250 | 2.3 | 3 | 19781105 | 936387 | 20717492 | 17782304.61 |  | 17782304.61 |  |  | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 |  |  | 0% | [8 empty] | Work started |  | 2.3 | 211.2343 | [6 empty] | 0%
18 | 2018-19 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/18-19/W-18 | 173124093 | Improvement of Bituminous carpeting Road on Ullarmore to Rahmangonj Bazar Road Under Gayabari Union at Ch.0.00m-2490m. including Construction of 2 Nos (1.50x1.50)m Box Culvert at Ch.142.00m & 630.0m and Construction of 1 Nos (2x3.00x3.00)m Box Culvert at Ch.197.00 m and Costruction of 1 Nos(1.500x1.00)m and Construction of 1 Nos (2x4.50x4.00) m Box Culvert at Ch.1922.00 m. and Costruction of 3 Nos(0.625x0.600) m U-Drain at Ch.50.0,480.0m&852m.Under Dimla Upazila,District Nilphamari. | JV of SA FE Shahipara, Nilphamari. | 0 | 2490 | 2.49 | 24.63 | 18674476.67 | 6963499.25 | 25637975.92 | 18551554.07 | 6917609.79 | 25469163.86 |  |  | 2019-06-24 | 2019-06-30 | 2019-07-06 | 05-07-2020 12-08-2020 |  | 2020-12-31 | 85% | 15993130 | 2955540 | 18948670 | 989931 | 247482 | 1237413 | 20186083 | 79.26% | BC Complete | #VALUE! | 2.47 | 213.4604 | #VALUE! | #VALUE! | 2594 | #VALUE! | #VALUE! | 85% | #VALUE!
19 | 2018-19 | Nilphamari | Jaldhaka | Village Road-BC | PRO/NIL/JAL/VR/18-19/W-19 | 173365087 | Improvement of Bituminous Carpeting Road on Gabroli RNGPS-Tin Babul house via Rath Bazar Road at Ch 1000.0m-2650.0m including Costruction of 2 Nos (1.00x1.00) Box Culvert at Ch 1450.0m&1720.0m and Costruction of 1 Nos(2.00x2.00)m Box Culvert at Ch 2620.0m Under Jaldhaka Upazila,District Lilphamari. | M/S. Mohsena Enterprise, Monshapara, Nilphamari. | 1000 | 2650 | 1.65 | 4.8 | 13626801.7 | 1172872 | 14799673.7 | 12495688.82 | 1075512.29 | 13571201.11 |  |  | 2019-06-24 | 2019-07-09 | 2019-07-15 | 2020-07-14 |  | 2020-12-31 | 60% | 7136510 | 0 | 7136510 | 0 | 0 | 0 | 7136510 | 52.59% | WBM & Structure complete, Work stopped due to shortage of stone chips | 170 | 1.65 | 142.595 | 371 | 0.26954 | 2585 | 696.8% | 100% | 60% | 40%
120 | 2019-20 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/JAL/VR/19-20/W-120 | 173124012 | Improvement of Bituminous Carpeting Road on Dakhin Sonakhuli-Dalia Taltola road Ch: 2150m-3650m including 2Nos 1x1.50mx 1.50 m U-Drain at Ch.Ch: 2388 m & 2630m and 2Nos 1x0.6250mx 0.60m m U-Drain at Ch: 2210 m & 2270m under Upazila: Dimla, Dist: Nilphamari | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 2150 | 3650 | 1.5 | 5 | 13285714 | 1575024 | 14860738 | 15643068 |  | 15643068 |  |  | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 |  |  | 0% | [8 empty] | Work started |  | 1.5 | 129.6318 | [6 empty] | 0%
141 | 2020-21 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/20-21/W-141 | 173125089 | Improvement of Kakina Chapani Madrasha-Tista Main Canal Road. Road Ch: 0.00m-1783.00m including Construction of 3Nos 1.50m x 1.50m RCCBox culvert at Ch: 625.0m,695.0m,1328.0m and 1Nos Single Vent2.00m x 2.00m RCCBox culvert at Ch: 1242.0m and 8Nos 7m longU-Drain 0.6250mm x 0.600m Drainage Culvert at Ch: 273.0m,362.0m, 467.0m, 540.0m, 727.0m,1347.0m,1475.0m, 1614.0m Under Upazila: Dimla, District:Nilphamari |  | 0 | 1783 | 1.783 | 16.5 | 15506594 | 3771630 | 19278224 | [20 empty] | Evaluation on going |  | 2.7 | 233.3372 | [6 empty] | 0%
140 | 2020-21 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/20-21/W-140 | 173124082 | Improvement of Dokhin Sonakhuli -Vajonchur via Khamatpara. Road Ch: 1000.00m-3040.00m including Construction of 4Nos 1.50m x 1.50m RCC Box culvert at Ch: 1153.0m, 1186.0m, 2054.0m, 2480.0m and 1Nos 2vent 3.00m x 2.00m RCC Box culvert at Ch: 1991.00m and 3Nos U-Drain 7m Long 0.625.mm x 0.600mm Drainage Culvert at Ch: 1652.00m,2260.00m, 2290.00m Under Upazila: Dimla, District:Nilphamari |  | 1000 | 3040 | 2.04 | 17.5 | 18745610 | 4438998 | 23184608 | [20 empty] | Evaluation on going |  | 2 | 172.8424 | [6 empty] | 0%
125 | 2019-20 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/19-20/W-125 | 173124083 | Improvement of Sonakhuli high School -Vendabari Road Ch: 00m-2155 m including 1Nos 1x3.00mx2.00m RCC. Box Culvert at Ch: 607m and 2Nos 1x1.50mx1.50m. RCC.Box Culvert at Ch: 720 m & 1167m and 1Nos 2x3.00mx2.00m RCC. Box Culvert at Ch: 206m Under Upazila: Dimla, District:Nilphamari. | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 0 | 2155 | 2.155 | 16 | 19440508 | 3953515 | 23394023 | 20069154.42 |  | 20069154.42 |  |  | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 |  |  | 0% | [8 empty] | Work started |  | 2.5 | 216.053 | [6 empty] | 0%
121 | 2019-20 | Nilphamari | Dimla | Village Road-HBB | PRO/NIL/DIM/VR/19-20/W-121 | 173125117 | Improvement of HBB Road on Sovangong Bazar- Astaf Ali House via Azgar rice mill road, under Balapara union Ch: 330m-1385 m Under Upazila: Dimla, District:Nilphamari. | Rainbow Enterprise, Khaga Kharibarim Dimla, Nilphamari | 330 | 1385 | 1.055 |  | 5468148 |  | 5468148 | 4548906.83 |  | 4548906.83 |  |  | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-05-24 |  |  | 0% | [8 empty] | Work started |  | 1 | 57.96 | [6 empty] | 0%
128 | 2020-21 | Nilphamari | Dimla | Maintenance-LCS | PRO/NIL/DIM/RMP/20-21/ MW-128 | 173123014 173124012 173125089 173124082 173124083 | i)Naotara U.P. Office-Motirbazar RD at ch. 3200-6400 m. ii)DakhinSonakhuli-DaliaTaltola at ch. 1500-3750 m. iii)Kakina Chapani Madrasha-Tista Main Canal at ch. 2700-3500 m. iv)Dkhin Sonakhuli-Vajonchur via Khamatpara at ch. 2000-4500 m. v)Sonakhuli High School- Vendabari at ch. 2500-3800 m. | LCS 1)Mst. Alena Akter & Srimati Golapi bala LCS 2)Mst. Hafezakhatun & Fozila Begum LCS 3) Mst Mamima Akter & Mst. Fozila Khatun LCS 4) Mst Lucky Begum & Homayra Begum LCS 5) Arzina Khatun & Nasima Begum | 3200 1500 2700 2000 2500 | 6400 3750 3500 4500 3800 | 10.05 |  | 5070735.37 |  | 5070735.37 | 5070735.37 |  | 5070735.37 |  |  |  | 2020-10-29 | 2020-11-01 | 2022-10-31 |  |  | 3% | 165000 |  | 165000 |  |  | 0 | 165000 | 3.254% | Work ongoing
129 | 2020-21 | Nilphamari | Jaldhaka | Maintenance-LCS | PRO/NIL/JAL/RMP/20-21/ MW-129 | 173365064 173365066 | i)WDB Bundh to WDB Bundh via Moratista Syphon at ch. 00-1215 m. ii)Moratista Syphon to WDB Bundh ch. 00-1506 m. |  | 0.00 0.00 | 1215 1506 | 2.721 |  | 1586360.82 |  | 1586360.82 | [20 empty] | LCS Group formation under process, Estimate approved on 16-7-20
|  | Nilphamari | Dimla | Large Market |  |  | Tunirhat | [31 empty] | 62.7 | [6 empty] | 0%
|  | Nilphamari | Dimla | Large Market |  |  | Babur hat | [31 empty] | 62.7 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Large Market |  |  | Bhabonchur Bazar | [31 empty] | 62.7 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Goulmunda Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Balagrm Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | kharkati Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | kaligonj Bangha bandhu Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | pathanpara hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Diabari Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Dakligonj hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Shibur hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Nilphamari | Jaldhaka | Small Market |  |  | Kathali Nayer hat | [31 empty] | 26.11 | [6 empty] | 0%
2 | 2018-19 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/18-19/W-02 | 152703010 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Koborstan to Sarkarhat Jongra UP Road at Ch. 00-2185m. Under Patgram Upazila, District Lalmonirhat. | M/S fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2185 | 2.19 | 0 | 16143845 | 0 | 16143845 | 13964438.783 | 0 | 13964438.783 |  |  | 28-03-19 | 11-04-19 | 2019-04-18 | 2020-03-17 |  | 02-04-2020 16-01-2021 | 100% | 11936905 |  | 11936905 | 1891364 |  | 1891364 | 13828269 | 99.02% | ফাইনাল বিল দেওয়া হয়েছে। | #VALUE! | 2 | 183.682 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 100% | #VALUE!
78 | 2019-20 | Lalmonirhat | Hatibandha | Union Road-BC | PRO/LAL/HATI/UNR/19-20/W-78 | 152333016 | Improvement of Bituminous carpeting Road Sadhur Bazar-Guddimari Road at Ch: 1500m-3700m including Construction of 4Nos 1x 0.90mX0.900 m RCC Box Culvert at Ch: 2475m,2600m,3200m & 3640.00m and 1Nos 1x 2.0mX1.50 m RCC Box Culvert at Ch: 3030m Under Hatibandha Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 1500 | 3700 | 2.2 | 5.2 | 21913908 | 1485646 | 23399554 | 17945425.306 | 1330683.679 | 19276108.985 |  |  | 18-03-20 | 2020-04-15 | 2020-04-22 | 2021-04-21 |  | 2021-07-22 | 40% | 6487500 |  | 6487500 | 1012500 |  | 1012500 | 7500000 | 38.91% | স্ট্রাকচারের কাজ চলছে। |  | 3 | 275.523 | [6 empty] | 0%
143 | 2020-21 | Lalmonirhat | Hatibandha | Union Road-BC | PRO/LAL/HATI/UNR/20-21/W-143 | 152333018 | Improvement of Patikapara UP office – Dawabari UP Road. Ch: 1000.0m-3000.0m including Construction of 3 Nos 7.00x 0.900m x 0.900m Cross-Drain Ch: 1004.0m,1219.0m,1950.0m Under Upazila: Hatibandha, District:Lalmonirhat |  | 1000 | 3000 | 2 | 4.05 | 17616923 | 609186 | 18226109 | [20 empty] | Tender under process |  | 2 | 183.682 | [6 empty] | 0%
57 | 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-57 | 152703020 | Improvement of Bituminous carpeting Road Jongra UP office (Futir Doba) to Sofinagadhat Road at Ch 00m-1000m. Under Patgram Upazila, District Lalmonirhat. | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 0 | 1000 | 1 | 0 | 8219318 | 0 | 8219318 | 7397386.2 |  | 7397386.2 |  |  | 2020-01-21 | 2020-02-18 | 2020-02-25 | 2021-02-24 |  | 2020-08-03 | 100% | 5699030 |  | 5699030 | 859292 |  | 859292 | 6558322 | 88.66% | ফাইনাল বিল হেড অফিসে দাখিল করা হয়েছে। |  | 1 | 91.841 | 372 | 0.26882 | 2361 | 634.7% | 100% | 100% | 0%
55 | 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-55 | 152703019 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Kabarstanhat to Lalitarhat Kuchlibari UP Road at Ch: 1435m-3435m including Construction of 4Nos (1x2.00x1.50)m RCC.Box Culvert and 1 No (2x4.50x2.50)m RCC.Box Culvert Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 1435 | 3435 | 2 | 20.5 | 15769651 | 5125861 | 20895512 | 14180790.473 | 4625170.346 | 18805960.819 |  |  | 2020-02-12 | 2020-02-18 | 2020-02-25 | 2021-02-24 |  | 2021-08-15 | 65% | 7813406 |  | 7823406 | 1250657 |  | 1250657 | 9074063 | 48.25% | WvweøDweGg Gi KvR Pigvb¦ |  | 2 | 183.682 | 372 | 0.26882 | 2361 | 634.7% | 100% | 65% | 35%
56 | 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-56 | 152703007 | Improvement of Bituminous carpeting Road on Kamerarhat Sreerampur UP via Dr.Hamidur Islam House Road at Ch: 900m-1995m Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 900 | 1995 | 1.095 | 0 | 9842242 | 0 | 9842242 | 8858017.8 |  | 8858017.8 |  |  | 2020-01-21 | 2020-02-28 | 2020-02-25 | 2021-02-24 |  | 2020-03-08 | 98% | 6795161 |  | 6795161 | 1071996 | 0 | 1071996 | 7867157 | 88.81% | কার্পেটিং শেষ। টার্পিং এর কাজ চলমান। |  | 1 | 91.841 | 362 | 0.27624 | 2351 | 649.4% | 100% | 98% | 2%
127 | 2019-20 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/19-20/W-127 | 152334090 | Improvement of Singimari Nebru House-Uttor Baraipara Masque Rd. Road Ch: 1150m -3260m including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch: 2122 m & 2952m Under Upazila: Hatibandha, District:Lalmonirhat. | Ali Ahamed & M/S Hossain trading & Construction, Patgram, Lalmonirhat | 1150 | 3260 | 2.11 | 2.7 | 18321870 | 447885 | 18769755 | 13933282.483 | 316686.366 | 14249968.849 |  |  | 2020-06-09 | 2020-09-15 | 2020-09-21 | 2021-09-20 |  | 2021-12-15 | 60% | 6401000 |  | 6401000 | 999000 |  | 999000 | 7400000 | 51.93% | Box cutting running |  | 2 | 172.8424 | 370 | 0.27027 | 2151 | 581.4% | 100% | 60% | 40%
| 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20-21/W-148 | 152335023 | Improvement of Singimari UP-Goddimari UP Border Road Ch: 00m -3000m including Construction of 2Nos 1.50m x 1.50m RCC Box Culvert at Ch:530m & 1300m and 1 Nos 0.900m x 0.900m Cross-Drain at Ch: 2660.00m and 1Nos 3.00m x 3.00m RCC Box Culvert at Ch:90.00m Under Upazila: Hatibandha, District: Lalmonirhat. |  | 0 | 3000 | 3 | 9.3 | 23832969 | 2358372 | 26191341 | [20 empty] | Tender under proess |  | 3 | 259.2636 | [6 empty] | 0%
142 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20-21/W-142 | 152335059 | Improvement of Hatibandha U.Z.R. at dhubni mauza to dhubni Madrasha Road Ch: 00m -1960m including Construction of 2Nos 0.900m x 0.900m Cross-Drain and 2Nos 1.50m x 1.50m Cross-Drain Under Upazila: Hatibandha, District: Lalmonirhat. |  | 0 | 1960 | 1.96 | 5.4 | 16810451 | 1515158 | 18325609 | 14210000.133 |  | 14210000.133 |  |  | 2020-11-19 | [14 empty] | NOA Issued on 19-11-20 |  | 2 | 172.8424 | [6 empty] | 0%
77 | 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-77 | 152704084 | Improvement of Bituminous carpeting Road on Kasirdanga-Bazar to 3 no Vothatkhata GPS Road at Ch: 00m-2000m including Construction of 6Nos 1x1.50x1.00 m RCC Box Culvert at Ch: 830m, 870m,1120m, 1200m,1566m &1800m and 3Nos 1x3.00x2.00 m RCC Box Culvert under Patgram Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 0 | 2000 | 2 | 15.5 | 20081664 | 3573248 | 23654912 | 16294425.218 | 3225783.064 | 19520208.282 |  |  | 18-03-20 | 15-04-2020 | 22-04-2020 | 21-04-2021 |  | 24-03-2021 | 45% | 4022306 |  | 4022306 | 661701 |  | 661701 | 4684007 | 24% | Sub-base and culvert complete |  | 2 | 172.8424 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705132 | MD. Obrotulla House More - Lolitarhat High School. | [30 empty] | 1 | 86.4212 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705013 | Nabinagar BOP-Shofinogre Hat | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
76 | 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-76 | 152705059 | Improvement of Bituminous carpeting Road on Nayerhat Mosque to Zero point of Dhagram UP Road at Ch: 1000m-4000m including construction of 1Nos 1x2.00x2.50 m RCC Box Culvert at Ch: 1310m Under Patgram Upazila ,District Lalmonirhat | Md. Abdul Hossain, Ghoramara Rangpur. | 1000 | 4000 | 3 | 2.5 | 24550502 | 648343 | 25198845 | 20536941.214 | 604889.741 | 21141830.955 |  |  | 18-03-20 | 30-04-20 | 2020-07-05 | 2021-06-02 |  | 29-04-21 | 92% | 10627823 |  | 10627823 | 1741579 |  | 1741579 | 12369402 | 58.51% | কার্পেটিং শেষ। |  | 3 | 259.2636 | [6 empty] | 0%
75 | 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-75 | 152705121 | Improvement of Bituminous carpeting Road on Lolitarhat – Liakot Prodhan House Via Kolshirmuk BOP & Graipul Road at Ch: 4000m-4950m Under Patgram Upazila ,District Lalmonirhat | GRP & RT (ZV), GL Roy Road, Rangpur. | 4000 | 4950 | 0.95 |  | 8246152 |  | 8246152 | 6982029.537 |  | 6982029.537 |  |  | 18-03-20 | 15-04-20 | 22-04-20 | 21-04-21 |  | 24-12-20 | 95% | 5722330 |  | 5722330 | 840533 |  | 840533 | 6562863 | 94% | কার্পেটিং শেষ। টার্পিং এর কাজ চলমান। |  | 2 | 172.8424 | [6 empty] | 0%
139 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-HBB | PRO/LAL/HATI/VR-HBB/20-21/W-139 | 152334018 | Improvement of Karbalardighi R&H Road-Dakhalibandha Hat Road. Road Ch: 0.00m-2550.00m including Construction of 2Nos 2.00m x 1.50m Box culvert on Karbalardighi R&H Road-Dakhalibandha Hat Road. C/D st Ch: 1072 m & 2500m. Under Upazila: Hatibandha, District:Lalmonirhat. |  | 0 | 2550 | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 |  | 11684286.298 |  |  | 2020-11-19 | [14 empty] | NOA Issued in 19-11-20 |  | 2.64 | 153.0144 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Village Road-HBB |  | 152704017 | Tangtindanga hat-H/O Khairul Islam | [30 empty] | 3.2 | 185.472 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Large Market |  |  | Nayer Hat | [31 empty] | 62.7 | [6 empty] | 0%
134 | 2020-21 | Lalmonirhat | Hatibandha | Large Market | PRO/LAL/HAT/LM/20-21/W-134 |  | Construction of Muktijoddha Bazar (LCS-1,2,3) | [7 empty] | 6206548 | [20 empty] | LCS Group formation completed,training will be arranged on 7-12-20 |  |  | 62.7 | [6 empty] | 0%
132 | 2020-21 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/20-21/W-132 |  | Construction of Sharkarar Hat (LCS-1,2,3) | LCS 1: Joyonty & Mst Rohima LCS 2: Ratna Rani & Mollika ray LCS 3: Taposhi Rani ray & Shaymoli | [6 empty] | 8399491 |  |  | 8399491 |  |  |  | 2020-10-14 |  | 2021-10-13 |  |  | 0% | [8 empty] | Contract signed |  |  | 41.77 | [6 empty] | 0%
67 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-67 |  | Construction of Shafinagar Hat, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Luna Parvin . SPC Name- Mst.Provati Rani. LCS Member Nos- 10. | [6 empty] | 1025309 |  |  | 1025309 |  |  |  | 2020-08-23 |  | 2020-11-22 |  |  | 95% | 377500 |  | 377500 |  |  | 0 | 377500 | 36.82% | Electrical work on going |  |  | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Medium Market |  |  | Burimari Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Medium Market |  |  | Kadhidanggahat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Patgram | Medium Market |  |  | Loliterhat | [31 empty] | 41.77 | [6 empty] | 0%
63 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-63 |  | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Lipi Begum . SPC Name- Mst.Merina Begum. LCS Member Nos- 15. | [6 empty] | 1760898 |  |  | 1760898 |  |  |  | 2020-09-15 |  | 2021-03-14 |  |  | 10% | 679500 |  | 679500 |  |  | 0 | 679500 | 38.59% | Work ongoing |  |  | 41.77 | [6 empty] | 0%
64 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-64 |  | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Nurzahan Begum . SPC Name- Mst.Laki Begum. LCS Member Nos- 10. | [6 empty] | 1494432 |  |  | 1494432 |  |  |  | 2020-09-15 |  | 2021-03-14 |  |  | 10% | 604000 |  | 604000 |  |  | 0 | 604000 | 40.42% | Work ongoing | [9 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shaniajan New bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shaniajan bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Cheatnai Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shadur Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Ghunti Bazar | [31 empty] | 41.77 | [6 empty] | 0%
| 2020-21 | Lalmonirhat | Hatibandha | Medium Market | PRO/LAL/PAT/MM/2020-21/W-149 |  | Construction of Dighirhat Bazar | [7 empty] | 5761607 | [20 empty] | LCS group formed, training will be arranged |  |  | 41.77 | [6 empty] | 0%
133 | 2020-21 | Lalmonirhat | Hatibandha | Medium Market | PRO/LAL/HAT/MM/20-21/W-133 |  | Construction of Nawdabash Hat (LCS-1,2,3) | [7 empty] | 6855792 | [20 empty] | LCS group formed, Stakeholder training arranged on 26-11-20 |  |  | 41.77 | [6 empty] | 0%
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Jawranihat Bazar | [31 empty] | 41.77 | [6 empty] | 0%
131 | 2020-21 | Lalmonirhat | Patgram | Maintenance-LCS | PRO/LAL/PAT/RMP/20-21/ MW-131 | 152703020 152705151 152705098 | i) Jongra UP office (Futir Doba) to Shafinagar hat road. Ii) Aftab More to Shofinogorhat via Hosnabad Community Clinic & Mokbul Jahanara Hossain GPS road. iii) Olerpar to Dahagram Chairman bari road. |  | 0 - 0 | 1000 - 1500 | 3.17 |  | 2012485.14 |  | 2012485.14 | 2012485.14 |  | 2012485.14 |  |  |  | 2020-10-27 |  | 2022-10-26 |  |  | 5% | [8 empty] | Work ongoing
3 | 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/18-19/W-03 | 152705151 | Improvement of Bituminous Carpeting Road on Altab More to Safinagarhat via Hasnabad Community Clinik & Mokbul Jahanara Hossin GPS at Ch. 700-1700m. Under Patgram Upazila, District Lalmonirhat. | M/S RML Enterprise, Hatibandha, Lalmonirhat. | 700 | 1700 | 1 | 0 | 6975415 | 0 | 6975415 | 6626644.25 | 0 | 6626644.25 |  |  | 2019-02-24 | 2019-03-18 | 2019-03-25 | 2020-03-24 |  | 2020-09-03 | 100% | 0 |  | 0 | 6625297 |  | 6625297 | 6625297 | 99.98% | ফাইনাল বিল হয়েছে। জামানত প্রদান করা হয়েছে। | 163 | 1 | 86.4212 | 372 | 0.26882 | 2698 | 725.3% | 100% | 100% | 0%
4 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR//18-19/W-04 | 152335060 | Improvement of Niz Sheck Sundor Jameh Mosque - Applax Embankment road. Ch. 500m-1765m. including Construction of 7.00x0.900mx 0.900m Cross drain at Ch. 995m under Hatibandha Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 500 | 1765 | 1.265 | 0.9 | 9940910 | 179692 | 10120602 | 8683000.48 | 156906.643 | 8839907.122 |  |  | 2019-03-28 | 2019-04-11 | 2019-04-18 | 2020-03-17 |  | 2020-04-09 | 100% | 0 | 0 | 0 | 8682822.84 | 156906.64 | 8839729.48 | 8839729.48 | 100% | ‡cf‡g›U Gi mKj †jqv‡ii KvR mgvß n‡q‡Q¦ BD‡Wªb Gi KvR mgvß n‡q‡Q¦‡cÖv‡Uw±f IqvK© Gi KvR †kl n‡q‡Q, Nvm jvMv‡bv nqwb¦ mg¯Í wej wRIwe n‡Z cÖ`vb Kiv i‡q‡Q¦ | 23 | 2 | 172.8424 | 341 | 0.29326 | 2674 | 784.2% | 100% | 100% | 0%
144 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20/21/W-144 | 152335060 | Improvement of Niz Sheck Sundor Jameh Mosque - Applax Embankment road. Ch. 1765.0m-2365.0m. including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch. 1886.0m & 2115.0m and 1Nos 1x 2.00m x 1.50m Box Culvert at Ch: 1979.0m under Hatibandha Upazila, District Lalmonirhat. |  | 1765 | 2365 | 0.6 | 5.2 | 4887744 | 1065231 | 5952975 | [20 empty] | Tender under process
5 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-05 | 152334015 | Improvement of Bituminous Carpeting Road on WAPDA Pucea road to Dimla Bordar road at Ch.0.00m-3000.0m. including Construction of 2.00x 2.00 Cross drain at Ch. 2415.00m and Construction of 2 Nos 7x0.900mx0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | M/S Islam Traders, Ghop Jossor, Lalmonirhat. | 0 | 3000 | 3 | 4.2 | 26653905.62 | 966016.9 | 27619922.52 | 23524180.35 | 880651.833 | 24404832.183 |  |  | 2019-03-28 | 2019-04-10 | 2019-04-17 | 2020-09-01 |  | 2020-10-01 | 100% | 20558148 |  | 20558148 | 3594965 |  | 3594965 | 24153113 | 98.97% | ফাইনাল বিল দেওয়া হয়েছে। | 30 | 3 | 259.2636 | 510 | 0.19608 | 2675 | 524.5% | 100% | 100% | 0%
33 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/ HATI/VR/18-19/W-33 | 152335034 | Improvement of Bituminous carpeting Road on Patikapara Dowabari Up Boder To Kapil Member house Road at Ch. 00-1000m. including Construction of 2.00 Nos 0.900m x 0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | Borsha Enterprise, Patgram, Lalmonirhat | 0 | 1000 | 1 | 1.8 | 7409383.06 | 359383.98 | 7768767.04 | 7020944.669 | 359383.981 | 7380328.65 |  |  | 2019-04-16 | 2019-04-30 | 2019-06-10 | 2020-06-09 |  | 2020-07-28 | 100% | 5735704.6 | 359366.44 | 6095071.04 | 1036149 | 0 | 1036149 | 7131220.04 | 96.62% | gvwU I Uvwc©s Gi KvR Pj‡Q¦ | 49 | 1 | 86.4212 | 406 | 0.24631 | 2655 | 653.9% | 100% | 100% | 0%
34 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-34 | 152334068 | Improvement of Bituminous carpeting Road on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. including Construction of 2.00 Nos (2.50x2.50) m Cross Drainges Structure and Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch. 0.00-2000.00m. | Anta & SH ZV, Patgram, Lalmonirhat | 0 | 2000 | 2 | 8 | 14532903 | 3136442 | 17669345 | 12863063.52 | 2771524.493 | 15634588.013 |  |  | 2019-05-29 | 2019-06-09 | 2019-06-10 | 2019-11-09 |  | 2019-12-05 | 100% | 12100676 | 0 | 12100676 | 1937636 | 0 | 1937636 | 14038312 | 89.79% | ফাইনাল বিল পেশ করেছেন | 26 | 2 | 172.8424 | 153 | 0.65359 | 2615 | 1709% | 100% | 100% | 0%
35 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-35 | 152334088 | Improvement of Bituminous carpeting Road R&H Nowabab Uddin House-Laxmi Kanto Chokider House at Ch.0.00m-1000.00m. including Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch.661.00m. Under Hatibanhda Upazila, District Lalmonirhat. | Nakshi Mobail Palace, Sadar, Kurigram | 0 | 1000 | 1 | 3 | 7141226.17 | 1123449 | 8264675.17 | 6784164.9 | 1067276.417 | 7851441.317 |  |  | 2019-04-16 | 2019-05-14 | 2019-05-21 | 2020-03-01 |  | 2020-04-27 | 100% | 5437695.58 | 1067276.42 | 6504972 | 918412 | 0 | 918412 | 7423384 | 94.55% | ফাইনাল বিল পেশ করেছেন এবং ব্যংক গারান্টি বৃ্ধি করেছেন 27/07/2020 ইং পর্যন্ত। | 57 | 1 | 86.4212 | 292 | 0.34247 | 2641 | 904.5% | 100% | 100% | 0%
36 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-36 | 152335033 | Improvement of Bituminous carpeting Road Paschim Bisondai Mouza To Sattar Chairman House Road Ch 0.00m-2000.00m including Construction of 4.00 Nos 7.00x0.900x0.900 Cross drain At Ch.113m, 417m, 1280m, &2560m Under Hatibandha Upazila, District Lalmonirhat. | M/S Alahi Box, Kaligonj, Lalmonirhat | 0 | 2000 | 2 | 3.6 | 14144485 | 858869.5 | 15003354.5 | 12406869.348 | 645062.75 | 13051932.098 |  |  | 2019-06-17 | 19-06-19 | 2019-06-26 | 2020-05-25 |  | 2020-06-02 | 100% | 11109467 | 0 | 11109467 | 1782955 | 0 | 1782955 | 12892422 | 98.78% | ফাইনাল বিল দেওয়া হয়েছে। | 8 | 2 | 172.8424 | 1900-12-06 | 0.29326 | 1907-02-17 | 763.9% | 100% | 100% | 0%
45 | 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-45 | 152335061 | Improvement of Bituminous carpeting Road on Applax Badth to Dimla Border Road at Ch 0.00m-1800.0m including Construction of 3.00 Nos 0.900 X 0.900 Cross drain at Ch. 400.00m, 700.00m & 1000.00m on Applax Badth to Dimla Border Road. Under Hatibanhda Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 0 | 1800 | 1.8 | 2.7 | 12752649 | 555765.89 | 13308414.89 | 11139339.451 | 435687.765 | 11575027.216 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 2020-06-16 |  | 2020-07-15 | 100% | 8908214 |  | 8908214 | 1460261 |  | 1460261 | 10368475 | 89.58% | ফাইনাল বিল প্রেরন করেছেন। | 29 | 1.8 | 155.5582 | 328 | 0.30488 | 2570 | 783.5% | 100% | 100% | 0%
46 | 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-46 | 152704023 | Improvement of Bituminous carpeting Road on Sarkarerhat Mosque to Borovita at Ch 0.00m-2500.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 0 | 2500 | 2.5 |  | 18846970 |  | 18846970 | 16388604.17 |  | 16388604.17 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) |  | 2020-07-16 | 75% | 0 |  | 0 | 10715326 |  | 10715326 | 10715326 | 65.38% | WBM complete | #VALUE! | 2.5 | 216.053 | #VALUE! | #VALUE! | 2570 | #VALUE! | #VALUE! | 75% | #VALUE!
47 | 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-47 | 152704034 | Improvement of Bituminous carpeting Road Dhobolsuti Mosque to Kamararhat Road at Ch 0.500m-3050.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 500 | 3050 | 2.55 |  | 18895406 |  | 18895406 | 16408287.34 |  | 16408287.34 |  |  | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) |  | 2020-07-16 | 75% | 0 | 0 | 0 | 9393335.62 |  | 9393335.62 | 9393335.62 | 57.25% | WvweøDweGg Gi KvR Pigvb¦ | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 2570 | #VALUE! | #VALUE! | 75% | #VALUE!
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153005 | Chikajani Up- Charmaguri hat road | [30 empty] | 2 | 183.682 | [6 empty] | 0%
99 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-99 | 339153005 | Rural road maintenance by LCS (Material & Wages) work on Chikajani UP Office to Chirmashuri Hat Sarak at Ch. 0.00-7500.00m Dewangonj Upazila, Jamalpur District (15 nos LCS worker) | Chairperson- Anowara Khatun, Secretary- Most. Azma Khatun , LCS Group-02 | 0 | 7500 | 7.5 |  | 3466985 |  | 3466985 | 3466985 |  | 3466985 |  |  |  | 2020-09-01 |  | 2022-08-31 |  |  | 9% | 228750 |  | 228750 |  |  | 0 | 228750 | 6.598% | Maintenance work ongoing
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153016 | Kharma Naya Bazar RHD-TilokpurMollapara | [30 empty] | 2 | 183.682 | [6 empty] | 0%
100 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-100 | 339153016 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD-Tilokpur Mollapara Sarak at Ch. 0.00-2190.00m Dewangonj Upazila, Jamalpur district (4 nos LCS worker) | Chairperson- Salma, Secretary- Safely Begum, LCS Group-03 | 0 | 2190 | 2.19 |  | 844565 |  | 844565 | 844565 |  | 844565 |  |  |  | 2020-09-01 |  | 2022-08-31 |  |  | 9% | 45750 |  | 45750 |  |  | 0 | 45750 | 5.417% | Maintenance work ongoing
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153011 | Dangdhara UP-Bottola Bazar. | [30 empty] | 2 | 183.682 | [6 empty] | 0%
|  | Jamalpur | Melandah | Union Road-BC |  | 339613007 | Ghoserpara UP (Beltoi Bazar)-Charshaguna Bazar Road. | [30 empty] | 3.45 | 316.8514 | [6 empty] | 0%
161 | 2020-21 | Jamalpur | Bakshigonj | Union Road-BC | PRO/JAM/BAK/UNR/20-21/W-161 | 339073012 | Improvement of Bituminous carpeting on Merurchar UP Office- Jabbergonj GC via Chinarchar Gudharaghat Road at Ch.2900-4050m. Including 2Nos 2x4.0mx4.5m Cross-Drain Under bakshiganj Upazila, District Jamalpur. |  | 2900 | 4050 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | [20 empty] | Estimate approved on Dec-20 |  | 1.7 | 156.1297 | [6 empty] | 0%
29 | 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-29 | 339075094 | Improvement of Bituminous carpeting Road on Airmari-Kamalerbarti Road at Ch.00.0-2850.0m including Contruction Of 1 Nos.(3.50x2.50) Cross Drainges Structure at Ch.1290.0m and Contruction Of 2 Nos.U-Drain at Ch.140m,1915m Under Bakshiganj Upazila, District Jamalpur. | M/S. Lokman Hossain, 987, Choybaria, Gokornoghat, Brahmanbaria | 0 | 2850 | 2.85 | 5.3 | 26012268 | 1488161 | 27500429 | 25428918.47 | 1405081.53 | 26834000 | 901520 | 27735520 | 2019-05-15 | 2019-05-27 | 2019-06-02 | 01-06-2020 15-02-2021 |  | 2020-08-20 | 40% | 5048909 | 0 | 5048909 | 366372 | 0 | 366372 | 5415281 | 19.52% | Protective work on going. 500m WBM Running , AS and Structure work running | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 2628 | #VALUE! | #VALUE! | 40% | #VALUE!
30 | 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-30 | 339075012 | Improvement of Bituminous carpeting Road on Gazirpara-Derur Bill Road at Ch.00.0-2000.0m Under Bakshiganj Upazila, District Jamalpur. including Contruction Of 1 Nos. U-Drain on Gazirpara-Derur Bill Road at Ch.1640.0m Under Bakshiganj Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2000 | 2 | 0.6 | 17514896.19 | 106751 | 17621647.19 | 15704206.21 | 95866.95 | 15800073.16 | 2293635.84 | 18093709 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 |  | 2024-06-26 | 100% | 14989602 |  | 14989602 | 1493260 |  | 1493260 | 16482862 | 91.1% | Final bill paid | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 2597 | #VALUE! | #VALUE! | 100% | #VALUE!
31 | 2018-19 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ ISL/VR/18-19/W-31 | 339294014 | Improvement of Bituminous carpeting Road on Bulakipara-Goalaerchar Road at Ch.00.0-2800.0m Under Islampur Upazila, District Jamalpur. including Contruction Of 5 Nos.0.600x0.625 U-Drain on Bulakipara-Goalaerchar Road at 552m, 570m, 790m, 865m & 1350m Under Islampur Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2800 | 2.8 | 3 | 21880314 | 487259 | 22367573 | 20176056.34 | 449424.22 | 20625480.56 | 1793382.44 | 22418863 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 |  | 2021-07-30 | 75% | 12771102 | 0 | 12771102 | 1033002 | 0 | 1033002 | 13804104 | 61.57% | WBM done (2350M) U-Drain work is Pending | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 2597 | #VALUE! | #VALUE! | 75% | #VALUE!
32 | 2018-19 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/18-19/W-32 | 339615037 | Improvement of Bituminous carpeting Road on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.00.0-1560m including Contuction Of 1 Nos.( 2x3.50x3.00m ) Cross Drainges Structure at Ch.887.0m and Contuction Of 1 Nos. (2x4.5x4.00m) Cross Drainges Structure at Ch.1219.0m and Contruction Of 6 Nos.0.750x0.750 RCC U-Drain on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.279m,705m,1082m,1139m,1281m,1377m Under Melandah Upazila, District Jamalpur. | M/S. Masum Constrution Chapatali, Sherpur Town, Sherpur. | 0 | 1560 | 1.56 | 22.6 | 16109475 | 6116386 | 22225861 | 14960841.55 | 3274302.46 | 18235144.01 | 1311883 | 19547027.01 | 2019-06-16 | 2019-06-30 | 2019-07-06 | 27-05-2020 31-11-2020 |  | 25-06-2020 27-12-2020 | 50% | 5581363 | 0 | 5581363 | 1081164 | 0 | 1081164 | 6662527 | 34.08% | AS rectification Complete, 4 nos U-drain Completed But Cross Drain is under preparation | #VALUE! | 1.53 | 132.2244 | #VALUE! | #VALUE! | 2594 | #VALUE! | #VALUE! | 50% | #VALUE!
37 | 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W-37 | 339154040 | Improvement of Bituminous carpeting Road on Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. including Construction Of 1 Nos.0.600mx0.625m U-Drain on Ch.1236.0m Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 930 | 2880 | 1.95 | 0.6 | 17332023 | 139931 | 17471954 | 14553724.76 | 117499.838 | 14671224.598 | -238869.598 | 14432355 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 31-12-2020 |  | 11-06-2020 31-12-2021 | 100% | 10262674 | 0 | 10262674 | 1151557 | 0 | 1151557 | 11414231 | 79.09% | BC completed.Length and Contact amount decresed(length is 1.5 instead on 1.9km). | #VALUE! | 2 | 172.8424 | #VALUE! | #VALUE! | 2612 | #VALUE! | #VALUE! | 100% | #VALUE!
38 | 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W- 38 | 339154029 | Improvement of Bituminous carpeting Road on Bhatkhawa RHD-Amkhowa Bazar Road at Ch.0.00-3250.0m including Construction Of 1 Nos. 3.00x3.00 Cross Drainges Structure Bhatkhawa RHD-Amkhowa Bazar Road at Ch.512.0m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3250 | 3.25 | 3 | 29145742 | 1305867 | 30451609 | 24564023.395 | 1130084.458 | 25694107.853 | 531265.15 | 26225373.003 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 05-05-2021 |  | 11-06-2020 31-12-2021 | 60% | 13890477 | 0 | 13890477 | 0 | 0 | 0 | 13890477 | 52.97% | WBM Complete | #VALUE! | 3 | 259.2636 | #VALUE! | #VALUE! | 2612 | #VALUE! | #VALUE! | 60% | #VALUE!
86 | 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W- 86 | 339154027 | Improvement of BC Road from Khorma naya Bazar via Vatipara Road from ch. 1300-2120.0m including 2Nos U-Drain (600X600mm) under Upazila Dewangonj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 1300 | 2120 | 0.82 | 2 | 7630923 | 211222 | 7842145 | 7057930.5 |  | 7057930.5 |  |  | 2020-02-24 | 2020-03-04 | 2020-03-10 | 2020-09-09 |  | 2020-12-30 | 80% | 4082679 | 0 | 4082679 |  | 0 | 0 | 4082679 | 57.85% | WBM Complete |  | 3 | 259.2636 | [5 empty] | 80% | -80%
101 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-101 | 339154027 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD- Molomgonj Bazar Vhatipara Sarak at Ch. 0.00-1500.00m Dewangonj Upazila, Jamalpur District (3 nos LCS worker) | Chairperson- Rima, Secretary- Most. Rowsuna, LCS Group-04 | 0 | 1500 | 1.5 |  | 630474 |  | 630474 | 630474 |  | 630474 |  |  |  | 2020-09-01 |  | 2022-08-31 |  |  | 9% | 61000 |  | 61000 |  |  | 0 | 61000 | 9.675% | Maintenance work ongoing | [8 empty] | 9% | -9%
102 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-102 | 339152003 | Rural road maintenance by LCS (Material & Wages) work on Pathorerchar RHD - Sanandabari GC Road at Ch. 0.00-1000.00m Dewangonj Upazila, Jamalpur District (2 nos LCS worker) | Chairperson- Most. Nazma Begum, Secretary- Most. Monowara Begum LCS Group-01 | 0 | 1000 | 1 |  | 420383 |  | 420383 | 420383 |  | 420383 |  |  |  | 2020-09-01 |  | 2022-08-31 |  |  | 9% | 30500 |  | 30500 |  |  | 0 | 30500 | 7.255% | Maintenance work ongoing | [8 empty] | 9% | -9%
88 | 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W-88 | 339154032 | Improvement of BC Road from Chakpara FRB - Sharkerpara FRB via Amkhowa Bazar road from ch. 700.00-3340.00m including Construction of 8 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-3-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert under Upazila Dewanganj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 700 | 3340 | 2.64 | 43.22 | 29816655 | 13631951 | 43448606 | 38202193.5 |  | 38202193.5 |  |  | 2020-04-26 | 2020-04-29 | 2020-05-05 | 2021-05-04 |  | 2021-12-31 | 5% | [8 empty] | Box cutting running |  | 2 | 172.8424 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Village Road-BC |  | 339584061 | Teguria Bazar-Pakrul- Kolikandi Road | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
| 2020-21 | Jamalpur | Madargonj | Village Road-BC | PRO/JAM/MAD/VR/20-21/W-147 | 339585035 | Improvement of Nobbachar Bazar- Tegaria H/O Khalek via Hidagari road at Ch.0.00-3000m.Under Madarganj Upazila, District Jamalpur including Construction of 2 Nos 2x4.5x4.5m Cross-Drain at Ch.275, 835m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2350m and 3 Nos U-Drain at Ch.01280, 1775, 2050m. |  | 0 | 3000 | 3 | 27.76 | 29816039.04 | 9284713.49 | 39100752.53 | [20 empty] | Tender under process, Estimate approved on 30-9-20 |  | 3 | 259.2636 | [6 empty] | 0%
85 | 2019-20 | Jamalpur | Madargonj | Village Road-BC | PRO/JAM/MAD/VR/19-20/W-85 | 339585030 | Improvement of BC Road from Gabergram Bazar Embankment- Bafatuddin Talukder High School road from ch. 3150-6240.00m including Construction of 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 2Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 2 Nos U-Drain(600X 600mm)under Upazila Madarganj, District- Jamalpur | M/S. Bilkis Enterprise & Md. Mizanur Rahman, Maderganj, Jamalpur. | 3150 | 6240 | 3.09 | 21.37 | 41239211 | 7541224 | 48780435 | 40250008.29 |  | 40250008.29 |  |  | 2020-04-26 | 2020-05-13 | 2020-05-19 | 2021-05-18 |  | 2021-08-05 | 20% | 4942880 |  | 4942880 |  |  | 0 | 4942880 | 12.28% | Structure and Box cutting complete |  | 3 | 259.2636 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Village Road-BC |  | 339584060 | Jonail-Koira UZR(Bow Bazar)-Khilkati via Purbo Shokhnagari | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
|  | Jamalpur | Bakshigonj | Village Road-BC |  | 339075096 | Battajure Nuton Bazar-Battajore Paschimpara via Shamisaya school road | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
160 | 2020-21 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/20-21/W-160 | 339074011 | Improvement of Bituminous carpeting on Gazirpare- Kamalerbarti Road at Ch.00-1755m.including Construction of 1Nos 2x4.0m x3.5m Cross-Drain and 2Nos 1x0.60m x 0.60m U-Drain and 3x4.0mx4.50m RCC Box Culvert Under bakshiganj Upazila, District Jamalpur. |  | 0 | 1755 | 1.755 | 24.409 | 15750792 | 7344798 | 23095590 | [20 empty] | Estimate approved on Dec-20 |  | 3 | 259.2636 | [6 empty] | 0%
|  | Jamalpur | Melandah | Village Road-BC |  | 339615106 | Mahmudpur Bazar - Adbaria H/o Shanbania Via Purba Mahamudpur GPS Road. | [30 empty] | 1.9 | 164.2003 | [6 empty] | 0%
|  | Jamalpur | Melandah | Village Road-BC |  | 339614111 | Mahmudpur bazar-Imampur H/O Shahjahan member Road | [30 empty] | 1 | 86.4212 | [6 empty] | 0%
|  | Jamalpur | Melandah | Village Road-BC |  | 339615108 | Mahmudpur Bazer - Imampur UZR Road. | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
159 | 2020-21 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/20-21/W-159 | 339615107 | Improvement of Bituminous carpeting on Dakhin Khashimara-Uttar Khashimara GPS Road at Ch.00-1300m. Including Construction of 1Nos 1x3.0m x2.5m Cross-Drain and 1Nos 0.75X 0.75m U-Drain Under Melandah Upazila, District Jamalpur. |  | 0 | 1300 | 1.3 | 3.75 | 12135909.52 | 1468744.46 | 13604653.98 | [20 empty] | Estimate approved on Dec-20 |  | 1.3 | 112.3476 | [6 empty] | 0%
|  | Jamalpur | Melandah | Village Road-BC |  | 339615072 | Bhaluka More UZR - Chinitola GPS Road. | [30 empty] | 1.5 | 129.6318 | [6 empty] | 0%
158 | 2020-21 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/20-21/W-158 | 339614030 | Improvement of Bituminous carpeting on Kashimara Bazar- Purarchar(Shahin Bazar) Road at Ch.00-2680m.Under Melandah Upazila, District Jamalpur |  | 0 | 2680 | 2.68 |  | 27176554.32 |  | 27176554.32 | [20 empty] | Estimate approved on Dec-20 |  | 2.5 | 216.053 | [6 empty] | 0%
|  | Jamalpur | Islampur | Village Road-BC |  | 339295009 | Deghair - Bhangbari Road | [30 empty] | 2.5 | 216.053 | [6 empty] | 0%
|  | Jamalpur | Islampur | Village Road-BC |  | 339295032 | Char Deghair Dakhil Madrasha-Mohez Mulla house road | [30 empty] | 2.5 | 216.053 | [6 empty] | 0%
|  | Jamalpur | Islampur | Village Road-BC |  | 339295033 | Char Shisua GPS-Changania RNGPS via Degahir road- | [30 empty] | 3 | 259.2636 | [6 empty] | 0%
83 | 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-83 | 339294035 | Improvement of BC Road from Napiterchar High School-Chandanpur village via Dasani Ferry Ghat road at ch. 00- 3000m. Including Construction of 2 Nos 1x0.600mx0.600m m U-Drain and 2 Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-2-vent-4.50m X 4.00m RCC Box Culvert under Islampur Upazila, District Jamalpur. | LE &ME (JV) Islampur, Jamalpur | 0 | 3000 | 3 | 21.28 | 32150814 | 7303197 | 39454011 | 33896614.39 | 0 | 33896614.39 |  |  | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-05-08 |  | 2021-05-06 | 30% | 4863211 |  | 4863211 |  |  | 0 | 4863211 | 14.35% | Protective work on going, 2 Nos CD Structure Completed and U-Drain is complete, Sand filling pending |  | 3 | 259.2636 | [6 empty] | 0%
84 | 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-84 | 339294067 | Improvement of BC Road from Dattapara R&H - Napiterchar Bazar via Adorsha Gramm road at ch. 00-3000.00m including Construction of 1 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 1Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-3-vent-4.50m X 4.50m RCC Box Culvert under Upazila Islampur, District- Jamalpur | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3000 | 3 | 30.56 | 33480233 | 10347691 | 43827924 | 36997789.33 | 0 | 36997789.33 |  |  | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-04-27 |  | 2021-05-06 | 15% | [8 empty] | Earth Filling done 1300m rest is running, CD Structure and U-Drain work is Pending |  | 3 | 259.2636 | [6 empty] | 0%
|  | Jamalpur | Islampur | Village Road-BC |  | 339294085 | Kazla-Kathma Bazar road. | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
|  | Jamalpur | Islampur | Village Road-BC |  | 339295017 | Kazla Kamar bari-Horindhora road. | [30 empty] | 2 | 172.8424 | [6 empty] | 0%
| 2020-21 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/20-21/W-146 | 339294087 | Improvement of Malmara Bazar-Napiterchar Bazar via Khairdirrkanda road at Ch.0.00-2000m.Under Islampur Upazila, District Jamalpur including Construction of 2 Nos 1X4.00m x 4.00m Cross-Drain at Ch.1800m, 1900m3 Nos U-Drain at Ch.1400, 1530, 1600m. |  | 0 | 2000 | 2 | 12.32 | 20380927 | 4267698.08 | 24648625.08 | [20 empty] | Tender under process,Estimate approved on 30-9-20 |  | 2 | 172.8424 | [6 empty] | 0%
| 2020-21 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/20-21/W-145 | 339294008 | Improvement of Malmara-Bolakipara road by BC at Ch.0.00-2500m.Under Islampur Upazila, District Jamalpur including Construction of 1 Nos 3X4.50m x 4.50m Cross-Drain at Ch.143m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2370m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2140m and 3 Nos U-Drain at Ch.1500, 1900m |  | 0 | 2500 | 2.5 | 25.97 | 24790595 | 8603044.14 | 33393639.14 | [20 empty] | Tender under process,Estimate approved on 30-9-20 |  | 3 | 259.2636 | [6 empty] | 0%
|  | Jamalpur | Melandah | Large Market |  |  | Mahmudpur | [31 empty] | 62.7 | [6 empty] | 0%
126 | 2019-20 | Jamalpur | Madargonj | Large Market | PRO/JAM/MAD/ LM/19-20/W- 126 |  | Construction of Milon Bazar Upazila: Madarganj, Dist:Jamalpur (02 nos LCS group) | LCS 01: Mst. Renura and Mst. Shikha & LCS 02: Mst. Ratna and Mst. Chanvanu | [6 empty] | 6013382 |  |  | 6013382 |  |  |  | 2020-10-09 |  | 2021-04-07 |  |  | 0% | [8 empty] | Training will be held on 1st week of Dec-20 |  |  | 62.7 | [6 empty] | 0%
2 | 2019-20 | Jamalpur | Sadar | Maintenance-Office | PRO/JAM/MAINT/19-20/MW-02 |  | Maintenance and repair work of LGED Office Building, Dist: Jamalpur | SHABUZ ENTERPRISE | [6 empty] | 186010 |  |  | 186010 |  |  |  | 2019-12-17 | 2019-12-19 | 2020-01-13 |  |  | 100% |  |  | 166478 |  |  | 19532 | 186010 | 100% | Final bill paid
|  | Jamalpur | Dewanganj | Large Market |  |  | Khorma bazar | [31 empty] | 62.7 | [6 empty] | 0%
|  | Jamalpur | Dewanganj | Large Market |  |  | Jhalur Char | [31 empty] | 62.7 | [6 empty] | 0%
|  | Jamalpur | Dewanganj | Large Market |  |  | Sanandabari | [31 empty] | 62.7 | [6 empty] | 0%
|  | Jamalpur | Dewanganj | Large Market |  |  | Molla Para Bazar | [31 empty] | 62.7 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Bhabki Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Talukpara Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Jhawgora Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Gazipur Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Shahin Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Char Gobindi Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Nalsia bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Millon Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Millon Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Saguna Bzar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Kahetpara bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Tegharia Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Medium Market |  |  | Gobindoganj Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Islampur | Medium Market |  |  | Duttapara Ananda Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Bakshigonj | Medium Market |  |  | Gazirpara Annanda Bazar | [31 empty] | 41.77 | [6 empty] | 0%
150 | 2020-21 | Jamalpur | Bakshigonj | Medium Market | PRO/JAM/BAK/ MM/20-21/W-150 |  | Construction of Paschim kamaler barti Bazar | [7 empty] | 6579551 | [20 empty] | Estimate approved on 05-11-20 |  |  | 41.77 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Medium Market |  |  | Nabbo Char Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Medium Market |  |  | Teguria bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Medium Market |  |  | Rayerchara Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Madargonj | Medium Market |  |  | Koali Kandi Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Dewanganj | Medium Market |  |  | Amkhowa Bazar | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Dewanganj | Medium Market |  |  | Char Maguri Hat | [31 empty] | 41.77 | [6 empty] | 0%
|  | Jamalpur | Melandah | Small Market |  |  | Bhaluka(Tarankandi Bazar) | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Mondalpara Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Shirajabad Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Malmara Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Akota Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Napiterchar Bazar | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Islampur | Small Market |  |  | Bulakip (ara Bazar) | [31 empty] | 26.11 | [6 empty] | 0%
|  | Jamalpur | Bakshigonj | Small Market |  |  | Merurchar | [31 empty] | 26.11 | [6 empty] | 0%
0%
0%
0%
0%
0%
0%
0%
[6 empty] | Total packages: | 138 | Nos of Est. Pkgs: | 138 |  | 258.993 | 646.949 | 1602857275.86 | 185142584.48 | 1875661359.2 | 1239007391.146 | 71186400.491 | 1352025708.968 | 6592816.832 | 128452847.013 | [6 empty] | 54.89% | 449369867.77 | 25740280.27 | 477110488.04 | 82171843.23 | 3810687.87 | 83618903.96 | 563234069 | 41.17%
[6 empty] | Nos of Contract Signed: |  | NOS of Contract Signed: | 113 |  |  |  |  | NOS of Estimated packages: | 138 |  | NOS of Contract Signed: | 113 | [16 empty] | 41.46%
Formulas:
Total Contract days = [Date of completion]-[Date of Contract Signed]
Days spent till now = AQ5-[Date of Contract Signed]
Date of completion = [Date of Contract Signed]+180

## Summary District
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Districtwise Summary of Progress
2020-11-01
District | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog. | remarks
Gaibandha | 19 | 17 | 49.017 | 76.3 | 235006442.71 | 14266497 | 249272939.71 | 201046485.134 | 9318495.44 | 210364980.574 | 0 | 81.86% | 97598655.59 | 19418817.41 | 117017473 | 16216352.77 | 3202433.23 | 19418786 | 136436259 | 64.86% | Kurigram and Lalmonirhat Large market+Rehabilitation Phy progr% should be updated in progress summary after getting update from district
Kurigram | 41 | 35 | 56.561 | 66.98 | 341851144.86 | 16934672.51 | 386058854.09 | 294372273.224 | 12787845.3 | 314600800.246 | 0 | 48.54% | 73934297 | 1123816 | 76564303 | 0 | 0 | 243035.72 | 76807338.72 | 24.41%
Nilphamari | 11 | 8 | 29.653 | 90.68 | 148111963.24 | 23885787.75 | 171997750.99 | 110830850.03 | 9050661.417 | 119881511.447 | 0 | 38.16% | 36105507 | 3771004 | 39876511 | 1822549 | 451348 | 2273897 | 42150408 | 35.16%
Rangpur | 10 | 10 | 22.287 | 62.7 | 99222764.06 | 18012596 | 124409629.06 | 85758461.96 | 17137431.8 | 109476434.23 | 0 | 40.42% | 32151145 | 0 | 33221912 | 2531805 | 0 | 2531805 | 35753717 | 32.66%
Lalmonirhat | 31 | 26 | 47.94 | 99.55 | 359632718.99 | 25479417.27 | 410854606.26 | 269844607.063 | 16419707.078 | 298944444.14 | 0 | 71.8% | 131016366.18 | 1426642.86 | 132453009.04 | 56475781.46 | 156906.64 | 56632688.1 | 189085697.14 | 63.25%
Jamalpur | 25 | 17 | 53.535 | 250.739 | 419032242 | 86563613.95 | 518374798.95 | 277154713.735 | 6472259.456 | 289826365.191 | 6592816.832 | 38.89% | 76432897 | 0 | 76599375 | 5125355 | 0 | 5144887 | 81744262 | 28.2%
TOTAL: | 137 | 113 | 258.993 | 646.949 | 1602857275.86 | 185142584.48 | 1860968579.06 | 1239007391.146 | 71186400.491 | 1343094535.828 | 6592816.832 | 55.27% | 447238867.77 | 25740280.27 | 475732583.04 | 82171843.23 | 3810687.87 | 86245098.82 | 561977681.86 | 41.64% | 0
Gaibandha
Union Road-BC | 9 | 7 | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 108416157.474 | 0 | 75.21% | 44253339.59 | 9073061.41 | 53326401 | 7559928.77 | 1513101.23 | 9073030 | 62399431 | 57.56%
Village Road-BC | 5 | 5 | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Village Road-HBB
Rehabilitation
Maintenance | 5 | 5 | 23.56 | 0 | 11882105.62 | 0 | 11882105.62 | 11257837.74 | 0 | 11257837.74 | 0 | 10% | 652950 | 0 | 652950 | 0 | 0 | 0 | 652950 | 5.8%
Small Market
Medium Market
Large market
Total: | 19 | 17 | 49.017 | 76.3 | 235006442.71 | 14266497 | 249272939.71 | 201046485.134 | 9318495.44 | 210364980.574 | 0 | 81.86% | 97598655.59 | 19418817.41 | 117017473 | 16216352.77 | 3202433.23 | 19418786 | 136436259 | 64.86%
Kurigram
Union Road-BC | 2 | 2 | 2.246 | 6.5 | 20464635 | 1149239 | 21613874 | 17986708.69 | 942642.23 | 18929350.922 | 0 | 48.57% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 15.75%
Village Road-BC | 21 | 20 | 37.56 | 50.48 | 295156835.76 | 13111939.51 | 308268775.27 | 254247480.214 | 9930071.07 | 264177551.284 | 0 | 48.05% | 61863379 | 1123816 | 62987195 | 0 | 0 | 0 | 62987195 | 23.84%
Village Road-HBB | 2 | 2 | 2.44 | 2.5 | 12549293.15 | 758362 | 13307655.15 | 12192176.48 | 0 | 12192176.48 | 0 | 93.64% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 59.79%
Rehabilitation | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance | 5 | 4 | 12.275 | 0 | 6708837.95 | 0 | 6708837.95 | 4727638.95 | 0 | 4727638.95 | 0 | 7.547% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Small Market | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Medium Market | 6 | 3 | 0 | 0 | 0 | 0 | 21471853 | 0 | 0 | 5691456 | 0 | 53.76% | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 1800000 | 31.63%
Large market | 1 | 1 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100%
Maintenance-Office Building | 1 | 1 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100%
Total: | 41 | 35 | 56.561 | 66.98 | 341851144.86 | 16934672.51 | 386058854.09 | 294372273.224 | 12787845.3 | 314600800.246 | 0 | 48.54% | 73934297 | 1123816 | 76564303 | 0 | 0 | 243035.72 | 76807338.72 | 24.41%
Nilphamari
Union Road-BC | 2 | 2 | 4.209 | 6.25 | 36707014.68 | 2010249.5 | 38717264.18 | 34451742.52 | 1057539.337 | 35509281.857 | 0 | 44.93% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 41.76%
Village Road-BC | 6 | 4 | 11.618 | 84.43 | 99279704.37 | 21875538.25 | 121155242.62 | 66759465.31 | 7993122.08 | 74752587.39 | 0 | 39.85% | 23129640 | 2955540 | 26085180 | 989931 | 247482 | 1237413 | 27322593 | 36.55%
Village Road-HBB | 1 | 1 | 1.055 | 0 | 5468148 | 0 | 5468148 | 4548906.83 | 0 | 4548906.83 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
Rehabilitation
Maintenance | 2 | 1 | 12.771 | 0 | 6657096.19 | 0 | 6657096.19 | 5070735.37 | 0 | 5070735.37 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
Small Market
Medium Market
Large market
Total: | 11 | 8 | 29.653 | 90.68 | 148111963.24 | 23885787.75 | 171997750.99 | 110830850.03 | 9050661.417 | 119881511.447 | 0 | 38.16% | 36105507 | 3771004 | 39876511 | 1822549 | 451348 | 2273897 | 42150408 | 35.16%
Rangpur
Union Road-BC | 3 | 3 | 5.03 | 27.3 | 44140805.37 | 7649876 | 51790681.37 | 40507873.83 | 7081554.16 | 47589427.99 | 0 | 61.94% | 20626683 | 0 | 20626683 | 922375 | 0 | 922375 | 21549058 | 45.28%
Village Road-BC | 3 | 3 | 5.982 | 35.4 | 50088377.48 | 10362720 | 60451097.48 | 42662695.68 | 10055877.64 | 52718573.32 | 0 | 24.37% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 24.14%
Village Road-HBB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Rehabilitation
Maintenance | 2 | 2 | 11.275 | 0 | 4993581.21 | 0 | 4993581.21 | 2587892.45 | 0 | 2587892.45 | 0 | 20.51% | 407250 | 0 | 407250 | 0 | 0 | 0 | 407250 | 15.74%
Small Market
Medium Market | 1 | 1 | 0 | 0 | 0 | 0 | 5032629 | 0 | 0 | 5032629 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Large market
Maintenance-Office Building | 1 | 1 | 0 | 0 | 0 | 0 | 2141640 | 0 | 0 | 1547911.47 | 0 | 90% | 0 | 0 | 1070767 | 0 | 0 | 0 | 1070767 | 69.17%
Total: | 10 | 10 | 22.287 | 62.7 | 99222764.06 | 18012596 | 124409629.06 | 85758461.96 | 17137431.8 | 109476434.23 | 0 | 40.42% | 32151145 | 0 | 33221912 | 2531805 | 0 | 2531805 | 35753717 | 32.66%
Lalmonirhat
Union Road-BC | 6 | 5 | 10.485 | 29.75 | 89505887 | 7220693 | 96726580 | 62346058.562 | 5955854.025 | 68301912.587 | 0 | 73.17% | 38732002 | 0 | 38742002 | 6085809 | 0 | 6085809 | 44827811 | 65.63%
Village Road-BC | 17 | 15 | 31.735 | 64.8 | 254024604.85 | 16787856.27 | 270812461.12 | 193801777.063 | 10463853.053 | 204265630.115 | 0 | 79.98% | 90623364.18 | 1426642.86 | 92050007.04 | 50389972.46 | 156906.64 | 50546879.1 | 142596886.14 | 69.81%
Village Road-HBB | 1 | 1 | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 | 0 | 11684286.298 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Rehabilitation
Maintenance | 1 | 1 | 3.17 | 0 | 2012485.14 | 0 | 2012485.14 | 2012485.14 | 0 | 2012485.14 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Small Market
Medium Market | 5 | 4 | 0 | 0 | 0 | 0 | 19535922 | 0 | 0 | 12680130 | 0 | 10.25% | 166100000% | 0% | 1661000 | 0 | 0 | 0 | 1661000 | 13.1%
Large market | 1 | 0 | 0 | 0 | 0 | 0 | 6206548 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Total: | 31 | 26 | 47.94 | 99.55 | 359632718.99 | 25479417.27 | 410854606.26 | 269844607.063 | 16419707.078 | 298944444.14 | 0 | 71.8% | 131016366.18 | 1426642.86 | 132453009.04 | 56475781.46 | 156906.64 | 56632688.1 | 189085697.14 | 63.25%
Jamalpur
Union Road-BC | 1 | 0 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Village Road-BC | 17 | 11 | 40.195 | 247.739 | 402363371.07 | 79648638.17 | 482012009.24 | 271792306.735 | 6472259.456 | 278264566.191 | 6592816.832 | 40.44% | 76432897 | 0 | 76432897 | 5125355 | 0 | 5125355 | 81558252 | 28.63%
Village Road-HBB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Rehabilitation
Maintenance | 4 | 4 | 12.19 | 0 | 5362407 | 0 | 5362407 | 5362407 | 0 | 5362407 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Small Market
Medium Market | 1 | 0 | 0 | 0 | 0 | 0 | 6579551 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Large market | 1 | 1 | 0 | 0 | 0 | 0 | 6013382 | 0 | 0 | 6013382 | 0 | 0
Maintenance-Office Building | 1 | 1 | 0 | 0 | 0 | 0 | 186010 | 0 | 0 | 186010 | 0 | 100% | 0 | 0 | 166478 | 0 | 0 | 19532 | 186010 | 100%
Total: | 25 | 17 | 53.535 | 250.739 | 419032242 | 86563613.95 | 518374798.95 | 277154713.735 | 6472259.456 | 289826365.191 | 6592816.832 | 38.89% | 76432897 | 0 | 76599375 | 5125355 | 0 | 5144887 | 81744262 | 28.2%

## Summary Component
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Componentwise Summary of Progress
2020-11-01
Component | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog. | DPP Length | Completed Work | DPP wise Progress
Union Road-BC | 23 | 19 | 39.064 | 109.8 | 340489859.26 | 32932115.75 | 373421975.01 | 258190221.816 | 20555909.012 | 278746130.83 | 0 | 66.78% | 119568699.59 | 9888525.41 | 129467225 | 15400730.77 | 1716967.23 | 17117698 | 146584923 | 52.59% | 61 | 26.0855 | 42.76%
Village Road-BC | 69 | 58 | 136.603 | 522.149 | 1185672177.34 | 148066106.73 | 1333738284.07 | 916154534.182 | 48715359.479 | 964869893.66 | 6592816.832 | 55.45% | 315858858.18 | 15851754.86 | 331710613.04 | 66771112.46 | 2093720.64 | 68864833.1 | 400575446.14 | 41.52% | 235 | 75.7482 | 32.23%
Village Road-HBB | 4 | 4 | 6.045 | 7.5 | 32107183.15 | 2229230 | 34336413.15 | 28425369.608 | 0 | 28425369.608 | 0 | 40.16% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 25.65% | 25 | 2.4278 | 9.711%
Rehabilitation | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 60 | 0 | 0%
Maintenance | 19 | 17 | 75.241 | 0 | 37616513.11 | 0 | 37616513.11 | 31018996.65 | 0 | 31018996.65 | 0 | 6.491% | 1060200 | 0 | 1060200 | 0 | 0 | 0 | 1060200 | 3.418% | 411 | 4.8838 | 1.188%
Small Market | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | [9 empty] | 15 | 0 | 0%
Medium Market | 13 | 8 | 0 | 0 | 0 | 0 | 52619955 | 0 | 0 | 23404215 | 0 | 18.63% | 3461000 | 0 | 3461000 | 0 | 0 | 0 | 3461000 | 14.79% | 100 | 1.4901 | 1.49% |  |  | Complt | DPP wise prog
Large market | 3 | 2 | 0 | 0 | 0 | 0 | 13094542.86 | 0 | 0 | 6887994.86 | 0 | 12.7% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 12.7% | 20 | 0.25395 | 1.27% | CD Struc | 1688 | 357.0601 | 21.15%
Maintenance-Office Building | 3 | 3 | 0 | 0 | 0 | 0 | 3202262.86 | 0 | 0 | 2608534.33 | 0 | 94.07% | 0 | 0 | 1990340 | 0 | 0 | 141049.86 | 2131389.86 | 81.71%
Total: | 137 | 113 | 258.993 | 646.949 | 1602857275.86 | 185142584.48 | 1860968579.06 | 1239007391.146 | 71186400.491 | 1343094535.828 | 6592816.832 | 55.19% | 447238867.77 | 25740280.27 | 475732583.04 | 82171843.23 | 3810687.87 | 86245098.82 | 561977681.86 | 41.64% |  |  |  | Women | 35
[24 empty] | Cyclone | 20
UNION ROAD -BC
District | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog.
Gaibandha | 9 | 7 | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 108416157.474 | 0 | 75.21% | 44253339.59 | 9073061.41 | 53326401 | 7559928.77 | 1513101.23 | 9073030 | 62399431 | 57.56%
Kurigram | 2 | 2 | 2.246 | 6.5 | 20464635 | 1149239 | 21613874 | 17986708.69 | 942642.23 | 18929350.922 | 0 | 48.57% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 15.75%
Nilphamari | 2 | 2 | 4.209 | 6.25 | 36707014.68 | 2010249.5 | 38717264.18 | 34451742.52 | 1057539.337 | 35509281.857 | 0 | 44.93% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 41.76%
Rangpur | 3 | 3 | 5.03 | 27.3 | 44140805.37 | 7649876 | 51790681.37 | 40507873.83 | 7081554.16 | 47589427.99 | 0 | 61.94% | 20626683 | 0 | 20626683 | 922375 | 0 | 922375 | 21549058 | 45.28%
Lalmonirhat | 6 | 5 | 10.485 | 29.75 | 89505887 | 7220693 | 96726580 | 62346058.562 | 5955854.025 | 68301912.587 | 0 | 73.17% | 38732002 | 0 | 38742002 | 6085809 | 0 | 6085809 | 44827811 | 65.63%
Jamalpur | 1 | 0 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
TOTAL: | 23 | 19 | 39.064 | 109.8 | 340489859.26 | 32932115.75 | 373421975.01 | 258190221.816 | 20555909.012 | 278746130.83 | 0 | 66.78% | 119568699.59 | 9888525.41 | 129467225 | 15400730.77 | 1716967.23 | 17117698 | 146584923 | 52.59%
VILLAGE ROAD-BC
Gaibandha | 5 | 5 | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Kurigram | 21 | 20 | 37.56 | 50.48 | 295156835.76 | 13111939.51 | 308268775.27 | 254247480.214 | 9930071.07 | 264177551.284 | 0 | 48.05% | 61863379 | 1123816 | 62987195 | 0 | 0 | 0 | 62987195 | 23.84%
Nilphamari | 6 | 4 | 11.618 | 84.43 | 99279704.37 | 21875538.25 | 121155242.62 | 66759465.31 | 7993122.08 | 74752587.39 | 0 | 39.85% | 23129640 | 2955540 | 26085180 | 989931 | 247482 | 1237413 | 27322593 | 36.55%
Rangpur | 3 | 3 | 5.982 | 35.4 | 50088377.48 | 10362720 | 60451097.48 | 42662695.68 | 10055877.64 | 52718573.32 | 0 | 24.37% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 24.14%
Lalmonirhat | 17 | 15 | 31.735 | 64.8 | 254024604.85 | 16787856.27 | 270812461.12 | 193801777.063 | 10463853.053 | 204265630.115 | 0 | 79.98% | 90623364.18 | 1426642.86 | 92050007.04 | 50389972.46 | 156906.64 | 50546879.1 | 142596886.14 | 69.81%
Jamalpur | 17 | 11 | 40.195 | 247.739 | 402363371.07 | 79648638.17 | 482012009.24 | 271792306.735 | 6472259.456 | 278264566.191 | 6592816.832 | 40.44% | 76432897 | 0 | 76432897 | 5125355 | 0 | 5125355 | 81558252 | 28.63%
TOTAL: | 69 | 58 | 136.603 | 522.149 | 1185672177.34 | 148066106.73 | 1333738284.07 | 916154534.182 | 48715359.479 | 964869893.66 | 6592816.832 | 55.45% | 315858858.18 | 15851754.86 | 331710613.04 | 66771112.46 | 2093720.64 | 68864833.1 | 400575446.14 | 41.52%
VILLAGE ROAD-HBB
Gaibandha
Kurigram | 2 | 2 | 2.44 | 2.5 | 12549293.15 | 758362 | 13307655.15 | 12192176.48 | 0 | 12192176.48 | 0 | 93.64% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 59.79%
Nilphamari | 1 | 1 | 1.055 | 0 | 5468148 | 0 | 5468148 | 4548906.83 | 0 | 4548906.83 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
Rangpur
Lalmonirhat | 1 | 1 | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 | 0 | 11684286.298 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Jamalpur
TOTAL: | 4 | 4 | 6.045 | 7.5 | 32107183.15 | 2229230 | 34336413.15 | 28425369.608 | 0 | 28425369.608 | 0 | 40.16% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 25.65%
Rehabilitation of Road
Gaibandha
Kurigram | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nilphamari
Rangpur
Lalmonirhat
Jamalpur
TOTAL: | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Road Maintenance by LCS
Gaibandha | 5 | 5 | 23.56 | 0 | 11882105.62 | 0 | 11882105.62 | 11257837.74 | 0 | 11257837.74 | 0 | 10% | 65295000% | 0% | 652950 | 0 | 0 | 0 | 652950 | 5.8%
Kurigram | 5 | 4 | 12.275 | 0 | 6708837.95 | 0 | 6708837.95 | 4727638.95 | 0 | 4727638.95 | 0 | 7.547% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Nilphamari | 2 | 1 | 12.771 | 0 | 6657096.19 | 0 | 6657096.19 | 5070735.37 | 0 | 5070735.37 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
Rangpur | 2 | 2 | 11.275 | 0 | 4993581.21 | 0 | 4993581.21 | 2587892.45 | 0 | 2587892.45 | 0 | 20.51% | 407250 | 0 | 407250 | 0 | 0 | 0 | 407250 | 15.74%
Lalmonirhat | 1 | 1 | 3.17 | 0 | 2012485.14 | 0 | 2012485.14 | 2012485.14 | 0 | 2012485.14 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Jamalpur | 4 | 4 | 12.19 | 0 | 5362407 | 0 | 5362407 | 5362407 | 0 | 5362407 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
TOTAL: | 19 | 17 | 75.241 | 0 | 37616513.11 | 0 | 37616513.11 | 31018996.65 | 0 | 31018996.65 | 0 | 6.491% | 1060200 | 0 | 1060200 | 0 | 0 | 0 | 1060200 | 3.418%
MEDIUM MARKET
Gaibandha
Kurigram | 6 | 3 | 0 | 0 | 0 | 0 | 21471853 | 0 | 0 | 5691456 | 0 | 53.76% | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 1800000 | 31.63%
Nilphamari
Rangpur | 1 | 1 | 0 | 0 | 0 | 0 | 5032629 | 0 | 0 | 5032629 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Lalmonirhat | 5 | 4 | 0 | 0 | 0 | 0 | 19535922 | 0 | 0 | 12680130 | 0 | 10.25% | 1661000 | 0 | 1661000 | 0 | 0 | 0 | 1661000 | 13.1%
Jamalpur | 1 | 0 | 0 | 0 | 0 | 0 | 6579551 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
TOTAL: | 13 | 8 | 0 | 0 | 0 | 0 | 52619955 | 0 | 0 | 23404215 | 0 | 18.63% | 3461000 | 0 | 3461000 | 0 | 0 | 0 | 3461000 | 14.79%
LARGE MARKET
Gaibandha
Kurigram | 1 | 1 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100%
Nilphamari
Rangpur
Lalmonirhat | 1 | 0 | 0 | 0 | 0 | 0 | 6206548 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Jamalpur | 1 | 1 | 0 | 0 | 0 | 0 | 6013382 | 0 | 0 | 6013382 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0%
TOTAL: | 3 | 2 | 0 | 0 | 0 | 0 | 13094542.86 | 0 | 0 | 6887994.86 | 0 | 12.7% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 12.7%
SMALL MARKET
Gaibandha
Kurigram | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Nilphamari
Rangpur
Lalmonirhat
Jamalpur
TOTAL: | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Maintenance-Office Bulilding
Kurigram | 1 | 1 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100%
Rangpur | 1 | 1 | 0 | 0 | 0 | 0 | 2141640 | 0 | 0 | 1547911.47 | 0 | 90% | 0 | 0 | 1070767 | 0 | 0 | 0 | 1070767 | 69.17%
Jamalpur | 1 | 1 | 0 | 0 | 0 | 0 | 186010 | 0 | 0 | 186010 | 0 | 100% | 0 | 0 | 166478 | 0 | 0 | 19532 | 186010 | 100%
TOTAL: | 3 | 3 | 0 | 0 | 0 | 0 | 3202262.86 | 0 | 0 | 2608534.33 | 0 | 94.07% | 0 | 0 | 1990340 | 0 | 0 | 141049.86 | 2131389.86 | 81.71%

## Gaibandha
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Gaibandha
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Union Road BC
1 | 2018-19 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/GAI-S/UNR/ 18-19/W-06 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | M/S Basundhara, Kurigram | 3600.00 4496.00 | 4150.00 7600.00 | 3.654 | 6 | 29444723.57 | 991093.47 | 30435817.04 | 29438902.5 | 991097.41 | 30429999.91 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 21-04-2020 31-12-2020 | 0 | 2020-12-31 | 65% | 10699800 | 2070100 | 12769900 | 1734520 | 335580 | 2070100 | 14840000 | 48.77% | WBM Complete. BC preparation ongoing
2 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-09 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2.000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure under khorda Rasulpur-Chandiapur Road at Ch.710.0m. Under Shdullapur, District Gaibandha. | Md.Khademul Islam Jewel, Gaibandha | 0 | 2000 | 2 | 6.2 | 16764810.71 | 1868067 | 18632877.71 | 17548454.17 | 1064613.71 | 18613067.88 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 17-03-2020 15-09-2020 | 0 | 2020-10-15 | 100% | 11273900 | 2138050 | 13411950 | 1797215 | 340834 | 2138049 | 15549999 | 83.54% | Work Completed
3 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-10 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | M/S SAJIN TRADERS JV | 1235 | 3235 | 2 | 0.6 | 17379171 | 145336 | 17524507 | 17391992.65 | 127964.94 | 17519957.59 | 0 | 0 | 2019-04-18 | 2019-05-08 | 2019-05-14 | 2020-03-21 | 0 | 2020-04-19 | 100% | 9841196 | 2228152 | 12069348 | 1840948 | 387204 | 2228152 | 14297500 | 81.61% | Work Completed
4 | 2018-19 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-12 | 132823017 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | Md. Mahomudun Nobi, Pirganj, Rangpur | 2627 | 3627 | 1 | 3.6 | 7673417 | 1106313 | 8779730 | 7289746.1 | 1050997.35 | 8340743.45 | 0 | 0 | 2019-03-21 | 2019-04-07 | 2019-04-13 | 2020-03-08 | 0 | 2020-03-31 | 100% | 5511343.59 | 1203622.41 | 6714966 | 1000461.77 | 203130.23 | 1203592 | 7918558 | 94.94% | Final Bill Paid
68 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 68 | 132823009 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 1500 | 2500 | 1 | 1 | 9588269 | 164366 | 9752635 | 8126474.979 | 0 | 8126474.979 | 0 | 0 | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 0 | 2021-05-13 | 70% | 3099996 | 608400 | 3708396 | 508586 | 99814 | 608400 | 4316796 | 53.12% | WBM complete
10 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-69 | 132823001 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.2000m-4000m. including 6Nos (0.625x0.600) m U-Drain on Khorda Rasulpur-Chandiapur Road at Ch: 2920m,2953m,3089m,3393m, 3582m & 3743m and 1x2.00mx2.00 m RCC Box Culvert at Ch: 2645m under khorda Rasulpur-Chandiapur Road under Shdullapur, District Gaibandha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | package holded
135 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/18-19/W-70 | 132823002 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.0m-1250m. including Costruction of 2Nos (0.625x0.600) m U-Drain on Mohishbandhi-Mirpur Road at Ch: 52m & 946m Under Shdullapur, District Gaibandha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | package holded
71 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 71 | 132823004 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | M/S Mafi Construction JV, Sadullapur, Gaibandha | 0 | 2000 | 2 | 14.3 | 16679589 | 2485578 | 19165167 | 14006744.15 | 2283645.85 | 16290390 | 0 | 0 | 2020-05-11 | 2020-05-18 | 2020-05-28 | 2021-05-28 | 0 | 2022-05-17 | 60% | 3119470 | 690265 | 3809735 | 565199 | 125066 | 690265 | 4500000 | 27.62% | WBM Complete
72 | 2019-20 | Gaibandha | Shadullapur | Union Road-BC | PRO/GAI/SAD/UNR/19-20/W- 72 | 132823015 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | Md.Shoeb Hossain Mona, Gaibandha | 0 | 1000 | 1 | 5.3 | 9822898 | 1226329 | 11049227 | 9095523.665 | 0 | 9095523.665 | 0 | 0 | 2020-05-11 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 0 | 2021-05-13 | 20% | 707634 | 134472 | 842106 | 112999 | 21473 | 134472 | 976578 | 10.74% | Stopped work due water in both side of road
| 2020-21 | Gaibandha | Saghata | Union Road-BC | PRO/GAI/SAG/UNR/20-21/W-135 | 132883015 | Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha. | 0 | 3526 | 6386 | 2.86 | 0 | 26773265 | 0 | 26773265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NOA Issued
| 2020-21 | Gaibandha | Sadar | Union Road-BC | PRO/GAI/SAD/UNR/ 20-21/W-136 | 132243029 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | 0 | 7627 | 8057 | 0.43 | 0 | 4238910 | 0 | 4238910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Evaluation on going
|  |  |  | Total: |  | NOS Est. Packages: | 9 | NOS Cont. Signed: | 7 |  | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 108416157.474 | 0 | 0 | [6 empty] | 75.21% | 44253339.59 | 9073061.41 | 53326401 | 7559928.77 | 1513101.23 | 9073030 | 62399431 | 57.56%
Village Road BC
1 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI/GAI-S/VR/18-19/W-07 | 132244011 | Improvement of Bituminous Carpeting Road on Fulbari-Badiakhali hat Road At Ch0.00m-1623m. &2300m-3100m. including Costruction of 10 U- drain (0.600mx0.625m) Fulbari-Badiakhali hat Road atCh0.00m-1623m. &2300m-3100m. Under Gaibandha Sadar Upazila, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 2300 | 1623 3100 | 2.423 | 6 | 22031940.04 | 1000431.53 | 23032371.57 | 22027478.06 | 1000435.54 | 23027913.6 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 24-03-2020 30-12-2020 | 0 | 2020-12-31 | 95% | 11900400 | 2349800 | 14250200 | 1962327 | 387473 | 2349800 | 16600000 | 72.09% | BC Complete
2 | 2018-19 | Gaibandha | Sadar | Village Road-BC | PRO/GAI /GAI-S/VR/18-19/W-08 | 132244021 | Improvement of Bituminous Carpeting Road on Ruper –Eslighat via Pramanik para Road at Ch.1500m-2980m including Costruction of 3 U- drain (0.600mX0.625m) at Ch.1280m,2300m,2640m. Under Gaibandha Sadar Upazila, District Gaibandha. | RSL Enterprise, gaibandha | 1500 | 2980 | 1.48 | 1.8 | 16529257.77 | 302110 | 16831367.77 | 16518512.1 | 302111.17 | 16820623.27 | 0 | 0 | 2019-04-18 | 2019-05-05 | 2019-05-11 | 2020-04-21 | 0 | 2020-04-23 | 100% | 11472451 | 2253310 | 13725761 | 1904749 | 348561 | 2253310 | 15979071 | 95% | Final Bill Paid
3 | 2018-19 | Gaibandha | Shadullapur | Village Road-BC | PRO/GAI/SAD/VR/18-19/W-11 | 132824014 | Improvement of Bituminous Road on Shdullapur Dhaperhat G.C road at Boxigonj Bazar toDhaperhat-Madarhat Road via Ambagan Road at Ch.0.00m-2480m. including Costruction of 11 Nos U-Drain 0.600mx0.625m at Ch.335m,720m,877m,1190m,1300m,1388m,1477m,1765m,1880m,1972m,&2226m. Under Shdullapur, District Gaibandha. | Md. Abdul Latif Hakkani, Gaibandha | 0 | 2480 | 2.48 | 6.6 | 20485874 | 1361706 | 21847580 | 20563288.22 | 1361711.78 | 21925000 | 0 | 0 | 2019-04-18 | 2019-05-15 | 2019-05-21 | 02-05-2020 31-07-2020 | 0 | 2020-07-31 | 100% | 13273661 | 2504677 | 15778338 | 2107080 | 397597 | 2504677 | 18283015 | 83.39% | Work Complete
4 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-13 | 132885163 | Improvement of Bituminous Road on Gatia H/O Taibor Master-Chitholia H/O Mahatab Member Road at Ch.0.00m-800m. including Costruction of 4 Nos U-Drain 0.600mx0.625m at Ch20m,135m,290m,&700m Under Saghata, District Gaibandha. | Md. Jakir Hossain, Gaibandha | 0 | 800 | 0.8 | 2.4 | 7459743 | 304702 | 7764445 | 7086755.8 | 282523.35 | 7369279.15 | 0 | 0 | 2019-03-21 | 2019-04-15 | 2019-04-21 | 2020-04-06 | 0 | 2019-12-29 | 100% | 5007817 | 994738 | 6002555 | 839420 | 155318 | 994738 | 6997293 | 94.95% | Final Bill Paid
5 | 2018-19 | Gaibandha | Saghata | Village Road-BC | PRO/GAI/SAG/VR/18-19/W-14 | 132884002 | Improvement of Bituminous Road on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Road at ch.600m-2930m. including Costruction of 10 Nos U-Drain 0.600mx0.625m at Ch.673m,735m,816m,925m,1387m,1760m,1920m,1987m,2150m,2493m.and Costruction of 3 Nos Slope Drain at Ch.1496m, 1745m, 2075m, and Costruction of 3 Nos (2.00mx2.00m) Cross Drainges Structure on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Roadat Ch.2395m,2590m, 2787m. Under Saghata, District Gaibandha. | M/S SAJIN TRADERS JV | 600 | 2930 | 2.33 | 22.5 | 18252469 | 3310465 | 21562934 | 20694775 | 853394.34 | 21548169.34 | 0 | 0 | 2019-04-18 | 2019-05-07 | 2019-05-13 | 2020-03-25 | 0 | 2020-04-23 | 100% | 11038037 | 2243231 | 13281268 | 1842848 | 400383 | 2243231 | 15524499 | 72.05% | Work Completed.
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 5 |  | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 0 | [6 empty] | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Maintenance by LCS
113 | 2019-20 | Gaibandha | Sundargonj | Maintenance-LCS | PRO/GAI/SUN/RMP/19-20/ MW-113 | 132915058 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Kapashia UP Office to Kashim Bazar- WAPDA Embankment via H/O Nesab Chairman (Kajir Char Ahammed Nagar Bazar) road, at Ch. 00-2300m. | 1.Mst. Momata Begum & Mst Ismat Ara Begum | 0 | 2300 | 2.3 | 0 | 1327224.49 | 0 | 1327224.49 | 1281224.49 | 0 | 1281224.49 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 75200 | 0 | 75200 | 0 | 0 | 0 | 75200 | 5.869% | Work on going,
114 | 2019-20 | Gaibandha | Sadar | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-114 | 132245158 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Salam bazar- Balata bazar via Mouja malibari Eidgah at ch. 00-2500m | 1.Mst. Mousi akter 2.Mst. Aduri | 0 | 2500 | 2.5 | 0 | 1331224.49 | 0 | 1331224.49 | 1281224.49 | 0 | 1281224.49 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 75200 | 0 | 75200 | 0 | 0 | 0 | 75200 | 5.869% | Work on going,
115 | 2019-20 | Gaibandha | Shadullapur | Maintenance-LCS | PRO/GAI/GAI_S/RMP/19-20/ MW-115 | 132823009 132823008 132823001 132823004 132823006 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Naldanga G.C.-Ramzibon U.P. office. Road at ch. 00-780m. 2. Idilpur U.P. office-Dhaperhat U.P. office road at ch. 00-2000m. 3. Khorda Rasulpur-chandiapur roadat ch. 00-1020m. 4. Bhatgram U.P office-Jamalpur Bazar at ch.00-2000m. 5 Chandiapur bazar-Rahmatpur GC via Rasulpur bazar at ch.00-2000m. | 1. Mst. Jobeda Begum & Mst. Sahada Begum Begum 2 Mst.Rony begum & Shoprati 3. bimoti rani & Mst .Rahima Begum. 4. Dulali begum & Mst. Salaha Begum 5. Mst. Aysa Begum & Mst. Lili Begum | 0.00 0.00 0.00 0.00 0.00 | 780 2000 1020 2000 2000 | 7.8 | 0 | 3639329.09 | 0 | 3639329.09 | 3483329.08 | 0 | 3483329.08 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 198850 | 0 | 198850 | 0 | 0 | 0 | 198850 | 5.709% | Work on going,
116 | 2019-20 | Gaibandha | Saghata | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-116 | 132885022 132885175 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Dighal Kandi- Digholkandi H/O Sonaullah Mirja at ch.00-2700m. 2. Chakili H/O Vikku sarker - Folia Bazar road at ch. 00-1900m. | 1.Mst. Fatema Begum & Mst.Rausan Ara 2. Rozina & Mst.salina | 0.00 0.00 | 2700 1900 | 4.6 | 0 | 2374181.13 | 0 | 2374181.13 | 2282181.12 | 0 | 2282181.12 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 128350 | 0 | 128350 | 0 | 0 | 0 | 128350 | 5.624% | Work on going,
117 | 2019-20 | Gaibandha | Fulchori | Maintenance-LCS | PRO/GAI/SAG/RMP/19-20/ MW-117 | 132213003 132213011 132214050 132215025 132215037 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Erandabari U.P H/Q-Algarchar bazar at ch.1170-2250m. 2. Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S at ch.00-2500m. 3. Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram at ch.1170-2000m. 4. Pachim Khatiamary H/O Jalal Member-Gucha gram at ch.00-1000m. 5 Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary at ch.00-950m. | 1. Mst. Diljan Begum & Mst. Forida Begum 2. Mst. Rajina & Mst. Kulsum 3. Mst. Balia Khatun & Mst. Anna Khatun 4. Mst. Amena Begum & Mst. Azima Khatun 5. Mst. Foyzan & Mst. Rasheda Begum | 1170 0.00 1170 0.00 0.00 | 2250 2500 2000 1000 950 | 6.36 | 0 | 3210146.42 | 0 | 3210146.42 | 2929878.56 | 0 | 2929878.56 | 0 | 0 | 0 | 2020-09-15 | 0 | 2022-09-14 | 0 | 0 | 10% | 175350 | 0 | 175350 | 0 | 0 | 0 | 175350 | 5.985% | Work on going,
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 5 |  | 23.56 | 0 | 11882105.62 | 0 | 11882105.62 | 11257837.74 | 0 | 11257837.74 | 0 | 0 | [6 empty] | 10% | 652950 | 0 | 652950 | 0 | 0 | 0 | 652950 | 5.8%
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 9 | 7 | 15.944 | 37 | 138365053.28 | 7987082.47 | 146352135.75 | 102897838.214 | 5518319.26 | 108416157.474 | 0 | 75.21% | 44253339.59 | 9073061.41 | 53326401 | 7559928.77 | 1513101.23 | 9073030 | 62399431 | 57.56%
Village-BC |  | 5 | 5 | 9.513 | 39.3 | 84759283.81 | 6279414.53 | 91038698.34 | 86890809.18 | 3800176.18 | 90690985.36 | 0 | 98.73% | 52692366 | 10345756 | 63038122 | 8656424 | 1689332 | 10345756 | 73383878 | 80.92%
Maintenance-LCS |  | 5 | 5 | 23.56 | 0 | 11882105.62 | 0 | 11882105.62 | 11257837.74 | 0 | 11257837.74 | 0 | 10% | 652950 | 0 | 652950 | 0 | 0 | 0 | 652950 | 5.8%
| Total: | 19 | 17 | 49.017 | 76.3 | 235006442.71 | 14266497 | 249272939.71 | 201046485.134 | 9318495.44 | 210364980.574 | 0 | 81.86% | 97598655.59 | 19418817.41 | 117017473 | 16216352.77 | 3202433.23 | 19418786 | 136436259 | 64.86% | 64.86%
Unallocated Packages:
|  | Gaibandha | Saghata | Union Road-BC |  | 132883015 | Bhangamore bazar-school bazar- Padumshahor UP
|  | Gaibandha | Fulchori | Union Road-BC |  | 132213003 | Erandabari U.P H/Q-Algarchar bazar
|  | Gaibandha | Fulchori | Union Road-BC |  | 132213011 | Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823004 | Bhatgram U.P office-Jamalpur Bazar
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823009 | Naldanga G.C.-Ramzibon U.P.office.
|  | Gaibandha | Shadullapur | Union Road-BC |  | 132823015 | Dholvanga-Mohipur Bazar
|  | Gaibandha | Sadar | Village Road-BC |  | 132244025 | Jugir ghat-Badsharghat Road.
|  | Gaibandha | Sadar | Village Road-BC |  | 132245056 | Salam bazar- Balayata bazar via Mouza malibari Edghah
|  | Gaibandha | Saghata | Village Road-BC |  | 132884061 | Trimohoni Khayaghat-Ullasonatola bazar Rd.
|  | Gaibandha | Saghata | Village Road-BC |  | 132884024 | Durgapur Sazahan Ali Govt. primary School - Pass Durgapur Govt. Primary School
|  | Gaibandha | Saghata | Village Road-BC |  | 132884038 | Boliarber GPS - Kamalerpara- Falia Pucca road
|  | Gaibandha | Sundargonj | Village Road-BC |  | 132914077 | Shaker Bazar-Wapda Embankment via Baraikandi road
|  | Gaibandha | Saghata | Village Road-HBB |  | 132885022 | Dighal Kandi- Digholkandi H/O Sonaullah Mirja
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132214036 | Fulchari Kheyaghat-Tengrakandi Road
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132214050 | Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132215025 | Pachim Khatiamary H/O Jalal Member-Gucha gram
|  | Gaibandha | Fulchori | Village Road-HBB |  | 132215037 | Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Ramdakua- Akotar Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Karent Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Mondoler hat
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915057 | Kashem Bazar- Hazari hat
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar- Kagia Char Ahmed Nagar Bazar
|  | Gaibandha | Sundargonj | Village Road-HBB |  | 132915058 | Koshim Bazar-Vati Kapasia Nuton Asraon Bazar
|  | Gaibandha | Fulchori | Large Market |  |  | Purbo Fulchari Bazar
|  | Gaibandha | Fulchori | Large Market |  |  | Sannasirchar Bazar
|  | Gaibandha | Sundargonj | Large Market |  |  | Kashem Bazar
|  | Gaibandha | Sadar | Medium Market |  |  | Balua Hat
|  | Gaibandha | Sadar | Medium Market |  |  | Puraton Badiakhali Hat
|  | Gaibandha | Sadar | Medium Market |  |  | Lenga Bazar Hat
|  | Gaibandha | Saghata | Medium Market |  |  | Ullah Sonatola Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Bhangamore
|  | Gaibandha | Saghata | Medium Market |  |  | Falia Bottola Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Ullah Bazar
|  | Gaibandha | Saghata | Medium Market |  |  | Dhakin Digholkandi
|  | Gaibandha | Saghata | Medium Market |  |  | Nayabondar Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Khatiamary Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Taltola Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Kayerhaat
|  | Gaibandha | Fulchori | Medium Market |  |  | Daluabari Haat
|  | Gaibandha | Fulchori | Medium Market |  |  | Jigabari Haat
|  | Gaibandha | Fulchori | Medium Market |  |  | Algharchar Bazar
|  | Gaibandha | Fulchori | Medium Market |  |  | Jhanjhor Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Naldanga kachari Bazar
|  | Gaibandha | Sundargonj | Medium Market |  |  | Belka Bazar
|  | Gaibandha | Sundargonj | Medium Market |  |  | Charoker Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Domer Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Moyej Mear Hat
|  | Gaibandha | Sundargonj | Medium Market |  |  | Jamaler Hat
|  | Gaibandha | Shadullapur | Medium Market |  |  | Boxigonj Bazar
|  | Gaibandha | Shadullapur | Medium Market |  |  | Kantanagar bazar
|  | Gaibandha | Saghata | Small Market |  |  | Futani Bazar
|  | Gaibandha | Fulchori | Small Market |  |  | Moshamari Bazar
|  | Gaibandha | Fulchori | Small Market |  |  | Katlamari Bazar
|  | Gaibandha | Sundargonj | Small Market |  |  | Shokher Hat

## Kurigram
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Kurigram
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+34 | 36 | 37
Union Road BC
| 2018-19 | Kurigram | Chilmari | Union Road-BC | PRO/KUR/CHI/UNR/18-19/W-21 | 149093002 | Improvement of Bituminous Carpating Road On Thanahat up office – Balabarihat via Kajaldanga hat at Ch.2985m-3455m. Under Chilmari Upazila, District Kurigram. | Nakshi Mobile Palace,Krishnopur, Kurigram | 2985 | 3455 | 0.47 | 0 | 4159071 | 0 | 4159071 | 3951117.45 | 0 | 3951117.45 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-25 | 0 | 2020-05-14 | 100% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 75.44% | All Item Completed.Final Bill Sent to H/Q
80 | 2019-20 | Kurigram | Nageswari | Union Road-BC | PRO/KUR/NAG/UNR/19-20/W-80 | 149613039 | Improvement of Ramkhana UP office to Sealkanda bazar Road at Ch: 1000m-2776m including Construction of 1Nos 1x2.00mx2.00m RCC. Box Culvert at Ch: 1727m and 4Nos 1x0.6250mx 0.625m m RCC. Box Culvert at Ch: 1080m,1390m,2022m & 2118.00m Under Upazila: Nageswari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 1000 | 2776 | 1.776 | 6.5 | 16305564 | 1149239 | 17454803 | 14035591.24 | 942642.23 | 14978233.472 | 0 | 0 | 2020-02-26 | 2020-03-15 | 2020-05-23 | 2021-05-22 | 0 | 2021-03-19 | 35% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Sub-base complete
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 2 |  | 2.246 | 6.5 | 20464635 | 1149239 | 21613874 | 17986708.69 | 942642.23 | 18929350.922 | 0 | 0 | [6 empty] | 48.57% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 15.75%
Village Road-BC
| 2018-19 | Kurigram | Chilmari | Village Road-BC | PRO/KUR/CHI/VR/18-19/W-20 | 149095036 | Improvement of Bituminous Carpating Road on Kutigram Madrasha Pacca Rd – Kachkol CARE Bridge via Eblus Chairman house Road Ch. 00m-790m. & Link Road 0.00-230.0m. Under Chilmari Upazila, District Kurigram. | M/S. S. T Enterprise, Nageswari, Kurigram | 0 0 | 790 230 | 1.02 | 0 | 7735062 | 0 | 7735062 | 7348308.9 | 0 | 7348308.9 | 0 | 0 | 2019-05-05 | 2019-05-26 | 2019-06-03 | 25-02-2020 30-05-2021 | 0 | 19-05-2020 30-05-2020 | 65% | 2668854 | 0 | 2668854 | 0 | 0 | 0 | 2668854 | 36.32% | Sand filling , Sub-base & WBM completed.
| 2018-19 | Kurigram | Sadar | Village Road-BC | PRO/KUR/KUR-S/VR/18-19/W-22 | 149525128 | Improvement of Bituminous Carpating Road on Paramali Dr. Sahabuddin Tepoti to Rajarhat Ch.000-1930m & at Ch.1585 Link Road Ch.0.00-264.0m including Contruction of 04 Nos. (0.625mx0.600m) U-Drain on Paramali Dr. Sahabuddin Tepoti to Rajarhat Road at Ch.90m,730m,1250m & 1770m . Kurigram Sader Upzila,District Kurigram | Md. Mahmud Alam Liton, Fulbari Pourashova,Fulbari | 0 0 | 1930 264 | 2.19 | 2.5 | 16229100 | 514550.2 | 16743650.2 | 16241461.24 | 501008.14 | 16742469.38 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 0 | 2021-05-27 | 65% | 9164025 | 0 | 9164025 | 0 | 0 | 0 | 9164025 | 54.74% | Ch. 0.00-2.190km sand filling Sub-base & WBM completed,3 Nos U-Drain completed. Turffing Work Running. [ Time Extension Under Process ]
| 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BUR/VR/18-19/W-24 | 149064036 | Improvement of Bituminous Carpating Road on Milon Bazar – Baladfia Bazar (End point H/O Nasir Uddin) at Ch.00-2000.0m. including Contruction of 03 Nos. 0.625mx0.600m U-Drain at Ch.1003m, 1685m Under Bhurungamari Upazila, District Kurigram., | M/S. Hamid Traders, Hospitalpara, Kurigram Sadar, Kurigram | 0 | 2000 | 2 | 1.88 | 14468747 | 275159 | 14743906 | 13429170.35 | 260283.77 | 13689454.12 | 0 | 0 | 2019-05-15 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 0 | 2020-11-20 | 100% | 9370863 | 233117 | 9603980 | 0 | 0 | 0 | 9603980 | 70.16% | All Item Completed.Final Bill Sent to H/Q
| 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KURI/NAW/VR/18-19/W-25 | 149615083 | Improvement of Bituminous Carpating Wabda Bazar – Berubari Abashon Road at Ch.00.0-1200.00m Under Nageswari Upazila, District Kurigram. ` | M/S. Fahim Traders, RK Road, Sadar Kurigram | 0 | 1200 | 1.2 | 0 | 9114248.72 | 0 | 9114248.72 | 8658536.55 | 0 | 8658536.55 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 | 0 | 2020-05-07 | 100% | 6573373 | 0 | 6573373 | 0 | 0 | 0 | 6573373 | 75.92% | All Item Completed.Final Bill Sent to H/Q
| 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KURI/RJP/VR/18-19/W-26 | 149084053 | Improvement of Bituminous Carpating Road on By Tangalipara- Pakhiura road at Ch.0.00-2000.0m.Under Rajibpur Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 0 | 2000 | 2 | 0 | 15018035 | 0 | 15018035 | 14211257.3 | 0 | 14211257.3 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-07 | 2020-05-30 | 0 | 29-05-2020 28-02-2021 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | No work at site, XEN Issued letter to Contractor
| 2018-19 | Kurigram | Ulipur | Village Road-BC | PRO/KURI/ULP/VR/18-19/W-27 | 149944098 | Improvement of Bituminous Carpating Road on Ramramhat Mosque – Hatiar Mela WAPDA Embankment via Kokire para road at Ch.0.00-2080.0m including Contruction Of 2 Nos.0.600mx0.625m U-Drain at Ch.??, ??m. and Contruction Of 1 Nos.Cross Drainge Structure at Ch.1485.0m. Under Ulipur Upzila, District Kurigram. | Milu Nowroj Abu Bakar, College Road, Kurigram Sadar, Kurigram | 0 | 2080 | 2.08 | 4.2 | 17817664.39 | 1159563.14 | 18977227.53 | 15698506.57 | 1143205.21 | 16841711.78 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 0 | 28-05-2020 31-02-2021 | 55% | 8981947 | 0 | 8981947 | 0 | 0 | 0 | 8981947 | 53.33% | Contractor wil start reamining work soon.Sand filling & Sub-base Up to 1950m, WMB 1950m Running 3 Nos U-Drain/1.Nos Cross Drain Completed,Palisading work 400m Completed . [ Time Extension Under Process ]
| 2018-19 | Kurigram | Fulbari | Village Road-BC | PRO/KURI/RAJ/VR/18-19/W-28 | 149775079 | Improvement of Bituminous Carpating Road on Mondir Mouja at H/O Nousher Ali- Khamar GPS Road at Ch.0.00m-2725.0m under Fulbari Upazila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2725 | 2.725 | 0 | 21122799.06 | 0 | 21122799.06 | 18424739.36 | 0 | 18424739.36 | 0 | 0 | 2019-05-20 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 0 | 21-05-2020 21-11-2020 | 40% | 5779701 | 0 | 5779701 | 0 | 0 | 0 | 5779701 | 31.37% | WBM complete. [ Time Extension Under Process ]
| 2018-19 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/18-19/W-39 | 149185051 | Improvement of Bituminous Carpating Road On Bokultola Bazar-H/O Nobiul Road at Ch. 00m – 1070.00m including Construction of U-drain (600mm X 0.625mm) at Ch.131m. Under Fulbari Upazila, District Kurigram. | M/S. Milon Traders, Nilkhanto, Khalilgonj Bazar, Kurigram Sadar, Kurigram | 0 | 1070 | 1.07 | 0.6 | 8949548.12 | 100532 | 9050080.12 | 8502070.714 | 95505.4 | 8597576.114 | 0 | 0 | 2019-05-05 | 2019-05-30 | 2019-06-06 | 2020-02-28 | 0 | 2020-02-13 | 100% | 5143774 | 0 | 5143774 | 0 | 0 | 0 | 5143774 | 59.83% | All Item Completed.
| 2018-19 | Kurigram | Nageswari | Village Road-BC | PRO/KUR/NAG/VR/18-19/W-40 | 149614060 | Improvement of Bituminous Carpating Road on Kherbari More UZR-Boitulah More via Taleberhat Road at Ch.1000-4070m including Construction Of 9 Nos. 0.600mx0.625mU-Drain at.Ch.1400m, 1780m, 1940m, 2220m, 3300m, 2244m, 3550m, 3680m & 3840m,Under Nageswari Upazila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 1000 | 4070 | 3.07 | 5.4 | 24836379.47 | 1048387.17 | 25884766.64 | 21156136.31 | 890699.56 | 22046835.87 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 0 | 10-09-2020 31-03-2021 | 90% | 1057593 | 890699 | 1948292 | 0 | 0 | 0 | 1948292 | 8.837% | BC work complete [ Time Extension Procedure Under Process ]
| 2018-19 | Kurigram | Rajibpur | Village Road-BC | PRO/KUR/RAJI/VR/18-19/W-41 | 149084053 | Improvement of Bituminous Carpating Road on Tangalipara- Pakhiura road at Ch.2000-4000m.Under Rajibpur Upzila, District Kurigram. | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 2000 | 4000 | 2 | 0 | 10723064 | 0 | 10723064 | 9828649 | 0 | 9828649 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 0 | 10-09-2020 31-03-2021 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contractor will start remaining work soon.Ch. 2.000-4.000km sand filling completed. AS Layer Running. [ Time Extension Procedure Under Process ]
| 2018-19 | Kurigram | Bhurungamari | Village Road-BC | PRO/KUR/BHU/VR/18-19/W-42 | 149064003 | Improvement of Bituminous Carpating Road on R&H Trimohoni – Shingjhar Road at Ch.325.00-2685.00m. including Construction Of 1 Nos. (4x4.00x4.00) m Cross Drianges Structure at Ch 1702.00m. and Construction Of 1 Nos. (2.00x2.00) m Cross Drianges Structure and Construction Of 14 Nos.0.600mx0.625m U-Drain at Ch.636m,714m,935m,960m,1051m,1201m,1355m,1550m,2003m,2166m,2230m,2586m,2767m&3330m.Under Bhurungamari Upzila, District Kurigram. | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 325 | 2685 | 2.36 | 14.9 | 16522104 | 6439018 | 22961122 | 14962086.19 | 6239684.88 | 21201771.07 | 0 | 0 | 2019-05-27 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 0 | 29-05-2020 28-02-2021 | 50% | 5749291 | 0 | 5749291 | 0 | 0 | 0 | 5749291 | 27.12% | Stopped work due water in both side of road
| 2018-19 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/18-19/W-43 | 149775095 | (C): Improvement of Bituminous Carpating Road on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.0.00m-2000.0m Under Rajarhat Upzila, District Kurigram. including (F): Construction Of 2 Nos.0.600mx0.625m U-Drain on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.1667m, &1924m. under Rajarhat Upzila, District Kurigram. | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 0 | 2000 | 2 | 1.2 | 16290727 | 186745 | 16477472 | 14742059.38 | 168353.11 | 14910412.49 | 0 | 0 | 2019-05-27 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 0 | 2020-05-28 | 100% | 7373958 | 0 | 7373958 | 0 | 0 | 0 | 7373958 | 49.46% | All Item has been Completed. Final bill sent to HQ
65 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W-65 | 149774012 | Improvement of Bituminus carpeting road Chandamari-Shyom Narayan at Biddyananda road at Ch: 1000m-2235m including 1 Nos(0.625X0.625)m U-Drain under Upazila: Rajarhat, District: Lalmonirhat. | M/S Khairul Enterprise | 1000 | 2235 | 1.235 | 1 | 6826143 | 101493 | 6927636 | 5907689.72 | 101493 | 6009182.72 | 0 | 0 | 2020-11-02 | 2020-02-17 | 2020-02-24 | 2020-08-23 | 0 | 2020-02-16 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Date over, no work at all
81 | 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 81 | 149185050 | Improvement of Uttar Kashipur Shenpara – Kashem Bazar Via Ghugurhat Road at Ch: 00m-2500m including Construction of 3Nos 1x0.600mx0.600m m RCC. Box Culvert at at Ch: 90m,270m,1437m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2500 | 2.5 | 3 | 21253035 | 317903 | 21570938 | 18298929.65 | 317903 | 18616832.65 | 0 | 0 | 2020-03-19 | 2020-03-29 | 2020-05-15 | 2021-05-14 | 0 | 2021-03-21 | 25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Box Cutting Completed,Sand Filling Running.
82 | 2019-20 | Kurigram | Fulbari | Village Road-BC | PRO/KUR/FUL/VR/19-20/W- 82 | 149185060 | Improvement of H/O Shajamal – Bokultola Bazar Via Abder Tale House Road at Ch: 00m-545.00m including Construction of 2Nos U-Drain at Ch: 124m,375m Under Upazila: Fulbari, District:Kurigram. | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 0 | 545 | 0.545 | 2 | 4620972 | 211935 | 4832907 | 4027967.48 | 211935 | 4239902.48 | 0 | 0 | 2020-02-26 | 2020-03-16 | 2020-05-02 | 2020-11-02 | 0 | 2020-09-06 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Box Cutting Completed,Sand Filling under running, Palisading and u-drain complete
| 2019-20 | Kurigram | Rowmari | Village Road-BC | PRO/KUR/ROW/VR/19-20/W-89 | 149794017 | Improvement of Boalmari Modho Mosque –Changtapara Via Danguapara Road at Ch: 1000m-3000m Under Upazila:Rowmari, District:Kurigram | M/S Hamid Traders | 1000 | 3000 | 2 | 0 | 17170453 | 0 | 17170453 | 15980384.43 | 0 | 15980384.43 | 0 | 0 | 2020-02-26 | 2020-03-16 | 2020-05-23 | 2021-05-22 | 0 | 2021-05-14 | 30% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work stopped now,Sand filling running
105 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W- 105 | 149774008 | Improvement of Rajmallir hat-Shakoa GPS road Ch: 00 m-1985.00m including Construction of 2x3.00mx3.00m Rcc.Box Culvert and 2 Nos0.925x0.925m U-Drain at Ch: 00 m-1985.00m Under Upazila: Razarhat, District:Kurigram. | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 0 | 1985 | 1.985 | 9.8 | 17188824 | 2342534 | 19531358 | 16512938.6 | 0 | 16512938.6 | 0 | 0 | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 | 0 | 2021-04-05 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contractor mobilization on going
104 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W- 104 | 149775066 | Improvement of WAPDA Emb.at Chaturvuj Mouza-Makli Mouja at Brahmmon para road Ch: 00m-2000m Under Upazila: Razarhat, District:Kurigram. | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 0 | 2000 | 2 | 0 | 18457590 | 0 | 18457590 | 15528767.62 | 0 | 15528767.62 | 0 | 0 | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 | 0 | 2021-04-05 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contractor mobilization on going
103 | 2019-20 | Kurigram | Rajarhat | Village Road-BC | PRO/KUR/RAJA/VR/19-20/W-103 | 149774067 | Improvement of Nazimkhan -Forkerhat at Boroghat Madrasha More-Bottalahat road Ch: 00m-1000m including Construction of 3Nos 1x0.6250mx 0.625m m U-Drain at Ch: 630m,840m &982m Under Upazila: Razarhat, District:Kurigram | Sheetal Construction,R.K Road,Khalilgong,Sadar, Kurigram | 0 | 1000 | 1 | 3 | 9000125 | 312627 | 9312752 | 7905979.71 | 0 | 7905979.71 | 0 | 0 | 2020-06-26 | 2020-07-20 | 2020-07-27 | 2021-07-26 | 0 | 2021-04-05 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contractor mobilization on going
106 | 2019-20 | Kurigram | Rowmari | Village Road-BC | PRO/KUR/ROW/VR/19-20/W- 106 | 149795038 | Improvement of Shaydabad to Shiber Dhangi FCD road Ch: 1000m-2000m Under Upazila: Rowmari, District:Kurigram. | M/s K.M Abu Bakar, Collage Road,Kurigram Sadar,Kurigram | 1000 | 2000 | 1 | 0 | 7923918 | 0 | 7923918 | 6881841.14 | 0 | 6881841.14 | 0 | 0 | 2020-06-26 | 2020-07-20 | 2020-09-01 | 2021-02-28 | 0 | 2021-03-28 | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WBM Complete
| 2020-21 | Kurigram | Rajarhat | Village Road-BC | PRO/KURI/RAJA/VR/ 19-20/W-130 | 0 | Improvement of Bazar Gate of Nazimkhan Union- Dangghat Kali Mondir via Ratiram Pathanpara GPS Road. road Ch: 0.0m-1580m including Construction of 1Nos 0.625m x 0.625m U-Drain at Ch: 427 m Under Upazila: Rajarhat, District:Kurigram. | 0 | 0 | 1580 | 1.58 | 1 | 13888297 | 101493 | 13989790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Evaluation on going
|  |  |  | Total: |  | NOS Est. Packages: | 21 | NOS Cont. Signed: | 20 |  | 37.56 | 50.48 | 295156835.76 | 13111939.51 | 308268775.27 | 254247480.214 | 9930071.07 | 264177551.284 | 0 | 0 | [6 empty] | 48.05% | 61863379 | 1123816 | 62987195 | 0 | 0 | 0 | 62987195 | 23.84%
Village Road HBB
| 2018-19 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/HBB/18-19/W-23 | 149064016 | Improvement of Bituminous Carpating Road on HBB from Pagla hat Bazar –Shangkose River Ghat at Ch.00-1390.0m. Under Bhurungamari Upazila, District Kurigram. | M/S. Akram Traders, Porchim Nageswari, Kurigram | 0 | 1390 | 1.39 | 0 | 7388648.15 | 0 | 7388648.15 | 7019215.6 | 0 | 7019215.6 | 0 | 0 | 2019-05-05 | 2019-05-28 | 2019-06-04 | 2020-02-27 | 0 | 2022-05-26 | 100% | 4290110 | 0 | 4290110 | 0 | 0 | 0 | 4290110 | 61.12% | All Item Completed.Final Bill Sent to H/Q
| 2019-20 | Kurigram | Bhurungamari | Village Road-HBB | PRO/KUR/BUR/VR/19-20/W- 98 | 149064029 | Improvement of Dhaldanga Bazar-Shilkhuri Kheya ghat road (HBB) Ch: 1200m-2250m including Construction of 1x2.00mx 2.00m RCC. Box Culvert on Ch: 1540m under Upazila:Bhurungamari, District:Kurigram. | M/S. Belal Construction,Horiswor Kaloea,Khalilgonj,Kurigram sadar,Kurigram. | 1200 | 2250 | 1.05 | 2.5 | 5160645 | 758362 | 5919007 | 5172960.88 | 0 | 5172960.88 | 0 | 0 | 2020-12-04 | 2020-04-21 | 2020-05-15 | 2021-09-14 | 0 | 2021-09-05 | 85% | 3000000 | 0 | 3000000 | 0 | 0 | 0 | 3000000 | 57.99% | HBB completed. Turfing on going.
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 2 |  | 2.44 | 2.5 | 12549293.15 | 758362 | 13307655.15 | 12192176.48 | 0 | 12192176.48 | 0 | 0 | [6 empty] | 93.64% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 59.79%
Rehabilitation of Road
66 | 2019-20 | Kurigram | Rajarhat | Rehabilitation-Village Road | PRO/KUR/RAJA/VR/19-20/RW-66 | 149774012 | Rehabilitation of Chandamari-Shyom Narayan at Biddyananda road at Ch:00m-1000m under Upazila: Rajarhat, District: Lalmonirhat. | M/S Khairul Enterprise | 0 | 1000 | 1 | 0 | 2479051 | 0 | 2479051 | 2030770.61 | 0 | 2030770.61 | 0 | 0 | 2020-11-02 | 2020-02-17 | 2020-02-24 | 2020-08-23 | 0 | 2020-02-16 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Date over, no work at all
| 2019-20 | Kurigram | Chilmari | Rehabilitation-Union Road | PRO/KUR/CHIL/UNR/19-20/RW-79 | 149093002 | Rehabilitation of Thanahat Up Office to Balabarihat via Kazaldanga Hat Road at Ch: 00m-1040m including Construction of 1Nos 1x3.00mx2.50mm RCC. Box Culvert at Ch: 15m and 1Nos 1x0.625mx0.600mm U-Drain at Ch: 760m and 1Nos 1x2.50mx2.00m m RCC. Box Culvert at Ch: 820m under Upazila:Chilmari, District:Kurigram | Md.Abul Hossain, Shaheb Bazar,Groramara,Rajshahi. | 0 | 1040 | 1.04 | 7.5 | 4492492 | 1915132 | 6407624 | 3187498.28 | 1915132 | 5102630.28 | 0 | 0 | 2020-07-04 | 2020-04-21 | 2020-05-15 | 2021-02-14 | 0 | 2021-04-19 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work will start soon
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 2 |  | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Road Maintenance by LCS
112 | 2019-20 | Kurigram | Ulipur | Maintenance-LCS | PRO/KUR/ULI/RMP/19-20/MW-112 | 149944076 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Mollahat-Panchim side of Mogholbacha UP simana road at Ulipur Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 4.000Km) | 0 | 0 | 0 | 4 | 0 | 1981199 | 0 | 1981199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Will be dropped
111 | 2019-20 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/ULI/RMP/19-20/MW-111 | 149525026 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Panchgachi Bazer-Nayani Para Sarak at Kurigram Sadar Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 1.650Km) | Beauti Begum / Santona Rani | 0 | 0 | 1.65 | 0 | 1114033 | 0 | 1114033 | 1114033 | 0 | 1114033 | 0 | 0 | 0 | 2020-07-27 | 2020-09-01 | 2022-08-31 | 0 | 0 | 8% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Maintenance work running
| 2020-21 | Kurigram | Sadar | Maintenance-LCS | PRO/KUR/KUR_S/RMP/19-20/ MW-122 | 149525029 | i)Kawnia Ghat-Kaggipara G.P. School | Mst Rashada Bebum / Mst Shanila Begum | 1500 | 4500 | 3 | 0 | 1311672.96 | 0 | 1311672.96 | 1311672.96 | 0 | 1311672.96 | 0 | 0 | 0 | 2020-07-27 | 2020-09-01 | 2022-08-31 | 0 | 0 | 8% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Maintenance work running
| 2020-21 | Kurigram | Rajarhat | Maintenance-LCS | PRO/KUR/RAJA/RMP/19-20/ MW-123 | 149775054 149774065 | i)Amtoli Bazar to Sakhoa GPS road. ii)Dino Bazar rail line to Amtail Bazar via Narayam Nember House. | i) Najma Begum / Sumi Begum ii) Anita Rani / Rasida Begum | 0 0 | 1800 1000 | 2.8 | 0 | 1587940.81 | 0 | 1587940.81 | 1587940.81 | 0 | 1587940.81 | 0 | 0 | 0 | 2020-08-09 | 2020-09-01 | 2022-08-31 | 0 | 0 | 8% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Maintenance work running
| 2020-21 | Kurigram | Rajibpur | Maintenance-LCS | PRO/KUR/RAJIRMP/19-20/ MW-124 | 149084006 | i) Boraidangi Collage Road. | Mrs. Joynob / Mrs. Lutfa | 0 | 0.825 | 0.825 | 0 | 713992.18 | 0 | 713992.18 | 713992.18 | 0 | 713992.18 | 0 | 0 | 0 | 2020-10-01 | 2020-11-01 | 2022-10-31 | 0 | 0 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Maintenance work running
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 4 |  | 12.275 | 0 | 6708837.95 | 0 | 6708837.95 | 4727638.95 | 0 | 4727638.95 | 0 | 0 | [6 empty] | 7.547% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Medium Market
61 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-61 | 0 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Gouribala and Bimala Rani | 0 | 0 | 0 | 0 | 0 | 0 | 2577497 | 0 | 0 | 2577497 | 0 | 0 | 0 | 2019-12-17 | 2019-12-29 | 2020-12-28 | 0 | 0 | 40% | 800000 | 0 | 800000 | 0 | 0 | 0 | 800000 | 31.04% | Male Toilet : ( Septic Tank & Soak Well) on going . Female : base On Going.
62 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-62 | 0 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Sagorika Bala and Anju Begum | 0 | 0 | 0 | 0 | 0 | 0 | 2579493 | 0 | 0 | 2579493 | 0 | 0 | 0 | 2019-12-17 | 2019-12-29 | 2020-12-28 | 0 | 0 | 60% | 800000 | 0 | 800000 | 0 | 0 | 0 | 800000 | 31.01% | 1 Nos Multipurpose Shed : Beam On Going. 1 Nos Multipurpose Shed : Column Completed. Internal CC Road On Goning.
87 | 2019-20 | Kurigram | Ulipur | Medium Market | PRO/KURI/ULI/MM/2019-20/W-87 | 0 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram | Joymala begum and Beuty Begum | 0 | 0 | 0 | 0 | 0 | 0 | 534466 | 0 | 0 | 534466 | 0 | 0 | 0 | 2020-01-12 | 2020-01-19 | 2020-07-18 | 0 | 0 | 90% | 200000 | 0 | 200000 | 0 | 0 | 0 | 200000 | 37.42% | Ground Raising : Earth Work On Going.
153 | 2020-21 | Kurigram | Bhurungamari | Medium Market | PRO/KUR/BUR/MM/20-21/W-153 | 0 | Construction of Boldia Hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5522607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on 22-11-20
155 | 2020-21 | Kurigram | Fulbari | Medium Market | PRO/KUR/FUL/MM/20-21/W- 155 | 0 | Construction of Shiberhat Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4605783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved in December-20 | 0 | 0 | 41.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 2020-21 | Kurigram | Fulbari | Medium Market | PRO/KUR/FUL/MM/20-21/W- 156 | 0 | Construction of Ghogurhat Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5652007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved in December-20
|  |  |  | Total: |  | NOS Est. Packages: | 6 | NOS Cont. Signed: | 3 |  | 0 | 0 | 0 | 0 | 21471853 | 0 | 0 | 5691456 | 0 | 0 | [6 empty] | 53.76% | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 1800000 | 31.63%
Large market
110 | 2019-20 | Kurigram | Sadar | Large Market | PRO/KURI/SAD/LM/19-20/W-110 | 0 | Construction of Jatiner Hat Upazila: Sadar, District: Kurigram (03 nos LCS group) | (LCS-01) Shamoli Rani /Mst.Banecha Begum (LCS-02) Mst. Lubna Begum / Kalpona Begum (LCS-03) Arifa Khatun / Srimoti Sumi Muhonto | 0 | 0 | 0 | 0 | 0 | 0 | 9805786 | 0 | 0 | 9805786 | 0 | 0 | 0 | 2020-06-30 | 0 | 2021-05-31 | 0 | 0 | 0% | 1600000 | 0 | 1600000 | 0 | 0 | 0 | 1600000 | 16.32% | Contact Signed.
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 9805786 | 0 | 0 | 9805786 | 0 | 0 | [6 empty] | 0% | 1600000 | 0 | 1600000 | 0 | 0 | 0 | 1600000 | 16.32%
Maintenance-Office Building
1 | 2019-20 | Kurigram | Sadar | Maintenance-Office | PRO/KUR/MAINT/19-20/W-1 | 0 | Maintenance work of LGED Office Building, Dist: Kurigram | M/S Afiya Traders, Krishnopur, Chorupara, Sadar, Kurigram | 0 | 0 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 0 | 0 | 2019-11-11 | 2019-11-11 | 2019-11-28 | 0 | 0 | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100% | Final bill paid
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 0 | [6 empty] | 100% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 100%
Small market
154 | 2020-21 | Kurigram | Bhurungamari | Small Market | PRO/KUR/BUR/SM/20-21/W-154 | 0 | Construction of Muktijoddha Hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on 22-11-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 0 |  | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 2 | 2 | 2.246 | 6.5 | 20464635 | 1149239 | 21613874 | 17986708.69 | 942642.23 | 18929350.922 | 0 | 48.57% | 2980808 | 0 | 2980808 | 0 | 0 | 0 | 2980808 | 15.75%
Village-BC |  | 21 | 20 | 37.56 | 50.48 | 295156835.76 | 13111939.51 | 308268775.27 | 254247480.214 | 9930071.07 | 264177551.284 | 0 | 48.05% | 61863379 | 1123816 | 62987195 | 0 | 0 | 0 | 62987195 | 23.84%
Village-HBB |  | 2 | 2 | 2.44 | 2.5 | 12549293.15 | 758362 | 13307655.15 | 12192176.48 | 0 | 12192176.48 | 0 | 93.64% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 59.79%
Rehabilitation |  | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance |  | 5 | 4 | 12.275 | 0 | 6708837.95 | 0 | 6708837.95 | 4727638.95 | 0 | 4727638.95 | 0 | 7.547% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Small market |  | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Medium market |  | 6 | 3 | 0 | 0 | 0 | 0 | 21471853 | 0 | 0 | 5691456 | 0 | 53.76% | 1800000 | 0 | 1800000 | 0 | 0 | 0 | 1800000 | 31.63%
Large market |  | 1 | 1 | 0 | 0 | 0 | 0 | 9805786 | 0 | 0 | 9805786 | 0 | 0% | 160000000% | 0% | 160000000% | 0% | 0% | 0% | 160000000% | 16.32%
Office Maintenance |  | 1 | 1 | 0 | 0 | 0 | 0 | 874612.86 | 0 | 0 | 874612.86 | 0 | 100% | 0% | 0% | 75309500% | 0% | 0% | 12151786% | 87461286% | 100%
| Total: | 41 | 35 | 56.561 | 66.98 | 341851144.86 | 16934672.51 | 394990027.23 | 294372273.224 | 12787845.3 | 323531973.386 | 0 | 46.93% | 72134297 | 1123816 | 73258113 | 0 | 0 | 0 | 73258113 | 22.64%
Unallocated Packages
|  | Kurigram | Nageswari | Union Road-BC |  | 149613039 | Ramkhana UP office to Sealkanda bazar
|  | Kurigram | Nageswari | Union Road-BC |  | 149613041 | Hasnabad UP Office - Newashi GC.
|  | Kurigram | Rajarhat | Union Road-BC |  | 149773010 | Burirhat-Gharialdanga UP office.
|  | Kurigram | Sadar | Village Road-BC |  | 149525029 | Kawnia Ghat-Kaggipara G.P. School
|  | Kurigram | Sadar | Village Road-BC |  | 149524014 | Nowbash BWDB Emb.-Nayerhat Emb.
|  | Kurigram | Sadar | Village Road-BC |  | 149525043 | Shop of Abul at BWDB Embank.-Velurbazar
|  | Kurigram | Sadar | Village Road-BC |  | 149525031 | Char Boraibari Rd
|  | Kurigram | Fulbari | Village Road-BC |  | 149185057 | Boroloi Bazar-Amsa Bazar
|  | Kurigram | Fulbari | Village Road-BC |  | 149185050 | Uttar Kasipur Sen para-Kashem Bazar via Ghogur hat
|  | Kurigram | Fulbari | Village Road-BC |  | 149185060 | H/O Shajamal- Bokultolabazar via Abder Tale house
|  | Kurigram | Bhurungamari | Village Road-BC |  | 149064020 | Thanaghat-Shahebganj Border Road
|  | Kurigram | Nageswari | Village Road-BC |  | 149615081 | Baparitary-Horibolarkuti via H/O Nur Islam Master
|  | Kurigram | Nageswari | Village Road-BC |  | 149614028 | Sarker tari UZR to Chanderhat
|  | Kurigram | Nageswari | Village Road-BC |  | 149614012 | Sadar Beparirghat - Momingonj bazar
|  | Kurigram | Rajarhat | Village Road-BC |  | 149774012 | Chandamari-Shyom Narayan at Biddyananda rd.
|  | Kurigram | Rajarhat | Village Road-BC |  | 149774029 | Rajmallihat hat-Nazimkhan UP (Jorsarar hat) via Battalarhat.
|  | Kurigram | Rajarhat | Village Road-BC |  | 149774008 | Rajmallir hat-Shakoa GPS.
|  | Kurigram | Rajarhat | Village Road-BC |  | 149775058 | Ramratan Mouza - Chinai UP gat road
|  | Kurigram | Rajarhat | Village Road-BC |  | 149775066 | WAPDA Embt. At Chaturvuj Mouja-Makli Mouja at Brammonpara
|  | Kurigram | Rajarhat | Village Road-BC |  |  | Nazimkhan- Forker at Boroghat Madrasha More to Boattalar Hat road.
|  | Kurigram | Ulipur | Village Road-BC |  | 149944076 | Mollahat-Panchim side of Mogholbacha UP simana
|  | Kurigram | Ulipur | Village Road-BC |  | 149944136 | Bozra U.P. office-Babur hat
|  | Kurigram | Rowmari | Village Road-BC |  | 149795038 | Shaydabad - Shiber Dhangi FCD
|  | Kurigram | Rowmari | Village Road-BC |  | 149795077 | Saidabad Bazar- west side Pakhiura hat via Komorvangi GPS
|  | Kurigram | Rowmari | Village Road-BC |  | 149794017 | Boalmari modho mosque - Changtapara via Danguapara
|  | Kurigram | Bhurungamari | Village Road-HBB |  | 149064029 | Dhaldanga bazar-Shilkhuri Kheyaghat ( end point South Bot Tola GPS)
|  | Kurigram | Rajarhat | Village Road-HBB |  |  | Bazar Gate of Nazimkhan Union- Dangghat Kali Mondir via Pathanpara GPS.
|  | Kurigram | Rajarhat | Large Market |  |  | Panga
|  | Kurigram | Chilmari | Large Market |  |  | Jorgach Hat
|  | Kurigram | Chilmari | Large Market |  |  | Thana Hat
|  | Kurigram | Chilmari | Large Market |  |  | Fakirar Hat
|  | Kurigram | Ulipur | Large Market |  |  | Sunamgonj Hat
|  | Kurigram | Ulipur | Large Market |  |  | Mollar Hat
|  | Kurigram | Rajibpur | Large Market |  |  | Rajibpur GC
|  | Kurigram | Sadar | Large Market |  |  | Jatiner Hat
|  | Kurigram | Sadar | Large Market |  |  | Panchgachi Hat
|  | Kurigram | Rajarhat | Medium Market |  |  | Burirhat
|  | Kurigram | Rajarhat | Medium Market |  |  | Sharisabari Hat
|  | Kurigram | Rajarhat | Medium Market |  |  | Chandamari Hat
|  | Kurigram | Rajarhat | Medium Market |  |  | Dangrar Hat
|  | Kurigram | Rajarhat | Medium Market |  |  | Chowrahat
|  | Kurigram | Rajarhat | Medium Market |  |  | Rajmallirhat
|  | Kurigram | Chilmari | Medium Market |  |  | karai Barisal
|  | Kurigram | Chilmari | Medium Market |  |  | Kachkol hat
|  | Kurigram | Nageswari | Medium Market |  |  | Chilakhana Hat
|  | Kurigram | Nageswari | Medium Market |  |  | Egaromatha Hat
|  | Kurigram | Nageswari | Medium Market |  |  | Berubari Hat
|  | Kurigram | Nageswari | Medium Market |  |  | Schooler Hat
|  | Kurigram | Nageswari | Medium Market |  |  | Monigonj Bazar
|  | Kurigram | Ulipur | Medium Market |  |  | Hatia Vobesh
|  | Kurigram | Rowmari | Medium Market |  |  | Saydabad Bazar
|  | Kurigram | Rowmari | Medium Market |  |  | Lawbari hat
|  | Kurigram | Rowmari | Medium Market |  |  | Baraikandhi Hat
|  | Kurigram | Fulbari | Medium Market |  |  | Boroloi Bazar
|  | Kurigram | Fulbari | Medium Market |  |  | Shiber Bazar
|  | Kurigram | Fulbari | Medium Market |  |  | Bokultala Bazar
|  | Kurigram | Fulbari | Medium Market |  |  | Ghogurhat Bazar
|  | Kurigram | Sadar | Medium Market |  |  | Sardob RDRS Bazar
|  | Kurigram | Sadar | Medium Market |  |  | Rajarhat Bazar
|  | Kurigram | Sadar | Medium Market |  |  | Hazir Hat
|  | Kurigram | Sadar | Medium Market |  |  | Nayer Hat
|  | Kurigram | Sadar | Medium Market |  |  | Shimultala Wapda Hat
|  | Kurigram | Sadar | Medium Market |  |  | Valur Hat
|  | Kurigram |  | Medium Market |  |  | Char Boraibari Hat
|  | Kurigram | Bhurungamari | Medium Market |  |  | Baldia Bazar
|  | Kurigram | Bhurungamari | Medium Market |  |  | Choudhurir Hat
|  | Kurigram | Rajarhat | Small Market |  |  | Kalirhat
|  | Kurigram | Rajarhat | Small Market |  |  | Fulkhar Chakla
|  | Kurigram | Rajarhat | Small Market |  |  | Amtola Bazar
|  | Kurigram | Rajarhat | Small Market |  |  | Kalirhat Bazar
|  | Kurigram | Rajarhat | Small Market |  |  | Battalar Hat
|  | Kurigram | Nageswari | Small Market |  |  | Taleber Hat
|  | Kurigram | Nageswari | Small Market |  |  | Wapda Hat
|  | Kurigram | Nageswari | Small Market |  |  | Chander Hat
|  | Kurigram | Nageswari | Small Market |  |  | Shialkanda Hat
|  | Kurigram | Nageswari | Small Market |  |  | Daknirpat Hat
|  | Kurigram | Nageswari | Small Market |  |  | Mina Bazar
|  | Kurigram |  | Small Market |  |  | New Annandapur Hat
|  | Kurigram | Sadar | Small Market |  |  | masterer Hat
|  | Kurigram | Bhurungamari | Small Market |  |  | Muktijodha Hat B
Note on N97: DELL: Update after getting Progress

## Nilphamari
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Nilphamari
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Union Road BC
| 2018-19 | Nilphamari | Dimla | Union Road-BC | PRO/NIL/DIM/UNR/18-19/W-44 | 173123002 | Improvement of Bituminous carpeting Road of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164 km Under Dimla Upazila,District Nilphamari including Construction of 1Nos (2.00x2.00)m Cross Drainges Structure .at Ch.2287m and Construction of 2 Nos 7.00m Long.0.625mx0.625m U-Drain on Ch.2785,4011.0m of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164.00km Under Dimla Upazila,District Nilphamari | M/S. Misuk Enterprise, Food Office Road, Nilphamari. | 2255 | 4164 | 1.909 | 3.25 | 16925909.68 | 1073862.5 | 17999772.18 | 16669437.91 | 1057539.337 | 17726977.247 | 0 | 0 | 2019-07-27 | 2019-08-07 | 2019-08-13 | 2020-08-12 | 0 | 2020-08-31 | 90% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 83.65% | BC Completed. Length and Contact amount decresed(length is 1.5 instead on 1.9km).
119 | 2019-20 | Nilphamari | Dimla | Union Road-BC | PRO/NIL/DIM/UNR/19-20/W-119 | 173123014 | Improvement of Bituminous carpeting Road of Naotara U.P Office-Motirbazar Rd. Ch: 950m-3250m including Construction of 1Nos 1x1.50mx 1.50 m U-Drain at Ch. 1159m and 2Nos 1mX0.6250mX 0.60m m U-Drain at Ch. 1389m under Upazila: Dimla, Dist: Nilphamari | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 950 | 3250 | 2.3 | 3 | 19781105 | 936387 | 20717492 | 17782304.61 | 0 | 17782304.61 | 0 | 0 | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work started
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 2 |  | 4.209 | 6.25 | 36707014.68 | 2010249.5 | 38717264.18 | 34451742.52 | 1057539.337 | 35509281.857 | 0 | 0 | [6 empty] | 44.93% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 41.76%
Village Road BC
| 2018-19 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/18-19/W-18 | 173124093 | Improvement of Bituminous carpeting Road on Ullarmore to Rahmangonj Bazar Road Under Gayabari Union at Ch.0.00m-2490m. including Construction of 2 Nos (1.50x1.50)m Box Culvert at Ch.142.00m & 630.0m and Construction of 1 Nos (2x3.00x3.00)m Box Culvert at Ch.197.00 m and Costruction of 1 Nos(1.500x1.00)m and Construction of 1 Nos (2x4.50x4.00) m Box Culvert at Ch.1922.00 m. and Costruction of 3 Nos(0.625x0.600) m U-Drain at Ch.50.0,480.0m&852m.Under Dimla Upazila,District Nilphamari. | JV of SA FE Shahipara, Nilphamari. | 0 | 2490 | 2.49 | 24.63 | 18674476.67 | 6963499.25 | 25637975.92 | 18551554.07 | 6917609.79 | 25469163.86 | 0 | 0 | 2019-06-24 | 2019-06-30 | 2019-07-06 | 05-07-2020 12-08-2020 | 0 | 2020-12-31 | 85% | 15993130 | 2955540 | 18948670 | 989931 | 247482 | 1237413 | 20186083 | 79.26% | BC Complete
| 2018-19 | Nilphamari | Jaldhaka | Village Road-BC | PRO/NIL/JAL/VR/18-19/W-19 | 173365087 | Improvement of Bituminous Carpeting Road on Gabroli RNGPS-Tin Babul house via Rath Bazar Road at Ch 1000.0m-2650.0m including Costruction of 2 Nos (1.00x1.00) Box Culvert at Ch 1450.0m&1720.0m and Costruction of 1 Nos(2.00x2.00)m Box Culvert at Ch 2620.0m Under Jaldhaka Upazila,District Lilphamari. | M/S. Mohsena Enterprise, Monshapara, Nilphamari. | 1000 | 2650 | 1.65 | 4.8 | 13626801.7 | 1172872 | 14799673.7 | 12495688.82 | 1075512.29 | 13571201.11 | 0 | 0 | 2019-06-24 | 2019-07-09 | 2019-07-15 | 2020-07-14 | 0 | 2020-12-31 | 60% | 7136510 | 0 | 7136510 | 0 | 0 | 0 | 7136510 | 52.59% | WBM & Structure complete, Work stopped due to shortage of stone chips
120 | 2019-20 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/JAL/VR/19-20/W-120 | 173124012 | Improvement of Bituminous Carpeting Road on Dakhin Sonakhuli-Dalia Taltola road Ch: 2150m-3650m including 2Nos 1x1.50mx 1.50 m U-Drain at Ch.Ch: 2388 m & 2630m and 2Nos 1x0.6250mx 0.60m m U-Drain at Ch: 2210 m & 2270m under Upazila: Dimla, Dist: Nilphamari | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 2150 | 3650 | 1.5 | 5 | 13285714 | 1575024 | 14860738 | 15643068 | 0 | 15643068 | 0 | 0 | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work started
125 | 2019-20 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/19-20/W-125 | 173124083 | Improvement of Sonakhuli high School -Vendabari Road Ch: 00m-2155 m including 1Nos 1x3.00mx2.00m RCC. Box Culvert at Ch: 607m and 2Nos 1x1.50mx1.50m. RCC.Box Culvert at Ch: 720 m & 1167m and 1Nos 2x3.00mx2.00m RCC. Box Culvert at Ch: 206m Under Upazila: Dimla, District:Nilphamari. | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 0 | 2155 | 2.155 | 16 | 19440508 | 3953515 | 23394023 | 20069154.42 | 0 | 20069154.42 | 0 | 0 | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-11-24 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work started
141 | 2020-21 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/20-21/W-141 | 173125089 | Improvement of Kakina Chapani Madrasha-Tista Main Canal Road. Road Ch: 0.00m-1783.00m including Construction of 3Nos 1.50m x 1.50m RCCBox culvert at Ch: 625.0m,695.0m,1328.0m and 1Nos Single Vent2.00m x 2.00m RCCBox culvert at Ch: 1242.0m and 8Nos 7m longU-Drain 0.6250mm x 0.600m Drainage Culvert at Ch: 273.0m,362.0m, 467.0m, 540.0m, 727.0m,1347.0m,1475.0m, 1614.0m Under Upazila: Dimla, District:Nilphamari | 0 | 0 | 1783 | 1.783 | 16.5 | 15506594 | 3771630 | 19278224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Evaluation on going
140 | 2020-21 | Nilphamari | Dimla | Village Road-BC | PRO/NIL/DIM/VR/20-21/W-140 | 173124082 | Improvement of Dokhin Sonakhuli -Vajonchur via Khamatpara. Road Ch: 1000.00m-3040.00m including Construction of 4Nos 1.50m x 1.50m RCC Box culvert at Ch: 1153.0m, 1186.0m, 2054.0m, 2480.0m and 1Nos 2vent 3.00m x 2.00m RCC Box culvert at Ch: 1991.00m and 3Nos U-Drain 7m Long 0.625.mm x 0.600mm Drainage Culvert at Ch: 1652.00m,2260.00m, 2290.00m Under Upazila: Dimla, District:Nilphamari | 0 | 1000 | 3040 | 2.04 | 17.5 | 18745610 | 4438998 | 23184608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Evaluation on going
|  |  |  | Total: |  | NOS Est. Packages: | 6 | NOS Cont. Signed: | 4 |  | 11.618 | 84.43 | 99279704.37 | 21875538.25 | 121155242.62 | 66759465.31 | 7993122.08 | 74752587.39 | 0 | 0 | [6 empty] | 39.85% | 23129640 | 2955540 | 26085180 | 989931 | 247482 | 1237413 | 27322593 | 36.55%
Village Road-HBB
121 | 2019-20 | Nilphamari | Dimla | Village Road-HBB | PRO/NIL/DIM/VR/19-20/W-121 | 173125117 | Improvement of HBB Road on Sovangong Bazar- Astaf Ali House via Azgar rice mill road, under Balapara union Ch: 330m-1385 m Under Upazila: Dimla, District:Nilphamari. | Rainbow Enterprise, Khaga Kharibarim Dimla, Nilphamari | 330 | 1385 | 1.055 | 0 | 5468148 | 0 | 5468148 | 4548906.83 | 0 | 4548906.83 | 0 | 0 | 2020-10-27 | 2020-11-19 | 2020-11-25 | 2021-05-24 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work started
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 1.055 | 0 | 5468148 | 0 | 5468148 | 4548906.83 | 0 | 4548906.83 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Road Maintenance by LCS
0 | 2020-21 | Nilphamari | Dimla | Maintenance-LCS | PRO/NIL/DIM/RMP/20-21/ MW-128 | 173123014 173124012 173125089 173124082 173124083 | i)Naotara U.P. Office-Motirbazar RD at ch. 3200-6400 m. ii)DakhinSonakhuli-DaliaTaltola at ch. 1500-3750 m. iii)Kakina Chapani Madrasha-Tista Main Canal at ch. 2700-3500 m. iv)Dkhin Sonakhuli-Vajonchur via Khamatpara at ch. 2000-4500 m. v)Sonakhuli High School- Vendabari at ch. 2500-3800 m. | LCS 1)Mst. Alena Akter & Srimati Golapi bala LCS 2)Mst. Hafezakhatun & Fozila Begum LCS 3) Mst Mamima Akter & Mst. Fozila Khatun LCS 4) Mst Lucky Begum & Homayra Begum LCS 5) Arzina Khatun & Nasima Begum | 3200 1500 2700 2000 2500 | 6400 3750 3500 4500 3800 | 10.05 | 0 | 5070735.37 | 0 | 5070735.37 | 5070735.37 | 0 | 5070735.37 | 0 | 0 | 0 | 2020-10-29 | 2020-11-01 | 2022-10-31 | 0 | 0 | 3% | 165000 | 0 | 165000 | 0 | 0 | 0 | 165000 | 3.254% | Work ongoing
| 2020-21 | Nilphamari | Jaldhaka | Maintenance-LCS | PRO/NIL/JAL/RMP/20-21/ MW-129 | 173365064 173365066 | i)WDB Bundh to WDB Bundh via Moratista Syphon at ch. 00-1215 m. ii)Moratista Syphon to WDB Bundh ch. 00-1506 m. | 0 | 0.00 0.00 | 1215 1506 | 2.721 | 0 | 1586360.82 | 0 | 1586360.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | LCS Group formation under process, Estimate approved on 16-7-20
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 1 |  | 12.771 | 0 | 6657096.19 | 0 | 6657096.19 | 5070735.37 | 0 | 5070735.37 | 0 | 0 | [6 empty] | 3% | 165000 | 0 | 165000 | 0 | 0 | 0 | 165000 | 3.254%
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 2 | 2 | 4.209 | 6.25 | 36707014.68 | 2010249.5 | 38717264.18 | 34451742.52 | 1057539.337 | 35509281.857 | 0 | 44.93% | 12975867 | 815464 | 13791331 | 832618 | 203866 | 1036484 | 14827815 | 41.76%
Village-BC |  | 6 | 4 | 11.618 | 84.43 | 99279704.37 | 21875538.25 | 121155242.62 | 66759465.31 | 7993122.08 | 74752587.39 | 0 | 39.85% | 23129640 | 2955540 | 26085180 | 989931 | 247482 | 1237413 | 27322593 | 36.55%
Village-HBB |  | 1 | 1 | 1.055 | 0 | 5468148 | 0 | 5468148 | 4548906.83 | 0 | 4548906.83 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
Maintenance |  | 2 | 1 | 12.771 | 0 | 6657096.19 | 0 | 6657096.19 | 5070735.37 | 0 | 5070735.37 | 0 | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO | UPDATE after WO
| Total: | 11 | 8 | 29.653 | 90.68 | 148111963.24 | 23885787.75 | 171997750.99 | 110830850.03 | 9050661.417 | 119881511.447 | 0 | 38.16% | 36105507 | 3771004 | 39876511 | 1822549 | 451348 | 2273897 | 42150408 | 35.16%
|  | Nilphamari | Dimla | Union Road-BC |  | 173123014 | Naotara U.P Office-Motirbazar Rd.
|  | Nilphamari | Dimla | Village Road-BC |  | 173124012 | Dakhin Sonakhuli-Dalia Taltola
|  | Nilphamari | Dimla | Village Road-BC |  | 173125089 | Kakina Chapani Madrasha-Tista Main Canal.
|  | Nilphamari | Dimla | Village Road-BC |  | 173124082 | Dkhi Sonakhuli - Vajonchur vai khamatpara
|  | Nilphamari | Dimla | Village Road-BC |  | 173124083 | Sonakhuli high School -Vendabari.
|  | Nilphamari | Dimla | Village Road-HBB |  | 173125117 | Sovangong Bazar- Astaf Ali House via Azgar rice mill road, under Balapara union
|  | Nilphamari | Dimla | Large Market |  |  | Tunirhat
|  | Nilphamari | Dimla | Large Market |  |  | Babur hat
|  | Nilphamari | Jaldhaka | Large Market |  |  | Bhabonchur Bazar
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Goulmunda Bazar
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Balagrm Bazar
|  | Nilphamari | Jaldhaka | Medium Market |  |  | kharkati Hat
|  | Nilphamari | Jaldhaka | Medium Market |  |  | kaligonj Bangha bandhu Bazar
|  | Nilphamari | Jaldhaka | Medium Market |  |  | pathanpara hat
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Diabari Hat
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Dakligonj hat
|  | Nilphamari | Jaldhaka | Medium Market |  |  | Shibur hat
|  | Nilphamari | Jaldhaka | Small Market |  |  | Kathali Nayer hat

## Rangpur
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Rangpur
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Union Road BC
| 2018-19 | Rangpur | Kaunia | Union Road-BC | PRO/RAN/KAU/UNR/18-19/W-16 | 185423012 | Improvement of Bituminous Carpeting Road on Sarai Up office (Zahir) to Eakota Bazar Via Udaynarayon Machari Govt.Primary School at Ch.2375m-3055m. Under Kaunia Upazila, District Rangpur. | M/S. Nila Enterprise, Shalbon, Rangpur | 2375 | 3055 | 0.68 | 0 | 5430014.69 | 0 | 5430014.69 | 5158514.25 | 0 | 5158514.25 | 0 | 0 | 2019-03-19 | 2019-04-09 | 2019-04-16 | 2020-02-15 | 0 | 2020-03-24 | 50% | 2569188 | 0 | 2569188 | 0 | 0 | 0 | 2569188 | 49.8% | WBM complete
| 2018-19 | Rangpur | Gangachara | Union Road-BC | PRO/RAN/KAU/GAN/UNR/18-19/W-17 | 185273020 | Improvement of Bituminous Carpeting Road on Kolkando UP (Binbina Ferrighat)-Abuliahat Upto Kaliganj Upazila Border (Tusvander UP) Road at Ch 00-2350m. including Costruction of 3 U- drain at Ch 00-2350m Under Gangachara Upazila, District Rangpur. | M/S. Onto & Tahity (JV), Rangpur | 0 | 2350 | 2.35 | 4.8 | 19971756.68 | 1573720 | 21545476.68 | 18763031.63 | 1476418.6 | 20239450.23 | 0 | 0 | 2019-04-15 | 2019-04-30 | 2019-05-06 | 2020-05-05 | - | 2020-06-03 | 100% | 16366218 | 0 | 16366218 | 922375 | 0 | 922375 | 17288593 | 85.42% | BC Complete
| 2019-20 | Rangpur | Kaunia | Union Road-BC | PRO/RAN/KAU/UNR/19-20/W-74 | 185423013 | Improvement of Bituminous carpeting Road on Sarai UP- Bhahishwler More bazar via Naira Pry.School Road at Ch: 1412m-3412m including Construction of 1Nos (0.625x0.625) m U-Drain at Ch: 1775m,2247m, 2537m,2590m & 3155m and 1Nos 3x4.50mx4.00 m RCC Box Culvert at Ch: 2127m and 1Nos 1x2.00mx2.00 m RCC Box Culvert at Ch: 2901m Under Upazila:Kaunia, District: Rangpur | KZ-AHC (JV) Kashimpur, Mithapukur, Rangpur | 1412 | 3412 | 2 | 22.5 | 18739034 | 6076156 | 24815190 | 16586327.95 | 5605135.56 | 22191463.51 | 0 | 0 | 2020-03-01 | 2020-03-25 | 2020-04-04 | 2021-04-03 | 0 | 2021-06-08 | 30% | 1691277 | 0 | 1691277 | 0 | 0 | 0 | 1691277 | 7.621% | WBM running
|  |  |  | Total: |  | NOS Est. Packages: | 3 | NOS Cont. Signed: | 3 |  | 5.03 | 27.3 | 44140805.37 | 7649876 | 51790681.37 | 40507873.83 | 7081554.16 | 47589427.99 | 0 | 0 | [6 empty] | 61.94% | 20626683 | 0 | 20626683 | 922375 | 0 | 922375 | 21549058 | 45.28%
Village Road BC
| 2018-19 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/18-19/W-15 | 185424019 | Improvement of Bituminous carpeting Road on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 00-1715m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | Md. Hafizur Rahman Burirhat, Rangpur. | 0 | 1715 | 1.715 | 0.6 | 13105734.48 | 106317 | 13212051.48 | 12748776.42 | 101028.9 | 12849805.32 | 0 | 0 | 2019-04-15 | 2019-04-30 | 2019-05-05 | 2020-03-22 | 2019-09-10 | 2020-04-20 | 100% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 99.04% | Final bill paid
| 2020-21 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/20-21/W-137 | 185424058 | Improvement of Bituminous carpeting on Jummarpar R&H - Mirbag Gramen Bank More Bazar. Road at Ch:00m-1482m including Construction of 2Nos 0.625x0.625 m U-Drain at Ch:315m & 465m Under Kaunia Upazila , District: Rangpur. | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 0 | 1482 | 1.482 | 2 | 13006125 | 271764 | 13277889 | 11157613.26 | 261511.74 | 11419125 | 0 | 0 | 2020-10-07 | 2020-11-15 | 2020-11-21 | 2021-10-05 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WO Issued, work will start
| 2020-21 | Rangpur | Kaunia | Village Road-BC | PRO/RAN/KAU/VR/20-21/W-138 | 185424060 | Improvement of Bituminous carpeting Road on Topical GC hat - Branter bazar via Gopidanga GPS. Road at Ch: 00m-2785m including Construction of 3Nos 0.625x0.625 m Drainage Structure at Ch:640m,1383m &1814m and 1Nos 1x1.500x1.50 m RCC Box Culvert at Ch: 551m and 1x2.00x2.00 m RCC Box Culvert at Ch: 128m 2x4.50x4.00 m RCC Box Culvert at Ch: 910m and 3x4.50x4.00 m RCC Box Culvert at Ch: 1607m Under Under Kaunia Upazila , District: Rangpur. | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 0 | 2785 | 2.785 | 32.8 | 23976518 | 9984639 | 33961157 | 18756306 | 9693337 | 28449643 | 0 | 0 | 2020-10-25 | 2020-11-15 | 2020-11-21 | 2022-04-04 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | WO Issued, work will start
|  |  |  | Total: |  | NOS Est. Packages: | 3 | NOS Cont. Signed: | 3 |  | 5.982 | 35.4 | 50088377.48 | 10362720 | 60451097.48 | 42662695.68 | 10055877.64 | 52718573.32 | 0 | 0 | [6 empty] | 24.37% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 24.14%
Medium Market
107 | 2019-20 | Rangpur | Kaunia | Medium Market | PRO/RAN/KAU/MM/19-20/W- 107 | 0 | Construction of Ekoter Hat Upazila:Kaunia, District: Rangpur, Under PROVATi3 Project. | Mst Sahida Khatun and Mst. Merina Begum (LCS-1)/Mst. Dolena and Mst. Sheuli Begum(LCS-2) | 0 | 0 | 0 | 0 | 0 | 0 | 5032629 | 0 | 0 | 5032629 | 0 | 0 | 0 | 2020-07-21 | 0 | 2021-07-21 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Training Complete
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 5032629 | 0 | 0 | 5032629 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Road Maintenance by LCS
108 | 2019-20 | Rangpur | Gangachara | Maintenance-LCS | PRO/RAN/GAN/RMP/19-20/MW-108 | 185275228 185275241 | (i) Rural road maintenance by LCS (Material & Wages) work on Char Nohali Bridger Bazar- Minar Bazar via Ashrayon Bazar (Bager hat) Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (ii) Rural road maintenance by LCS (Material & Wages) work on Kutub hat(konabari) - Khamer mohona GPS via uttor kishamot Gonesh GPS Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | Mst. Ayouli Begum & Mst. Anufa Begum (LCS-01) Mst. Monzila Begum & Mst. Rabeya Begum(LCS-02) | 0 | 0 | 9 | 0 | 3666856.72 | 0 | 3666856.72 | 1261167.96 | 0 | 1261167.96 | 0 | 0 | 0 | 2020-06-01 | 0 | 2022-05-31 | 0 | 0 | 20% | 216000 | 0 | 216000 | 0 | 0 | 0 | 216000 | 17.13% | Work on going ,Pkg#3 package already done from other project.
109 | 2019-20 | Rangpur | Kaunia | Maintenance-LCS | PRO/RAN/KAU/RMP/19-20/MW-109 | 185423013 | Rural road maintenance by LCS (Material & Wages) work on Sarai UP-Bhahishwler more Bazar via Naira Pry. School Sarak at Kaunia Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | Mst. Rabeya Khatun & Mst. Rugina Begum | 0 | 0 | 2.275 | 0 | 1326724.49 | 0 | 1326724.49 | 1326724.49 | 0 | 1326724.49 | 0 | 0 | 0 | 2020-06-01 | 0 | 2022-05-31 | 0 | 0 | 21% | 191250 | 0 | 191250 | 0 | 0 | 0 | 191250 | 14.42% | Work on going
|  |  |  | Total: |  | NOS Est. Packages: | 2 | NOS Cont. Signed: | 2 |  | 11.275 | 0 | 4993581.21 | 0 | 4993581.21 | 2587892.45 | 0 | 2587892.45 | 0 | 0 | [6 empty] | 20.51% | 407250 | 0 | 407250 | 0 | 0 | 0 | 407250 | 15.74%
Maintenance-Office Building
3 | 2019-20 | Rangpur | Gangachara | Maintenance-Office | PRO/RANG/MAINT/19-20/MW-3 | 0 | Repair & maintenance work of LGED office building, Dist: Rangpur | M/S Tahity Enterprise | 0 | 0 | 0 | 0 | 0 | 0 | 2141640 | 0 | 0 | 1547911.47 | 0 | 0 | 2020-08-25 | 2020-09-09 | 2020-09-15 | 2021-01-14 | 0 | 2021-05-07 | 90% | 0 | 0 | 1070767 | 0 | 0 | 0 | 1070767 | 69.17% | 0
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 2141640 | 0 | 0 | 1547911.47 | 0 | 0 | [6 empty] | 90% | 0 | 0 | 1070767 | 0 | 0 | 0 | 1070767 | 69.17%
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 3 | 3 | 5.03 | 27.3 | 44140805.37 | 7649876 | 51790681.37 | 40507873.83 | 7081554.16 | 47589427.99 | 0 | 61.94% | 20626683 | 0 | 20626683 | 922375 | 0 | 922375 | 21549058 | 45.28%
Village-BC |  | 3 | 3 | 5.982 | 35.4 | 50088377.48 | 10362720 | 60451097.48 | 42662695.68 | 10055877.64 | 52718573.32 | 0 | 24.37% | 11117212 | 0 | 11117212 | 1609430 | 0 | 1609430 | 12726642 | 24.14%
Medium Market |  | 1 | 1 | 0 | 0 | 0 | 0 | 5032629 | 0 | 0 | 5032629 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance |  | 2 | 2 | 11.275 | 0 | 4993581.21 | 0 | 4993581.21 | 2587892.45 | 0 | 2587892.45 |  | 20.51% | 407250 | 0 | 407250 | 0 | 0 | 0 | 407250 | 15.74%
Office-Maint. |  | 1 | 1 | 0 | 0 | 0 | 0 | 2141640 | 0 | 0 | 1547911.47 | 0 | 90% | 0% | 0% | 107076700% | 0% | 0% | 0% | 107076700% | 69.17%
| Total: | 10 | 10 | 22.287 | 62.7 | 99222764.06 | 18012596 | 124409629.06 | 85758461.96 | 17137431.8 | 109476434.23 | 0 | 40.42% | 32151145 | 0 | 33221912 | 2531805 | 0 | 2531805 | 35753717 | 32.66%
Unallocated Packages:
|  | Rangpur | Kaunia | Village Road-BC |  | 185424016 | Haragach pucca road-Joybangla Bazar Rd.
|  | Rangpur | Kaunia | Village Road-BC |  | 185424058 | Jummarpar R&H - Mirbag Gramen Bank More Bazar.
|  | Rangpur | Kaunia | Village Road-BC |  | 185424060 | Topical GC hat - Branter bazar via Gopidanga GPS.
|  | Rangpur | Gangachara | Village Road-BC |  | 185275115 | Bagerhat to Sankordho Hafazia Madrasha
|  | Rangpur | Gangachara | Village Road-BC |  | 185275107 | Balatary Chowpati - Joydeb Dolapara Road
|  | Rangpur | Gangachara | Village Road-HBB |  | 185275134 | Betgari Kachua UZR near Patakhowa more - Sudhuir Master's house road
|  | Rangpur | Kaunia | Medium Market |  |  | Ekotarhat
|  | Rangpur | Kaunia | Medium Market |  |  | Bhaier Hat
|  | Rangpur | Kaunia | Medium Market |  |  | Bhutsora(Mirbag)Hat
|  | Rangpur | Kaunia | Medium Market |  |  | Haqueer hat
|  | Rangpur | Gangachara | Medium Market |  |  | Babubazar
|  | Rangpur | Gangachara | Medium Market |  |  | Abuliarhat
|  | Rangpur | Gangachara | Small Market |  |  | Bagerhat
|  | Rangpur | Gangachara | Small Market |  |  | Ichli Bazar(SKS Bazar)

## Lalmonirhat
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Lalmonirhat
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Union Road BC
| 2018-19 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/18-19/W-02 | 152703010 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Koborstan to Sarkarhat Jongra UP Road at Ch. 00-2185m. Under Patgram Upazila, District Lalmonirhat. | M/S fahim Traders, Kurigram Sadar, Kurigram. | 0 | 2185 | 2.19 | 0 | 16143845 | 0 | 16143845 | 13964438.783 | 0 | 13964438.783 | 0 | 0 | 28-03-19 | 11-04-19 | 2019-04-18 | 2020-03-17 | 0 | 02-04-2020 16-01-2021 | 100% | 11936905 | 0 | 11936905 | 1891364 | 0 | 1891364 | 13828269 | 99.02% | ফাইনাল বিল দেওয়া হয়েছে।
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-57 | 152703020 | Improvement of Bituminous carpeting Road Jongra UP office (Futir Doba) to Sofinagadhat Road at Ch 00m-1000m. Under Patgram Upazila, District Lalmonirhat. | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 0 | 1000 | 1 | 0 | 8219318 | 0 | 8219318 | 7397386.2 | 0 | 7397386.2 | 0 | 0 | 2020-01-21 | 2020-02-18 | 2020-02-25 | 2021-02-24 | 0 | 44046 | 100% | 5699030 | 0 | 5699030 | 859292 | 0 | 859292 | 6558322 | 88.66% | ফাইনাল বিল হেড অফিসে দাখিল করা হয়েছে।
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-55 | 152703019 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Kabarstanhat to Lalitarhat Kuchlibari UP Road at Ch: 1435m-3435m including Construction of 4Nos (1x2.00x1.50)m RCC.Box Culvert and 1 No (2x4.50x2.50)m RCC.Box Culvert Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 1435 | 3435 | 2 | 20.5 | 15769651 | 5125861 | 20895512 | 14180790.473 | 4625170.346 | 18805960.819 | 0 | 0 | 2020-02-12 | 2020-02-18 | 2020-02-25 | 2021-02-24 | 0 | 44423 | 65% | 7813406 | 0 | 7823406 | 1250657 | 0 | 1250657 | 9074063 | 48.25% | WvweøDweGg Gi KvR Pigvb¦
| 2019-20 | Lalmonirhat | Patgram | Union Road-BC | PRO/LAL/PAT/UNR/19-20/W-56 | 152703007 | Improvement of Bituminous carpeting Road on Kamerarhat Sreerampur UP via Dr.Hamidur Islam House Road at Ch: 900m-1995m Under Patgram Upazila ,District Lalmonirhat . | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 900 | 1995 | 1.095 | 0 | 9842242 | 0 | 9842242 | 8858017.8 | 0 | 8858017.8 | 0 | 0 | 2020-01-21 | 2020-02-28 | 2020-02-25 | 2021-02-24 | 0 | 43898 | 98% | 6795161 | 0 | 6795161 | 1071996 | 0 | 1071996 | 7867157 | 88.81% | কার্পেটিং শেষ। টার্পিং এর কাজ চলমান।
| 2019-20 | Lalmonirhat | Hatibandha | Union Road-BC | PRO/LAL/HATI/UNR/19-20/W-78 | 152333016 | Improvement of Bituminous carpeting Road Sadhur Bazar-Guddimari Road at Ch: 1500m-3700m including Construction of 4Nos 1x 0.90mX0.900 m RCC Box Culvert at Ch: 2475m,2600m,3200m & 3640.00m and 1Nos 1x 2.0mX1.50 m RCC Box Culvert at Ch: 3030m Under Hatibandha Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 1500 | 3700 | 2.2 | 5.2 | 21913908 | 1485646 | 23399554 | 17945425.306 | 1330683.679 | 19276108.985 | 0 | 0 | 18-03-20 | 2020-04-15 | 2020-04-22 | 2021-04-21 | 0 | 44399 | 40% | 6487500 | 0 | 6487500 | 1012500 | 0 | 1012500 | 7500000 | 38.91% | স্ট্রাকচারের কাজ চলছে।
143 | 2020-21 | Lalmonirhat | Hatibandha | Union Road-BC | PRO/LAL/HATI/UNR/20-21/W-143 | 152333018 | Improvement of Patikapara UP office – Dawabari UP Road. Ch: 1000.0m-3000.0m including Construction of 3 Nos 7.00x 0.900m x 0.900m Cross-Drain Ch: 1004.0m,1219.0m,1950.0m Under Upazila: Hatibandha, District:Lalmonirhat | 0 | 1000 | 3000 | 2 | 4.05 | 17616923 | 609186 | 18226109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under process | 0 | 2 | 183.682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total: |  | NOS Est. Packages: | 6 | NOS Cont. Signed: | 5 |  | 10.485 | 29.75 | 89505887 | 7220693 | 96726580 | 62346058.562 | 5955854.025 | 68301912.587 | 0 | 0 | [6 empty] | 73.17% | 38732002 | 0 | 38742002 | 6085809 | 0 | 6085809 | 44827811 | 65.63%
Village Road BC
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/18-19/W-03 | 152705151 | Improvement of Bituminous Carpeting Road on Altab More to Safinagarhat via Hasnabad Community Clinik & Mokbul Jahanara Hossin GPS at Ch. 700-1700m. Under Patgram Upazila, District Lalmonirhat. | M/S RML Enterprise, Hatibandha, Lalmonirhat. | 700 | 1700 | 1 | 0 | 6975415 | 0 | 6975415 | 6626644.25 | 0 | 6626644.25 | 0 | 0 | 2019-02-24 | 2019-03-18 | 2019-03-25 | 2020-03-24 | 0 | 2020-09-03 | 100% | 0 | 0 | 0 | 6625297 | 0 | 6625297 | 6625297 | 99.98% | ফাইনাল বিল হয়েছে। জামানত প্রদান করা হয়েছে।
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR//18-19/W-04 | 152335060 | Improvement of Niz Sheck Sundor Jameh Mosue Applax Embankment road. Ch. 500m-1765m. including Construction of 7.00x0.900mx 0.900m Cross drain at Ch. 995m under Hatibandha Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 500 | 1765 | 1.265 | 0.9 | 9940910 | 179692 | 10120602 | 8683000.48 | 156906.643 | 8839907.122 | 0 | 0 | 2019-03-28 | 2019-04-11 | 2019-04-18 | 2020-03-17 | 0 | 2020-04-09 | 100% | 0 | 0 | 0 | 8682822.84 | 156906.64 | 8839729.48 | 8839729.48 | 100% | ‡cf‡g›U Gi mKj †jqv‡ii KvR mgvß n‡q‡Q¦ BD‡Wªb Gi KvR mgvß n‡q‡Q¦‡cÖv‡Uw±f IqvK© Gi KvR †kl n‡q‡Q, Nvm jvMv‡bv nqwb¦ mg¯Í wej wRIwe n‡Z cÖ`vb Kiv i‡q‡Q¦
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-05 | 152334015 | Improvement of Bituminous Carpeting Road on WAPDA Pucea road to Dimla Bordar road at Ch.0.00m-3000.0m. including Construction of 2.00x 2.00 Cross drain at Ch. 2415.00m and Construction of 2 Nos 7x0.900mx0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | M/S Islam Traders, Ghop Jossor, Lalmonirhat. | 0 | 3000 | 3 | 4.2 | 26653905.62 | 966016.9 | 27619922.52 | 23524180.35 | 880651.833 | 24404832.183 | 0 | 0 | 2019-03-28 | 2019-04-10 | 2019-04-17 | 2020-09-01 | 0 | 2020-10-01 | 100% | 20558148 | 0 | 20558148 | 3594965 | 0 | 3594965 | 24153113 | 98.97% | ফাইনাল বিল দেওয়া হয়েছে।
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/ HATI/VR/18-19/W-33 | 152335034 | Improvement of Bituminous carpeting Road on Patikapara Dowabari Up Boder To Kapil Mamber house Road at Ch. 00-1000m. including Construction of 2.00 Nos 0.900m x 0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | Borsha Enterprise, Patgram, Lalmonirhat | 0 | 1000 | 1 | 1.8 | 7409383.06 | 359383.98 | 7768767.04 | 7020944.669 | 359383.981 | 7380328.65 | 0 | 0 | 2019-04-16 | 2019-04-30 | 2019-06-10 | 2020-06-09 | 0 | 2020-07-28 | 100% | 5735704.6 | 359366.44 | 6095071.04 | 1036149 | 0 | 1036149 | 7131220.04 | 96.62% | gvwU I Uvwc©s Gi KvR Pj‡Q¦
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-34 | 152334068 | Improvement of Bituminous carpeting Road on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. including(D): Construction of 2.00 Nos (2.50x2.50) m Cross Drainges Structure on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat.(Structure)(E): Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. (Structure) | Anta & SH ZV, Patgram, Lalmonirhat | 0 | 2000 | 2 | 8 | 14532903 | 3136442 | 17669345 | 12863063.52 | 2771524.493 | 15634588.013 | 0 | 0 | 2019-05-29 | 2019-06-09 | 2019-06-10 | 2019-11-09 | 0 | 2019-12-05 | 100% | 12100676 | 0 | 12100676 | 1937636 | 0 | 1937636 | 14038312 | 89.79% | ফাইনাল বিল পেশ করেছেন
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-35 | 152334088 | Improvement of Bituminous carpeting Road R&H Nowabab Uddin House-Laxmi Kanto Chokider House at Ch.0.00m-1000.00m. including Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch.661.00m. Under Hatibanhda Upazila, District Lalmonirhat. | Nakshi Mobail Palace, Sadar, Kurigram | 0 | 1000 | 1 | 3 | 7141226.17 | 1123449 | 8264675.17 | 6784164.9 | 1067276.417 | 7851441.317 | 0 | 0 | 2019-04-16 | 2019-05-14 | 2019-05-21 | 2020-03-01 | 0 | 2020-04-27 | 100% | 5437695.58 | 1067276.42 | 6504972 | 918412 | 0 | 918412 | 7423384 | 94.55% | ফাইনাল বিল পেশ করেছেন এবং ব্যংক গারান্টি বৃ্ধি করেছেন 27/07/2020 ইং পর্যন্ত।
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-36 | 152335033 | Improvement of Bituminous carpeting Road Paschim Bisondai Mouza To Sattar Chairman House Road Ch 0.00m-2000.00m including Construction of 4.00 Nos 7.00x0.900x0.900 Cross drain At Ch.113m, 417m, 1280m, &2560m Under Hatibandha Upazila, District Lalmonirhat. | M/S Alahi Box, Kaligonj, Lalmonirhat | 0 | 2000 | 2 | 3.6 | 14144485 | 858869.5 | 15003354.5 | 12406869.348 | 645062.75 | 13051932.098 | 0 | 0 | 2019-06-17 | 19-06-19 | 2019-06-26 | 2020-05-25 | 0 | 2020-06-02 | 100% | 11109467 | 0 | 11109467 | 1782955 | 0 | 1782955 | 12892422 | 98.78% | ফাইনাল বিল দেওয়া হয়েছে।
| 2018-19 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-45 | 152335061 | Improvement of Bituminous carpeting Road on Applax Badth to Dimla Border Road at Ch 0.00m-1800.0m including Construction of 3.00 Nos 0.900 X 0.900 Cross drain at Ch. 400.00m, 700.00m & 1000.00m on Applax Badth to Dimla Border Road. Under Hatibanhda Upazila, District Lalmonirhat. | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 0 | 1800 | 1.8 | 2.7 | 12752649 | 555765.89 | 13308414.89 | 11139339.451 | 435687.765 | 11575027.216 | 0 | 0 | 2019-07-08 | 2019-07-24 | 2019-07-31 | 2020-06-16 | 0 | 2020-07-15 | 100% | 8908214 | 0 | 8908214 | 1460261 | 0 | 1460261 | 10368475 | 89.58% | ফাইনাল বিল প্রেরন করেছেন।
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-46 | 152704023 | Improvement of Bituminous carpeting Road on Sarkarerhat Mosque to Borovita at Ch 0.00m-2500.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 0 | 2500 | 2.5 | 0 | 18846970 | 0 | 18846970 | 16388604.17 | 0 | 16388604.17 | 0 | 0 | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) | 0 | 2020-07-16 | 75% | 0 | 0 | 0 | 10715326 | 0 | 10715326 | 10715326 | 65.38% | WBM complete
| 2018-19 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/HATI/VR/18-19/W-47 | 152704034 | Improvement of Bituminous carpeting Road Dhobolsuti Mosque to Kamararhat Road at Ch 0.500m-3050.0m. Under Patgram Upazila, District Lalmonirhat. | Fahim Traders, Kurigram Sadar, Kurigram | 500 | 3050 | 2.55 | 0 | 18895406 | 0 | 18895406 | 16408287.34 | 0 | 16408287.34 | 0 | 0 | 2019-07-08 | 2019-07-24 | 2019-07-31 | 16-06-2020 31-12-2020 (xen sent time ext. prayer) | 0 | 2020-07-16 | 75% | 0 | 0 | 0 | 9393335.62 | 0 | 9393335.62 | 9393335.62 | 57.25% | WvweøDweGg Gi KvR Pigvb¦
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-75 | 152705121 | Improvement of Bituminous carpeting Road on Lolitarhat – Liakot Prodhan House Via Kolshirmuk BOP & Graipul Road at Ch: 4000m-4950m Under Patgram Upazila ,District Lalmonirhat | GRP & RT (ZV), GL Roy Road, Rangpur. | 4000 | 4950 | 0.95 | 0 | 8246152 | 0 | 8246152 | 6982029.537 | 0 | 6982029.537 | 0 | 0 | 18-03-20 | 15-04-20 | 22-04-20 | 21-04-21 | 0 | 24-12-20 | 95% | 5722330 | 0 | 5722330 | 840533 | 0 | 840533 | 6562863 | 94% | কার্পেটিং শেষ। টার্পিং এর কাজ চলমান।
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-76 | 152705059 | Improvement of Bituminous carpeting Road on Nayerhat Mosque to Zero point of Dhagram UP Road at Ch: 1000m-4000m including construction of 1Nos 1x2.00x2.50 m RCC Box Culvert at Ch: 1310m Under Patgram Upazila ,District Lalmonirhat | Md. Abdul Hossain, Ghoramara Rangpur. | 1000 | 4000 | 3 | 2.5 | 24550502 | 648343 | 25198845 | 20536941.214 | 604889.741 | 21141830.955 | 0 | 0 | 18-03-20 | 30-04-20 | 2020-07-05 | 2021-06-02 | 0 | 29-04-21 | 92% | 10627823 | 0 | 10627823 | 1741579 | 0 | 1741579 | 12369402 | 58.51% | কার্পেটিং শেষ।
| 2019-20 | Lalmonirhat | Patgram | Village Road-BC | PRO/LAL/PAT/VR/19-20/W-77 | 152704084 | Improvement of Bituminous carpeting Road on Kasirdanga-Bazar to 3 no Vothatkhata GPS Road at Ch: 00m-2000m including Construction of 6Nos 1x1.50x1.00 m RCC Box Culvert at Ch: 830m, 870m,1120m, 1200m,1566m &1800m and 3Nos 1x3.00x2.00 m RCC Box Culvert under Patgram Upazila ,District Lalmonirhat | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 0 | 2000 | 2 | 15.5 | 20081664 | 3573248 | 23654912 | 16294425.218 | 3225783.064 | 19520208.282 | 0 | 0 | 18-03-20 | 15-04-2020 | 22-04-2020 | 21-04-2021 | 0 | 24-03-2021 | 45% | 4022306 | 0 | 4022306 | 661701 | 0 | 661701 | 4684007 | 24% | Sub-base and culvert complete
| 2019-20 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/19-20/W-127 | 152334090 | Improvement of Singimari Nebru House-Uttor Baraipara Masque Rd. Road Ch: 1150m -3260m including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch: 2122 m & 2952m Under Upazila: Hatibandha, District:Lalmonirhat. | Ali Ahamed & M/S Hossain trading & Construction, Patgram, Lalmonirhat | 1150 | 3260 | 2.11 | 2.7 | 18321870 | 447885 | 18769755 | 13933282.483 | 316686.366 | 14249968.849 | 0 | 0 | 2020-06-09 | 2020-09-15 | 2020-09-21 | 2021-09-20 | 0 | 44545 | 60% | 6401000 | 0 | 6401000 | 999000 | 0 | 999000 | 7400000 | 51.93% | Box cutting running
142 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20-21/W-142 | 152335059 | Improvement of Hatibandha U.Z.R. at dhubni mauza to dhubni Madrasha Road Ch: 00m -1960m including Construction of 2Nos 0.900m x 0.900m Cross-Drain and 2Nos 1.50m x 1.50m Cross-Drain Under Upazila: Hatibandha, District: Lalmonirhat. | 0 | 0 | 1960 | 1.96 | 5.4 | 16810451 | 1515158 | 18325609 | 14210000.133 | 0 | 14210000.133 | 0 | 0 | 2020-11-19 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NOA Issued on 19-11-20
144 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20/21/W-144 | 152335060 | Improvement of Niz Sheck Sundor Jameh Mosque - Applax Embankment road. Ch. 1765.0m-2365.0m. including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch. 1886.0m & 2115.0m and 1Nos 1x 2.00m x 1.50m Box Culvert at Ch: 1979.0m under Hatibandha Upazila, District Lalmonirhat. | 0 | 1765 | 2365 | 0.6 | 5.2 | 4887744 | 1065231 | 5952975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under process
0 | 2020-21 | Lalmonirhat | Hatibandha | Village Road-BC | PRO/LAL/HATI/VR/20-21/W-148 | 152335023 | Improvement of Singimari UP-Goddimari UP Border Road Ch: 00m -3000m including Construction of 2Nos 1.50m x 1.50m RCC Box Culvert at Ch:530m & 1300m and 1 Nos 0.900m x 0.900m Cross-Drain at Ch: 2660.00m and 1Nos 3.00m x 3.00m RCC Box Culvert at Ch:90.00m Under Upazila: Hatibandha, District: Lalmonirhat. | 0 | 0 | 3000 | 3 | 9.3 | 23832969 | 2358372 | 26191341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under proess
|  |  |  | Total: |  | NOS Est. Packages: | 17 | NOS Cont. Signed: | 15 |  | 31.735 | 64.8 | 254024604.85 | 16787856.27 | 270812461.12 | 193801777.063 | 10463853.053 | 204265630.115 | 0 | 0 | [6 empty] | 79.98% | 90623364.18 | 1426642.86 | 92050007.04 | 50389972.46 | 156906.64 | 50546879.1 | 142596886.14 | 69.81%
Medium Market
67 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-67 | 0 | Construction of Shafinagar Hat, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Luna Parvin . SPC Name- Mst.Provati Rani. LCS Member Nos- 10. | 0 | 0 | 0 | 0 | 0 | 0 | 1025309 | 0 | 0 | 1025309 | 0 | 0 | 0 | 2020-08-23 | 0 | 2020-11-22 | 0 | 0 | 95% | 377500 | 0 | 377500 | 0 | 0 | 0 | 377500 | 36.82% | Electrical work on going
63 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-63 | 0 | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Lipi Begum . SPC Name- Mst.Merina Begum. LCS Member Nos- 15. | 0 | 0 | 0 | 0 | 0 | 0 | 1760898 | 0 | 0 | 1760898 | 0 | 0 | 0 | 2020-09-15 | 0 | 2021-03-14 | 0 | 0 | 10% | 679500 | 0 | 679500 | 0 | 0 | 0 | 679500 | 38.59% | Work ongoing
64 | 2019-20 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/2019-20/W-64 | 0 | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat | CPC Name- Mst.Nurzahan Begum . SPC Name- Mst.Laki Begum. LCS Member Nos- 10. | 0 | 0 | 0 | 0 | 0 | 0 | 1494432 | 0 | 0 | 1494432 | 0 | 0 | 0 | 2020-09-15 | 0 | 2021-03-14 | 0 | 0 | 10% | 604000 | 0 | 604000 | 0 | 0 | 0 | 604000 | 40.42% | Work ongoing
| 2020-21 | Lalmonirhat | Patgram | Medium Market | PRO/LAL/PAT/MM/20-21/W-132 | 0 | Construction of Sharkarar Hat (LCS-1,2,3) | LCS 1: Joyonty & Mst Rohima LCS 2: Ratna Rani & Mollika ray LCS 3: Taposhi Rani ray & Shaymoli | 0 | 0 | 0 | 0 | 0 | 0 | 8399491 | 0 | 0 | 8399491 | 0 | 0 | 0 | 2020-10-14 | 0 | 2021-10-13 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Contract signed
| 2020-21 | Lalmonirhat | Hatibandha | Medium Market | PRO/LAL/HAT/MM/20-21/W-133 | 0 | Construction of Nawdabash Hat (LCS-1,2,3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6855792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | LCS group formed, Stakeholder training arranged on 26-11-20
|  |  |  | Total: |  | NOS Est. Packages: | 5 | NOS Cont. Signed: | 4 |  | 0 | 0 | 0 | 0 | 19535922 | 0 | 0 | 12680130 | 0 | 0 | [6 empty] | 10.25% | 1661000 | 0 | 1661000 | 0 | 0 | 0 | 1661000 | 13.1%
Large Market
| 2020-21 | Lalmonirhat | Hatibandha | Large Market | PRO/LAL/HAT/LM/20-21/W-134 | 0 | Construction of Muktijoddha Bazar (LCS-1,2,3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6206548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | LCS Group formation completed,training will be arranged on 7-12-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 0 |  | 0 | 0 | 0 | 0 | 6206548 | 0 | 0 | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Road Maintenance by LCS
133 | 2020-21 | Lalmonirhat | Patgram | Maintenance-LCS | PRO/LAL/PAT/RMP/20-21/ MW-131 | 152703020 152705151 152705098 | i) Jongra UP office (Futir Doba) to Shafinagar hat road. Ii) Aftab More to Shofinogorhat via Hosnabad Community Clinic & Mokbul Jahanara Hossain GPS road. iii) Olerpar to Dahagram Chairman bari road. | 0 | 0 - 0 | 1000 - 1500 | 3.17 | 0 | 2012485.14 | 0 | 2012485.14 | 2012485.14 | 0 | 2012485.14 | 0 | 0 | 0 | 44131 | 0 | 44860 | 0 | 0 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Work ongoing
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 3.17 | 0 | 2012485.14 | 0 | 2012485.14 | 2012485.14 | 0 | 2012485.14 | 0 | 0 | [6 empty] | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Village Road-HBB
| 2020-21 | Lalmonirhat | Hatibandha | Village Road-HBB | PRO/LAL/HATI/VR-HBB/20-21/W-139 | 152334018 | Improvement of Karbalardighi R&H Road-Dakhalibandha Hat Road. Road Ch: 0.00m-2550.00m including Construction of 2Nos 2.00m x 1.50m Box culvert on Karbalardighi R&H Road-Dakhalibandha Hat Road. C/D st Ch: 1072 m & 2500m. Under Upazila: Hatibandha, District:Lalmonirhat. | 0 | 0 | 2550 | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 | 0 | 11684286.298 | 0 | 0 | 44154 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | NOA Issued in 19-11-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 | 0 | 11684286.298 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
UNC-BC |  | 6 | 5 | 10.485 | 29.75 | 89505887 | 7220693 | 96726580 | 62346058.562 | 5955854.025 | 68301912.587 | 0 | 73.17% | 38732002 | 0 | 38742002 | 6085809 | 0 | 6085809 | 44827811 | 65.63%
Village-BC |  | 17 | 15 | 31.735 | 64.8 | 254024604.85 | 16787856.27 | 270812461.12 | 193801777.063 | 10463853.053 | 204265630.115 | 0 | 79.98% | 90623364.18 | 1426642.86 | 92050007.04 | 50389972.46 | 156906.64 | 50546879.1 | 142596886.14 | 69.81%
Medium Market |  | 5 | 4 | 0 | 0 | 0 | 0 | 19535922 | 0 | 0 | 12680130 | 0 | 10.25% | 166100000% | 0% | 166100000% | 0% | 0% | 0% | 166100000% | 13.1%
Maintenance |  | 1 | 1 | 3.17 | 0 | 2012485.14 | 0 | 2012485.14 | 2012485.14 | 0 | 2012485.14 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Village-HBB |  | 1 | 1 | 2.55 | 5 | 14089742 | 1470868 | 15560610 | 11684286.298 | 0 | 11684286.298 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Large Market |  | 1 | 0 | 0 | 0 | 0 | 0 | 6206548 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
| Total: | 31 | 26 | 47.94 | 99.55 | 359632718.99 | 25479417.27 | 410854606.26 | 269844607.063 | 16419707.078 | 298944444.14 | 0 | 71.8% | 131016366.18 | 1426642.86 | 132453009.04 | 56475781.46 | 156906.64 | 56632688.1 | 189085697.14 | 63.25%
Unallocated Packages:
|  | Lalmonirhat | Hatibandha | Union Road-BC |  | 152333016 | Shadur Bazar to Goddimari
|  | Lalmonirhat | Hatibandha | Union Road-BC |  | 152333018 | Patikapara up office to Dauabari up office
|  | Lalmonirhat | Patgram | Union Road-BC |  | 152703020 | Jongra UP office (Futir Doba) to Shafinagar hat .
|  | Lalmonirhat | Patgram | Union Road-BC |  | 152703019 | Patgram Zila road at kabarstanhat to Lalitarhat Kuchlibari UP.
|  | Lalmonirhat | Patgram | Union Road-BC |  | 152703007 | Kamererhat-Sreerampur UP via Dr. hamidul islam house.
|  | Lalmonirhat | Hatibandha | Village Road-BC |  | 152334090 | Singimari Nebru House - Uttor Baraipara Masque
|  | Lalmonirhat | Hatibandha | Village Road-BC |  | 152335023 | Singmari UP office-Goddimari UP. Border
|  | Lalmonirhat | Hatibandha | Village Road-BC |  | 152335059 | Hatibandha U.Z.R. at dhubni mauza to dhubni Madrasha .
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152704084 | Kashirdanga Bazar to 3 no Vote hat Khata GPS via H/O Md.Mannan.
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705132 | MD. Obrotulla House More - Lolitarhat High School.
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705013 | Nabinagar BOP-Shofinogre Hat
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705059 | Nayerhat Mosque to Zero point of Dahagram UP.
|  | Lalmonirhat | Patgram | Village Road-BC |  | 152705121 | Lolitarhat to Liakot Prodhan house via Kolshirmuk BOP & Greirpul.
|  | Lalmonirhat | Hatibandha | Village Road-HBB |  | 152334018 | Karbalardighi R&H road-Dakhalibandha hat
|  | Lalmonirhat | Patgram | Village Road-HBB |  | 152704017 | Tangtindanga hat-H/O Khairul Islam
|  | Lalmonirhat | Patgram | Large Market |  |  | Nayer Hat
|  | Lalmonirhat | Hatibandha | Large Market |  |  | Muktijoddha Bazar
|  | Lalmonirhat | Patgram | Medium Market |  |  | Sharkarar Hat
|  | Lalmonirhat | Patgram | Medium Market |  |  | Shafinagar Hat
|  | Lalmonirhat | Patgram | Medium Market |  |  | Burimari Hat
|  | Lalmonirhat | Patgram | Medium Market |  |  | Kadhidanggahat
|  | Lalmonirhat | Patgram | Medium Market |  |  | Loliterhat
|  | Lalmonirhat | Patgram | Medium Market |  |  | Kamrarhat
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shaniajan New bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shaniajan bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Cheatnai Hat
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Shadur Bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Ghunti Bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Dighirhat Bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Nawdabash Bazar
|  | Lalmonirhat | Hatibandha | Medium Market |  |  | Jawranihat Bazar

## Jamalpur
Promoting Resilience of Vulnerable though Access to Infrastructure Improved Skill and Information (PROVATi³)
Local Government Engineering Department
District: Jamalpur
Sl No. | Financial Year | District | Upazila | Component | Package No. | Road ID | Package description (including C/D Structure) | Name of the Contractor | Chainage (From) | Chainage (to) | Road Length (km) | Structure Length (m) | Estimated cost (Road) | Estimated cost (Structure) | Total Estimated Cost | Contract amount (Road) | Contract amount (C/D Structure) (Structure) | Total Contract Amount | Variation Amount | Revised Contract Amount | Date of NOA issued | Date of Contract Signed | Date of Commencement | Date of completion | Actual date of Completion | Expire date of Performance Gurantee | Physical Progress (%) | RPA Fund Spend (Road) | RPA Fund Spend (CD/Structure) | Total RPA fund Spend | GOB Fund Spend (Road) | GOB fund spend (CD/Structure) | Total GOB Fund Spend | Total fund spend | Financial Progress (%) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16=14+15 | 17 | 18 | 19=17+18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31=29+30 | 32 | 33 | 34=32+33 | 35=31+33 | 36 | 37
Village Road BC
| 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-29 | 339075094 | Improvement of Bituminous carpeting Road on Airmari-Kamalerbarti Road at Ch.00.0-2850.0m including Contruction Of 1 Nos.(3.50x2.50) Cross Drainges Structure at Ch.1290.0m and Contruction Of 2 Nos.U-Drain at Ch.140m,1915m Under Bakshiganj Upazila, District Jamalpur. | M/S. Lokman Hossain, 987, Choybaria, Gokornoghat, Brahmanbaria | 0 | 2850 | 2.85 | 5.3 | 26012268 | 1488161 | 27500429 | 25428918.47 | 1405081.53 | 26834000 | 901520 | 27735520 | 2019-05-15 | 2019-05-27 | 2019-06-02 | 01-06-2020 15-02-2021 | 0 | 2020-08-20 | 40% | 5048909 | 0 | 5048909 | 366372 | 0 | 366372 | 5415281 | 19.52% | Protective work on going. 500m WBM Running , AS and Structure work running
| 2018-19 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/18-19/W-30 | 339075012 | Improvement of Bituminous carpeting Road on Gazirpara-Derur Bill Road at Ch.00.0-2000.0m Under Bakshiganj Upazila, District Jamalpur. including Contruction Of 1 Nos. U-Drain on Gazirpara-Derur Bill Road at Ch.1640.0m Under Bakshiganj Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2000 | 2 | 0.6 | 17514896.19 | 106751 | 17621647.19 | 15704206.21 | 95866.95 | 15800073.16 | 2293635.84 | 18093709 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 | 0 | 2024-06-26 | 100% | 14989602 | 0 | 14989602 | 1493260 | 0 | 1493260 | 16482862 | 91.1% | Final bill paid
| 2018-19 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ ISL/VR/18-19/W-31 | 339294014 | Improvement of Bituminous carpeting Road on Bulakipara-Goalaerchar Road at Ch.00.0-2800.0m Under Islampur Upazila, District Jamalpur. including Contruction Of 5 Nos.0.600x0.625 U-Drain on Bulakipara-Goalaerchar Road at 552m, 570m, 790m, 865m & 1350m Under Islampur Upazila, District Jamalpur. | M/S. Bilkis Enterprise Melandah, Jamalpur. | 0 | 2800 | 2.8 | 3 | 21880314 | 487259 | 22367573 | 20176056.34 | 449424.22 | 20625480.56 | 1793382.44 | 22418863 | 2019-06-15 | 2019-06-27 | 2019-07-03 | 02-07-2020 31-12-2020 | 0 | 2021-07-30 | 75% | 12771102 | 0 | 12771102 | 1033002 | 0 | 1033002 | 13804104 | 61.57% | WBM done (2350M) U-Drain work is Pending
| 2018-19 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/18-19/W-32 | 339294015 | Improvement of Bituminous carpeting Road on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.00.0-1560m including Contuction Of 1 Nos.( 2x3.50x3.00m ) Cross Drainges Structure at Ch.887.0m and Contuction Of 1 Nos. (2x4.5x4.00m) Cross Drainges Structure at Ch.1219.0m and Contruction Of 6 Nos.0.750x0.750 RCC U-Drain on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.279m,705m,1082m,1139m,1281m,1377m Under Melandah Upazila, District Jamalpur. | M/S. Masum Constrution Chapatali, Sherpur Town, Sherpur. | 0 | 1560 | 1.56 | 22.6 | 16109475 | 6116386 | 22225861 | 14960841.55 | 3274302.46 | 18235144.01 | 1311883 | 19547027.01 | 2019-06-16 | 2019-06-30 | 2019-07-06 | 27-05-2020 31-11-2020 | 0 | 25-06-2020 27-12-2020 | 50% | 5581363 | 0 | 5581363 | 1081164 | 0 | 1081164 | 6662527 | 34.08% | AS rectification Complete, 4 nos U-drain Completed But Cross Drain is under preparation
| 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W-37 | 339154040 | Improvement of Bituminous carpeting Road on Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. including Construction Of 1 Nos.0.600mx0.625m U-Drain on Ch.1236.0m Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 930 | 2880 | 1.95 | 0.6 | 17332023 | 139931 | 17471954 | 14553724.76 | 117499.838 | 14671224.598 | -238869.598 | 14432355 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 31-12-2020 | 0 | 11-06-2020 31-12-2021 | 100% | 10262674 | 0 | 10262674 | 1151557 | 0 | 1151557 | 11414231 | 79.09% | BC completed.Length and Contact amount decresed(length is 1.5 instead on 1.9km).
| 2018-19 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/18-19/W- 38 | 339154029 | Improvement of Bituminous carpeting Road on Bhatkhawa RHD-Amkhowa Bazar Road at Ch.0.00-3250.0m including Construction Of 1 Nos. 3.00x3.00 Cross Drainges Structure Bhatkhawa RHD-Amkhowa Bazar Road at Ch.512.0m Under Dewangonj Upazila, District Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3250 | 3.25 | 3 | 29145742 | 1305867 | 30451609 | 24564023.395 | 1130084.458 | 25694107.853 | 531265.15 | 26225373.003 | 2019-05-30 | 2019-06-12 | 2019-06-18 | 13-05-2020 05-05-2021 | 0 | 11-06-2020 31-12-2021 | 60% | 13890477 | 0 | 13890477 | 0 | 0 | 0 | 13890477 | 52.97% | WBM Complete
| 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-83 | 339294035 | Improvement of BC Road from Napiterchar High School-Chandanpur village via Dasani Ferry Ghat road at ch. 00- 3000m. Including Construction of 2 Nos 1x0.600mx0.600m m U-Drain and 2 Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-2-vent-4.50m X 4.00m RCC Box Culvert under Islampur Upazila, District Jamalpur. | LE &ME (JV) Islampur, Jamalpur | 0 | 3000 | 3 | 21.28 | 32150814 | 7303197 | 39454011 | 33896614.39 | 0 | 33896614.39 | 0 | 0 | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-05-08 | 0 | 2021-05-06 | 30% | 4863211 | 0 | 4863211 | 0 | 0 | 0 | 4863211 | 14.35% | Protective work on going, 2 Nos CD Structure Completed and U-Drain is complete, Sand filling pending
| 2019-20 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/19-20/W-84 | 339294067 | Improvement of BC Road from Dattapara R&H - Napiterchar Bazar via Adorsha Gramm road at ch. 00-3000.00m including Construction of 1 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 1Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-3-vent-4.50m X 4.50m RCC Box Culvert under Upazila Islampur, District- Jamalpur | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 0 | 3000 | 3 | 30.56 | 33480233 | 10347691 | 43827924 | 36997789.33 | 0 | 36997789.33 | 0 | 0 | 2020-04-26 | 2020-05-20 | 2020-05-26 | 2021-04-27 | 0 | 2021-05-06 | 15% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Earth Filling done 1300m rest is running, CD Structure and U-Drain work is Pending
| 2019-20 | Jamalpur | Madargonj | Village Road-BC | PRO/JAM/MAD/VR/19-20/W-85 | 339585030 | Improvement of BC Road from Gabergram Bazar Embankment- Bafatuddin Talukder High School road from ch. 3150-6240.00m including Construction of 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 2Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 2 Nos U-Drain(600X 600mm)under Upazila Madarganj, District- Jamalpur | M/S. Bilkis Enterprise & Md. Mizanur Rahman, Maderganj, Jamalpur. | 3150 | 6240 | 3.09 | 21.37 | 41239211 | 7541224 | 48780435 | 40250008.29 | 0 | 40250008.29 | 0 | 0 | 2020-04-26 | 2020-05-13 | 2020-05-19 | 2021-05-18 | 0 | 2021-08-05 | 20% | 4942880 | 0 | 4942880 | 0 | 0 | 0 | 4942880 | 12.28% | Structure and Box cutting complete
| 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W- 86 | 339154027 | Improvement of BC Road from Khorma naya Bazar via Vatipara Road from ch. 1300-2120.0m including 2Nos U-Drain (600X600mm) under Upazila Dewangonj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 1300 | 2120 | 0.82 | 2 | 7630923 | 211222 | 7842145 | 7057930.5 | 0 | 7057930.5 | 0 | 0 | 2020-02-24 | 2020-03-04 | 2020-03-10 | 2020-09-09 | 0 | 2020-12-30 | 80% | 4082679 | 0 | 4082679 | 0 | 0 | 0 | 4082679 | 57.85% | WBM Complete
| 2019-20 | Jamalpur | Dewanganj | Village Road-BC | PRO/JAM/DEW/VR/19-20/W-88 | 339154032 | Improvement of BC Road from Chakpara FRB - Sharkerpara FRB via Amkhowa Bazar road from ch. 700.00-3340.00m including Construction of 8 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-3-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert under Upazila Dewanganj, District- Jamalpur. | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 700 | 3340 | 2.64 | 43.22 | 29816655 | 13631951 | 43448606 | 38202193.5 | 0 | 38202193.5 | 0 | 0 | 2020-04-26 | 2020-04-29 | 2020-05-05 | 2021-05-04 | 0 | 2021-12-31 | 5% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Box cutting running
0 | 2020-21 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/20-21/W-145 | 339294008 | Improvement of Malmara-Bolakipara road by BC at Ch.0.00-2500m.Under Islampur Upazila, District Jamalpur including Construction of 1 Nos 3X4.50m x 4.50m Cross-Drain at Ch.143m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2370m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2140m and 3 Nos U-Drain at Ch.1500, 1900m | 0 | 0 | 2500 | 2.5 | 25.97 | 24790595 | 8603044.14 | 33393639.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under process,Estimate approved on 30-9-20
0 | 2020-21 | Jamalpur | Islampur | Village Road-BC | PRO/JAM/ISL/VR/20-21/W-146 | 339294087 | Improvement of Malmara Bazar-Napiterchar Bazar via Khairdirrkanda road at Ch.0.00-2000m.Under Islampur Upazila, District Jamalpur including Construction of 2 Nos 1X4.00m x 4.00m Cross-Drain at Ch.1800m, 1900m3 Nos U-Drain at Ch.1400, 1530, 1600m. | 0 | 0 | 2000 | 2 | 12.32 | 20380927 | 4267698.08 | 24648625.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under process,Estimate approved on 30-9-20
0 | 2020-21 | Jamalpur | Madargonj | Village Road-BC | PRO/JAM/MAD/VR/20-21/W-147 | 339585035 | Improvement of Nobbachar Bazar- Tegaria H/O Khalek via Hidagari road at Ch.0.00-3000m.Under Madarganj Upazila, District Jamalpur including Construction of 2 Nos 2x4.5x4.5m Cross-Drain at Ch.275, 835m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2350m and 3 Nos U-Drain at Ch.01280, 1775, 2050m. | 0 | 0 | 3000 | 3 | 27.76 | 29816039.04 | 9284713.49 | 39100752.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Tender under process, Estimate approved on 30-9-20
158 | 2020-21 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/20-21/W-158 | 339614030 | Improvement of Bituminous carpeting on Kashimara Bazar- Purarchar(Shahin Bazar) Road at Ch.00-2680m.Under Melandah Upazila, District Jamalpur | 0 | 0 | 2680 | 2.68 | 0 | 27176554.32 | 0 | 27176554.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on Dec-20
159 | 2020-21 | Jamalpur | Melandah | Village Road-BC | PRO/JAM/MEL/VR/20-21/W-159 | 339615107 | Improvement of Bituminous carpeting on Dakhin Khashimara-Uttar Khashimara GPS Road at Ch.00-1300m. Including Construction of 1Nos 1x3.0m x2.5m Cross-Drain and 1Nos 0.75X 0.75m U-Drain Under Melandah Upazila, District Jamalpur. | 0 | 0 | 1300 | 1.3 | 3.75 | 12135909.52 | 1468744.46 | 13604653.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on Dec-20
160 | 2020-21 | Jamalpur | Bakshigonj | Village Road-BC | PRO/JAM/BAK/VR/20-21/W-160 | 339074011 | Improvement of Bituminous carpeting on Gazirpare- Kamalerbarti Road at Ch.00-1755m.including Construction of 1Nos 2x4.0m x3.5m Cross-Drain and 2Nos 1x0.60m x 0.60m U-Drain and 3x4.0mx4.50m RCC Box Culvert Under bakshiganj Upazila, District Jamalpur. | 0 | 0 | 1755 | 1.755 | 24.409 | 15750792 | 7344798 | 23095590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on Dec-20
|  |  |  | Total: |  | NOS Est. Packages: | 17 | NOS Cont. Signed: | 11 |  | 40.195 | 247.739 | 402363371.07 | 79648638.17 | 482012009.24 | 271792306.735 | 6472259.456 | 278264566.191 | 6592816.832 | 128452847.013 | [6 empty] | 40.44% | 76432897 | 0 | 76432897 | 5125355 | 0 | 5125355 | 81558252 | 28.63%
Road Maintenance by LCS
99 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-99 | 339153005 | Rural road maintenance by LCS (Material & Wages) work on Chikajani UP Office to Chirmashuri Hat Sarak at Ch. 0.00-7500.00m Dewangonj Upazila, Jamalpur District (15 nos LCS worker) | Chairperson- Anowara Khatun, Secretary- Most. Azma Khatun , LCS Group-02 | 0 | 7500 | 7.5 | 0 | 3466985 | 0 | 3466985 | 3466985 | 0 | 3466985 | 0 | 0 | 0 | 2020-09-01 | 0 | 2022-08-31 | 0 | 0 | 9% | 228750 | 0 | 228750 | 0 | 0 | 0 | 228750 | 6.598% | Maintenance work ongoing
100 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-100 | 339153016 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD-Tilokpur Mollapara Sarak at Ch. 0.00-2190.00m Dewangonj Upazila, Jamalpur district (4 nos LCS worker) | Chairperson- Salma, Secretary- Safely Begum, LCS Group-03 | 0 | 2190 | 2.19 | 0 | 844565 | 0 | 844565 | 844565 | 0 | 844565 | 0 | 0 | 0 | 2020-09-01 | 0 | 2022-08-31 | 0 | 0 | 9% | 45750 | 0 | 45750 | 0 | 0 | 0 | 45750 | 5.417% | Maintenance work ongoing
101 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-101 | 339154027 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD- Molomgonj Bazar Vhatipara Sarak at Ch. 0.00-1500.00m Dewangonj Upazila, Jamalpur District (3 nos LCS worker) | Chairperson- Rima, Secretary- Most. Rowsuna, LCS Group-04 | 0 | 1500 | 1.5 | 0 | 630474 | 0 | 630474 | 630474 | 0 | 630474 | 0 | 0 | 0 | 2020-09-01 | 0 | 2022-08-31 | 0 | 0 | 9% | 61000 | 0 | 61000 | 0 | 0 | 0 | 61000 | 9.675% | Maintenance work ongoing
102 | 2019-20 | Jamalpur | Dewanganj | Maintenance-LCS | PRO/JAM/DEW/RMP/19-20/MW-102 | 339152003 | Rural road maintenance by LCS (Material & Wages) work on Pathorerchar RHD - Sanandabari GC Road at Ch. 0.00-1000.00m Dewangonj Upazila, Jamalpur District (2 nos LCS worker) | Chairperson- Most. Nazma Begum, Secretary- Most. Monowara Begum LCS Group-01 | 0 | 1000 | 1 | 0 | 420383 | 0 | 420383 | 420383 | 0 | 420383 | 0 | 0 | 0 | 2020-09-01 | 0 | 2022-08-31 | 0 | 0 | 9% | 30500 | 0 | 30500 | 0 | 0 | 0 | 30500 | 7.255% | Maintenance work ongoing
|  |  |  | Total: |  | NOS Est. Packages: | 4 | NOS Cont. Signed: | 4 |  | 12.19 | 0 | 5362407 | 0 | 5362407 | 5362407 | 0 | 5362407 | 0 | 0 | [6 empty] | 9% | 366000 | 0 | 366000 | 0 | 0 | 0 | 366000 | 6.825%
Large market
126 | 2019-20 | Jamalpur | Madargonj | Large Market | PRO/JAM/MAD/ LM/19-20/W- 126 | 0 | Construction of Milon Bazar Upazila: Madarganj, Dist:Jamalpur (02 nos LCS group) | LCS 01: Mst. Renura and Mst. Shikha & LCS 02: Mst. Ratna and Mst. Chanvanu | 0 | 0 | 0 | 0 | 0 | 0 | 6013382 | 0 | 0 | 6013382 | 0 | 0 | 0 | 2020-10-09 | 0 | 2021-04-07 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Training will be held on 1st week of Dec-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 6013382 | 0 | 0 | 6013382 | 0 | 0 | [6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Medium Market
150 | 2020-21 | Jamalpur | Bakshigonj | Medium Market | PRO/JAM/BAK/ MM/20-21/W-150 | 0 | Construction of Paschim kamaler barti Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6579551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on 05-11-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 0 |  | 0 | 0 | 0 | 0 | 6579551 | 0 | 0 | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Maintenance-Office Building
2 | 2019-20 | Jamalpur | Sadar | Maintenance-Office | PRO/JAM/MAINT/19-20/MW-02 | 0 | Maintenance and repair work of LGED Office Building, Dist: Jamalpur | SHABUZ ENTERPRISE | 0 | 0 | 0 | 0 | 0 | 0 | 186010 | 0 | 0 | 186010 | 0 | 0 | 0 | 2019-12-17 | 2019-12-19 | 2020-01-13 | 0 | 0 | 100% | 0 | 0 | 166478 | 0 | 0 | 19532 | 186010 | 100% | Final bill paid
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 1 |  | 0 | 0 | 0 | 0 | 186010 | 0 | 0 | 186010 | 0 | 0 | [6 empty] | 100% | 0 | 0 | 166478 | 0 | 0 | 19532 | 186010 | 100%
Union Road
161 | 2020-21 | Jamalpur | Bakshigonj | Union Road-BC | PRO/JAM/BAK/UNR/20-21/W-161 | 339073012 | Improvement of Bituminous carpeting on Merurchar UP Office- Jabbergonj GC via Chinarchar Gudharaghat Road at Ch.2900-4050m. Including 2Nos 2x4.0mx4.5m Cross-Drain Under bakshiganj Upazila, District Jamalpur. | 0 | 2900 | 4050 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Estimate approved on Dec-20
|  |  |  | Total: |  | NOS Est. Packages: | 1 | NOS Cont. Signed: | 0 |  | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 0 | 0 | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Union Road BC
|  |  |  | Total: |  | NOS Est. Packages: | 0 | NOS Cont. Signed: | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
Summary
FY-2018-19
Component |  | Nos of Est. | Nos of Contr. | Road length | STR length | Est. Road | Est. Structure | Total Est. | Contr. Road | Contr. Structure | Total Contract | Variation | Phy Prog. | RPA Road | RPA Struc. | RPA Total | GOB Road | GOB Struc. | GOB Total | Total Paid | Fin. Prog.
Union-BC |  | 1 | 0 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Village-BC |  | 17 | 11 | 40.195 | 247.739 | 402363371.07 | 79648638.17 | 482012009.24 | 271792306.735 | 6472259.456 | 278264566.191 | 6592816.832 | 40.44% | 76432897 | 0 | 76432897 | 5125355 | 0 | 5125355 | 81558252 | 28.63%
Maintenance-LCS |  | 4 | 4 | 12.19 | 0 | 5362407 | 0 | 5362407 | 5362407 | 0 | 5362407 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Large Market |  | 1 | 1 |  |  | 0 | 0 | 6013382 | 0 | 0 | 6013382 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Medium Market |  | 1 | 0 | 0 | 0 | 0 | 0 | 6579551 | 0 | 0 | 0 | 0 | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO | Update after WO
Office-Maint. |  | 1 | 1 | 0 | 0 | 0 | 0 | 186010 | 0 | 0 | 186010 | 0 | 100% | 0 | 0 | 166478 | 0 | 0 | 19532 | 186010 | 100%
| Total: | 25 | 17 | 53.535 | 250.739 | 419032242 | 86563613.95 | 518374798.95 | 277154713.735 | 6472259.456 | 289826365.191 | 6592816.832 | 38.89% | 76432897 | 0 | 76599375 | 5125355 | 0 | 5144887 | 81744262 | 27.58%
Unallocated Packages
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153005 | Chikajani Up- Charmaguri hat road
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153016 | Kharma Naya Bazar RHD-TilokpurMollapara
|  | Jamalpur | Dewanganj | Union Road-BC |  | 339153011 | Dangdhara UP-Bottola Bazar.
|  | Jamalpur | Bakshigonj | Union Road-BC |  | 339073012 | Merurchar UP Office - Jabbergonj GC via Chinarchar Gudaraghat road
|  | Jamalpur | Melandah | Union Road-BC |  | 339613007 | Ghoserpara UP (Beltoi Bazar)-Charshaguna Bazar Road.
|  | Jamalpur | Dewanpur | Village Road-BC |  | 339154027 | Kharma Naya Bazar RHD- Molomgonj Bazar Vhatipara
|  | Jamalpur | Dewanpur | Village Road-BC |  | 339154032 | Chakpara FRB to Sarkerpara FRB via Amkhowa Bazar
|  | Jamalpur | Madargonj | Village Road-BC |  | 339584061 | Teguria Bazar-Pakrul- Kolikandi Road
|  | Jamalpur | Madargonj | Village Road-BC |  | 339585035 | Nobbachar Bazar- Taguria h/o Khalek via Hidagari road.
|  | Jamalpur | Madargonj | Village Road-BC |  | 339585030 | Gabergram Bazar Embank- Bafatuddin Talukder high school road.
|  | Jamalpur | Madargonj | Village Road-BC |  | 339584060 | Jonail-Koira UZR(Bow Bazar)-Khilkati via Purbo Shokhnagari
|  | Jamalpur | Bakshigonj | Village Road-BC |  | 339075096 | Battajure Nuton Bazar-Battajore Paschimpara via Shamisaya school road
|  | Jamalpur | Bakshigonj | Village Road-BC |  | 339074011 | Gazirpara-Kamalerbatti road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339615106 | Mahmudpur Bazar - Adbaria H/o Shanbania Via Purba Mahamudpur GPS Road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339614111 | Mahmudpur bazar-Imampur H/O Shahjahan member Road
|  | Jamalpur | Melandah | Village Road-BC |  | 339615108 | Mahmudpur Bazer - Imampur UZR Road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339615107 | Nalsia (Khashimara) - Utter Khashimara GPS Road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339615037 | Kangalkursha RHD to Tarakandi bazar UZR Road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339615072 | Bhaluka More UZR - Chinitola GPS Road.
|  | Jamalpur | Melandah | Village Road-BC |  | 339614030 | Khashimara bazar-Purarchar(Shahin Bazar) Road.
|  | Jamalpur | Islampur | Village Road-BC |  | 339295009 | Deghair - Bhangbari Road
|  | Jamalpur | Islampur | Village Road-BC |  | 339295032 | Char Deghair Dakhil Madrasha-Mohez Mulla house road
|  | Jamalpur | Islampur | Village Road-BC |  | 339295033 | Char Shisua GPS-Changania RNGPS via Degahir road-
|  | Jamalpur | Islampur | Village Road-BC |  | 339294035 | Napiterchar High School -Chandanpur village via Dasani River Ferry Ghat road.
|  | Jamalpur | Islampur | Village Road-BC |  | 339294067 | Duttapara R&H to Napiterchar Bazar via Adorsha Gramm road
|  | Jamalpur | Islampur | Village Road-BC |  | 339294087 | Malmara Bazar-Napiterchar Bazar road.
|  | Jamalpur | Islampur | Village Road-BC |  | 339294008 | Malmara - Bulakipara road.
|  | Jamalpur | Islampur | Village Road-BC |  | 339294085 | Kazla-Kathma Bazar road.
|  | Jamalpur | Islampur | Village Road-BC |  | 339295017 | Kazla Kamar bari-Horindhora road.
|  | Jamalpur | Melandah | Large Market |  |  | Mahmudpur
|  | Jamalpur | Madargonj | Large Market |  |  | Milon Bazar
|  | Jamalpur | Dewanganj | Large Market |  |  | Khorma bazar
|  | Jamalpur | Dewanganj | Large Market |  |  | Jhalur Char
|  | Jamalpur | Dewanganj | Large Market |  |  | Sanandabari
|  | Jamalpur | Dewanganj | Large Market |  |  | Molla Para Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Bhabki Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Talukpara Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Jhawgora Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Gazipur Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Shahin Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Char Gobindi Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Nalsia bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Millon Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Millon Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Saguna Bzar
|  | Jamalpur | Melandah | Medium Market |  |  | Kahetpara bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Tegharia Bazar
|  | Jamalpur | Melandah | Medium Market |  |  | Gobindoganj Bazar
|  | Jamalpur | Islampur | Medium Market |  |  | Duttapara Ananda Bazar
|  | Jamalpur | Bakshigonj | Medium Market |  |  | Gazirpara Annanda Bazar
|  | Jamalpur | Bakshigonj | Medium Market |  |  | parchim kamalerbatti Bazar
|  | Jamalpur | Madargonj | Medium Market |  |  | Nabbo Char Bazar
|  | Jamalpur | Madargonj | Medium Market |  |  | Teguria bazar
|  | Jamalpur | Madargonj | Medium Market |  |  | Rayerchara Bazar
|  | Jamalpur | Madargonj | Medium Market |  |  | Koali Kandi Bazar
|  | Jamalpur | Dewanganj | Medium Market |  |  | Amkhowa Bazar
|  | Jamalpur | Dewanganj | Medium Market |  |  | Char Maguri Hat
|  | Jamalpur | Melandah | Small Market |  |  | Bhaluka(Tarankandi Bazar)
|  | Jamalpur | Islampur | Small Market |  |  | Mondalpara Bazar
|  | Jamalpur | Islampur | Small Market |  |  | Shirajabad Bazar
|  | Jamalpur | Islampur | Small Market |  |  | Malmara Bazar
|  | Jamalpur | Islampur | Small Market |  |  | Akota Bazar
|  | Jamalpur | Islampur | Small Market |  |  | Napiterchar Bazar
|  | Jamalpur | Islampur | Small Market |  |  | Bulakip (ara Bazar)
|  | Jamalpur | Bakshigonj | Small Market |  |  | Merurchar

## Sheet2
Difference from Previous Month
Component | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog.
Union Road-BC | 1 | 2 | 1.15 | 3 | 11306463.93 | 6914975.78 | 18221439.71 | 28412878.581 | 11560989.585 | 39973868.166 | 0 | 8.312% | 29793479 | 2880429 | 32683908 | 2053180 | 565721 | 2618901 | 35302809 | 5.981%
Village Road-BC | 7 | 10 | 16.235 | 103.509 | 153883785.88 | 33327370.17 | 187211156.05 | 136768278.761 | 14102207.911 | 149968966.672 | -238869.598 | 1.195% | 72921181.01 | 3720581.99 | 76641763 | 6444306.99 | 373710.01 | 6818017 | 83459780 | 2.601%
Village Road-HBB | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 16233193.128 | 0 | 16233193.128 | 0 | -47.11% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34.15%
Rehabilitation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance | 0 | 17 | 0 | 0 | 25333325.83 | 0 | -420382.93 | 31018996.65 | 0 | 17020198.59 | 0 | 6.491% | 1060200 | 0 | 1060200 | 0 | 0 | 0 | 1060200 | 3.418%
Small Market | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Medium Market | 4 | 2 | 0 | 0 | 0 | 0 | 22787810 | 0 | 0 | 8399491 | 0 | 2.381% | 1283500 | 0 | 1283500 | 0 | 0 | 0 | 1283500 | 0.2758%
Large market | 0 | 2 | 0 | 0 | 0 | 0 | -8931173.14 | 0 | 0 | 6887994.86 | 0 | 12.7% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 12.7%
Total: | 13 | 35 | 17.385 | 106.509 | 190523575.64 | 40242345.95 | 222920807.69 | 212433347.12 | 25663197.496 | 238483712.416 | -238869.598 | -0.148% | 105058360.01 | 6601010.99 | 112422466 | 8497486.99 | 939431.01 | 9558435.86 | 121980901.86 | 2.149%
This Month
Component | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog.
Union Road-BC | 23 | 19 | 39.064 | 109.8 | 340489859.26 | 32932115.75 | 373421975.01 | 258190221.816 | 20555909.012 | 278746130.83 | 0 | 66.78% | 119568699.59 | 9888525.41 | 129467225 | 15400730.77 | 1716967.23 | 17117698 | 146584923 | 52.59%
Village Road-BC | 69 | 58 | 136.603 | 522.149 | 1185672177.34 | 148066106.73 | 1333738284.07 | 916154534.182 | 48715359.479 | 964869893.66 | 6592816.832 | 55.45% | 315858858.18 | 15851754.86 | 331710613.04 | 66771112.46 | 2093720.64 | 68864833.1 | 400575446.14 | 41.52%
Village Road-HBB | 4 | 4 | 6.045 | 7.5 | 32107183.15 | 2229230 | 34336413.15 | 28425369.608 | 0 | 28425369.608 | 0 | 40.16% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 25.65%
Rehabilitation | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance | 19 | 17 | 75.241 | 0 | 37616513.11 | 0 | 37616513.11 | 31018996.65 | 0 | 31018996.65 | 0 | 6.491% | 1060200 | 0 | 1060200 | 0 | 0 | 0 | 1060200 | 3.418%
Small Market | 1 | 0 | 0 | 0 | 0 | 0 | 4051958 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Medium Market | 13 | 8 | 0 | 0 | 0 | 0 | 52619955 | 0 | 0 | 23404215 | 0 | 18.63% | 3461000 | 0 | 3461000 | 0 | 0 | 0 | 3461000 | 14.79%
Large market | 3 | 2 | 0 | 0 | 0 | 0 | 13094542.86 | 0 | 0 | 6887994.86 | 0 | 12.7% | 0 | 0 | 753095 | 0 | 0 | 121517.86 | 874612.86 | 12.7%
Total: | 137 | 113 | 258.993 | 646.949 | 1602857275.86 | 185142584.48 | 1860968579.06 | 1239007391.146 | 71186400.491 | 1343094535.828 | 6592816.832 | 55.19% | 447238867.77 | 25740280.27 | 475732583.04 | 82171843.23 | 3810687.87 | 86245098.82 | 561977681.86 | 41.64%
Previous Month
District | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog.
Union Road-BC | 22 | 17 | 37.914 | 106.8 | 329183395.33 | 26017139.97 | 355200535.3 | 229777343.235 | 8994919.427 | 238772262.664 | 0 | 58.46% | 89775220.59 | 7008096.41 | 96783317 | 13347550.77 | 1151246.23 | 14498797 | 111282114 | 46.61%
Village Road-BC | 62 | 48 | 120.368 | 418.64 | 1031788391.46 | 114738736.56 | 1146527128.02 | 779386255.421 | 34613151.568 | 814900926.988 | 6831686.43 | 54.26% | 242937677.17 | 12131172.87 | 255068850.04 | 60326805.47 | 1720010.63 | 62046816.1 | 317115666.14 | 38.91%
Village Road-HBB | 4 | 2 | 6.045 | 7.5 | 32107183.15 | 2229230 | 34336413.15 | 12192176.48 | 0 | 12192176.48 | 0 | 87.27% | 7290110 | 0 | 7290110 | 0 | 0 | 0 | 7290110 | 59.79%
Rehabilitation | 2 | 2 | 2.04 | 7.5 | 6971543 | 1915132 | 8886675 | 5218268.89 | 1915132 | 7133400.89 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Maintenance | 19 | 0 | 75.241 | 0 | 12283187.28 | 0 | 38036896.04 | 0 | 0 | 13998798.06 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Small Market
Medium Market | 9 | 6 | 0 | 0 | 0 | 0 | 29832145 | 0 | 0 | 15004724 | 0 | 16.25% | 2177500 | 0 | 2177500 | 0 | 0 | 0 | 2177500 | 14.51%
Large market | 3 | 0 | 0 | 0 | 0 | 0 | 22025716 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Total: | 121 | 75 | 241.608 | 540.44 | 1412333700.22 | 144900238.53 | 1634845508.51 | 1026574044.026 | 45523202.995 | 1102002289.082 | 6831686.43 | 53.98% | 342180507.76 | 19139269.28 | 361319777.04 | 73674356.24 | 2871256.86 | 76545613.1 | 437865390.14 | 39.49%

## Sheet1
FY 2019-2020 Packages status
District | Nos of Estimate | Nos of Tender invited | Nos of Evaluation on going | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount
Gaibandha | 10 | 3 | 3 | 8 | 30.85 | 20.6 | 78985036.62 | 3876273 | 82861309.62 | 42486580.534 | 2283645.85 | 44770226.384
Kurigram | 27 | 11 | 8 | 21 | 30.986 | 36.3 | 151475946.95 | 7210718 | 185959701.67 | 120198958.31 | 3489105.23 | 131128745.262
Nilphamari | 8 |  |  | 5 | 23.604 | 58 | 98884775.19 | 14675554 | 113560329.19 | 63114169.23 | 0 | 63114169.23
Rangpur | 7 | 1 | 1 | 7 | 17.542 | 57.3 | 60715258.21 | 16332559 | 84222086.21 | 49088139.66 | 15559984.3 | 71228664.43
Lalmonirhat | 20 | 7 | 4 | 15 | 27.635 | 75.35 | 206195621.14 | 18299798 | 250237889.14 | 127718576.092 | 16419707.078 | 156818413.169
Jamalpur | 19 | 5 | 1 | 11 | 39.125 | 215.639 | 291037523.81 | 76919258.95 | 380735725.76 | 161766943.01 | 0 | 167966335.01
TOTAL: | 91 | 27 | 17 | 67 | 169.742 | 463.189 | 887294161.92 | 137314160.95 | 1097577041.59 | 564373366.836 | 37752442.458 | 635026553.485
2018-2019
District | Nos of Estimate | Nos of Contract Signed | Road length (km) | C/D Structure length (m) | Estimated amount (Road) | Estimated amount C/D Structure | Total Estimated amount | Contact Signed amount (Road) | Contact Signed amount (C/D Structure) | Total Contract Signed amount | Variation | Phy Prog. | RPA Bill paid (Road) | RPA Bill paid (Structure) | RPA Bill paid Total | GOB Bill paid (Road) | GOB Bill paid (Structure) | GOB Bill paid Total | Total Bill Paid | Fin. Prog.
Gaibandha | 9 | 9 | 18.167 | 55.7 | 156021406.09 | 10390224 | 166411630.09 | 158559904.6 | 7034849.59 | 165594754.19 | 0 | 38.05% | 14332350 | 3655549 | 17987899 | 2277503 | 595998 | 2873501 | 20861400 | 12.6%
Kurigram | 14 | 14 | 25.575 | 30.68 | 190375197.91 | 9723954.51 | 200099152.42 | 174173314.914 | 9298740.07 | 183472054.984 | 0 | 22.87% | 2123205 | 0 | 2123205 | 0 | 0 | 0 | 2123205 | 1.157%
Nilphamari | 3 | 3 | 6.049 | 32.68 | 49227188.05 | 9210233.75 | 58437421.8 | 47716680.8 | 9050661.417 | 56767342.217 | 0 | 3.123% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Rangpur | 3 | 3 | 4.745 | 5.4 | 38507505.85 | 1680037 | 40187542.85 | 36670322.3 | 1577447.5 | 38247769.8 | 0 | 47.79% | 9202625 | 0 | 9202625 | 600000 | 0 | 600000 | 9802625 | 25.63%
Lalmonirhat | 11 | 11 | 20.305 | 24.2 | 153437097.85 | 7179619.27 | 160616717.12 | 142126030.971 | 0 | 142126030.971 | 0 | 44.8% | 21471677 | 0 | 21471677 | 15500000 | 0 | 15500000 | 36971677 | 26.01%
Jamalpur | 6 | 6 | 14.41 | 35.1 | 127994718.19 | 9644355 | 137639073.19 | 115387770.725 | 6472259.456 | 121860030.181 | 0 | 13.02% | 4320516 | 0 | 4320516 | 600000 | 0 | 600000 | 4920516 | 4.038%
TOTAL: | 46 | 46 | 89.251 | 183.76 | 715563113.94 | 47828423.53 | 763391537.47 | 674634024.31 | 33433958.033 | 708067982.343 | 0 | 28.89% | 51450373 | 3655549 | 55105922 | 18977503 | 595998 | 19573501 | 74679423 | 10.55%