## September-2020
Sunamganj Pourashava
Sunamganj Pourashava Infrastructure Improvement Project (SPIIP)
Monthly Progress Report (Physical & Financial)
District : Sunamganj | [17 empty] | Reporting Month : September, 2020
Sl. No. | Pourashava | Package No. | Name of Scheme with Chainage & ID No. | Quantity |  | Estimate Cost |  |  | Cost of Salvage Material (Tk.) | Tender Receiving Date | Name of Contractor | Date of NOA issued | Date of Contract/ Revised Contract. | Contract/ Variation Amount (Tk.) | Work Commencement Date | Physical progress (%) | Date of Completion as per contract | Validity date of Bank Guarantee | Payment Amount for |  |  | Financial Progress (%) | Remarks
|  |  |  | Road (Km) | Struct./ Drain (km) | Road (Tk.) | Struct. (Tk.) | Total | [10 empty] | Road (Tk.) | Bridge/ Culvert (Tk.) | Remaining Payment (Tk.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Sunamganj | 415134 PD/SPIIP/RD-01 | (a) Beautification & Widening of river side road. (from Uttor Arpinnagar community center to Teghoria ghat).Ch00-184m. | 0.184 |  | 12076692 |  | 12076692 | - | 2020-06-02 | M/S Suchona Trading | 2020-01-03 | NA | 10869022.8 | 2020-08-03 | 70% | 2020-07-09 | online deposit. not released yet | 9000000 |  | 1869022.8 | 82.8%
|  |  | (b) Development of road from River side to House of Ali Hussain at Uttar Arpinnagar.ch00-140m. | 0.14 |  | 1852870 |  | 1852870 | - |  |  |  |  | 1667583 |  | 100% |  |  | 1028751 |  | 638832 | 61.69%
Package Total = |  |  |  | 0.324 |  | 13929562 |  | 13929562 | - |  |  |  |  | 12536605.8 |  | 85% |  |  | 10028751 |  | 2507854.8 | 72.25%
2 | Sunamganj | 415213 PD/SPIIP / RD-75 | Construction of 2 nos. Ghatla at Uttar Arpinnagar at ch:70 & 120m. |  | 2 | 2820447 |  | 2679424.593 | - | 2020-06-02 | M/S Pradeep Enterprise | 2020-01-03 | NA | 2679424.593 | 2020-08-03 | 95% | 2020-07-09 | do | 2142475 |  | 2142475.67 | 79.96%
Package Total = |  |  |  | 0 | 2 | 2679424.593 |  | 2679424.593 | - |  |  |  |  | 2679424.593 |  | 95% |  |  | 2142475 |  | 2142475.67 | 79.96%
3 | Sunamganj | 436156 PD/SPIIP/ RD-02 | (a) Rehab of Arpinnagar K.B.Maktab BC road from R & H to West bazar Mosque (ch:00-454m). | 0.454 |  | 2457659 |  | 2457659 | - | 25-03-2020 | M/S Riya Enterprise | 2020-08-06 | NA | 2334776.05 | 14/7/2020 | 0% | 14/1/2021 | do | 0 |  | 0 | 0
|  |  | b) Rehab.of RCC Road from Arpinnagar K.B Maktab road to house of Mr.Nurul Goni. (ch:00-95m). | 0.095 |  | 506023.24 |  | 506023.24 | - |  |  |  |  | 480722.078 |  | 0% |  |  | 0 |  | 0 | 0
|  |  | (c)Rehab of Boropara RCC road from house of Manik miah to river Surma (ch:00-287m) | 0.287 |  | 2656491 |  | 2656491 | - |  |  |  |  | 2523666.45 |  | 15% |  |  | 0 |  | 0 | 0
Package Total = |  |  |  | 0.836 |  | 5620173.24 |  | 5620173.24 | - |  |  |  |  | 5339164.578 |  | 5% |  |  | 0 |  | 0 | 0%
4 | Sunamganj | 436189 PD/SPIIP/ RD-03 | (a) Development of C.Eidgah RCC road & Rehab of RCC road from Teghoria govt pond to Moyner point.(ch:00-310 & ch: 310-690m.) | 0.69 |  | 10376001 |  | 10376001 | - | 25-03-2020 | Md. Atiqur Rahman | 2020-02-06 | NA | 9338400.9 | 2020-07-07 | 75% | 2021-06-01 | do | 7000000 |  | 2338400.9 | 74.96%
|  |  | (b) Rehabilitation of Electric supply RCC road (ch:00-190m) | 0.19 |  | 2343624.23 |  | 2343624.23 | - |  |  |  |  | 2109261.807 |  | 75% |  |  | 1476482 |  | 632779.807 | 70%
Package Total = |  |  |  | 0.88 |  | 12719625.23 |  | 12719625.23 | - |  |  |  |  | 11447662.707 |  | 75% |  |  | 8476482 |  | 2971180.707 | 72.48%
5 | Sunamganj | 436295 PD/SPIIP/ RD-04 | Rehabilitatoin of Kalipur RCC road ( ch: 00-1430m) | 1.43 |  | 14462294.05 |  | 14462294.05 | - | 25-03-2020 | Md. Rezaul Alam | 2020-04-06 | NA | 13016964.54 | 2020-03-07 | 15% | 2021-04-01 | do | 1952544 |  | 11064420.54 | 15%
Package Total = |  |  |  | 1.43 |  | 14462294.05 |  | 14462294.05 | - |  |  |  |  | 13016964.54 |  | 15% |  |  | 1952544 |  | 11064420.54 | 15%
6 | Sunamganj | 436438 PD/SPIIP/ RD-05 | (a) Rehabilitation of RCC road from Bihari point to Moyner point(ch:00-175) | 0.175 |  | 3507030.13 |  | 3507030.13 | - | 30-03-2020 | Md. Rezaul Alam | 2020-04-06 | NA | 3156327.11 | 2020-02-07 | 98% | 2021-04-01 | do | 2840694 |  | 315633.11 | 90%
|  |  | (b) Rehab.of RCC road from Kazir point to BIAM Laboratory School (ch:00-265m. Link ch:00-30) | 0.295 |  | 4008670.69 |  | 4008670.69 | - |  |  |  |  | 3607803.62 |  | 98% |  |  | 3247022 |  | 360781.62 | 90%
|  |  | (c) Rehabilitatoin of RCC road from Wayeskhali Police line to Gonipur culvert (ch:00-658m) | 0.658 |  | 5683920 |  | 5683920 | - |  |  |  |  | 5115528.008 |  | 60% |  |  | 2813000 |  | 2302528.008 | 54.99%
Package Total = |  |  |  | 1.128 |  | 13199620.82 |  | 13199620.82 | - |  |  |  |  | 11879658.738 |  | 85.33% |  |  | 8900716 |  | 2978942.738 | 54.99%
7 | Sunamganj | 436441 PD/SPIIP/ RD-06 | (a)Rehabilitation of road from Kazir point to Sluice Gate at Dhupakhali (ch:00-980m) | 0.98 |  | 6957948 |  | 6957948 | - | 30-03-2020 | M/S Mahbub Enterprise | 2020-07-06 | NA | 6262153.2 | 19/7/20 | 25% | 18/1/2021 | do | 0 |  | 0 | 0%
|  |  | (b)Rehabilitation of Natunpara main road by BC & RCC (ch:00-970 & Link-ch:00-58m) | 1.028 |  | 5586560.67 |  | 5586560.67 | - |  |  |  |  | 5027904.603 |  | 25% |  |  | 0 |  | 0 | 0%
Package Total = |  |  |  | 2.008 |  | 12544508.67 |  | 12544508.67 | - |  |  |  |  | 11290057.803 |  | 25% |  |  | 0 |  | 0 | 0%
8 | Sunamganj | 436443 PD/SPIIP/RD-07 | Development of DS road from traffic point to Kajir point.(ch:00-1020m). | 1.02 |  | 12911768.71 |  | 12911768.71 | - | 30-03-2020 | M/S Priti Enterprise | 2020-07-06 | NA | 11620591.839 | 2020-04-07 | 60% | 2021-04-01 | do | 6391325 |  | 5229266.839 | 55%
Package Total = |  |  |  | 1.02 |  | 12911768.71 |  | 12911768.71 | - |  |  |  |  | 11620591.839 |  | 60% |  |  | 6391325 |  | 5229266.839 | 55%
9 | Sunamganj | 436446 PD/SPIIP/ RD-38 | (a)Construction of RCC secondary drain from Kamarkhal to new court point.(ch:00-580) |  | 0.58 | 10663506 |  | 10663506 | - | 30-03-2020 | M/S Nazma Engineering | 2020-02-06 | NA | 9597155.4 | 2020-06-07 | 25% | 2021-06-01 | do | 0 |  | 0 | 0%
|  |  | (b)Construction of Secondary Drain at Boropara (ch:00-110 & ch: 00-97m) |  | 0.207 | 3601913.99 |  | 3601913.99 | - |  |  |  |  | 3241722.591 |  | 0% |  |  | 0 |  | 0 | 0%
Package Total = |  |  |  |  | 0.787 | 14265419.99 |  | 14265419.99 | - |  |  |  |  | 12838877.991 |  | 12.5% |  |  | 0 |  | 0 | 0%
10 | Sunamganj | 436447 PD/SPIIP/RD-39 | (a) Construction of secondary drain at West Natunpara road(Main- ch:180-320m,L-1 ch:00-166m,L2-ch: 00-70m & L3-ch:00-135m) |  | 0.511 | 8368803 |  | 8368803 | - | 30-03-2020 | Md. Atiqur Rahman | 2020-02-06 | NA | 8305283.79 | 2020-06-07 | 0% | 2021-06-01 | do | 0 |  | 0 | 0%
|  |  | (b) Construction of RCC secondary drain from Jamtola Mollabari to Jamaipara via Nurani(ch:00-300m). |  | 0.3 | 6513186.03 |  | 6513186.03 | - |  |  |  |  | 6463776.971 |  | 0% |  |  | 0 |  | 0 | 0%
Package Total = |  |  |  |  | 0.811 | 14881989.03 |  | 14881989.03 | - |  |  |  |  | 14769060.761 |  | 0% |  |  | 0 |  | 0 | 0%
11 | Sunamganj | 436454 PD/SPIIP/RD-41 | (a) Construction of RCC primary drain from near Alimabag Mosque to Public Library(ch:00-350m &link ch:00-50m) |  | 0.4 | 6530706 |  | 6530706 | - | 30-03-2020 | Md. Atiqur Rahman | 2020-02-06 | NA | 5877635.4 | 2020-06-07 | 0% | 2021-06-01 | do | 0 |  | 0 | 0%
|  |  | (b) Construction of RCC secondary drain at Shulloghar village road (ch:00-385 & link-ch:00-55m). |  | 0.44 | 8695272.01 |  | 8695272.01 | - |  |  |  |  | 7825744.809 |  | 25% |  |  |  |  | 7825744.809 | 0%
Package Total = |  |  |  |  | 0.84 | 15225978.01 |  | 15225978.01 | - |  |  |  |  | 13703380.209 |  | 12.5% |  |  | 0 |  | 7825744.809 | 0%
12 | Sunamganj | 436456 PD/SPIIP/RD-42 | Construction of main drain from culvert near M.r Aftabuddin’s house to Bodipur Bridge(ch:00-385 & link-ch:00-150m). |  | 0.535 | 9329435.44 |  | 9329435.44 | - | 25-03-2020 | M/S Maa Enterprise | 2020-02-06 | NA | 8862963.668 | 2020-05-07 | 40% | 2021-06-01 | do | 3530785 |  | 5332178.668 | 39.84%
Package Total = |  |  |  |  | 0.535 | 9329435.44 |  | 9329435.44 | - |  |  |  |  | 8862963.668 |  | 40% |  |  | 3530785 |  | 5332178.668 | 39.84%
13 | Sunamganj | 436463 PD/SPIIP/RD-43 | Construction of secondary drain at Abul Hosain road from House of Mr. Rokes Lais to Central Graveyard (ch:00-535 & Link- ch:00-70m). |  | 0.605 | 12379879.47 |  | 12379879.47 | - | 30-03-2020 | Md. Rezaul Alam | 2020-04-06 | NA | 11141891.523 | 2020-05-07 | 0% | 2021-04-01 | do | 0 |  | 0 | 0%
Package Total = |  |  |  |  | 0.605 | 12379879.47 |  | 12379879.47 | - |  |  |  |  | 11141891.523 |  | 0% |  |  | 0 |  | 0 | 0%
14 | Sunamganj | 445802 PD/SPIIP/ RD-37 | Construction of RCC drain at Arpinnagar (ch: 00-468m) Link drain at west side of Arpinnagar graveyard (ch:00- 95m) |  | 0.563 | 14764241.46 |  | 14764241.46 | - | 30-03-2020 | M/S Hasan Enterprise | 2020-02-06 | NA | 14741872.884 | 2020-05-07 | 45% | 2021-06-01 | do | 5476922 |  | 9264950.884 | 37.15%
Package Total = |  |  |  |  | 0.563 | 14764241.46 |  | 14764241.46 | - |  |  |  |  | 14741872.884 |  | 45% |  |  | 5476922 |  | 9264950.884 | 37.15%
15 | Sunamganj | 457848 PD/SPIIP/ RD-40 | (a) Construction of East Natunpara RCC Drain( ch:00-160m). |  | 0.16 | 3222930 |  | 3222930 | - | 18-05-2020 | M/S Akil Enterprise | 23/6/20 | NA | 2900637 | 13/7/20 | 0% | 14/1/21 | do | 0 |  | 0 | 0%
|  |  | (b) Construction of RCC secondary drain in front of Gusaibari(ch:00-107m) |  | 0.107 | 2273814 |  | 2273814 | - |  |  |  |  | 2046432.6 |  | 0% |  |  | 0 |  | 0 | 0%
|  |  | (c) Construction of Masonry drain from Town Girls primary school to front of Sweeper colony including footpath (ch:00-272m) |  | 0.272 | 5568764.19 |  | 5568764.19 | - |  |  |  |  | 5011887.771 |  | 40% |  |  | 2000000 |  | 3011887.771 | 39.91%
Package Total = |  |  |  |  | 0.539 | 11065508.19 |  | 11065508.19 | - | - | - | - | - | 9958957.371 | - | 13.33% | - | - | 2000000 |  | 7958957.371 | 13.3% | -
Grand Total = |  |  |  | 7.626 | 4.68 | 179979428.903 |  | 179979428.903 | - | - | - | - | - | 165827135.005 | - | 37.91% | - | - | 48900000 |  | 57275973.026 | 29.49% | -
Fund Received |  | 2019-20 | 48900000
|  | (Sontosh Kumer Das) | [8 empty] | (Kali Krishna Paul) | [7 empty] | (Engr. Mir Musharraf Hossain)
|  | Accountant | [8 empty] | Assistant Engineer | [7 empty] | Executive Engineer
|  | Sunamganj Pourashava. | [8 empty] | Sunamganj Pourashava. | [7 empty] | Sunamganj Pourashava.