## Sheet1
Rural Access Road Improvement Project ( RARIP) in sylhet Division
Monthly Progress Report ( Physical & Financial)
District:- Habigonj
Month:- December-20
SL No | Upazila | Package No | Name of Scheme with location ( Chainage) | Quantity |  | Estimated Cost |  |  | Cost of Salvage Material (Tk) | Tender receiving date | Name of Contractor | Date of NOA Issued | Date of Contract | Contract amount(Tk) | Work Commencement Date | Physical Progress | Pland/Actual Date of Completion | Payment Status |  |  | Fin. Prog (%) | Remarks
|  |  |  | Rd (Km) | St. (M) | Road | Str. | Total | [9 empty] | Final Bill (Tk) | Payment made(Tk) | Remaining Payment (Tk)
April' 2020 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Nabiganj | LGED/RARIP/HAB/VR/18-19/W-80 | Nabiganj-Rudragram-Chandpur Road (Ch. 00-1000m) NabiganjUpazila, ID no: under 636775033, District: Habigonj | 1 | 0.6 | 6966345 | — | 6966345 | 547308 | 22-10-18 | Rabindra Kumar Pal | 2018-12-17 | 08-01-19 | 6956768.83 | 2019-01-11 | 100% | 12-01-20 | _ | 5650000 | 1306768.83 | 81.22%
2 | Nabiganj | LGED/RARIP/HAB/VR/18-19/W-81 | Nabiganj-Habiganj-Siddikpur Pry.School Road (Ch. 00-1000m) under NabiganjUpazila, ID no: 636775177, District: Habigonj | 1 | 0 | 6834324 | — | 6834324 | 0 | 22-10-18 | Rabindra Kumar Pal | 2018-12-17 | 08-01-19 | 6829994.34 | 2019-01-11 | 75% | 12-01-20 | _ | 2390000 | 4439994.34 | 34.99% | AS Complete
3 | Sadar | LGED/RARIP/HAB/VR/18-19/W-84 | Garur bazar Road (Ch. 2000-3500m) under SadarUpazila, ID no: 636445061, District: Habigonj | 1.5 | 0 | 10330853 | — | 10330853 | 0 | 22-10-18 | Md Taj Uddin | 2018-12-17 | 07-01-19 | 10315625 | 2019-01-11 | 95% | 12-01-20 | _ | 672500 | 9643125 | 6.519%
4 | Sadar | LGED/RARIP/HAB/VR/18-19/W-85 | TitokhaiChandpur via Mirzapur Road (Ch. 3290-4765m) under SadarUpazila, ID no: 636444043, District: Habigonj | 1.475 | 0 | 10125352 | — | 10125352 | 0 | 22-10-18 | M/S Neon Enterprise | 2018-12-17 | 03-01-19 | 10123048.81 | 2019-01-08 | 100% | 09-01-20 | _ | 7000000 | 3123048.81 | 69.15% | WBM Complete
5 | Sadar | LGED/RARIP/HAB/VR/18-19/W-86 | PoilNatun bazar-Karangi Embankment Road (Ch. 00-1010m) under Sadar Upazila, ID no:636444049, District: Habigonj | 1.01 | 0 | 7263371 | — | 7263371 | 134532 | 22-10-18 | M/S Neon Enterprise | 2018-12-17 | 03-01-19 | 7262749.84 | 2019-01-08 | 100% | 09-01-20 | _ | 4834000 | 2428749.84 | 66.56% | WBM Complete
6 | Chunarughat | LGED/RARIP/HAB/VR/18-19/W-87 | Shaistaganj Puran bazar-Ulukandi-Borompur Road (Ch. 1775-2775m) under Chunarughat Upazila, ID no: 636264032, District: Habigonj | 1 | 0 | 8313943 | — | 8313943 | 57333 | 22-10-18 | Md Noor Ali | 2018-12-17 | 07-01-19 | 8302000.98 | 2019-01-11 | 100% | 12-01-20 | _ | 4835000 | 3467000.98 | 58.24% | WBM Complete
7 | Chunarughat | LGED/RARIP/HAB/VR/18-19/W-88 | Shatiajuri - Daragaon Road (Ch.1000-2000m) under Chunarughat Upazila, ID no:636264010, District: Habigonj | 1 | 5.4 | 8133094 | — | 8133094 | 32014 | 22-10-18 | Md Noor Ali | 2018-12-17 | 07-01-19 | 8131645.17 | 2019-01-11 | 85% | 12-01-20 | _ | 193680 | 7937965.17 | 2.382% | AS ongoing
8 | Madhabpur | LGED/RARIP/HAB/VR/18-19/W-89 | D.C Road - Bijoynagor Murtaza Ali bari Road (Ch. 00-1200m) under Madhubpur Upazila, ID no:636714116, District: Habigonj | 1.2 | 1.875 | 9240741 | — | 9240741 | 124551 | 22-10-18 | M/S Roni Traders | 2018-12-17 | 07-01-19 | 9002284.63 | 2019-01-11 | 100% | 12-01-20 | _ | 430400 | 8571884.63 | 4.781% | WBM Ongoing
9 | Madhabpur | LGED/RARIP/HAB/VR/18-19/W-90 | Montola Rail Station-SundadilVati Bari via Razapur Road (Ch. 2400-3400m) under MadhubpurUpazila, ID no: 636714018, District: Habigonj | 1 | 0 | 8174645 | — | 8174645 | 0 | 22-10-18 | M/S Roni Traders | 2018-12-17 | 07-01-19 | 8076364.72 | 2019-01-11 | 100% | 12-01-20 | _ | 522880 | 7553484.72 | 6.474% | WBM Ongoing
10 | Nabiganj | LGED/RARIP/HAB/VR/18-19/W-112 | Kamargoan-Doulatpur-Hossainpur Road (Ch. 1550-2550m) under NabiganjUpazila, ID no: 636774028, District: Habigonj | 1 | 0 | 6863452 | — | 6863452 | 0 | 22-10-18 | M/S Neon Enterprise | 2018-12-17 | 03-01-19 | 10278066.7 | 2019-01-08 | 100% | 09-01-20 | _ | 4878480 | 5399586.7 | 47.46% | WBM Complete
| Lakhai |  | Rarishal- Balashri River Road (Ch. 1750-2250m) under LakhaiUpazila, ID no: 636684002, District: Habigonj | 0.5 | 0 | 3416484 | — | 3416484 | 0 | [6 empty] | 100% | [5 empty] | WBM Complete
|  |  | Sub Total Tk= | 1.5 | 0 | 10279936 |  | 10279936 | 0 |  |  |  |  | 10278066.7 |  |  |  |  | 4878480 | 5399586.7
11 | Sadar | LGED/RARIP/HAB/VR/18-19/W-113 | Machulia Bridge- Moshajan bridge Road (Ch. 3000-4000m) SadarUpazila, ID no: 636444056, District: Habigonj | 1 | 0 | 6838185 | — | 6838185 | 0 | 22-10-18 | Md Golam Faruk | 2018-12-17 | 08-01-19 | 11372251.4 | 2019-01-11 | 90% | 12-01-20 | _ | 4140000 | 7232251.4 | 36.4% | WBM Complete
| Madhabpur |  | Horaspur Bazar -Durgapur Road Via Bangabir School Road (Ch. 00-632m) under MadhubpurUpazila, ID no:636714101, District: Habigonj | 0.632 | 2.5 | 4731713 | — | 4731713 | 267557 | [6 empty] | 85% | [5 empty] | Sand filling on going
|  |  | Sub Total Tk= | 1.632 | 2.5 | 11569898 |  | 11569898 | 267557 |  |  |  |  | 11372251.4 |  |  |  |  | 4140000 | 7232251.4
12 | Chunarughat | LGED/RARIP/HAB/VR/17-18/W-114 | PakuriaBattala -Kalenga Rd via Mirashi Road (Ch. 9400-10400m) under ChunarughatUpazila, ID no: 636264053, District: Habigonj | 1 | 0 | 8255128 | — | 8255128 | 39925 | 22-10-18 | Md Taj Uddin | 2018-12-17 | 07-01-19 | 8233929.26 | 2019-01-11 | 75% | 12-01-20 | _ | 1780975 | 6452954.26 | 21.63% | AS Work Complete
13 | Chunarughat | LGED/RARIP/HAB/VR/17-18/W-115 | Kalishiri -Sawtail lane road (Ch. 00-1000m) under ChunarughatUpazila, ID no:636264005, District: Habigonj | 1 | 0 | 7616436 | — | 7616436 | 50795 | 22-10-18 | Md Kamal Ahmed | 2018-12-17 | 07-01-19 | 7614442.38 | 2019-01-11 | 97% | 12-01-20 | _ | 5056000 | 2558442.38 | 66.4% | WBM Complete
14 | Nabiganj | LGED/RARIP/HAB/VR/17-18/W-116 | Ramjanpur-Prajatpur via Bani Road (Ch. 1124-2124m) under NabiganjUpazila, ID no:636775157, District: Habigonj | 1 | 0 | 7760213 | — | 7760213 | 0 | 22-10-18 | M/S Neon Enterprise | 2018-12-17 | 03-01-19 | 7758046.28 | 2019-01-08 | 100% | 09-01-20 | _ | 5588000 | 2170046.28 | 72.03% | WBM Complete
15 | Sadar | LGED/RARIP/HAB/RHB/17-18/W-136 | a) Shahjibazar - Shadurbazar road to Nurpur UP-Kesobpur bazar Road (Ch. 00-1000m) under sadarupazila, ID no: 636443012, District: Habigonj | 1 | 0 | 2618406 | — | 2618406 | 0 | 05-11-18 | Md Taj Uddin | 2018-12-17 | 07-01-19 | 11047367.68 | 2019-01-11 | 100% | 12-01-20 | _ | 8090000 | 2957367.68 | 73.23%
| Sadar |  | b) Nurpur (NHW)-Shutang GC- Amirpur road (Ch. 2350-3980m & Ch. 4575-6078m ) under sadarupazila, ID no: 636443007, District: Habigonj | 3.133 | 0 | 5802550 | — | 5802550 | 0 | [6 empty] | 100%
| Sadar |  | c) Dariapur-Etabarpur rail line road (Ch. 00-900m) under SadarUpazila, ID no: 636444006, District: Habigonj | 0.9 | 0 | 1787804 | — | 1787804 | 0 | [6 empty] | 100%
| Sadar |  | d) Duliakhali-Katiadibazar road (Ch. 00-400m) under SadarUpazila, ID no: 636444036, District: Habigonj | 0.4 | 0 | 845716 | — | 845716 | 0 | [6 empty] | 100%
|  |  | Sub Total Tk= | 5.433 | 0 | 11054476 |  | 11054476 | 0 |  |  |  |  | 11047367.68 |  |  |  |  | 8090000 | 2957367.68
16 | Sadar | LGED/RARIP/HAB/RHB/17-18/W-137 | a) Duliakhal (DR)-Gopalganj Bazar Via Alapur road (Ch. 00-2700m) under SadarUpazila, ID no: 636444061, District: Habigonj | 2.7 | 0 | 6439559 | — | 6439559 | 0 | 05-11-18 | Rabindra Kumar Pal | 2018-12-17 | 08-01-19 | 11093726.32 | 2019-01-11 | 100% | 12-01-20 | _ | 4693040 | 6400686.32 | 42.3% | Edging work ongoing
| Baniyachong |  | b) Baniachong North East Up HQ - Baniachong South West Up HQ via 5/6 Bazar road (Ch. 00-679m) under BaniachongUpazila, ID no: 636113001, District: Habigonj | 0.679 | 0 | 2835234 | — | 2835234 | 0 | [6 empty] | 100%
| Lakhai |  | c) Bulla Bazar - Singhagram Road (Ch. 00-810m) under LakhaiUpazila, ID no: 636684006, District: Habigonj | 0.81 | 0 | 1823892 | — | 1823892 | 0 | [6 empty] | 100%
|  |  | Sub Total Tk= | 4.189 | 0 | 11098685 |  | 11098685 | 0 |  |  |  |  | 11093726.32 |  |  |  |  | 4693040 | 6400686.32
17 | Bahubal | LGED/RARIP/HAB/RHB/17-18/W-138 | a) Mirpur-Nondonpur road (Ch. 00-2000m) under BahubalUpazila, ID no: 636054066, District: Habigonj , | 2 | 0 | 3497668 | — | 3497668 | 0 | 05-11-18 | M/S Bengal Construction | 2018-12-17 | 08-01-19 | 10790571.04 | 2019-01-11 | 100% | 12-01-20 | _ | 5403920 | 5386651.04 | 50.08%
| Madhabpur |  | b) Montala BDR (Bahara UP) Camp-Anandabazar road via Horinkula BDR Camp road (Ch. 00-2000m) under MadhabpurUpazila, ID no: 636713007, District: Habigonj | 2 | 0 | 5086323 | — | 5086323 | 0 | [6 empty] | 95%
| Nabiganj |  | c) Nabigonj College-Pangari-Farmgonj Bazar road (Ch. 3950-4930m) under NabigonjUpazila, ID no: 636773007, District: Habigonj | 0.98 | 0 | 2257246 | — | 2257246 | 0 | [6 empty] | 100%
|  |  | Sub Total Tk= | 4.98 | 0 | 10841237 |  | 10841237 | 0 |  |  |  |  | 10790571.04 |  |  |  |  | 5403920 | 5386651.04
18 | Nabiganj | LGED/RARIP/HAB/RHB/17-18/W-139 | a) Dawpara- Satok Bazar Road (Ch. 00-2500m) under NabigonjUpazila, ID no: 636773010, District: Habigonj | 2.5 | 0 | 10914527 | — | 10914527 | 0 | 05-11-18 | Md Golam Faruk | 2018-12-17 | 08-01-19 | 10898570.85 | 2019-01-11 | 100% | 12-01-20 | _ | 8713600 | 2184970.85 | 79.95%
19 | Baniyachong | LGED/RARIP/HAB/RHB/17-18/W-142 | a) Adrasha Bazar tor-5/6 No Bazar road Via Topkhana road (Ch. 00-1745m) under BaniachongUpazila, ID no: 636114016, District: Habigonj , | 1.745 | 0 | 5485627 | — | 5485627 | 0 | 05-11-18 | Md Golam Faruk | 2018-12-17 | 10-01-19 | 11540094.6 | 2019-01-15 | 100% | 16-01-20 | _ | 4182910 | 7357184.6 | 36.25%
| Azmirigonj |  | b) Paschimbag - Azmiriganj Road (Ch. 00-2050m) under AzmiriganjUpazila, ID no: 636023001, District: Habigonj | 2.05 | 0 | 5460039 | — | 5460039 | 0 | [6 empty] | 95%
| Baniyachong |  | c) Khagaura UP Office-Uzirpur Bazar road Via Khagaura Bazar road (Ch. 4185-4500m) under BaniachongUpazila, ID no: 636113003, District: Habigonj | 0.315 | 0 | 629125 | — | 629125 | 0 | [6 empty] | 100%
|  |  | Sub Total Tk= | 4.11 | 0 | 11574791 |  | 11574791 | 0 |  |  |  |  | 11540094.6 |  |  |  |  | 4182910 | 7357184.6
20 | Chunarughat | LGED/RARIP/HAB/RHB/17-18/W-143 | a) PakuriaBattola - Taltola (Mirashi - Kalenga road (Ch. 00-3100m) under ChunarughatUpazila, ID no: 636264082, District: Habigonj, | 3.1 | 0 | 7690358 | — | 7690358 | 0 | 05-11-18 | Md Kamal Ahmed | 2018-12-17 | 07-01-19 | 11023707.8 | 2019-01-11 | 100% | 12-01-20 | _ | 9546000 | 1477707.8 | 86.6%
| Lakhai |  | b) Kaliadara RHD-Teghoria-Kaluk Road (Ch. 00-1500m) under LakhaiUpazila, ID no: 636685033, District: Habigonj | 1.5 | 0 | 3337718 | — | 3337718 | 0 | [6 empty] | 100%
|  |  | Sub Total Tk= | 4.6 | 0 | 11028076 | — | 11028076 | 0 |  |  |  |  | 11023707.8 |  |  |  |  | 9546000 | 1477707.8
21 | Bahubal | LGED /RARIP/HAB/UNR/18-19/W-08 | a) Snanghat UP office- Raisgonj bazar road (Ch. 3200-4334m) under BahubalUpazila, ID no: 636053001, District: Habigonj | 1.134 | 0 | 7494679 | — | 7494679 | 0 | 2018-12-10 | M/S Neon Enterprise | 2019-05-29 | 2019-06-25 | 21462107.66 | 2019-07-01 | 55% | 2020-06-30 | — | 0 | 21462107.66 | 0% | —
| Bahubal |  | b) Bahubal UP office- Rajapur bazar road (Ch. 2600-2690m & 3000-3450m) under BahubalUpazila, ID no: 636053010, District: Habigonj | 0.54 | 0 | 3918117 | — | 3918117 | 0 | [6 empty] | 100% |  | —
| Sadar |  | c) Nurpur (NHW)-Shutang GC-Aminpur road (Ch. 1450-2350m & 3980-4250m) under SadarUpazila, ID no: 636443007, District: Habigonj | 1.17 | 4 | 10243662 | — | 10243662 | 440524 | [6 empty] | 60% |  | —
|  |  | Sub Total Tk= | 2.844 | 4 | 21656458 |  | 21656458 | 440524 |  |  |  |  | 21462107.66 |  |  |  |  | 0 | 21462107.66
22 | Madhabpur | LGED/RARIP/HAB/UNR/18-19/W-12 | a) Madhabpur R&H-Sultanpur-Gateghar Bazar-Shajahanpur UP road (Ch. 2235-4235m) under MadhabpurUpazila, ID no: 636713010, District: Habigonj | 2 | 0 | 14753461 | — | 14753461 | 241169 | 2018-12-10 | Md Mizanur Rahaman Shahim | 2019-05-29 | 2019-06-25 | 37666716.21 | 2019-07-01 | 70% | 2020-06-30 | — | 0 | 37666716.21 | 0% | —
| Chunarughat |  | b) Chunarughat UP office- Shakir Mohammad bazar road (Ch. 850-2350m) under ChunarughatUpazila, ID no: 636263010, District: Habigonj | 1.5 | 4.875 | 11778120 | — | 11778120 | 99381 | [6 empty] | 95% |  | —
| Chunarughat |  | c) Deurgach UP office (Chunarughat Rail Station)-Amorote Bazar (Rail Station) road (Ch. 3080-4680m) under ChunarughatUpazila, ID no: 636263003, District: Habigonj | 1.6 | 0 | 11397739 | — | 11397739 | 0 | [6 empty] | 100% |  | —
|  |  | Sub Total Tk= | 5.1 | 4.875 | 37929320 | — | 37929320 | 340550 |  |  |  |  | 37666716.21 |  |  |  |  | 0 | 37666716.21
23 | Bahubal | LGED/RARIP/HAB/VR/18-19/W-82 | a) Laskarpur Rail way-Mirpur Ekdala Road (Ch. 2600-3555m) under BahubalUpazila, ID no: 636054063, District: Habigonj | 0.955 | 0.625 | 6516486 | — | 6516486 | 0 | 2018-12-18 | M/S Neon Enterprise | 2019-04-17 | 2019-05-12 | 14146667.62 | 2019-05-19 | 100% | 2020-05-18 | — | 0 | 14146667.62 | 0% | —
| Bahubal |  | b) Bishwa Road-Hafizpur-Dimura via Mirpur Dhuliakhal Road (Bishwa Road-HafizpurDimura via Dhuliakhal Road) (Ch. 800-2100m) under BahubalUpazila, ID no: 636054034, District: Habigonj | 1.3 | 0.625 | 8925069 | — | 8925069 | 0 | [6 empty] | 100% |  | —
|  |  | Sub Total Tk= | 2.255 | 1.25 | 15441555 |  | 15441555 | 0 |  |  |  |  | 14146667.62 |  |  |  |  | 0 | 14146667.62
24 | Baniyachong | LGED/RARIP/HAB/VR/18-19/W-83 | Adrasha Bazar- SholatekaGondabpur via Mojlishpur Road (Ch. 00-1015m) under BaniachongUpazila, ID no: 636115049, District: Habigonj | 1.015 | 0 | 7385154 | — | 7385154 | 293807 | 18.12.18 | Mizanur Rahman Shamim | 25.2.19 | 21.3.19 | 7248471.72 | — | 100% | 27.3.20 | — | 0 | 7248471.72 | 0% | —
25 | Bahubal | LGED/RARIP/HAB/VR/18-19/W-92 | Khagaura-Algahati road (Ch. 00-1200m) under BahubalUpazila, ID no:636055015, District: Habigonj | 1.2 | 0 | 8209287 | — | 8209287 | 0 | 18.12.18 | M/S Neon Enterprise | 25.2.19 | 21.3.19 | 8025248 | — | 100% | 27.3.20 | — | 5000000 | 3025248 | 62.3% | WBM Complete
26 | Nabiganj | LGED/RARIP/HAB/VR/18-19/W-93 | Barogaon Dakin Tila imam tea garden Road (Ch. 00-1000m) under NabigonjUpazila, ID no: 636775060, District: Habigonj. | 1 | 0.6 | 6840437 | 754135 | 7594572 | 0 | 18.12.18 | MD. Shoyeb Ahmed | 29.8.19 | 23.9.19 | 7162041.25 | 2019-10-01 | 30% | 2020-10-30 | — | 0 | 0 | 0%
27 | Nabiganj | LGED/RARIP/HAB/VR/18-19/W-94 | Rustampur- Dharmonagar Road (Ch. 00-1000m) under NabigonjUpazila, ID no: 636774031, District: Habigonj. | 1 | 0 | 7351203 | — | 7351203 | 1734389.74 | 18.12.18 | Mizanur Rahman Shamim | 25.02.19 | 21.3.19 | 6851673.94 | 2019-03-28 | 50% | 27.3.20 | 2020-03-27 | 0 | 6851673.94 | 0% | —
28 | Sadar | LGED/RARIP/HAB/VR/ 18-19/W-95 | a) Aushpara- Hatirthan Road (Ch. 00-1277m) under SadarUpazila, ID no: 636444030, District: Habigonj. | 1.277 | 4.5 | 9347740 | — | 9347740 | 701522 | 18.12.18 | Md. Tajuddin | 2019-04-17 | 2019-05-12 | 17744844.68 | 2019-05-19 | 93% | 2020-05-18 | — | 0 | 17744844.68 | 0% | —
| Sadar |  | b) Shaistagonj R&H to Katiadi bazar road via Laskarpur Pry. School Road (Ch. 550-1760m) under SadarUpazila, ID no: 636444055, District: Habigonj. | 1.21 | 4.7 | 9388821 | — | 9388821 | 314752 | [6 empty] | 97% |  | —
|  |  | Sub Total Tk= | 2.487 | 9.2 | 18736561 |  | 18736561 | 1016274 |  |  |  |  | 17744844.68 |  |  |  |  | 0 | 17744844.68
29 | Sadar | LGED /RARIP/ HAB/UNR/18-19/W-09 | a) Katiadi Bazar -Laskarpur UP -WDB embankment (Ch. 5950-6510m) under SadarUpazila, ID no: 636443005, District: Habigonj | 0.56 | 1 | 3964150 | — | 3964150 | 0 | 07.05.19 | — | — | — | 0 | _ | — | _ | — | 0 | 0 | _ | Tender Sent to HQ for Evaluation
| Nabiganj |  | b) Nabiganj bazar-Ratanpur via Naharpur road (Ch. 2895-4135m) under NabiganjUpazila, ID no: 636773004, District: Habigonj | 1.24 | 0.6 | 8905431 | — | 8905431 | 114103 | [6 empty] | — |  | — | 0 | 0 | _
| Nabiganj |  | c) Vanudev-Kalabhapur Road (Ch. 4500-6660m) under NabiganjUpazila, ID no: 636773018, District: Habigonj | 2.16 | 0 | 16861114 | — | 16861114 | 336735 | [6 empty] | — |  | — | 0 | 0 | —
| Azmirigonj |  | d) Paschimbag-Azmirigonj submersible road (Ch. 3400-5400m) under AzmirigonjUpazila, ID no: 636023001, District: Habigonj (Submersible) | 2 | 0 | 21799737 | — | 21799737 | 0 | [6 empty] | — |  | — | 0 | 0 | —
| Baniyachong |  | e) Hiala Bazar-Mokrampur UP Office road (Ch. 1000-2900m) under Baniachong Upazila, ID no: 636113007, District: Habigonj | 1.9 | 5.2 | 18347599 | — | 18347599 | 170989 | [6 empty] | — |  | — | 0 | 0 | —
|  |  | Sub Total Tk= | 7.86 | 6.8 | 69878031 |  | 69878031 | 621827 |  |  |  |  | 0 |  |  |  |  | 0 | 0
30 | Baniyachong | LGED/RARIP/HAB/RHB/18-19/W-147 | a) Baruiuri Up Office - Kadupur Bazar via Chilarai - Kalaingura Road (Ch. 3300-7140m) under Baniachong Upazila, ID no: 636113012, District: Habigonj | 3.84 | 0 | 8662244 | — | 8662244 | 0 | 18.12.18 | Md. Noor Ali | 2019-05-29 | 2019-06-25 | 17543104.9 | 2019-07-01 | 80% | 2020-06-30 | — | 0 | 17543104.9 | 0% | _
| Madhabpur |  | b) Adaoir GC-Dhankura-Patuli-Bulla UP road (Ch. 1000-2000m ) under Madhabpur upazila, ID no: 636713011, District: Habigonj | 1 | 0 | 3166810 | — | 3166810 | 0 | [6 empty] | 80% |  | —
| Bahubal |  | c) Mirpur UP Office-Mohasoy Bazar road (Ch. 3000-6000m) under Bahubal Upazila, ID no: 636053002, District: Habigonj | 3 | 0 | 5748320 | — | 5748320 | 0 | [6 empty] | 100% |  | —
|  |  | Sub Total Tk= | 7.84 | 0 | 17577374 |  | 17577374 | 0 |  |  |  |  | 17543104.9 |  |  |  |  | 0 | 17543104.9
|  |  | Grand Total Tk= | 74.73 | 37.1 | 398381451 |  | 399135586 | 5701386.74 |  |  |  |  | 324502132.61 |  |  |  |  | 93601385 | 223738706.36

## Sheet2
Rural Access Road Improvement Project ( RARIP) in sylhet Division
Monthly Progress Report ( Physical & Financial)
District:- Habigonj
Month:- 10 June 2019
SL No | Upazila | Package No | Name of Scheme with location ( Chainage) | Quantity |  | Estimated Cost |  |  | Cost of Salvage Material (Tk) | Tender receiving date | Name of Contractor | Date of NOA Issued | Date of Contract | Contract amount(Tk) | Work Commencement Date | Physical Progress | Pland/Actual Date of Completion | Payment Status |  |  | Fin. Prog (%) | Remarks
|  |  |  | Rd (Km) | St. (M) | Road | Str. | Total | [9 empty] | Final Bill (Tk) | Payment made(Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23

## Sheet3
Rural Access Road Improvement Project ( RARIP) in sylhet Division
Monthly Progress Report ( Physical & Financial)
District:- Habigonj
Month:- 10 June 2019
SL No | Upazila | Package No | Name of Scheme with location ( Chainage) | Quantity |  | Estimated Cost |  |  | Cost of Salvage Material (Tk) | Tender receiving date | Name of Contractor | Date of NOA Issued | Date of Contract | Contract amount(Tk) | Work Commencement Date | Physical Progress | Pland/Actual Date of Completion | Payment Status |  |  | Fin. Prog (%) | Remarks
|  |  |  | Rd (Km) | St. (M) | Road | Str. | Total | [9 empty] | Final Bill (Tk) | Payment made(Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Bahubal | LGED/RARIP/HAB/RHB/17-18/W-138 | a) Mirpur-Nondonpur road (Ch. 00-2000m) under BahubalUpazila, ID no: 636054066, District: Habigonj , | 2 | 0 | 3497668 | — | 3497668 |  | 05-11-18 | M/S Bengal Construction | 2018-12-17 | 08-01-19 | 10790571.04 |  | 100% | 12-01-20 |  | 4003713 |  |  | Carpeting Done
2 | Bahubal | LGED /RARIP/HAB/UNR/18-19/W-08 | a) Snanghat UP office- Raisgonj bazar road (Ch. 3200-4334m) under BahubalUpazila, ID no: 636053001, District: Habigonj | 1.134 | 0 | 7494679 | — | 7494679 |  |  | M/S Neon Enterprise |  |  | 21462107.66 | NOA under process. | — | — | — | 0 | — | — | NOA under process.
| Bahubal |  | b) Bahubal UP office- Rajapur bazar road (Ch. 2600-2690m & 3000-3450m) under BahubalUpazila, ID no: 636053010, District: Habigonj | 0.54 | 0 | 3918117 | — | 3918117 | [7 empty] | — | — | — | 0 | — | —
3 | Bahubal | LGED/RARIP/HAB/VR/18-19/W-82 | a) Laskarpur Rail way-Mirpur Ekdala Road (Ch. 2600-3555m) under BahubalUpazila, ID no: 636054063, District: Habigonj | 0.955 | 0.625 | 6516486 | — | 6516486 | [5 empty] | 14146667.62 | Contract Sign under process. | — | — | — | 0 | — | — | Contract Sign under process.
| Bahubal |  | b) Bishwa Road-Hafizpur-Dimura via Mirpur Dhuliakhal Road (Bishwa Road-HafizpurDimura via Dhuliakhal Road) (Ch. 800-2100m) under BahubalUpazila, ID no: 636054034, District: Habigonj | 1.3 | 0.625 | 8925069 | — | 8925069 | [7 empty] | — | — | — | 0 | — | —
4 | Bahubal | LGED/RARIP/HAB/VR/18-19/W-92 | Khagaura-Algahati road (Ch. 00-1200m) under BahubalUpazila, ID no:636055015, District: Habigonj | 1.2 | 0 | 8209287 | — | 8209287 |  |  | M/S Neon Enterprise | 21.3.19 | 21.3.19 | 8025248 |  | 30% | 27.3.20 |  | 0 |  |  | AS Work Complete
5 | Bahubal | LGED/RARIP/HAB/RHB/18-19/W-147 | c) Mirpur UP Office-Mohasoy Bazar road (Ch. 3000-6000m) under Bahubal Upazila, ID no: 636053002, District: Habigonj | 3 | 0 | 5748320 | — | 5748320 |  |  | Md.Noor ali | — | — |  |  | — | — | — | 0 | — | —