## September,20
Rural Access Road Improvement Project Under Sylhet Division (RARIP)
Monthly Progress Report (Physical & Financial)
District: Moulvibazar. | [16 empty] | Reporting Month: December-2020
Sl No. | Upazila | Package No. | Name of Scheme with Chainage & ID No | Quantity |  | Estimated Cost (Tk) |  |  | Cost of Salvage Material (Tk) | Tender Receiving Date | Name of Contractor | Date of NOA Issued | Date of Contract/Revised Contract | Contract /Variation Amount (Tk) | Work Commencement Date | Phy. Prog. (%) | Date of Comple-tion as per contract | Payment Amount for |  |  | Fin. Prog (%) | Remarks
|  |  |  | Road (km) | Struct. (m) | Road | Struct. | Total | [9 empty] | Road (Tk) | Bridge/ Culvert (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Sadar | LGED/RARIP/MOU/VR/18-19/W-67 | Improvement of R&H(Raysree)-Kamarkapon Road (Ch. 00-1365m) Salvage Cost. 149385/= under Sadar Upazila, ID no: 658744003, District: Moulvibazar. | 1.365 |  | 11126984 |  | 11126984 | 149385 | 24.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 29.12.19 | 24.12.18 | 10743506 | 30.12.18 | 100% | 29.12.19 | 9614724 |  |  | 0.89493
2 | Sadar | LGED/RARIP/MOU/VR/18-19/W-68 | (a) Improvement of Monu Barage Taltola (Kulaura) road (Ch. 00-1730m) under Sadar Upazila, ID no: 658744128, District: Moulvibazar | 2.73 |  | 18778190 |  | 18778190 |  | 24.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 7.1.19 | 22.01.19 | 18766039.35 | 28.1.19 | 100% | 28.01.20 | 12483429 |  |  | 0.66521
| Barlekha |  | (b) Improvement of Dasherbazar -Fakirbazar road to Chandgram GC road via Talukdarpara – Tuka road (Ch. 2000 -3000m) under Baralekha Upazila, ID no: 6658144058, District: Moulvibazar. | [12 empty] | 100%
3 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-69 | Improvement of Chowdhury bazar RHD-Busbal Udna Rd. (Ch. 1000-2000m) under Rajnagor Upazila, ID no:658804020, District: Moulvibazar. | 1 |  | 7322506 |  | 7322506 | 2816940 | 24.10.18 | B. M Trade Center | 29.11.18 | 26.12.18 | 7315007 | 01.01.19 | 65% | 01.01.20 | 3815081 |  |  | 0.52154 | WBM Complete
4 | Sreemangal | LGED/RARIP/MOU/VR/18-19/W-70 | Dackchara TE-Hailhaor road via Nowagaon village (Ch. 00-1650m) under Sreemongol Upazila, ID no: 658834077, District: Moulvibazar. | 1.65 |  | 11691953 |  | 11691953 |  | 24.10.18 | PD-JVCA (M/S Priti Enterprise & M/S Debangshu Sen) | 29.11.18 | 26.12.18 | 11661112.45 | 01.01.19 | 100% | 01.01.20 | 6253929 |  |  | 0.53631
5 | Barlekha | LGED/RARIP/MOU/VR/18-19/W-75 | (a) Improvement of Shahbazpur UP office-Btotrashree GPS via Uzanipara Reg. Primary School - Rail Station road (Ch. 1700 -2700m) under Baralekha Upazila, ID no: 6658144091, District: Moulvibazar | 1.61 |  | 10506182 |  | 10506182 |  | 24.10.18 | M/S Sharif Enterprise, Barlekha Moulvibazar. 01715-525005 | 29.11.18 | 27.12.18 | 10448418 | 02.01.19 | 100% | 29.11.19 | 4684085
| Juri |  | (b) Improvement of Bhugtera - Biswanathpur Road (Ch. 3190-3800m) under Juri Upazila, ID no: 658844031, District: Moulvibazar | [12 empty] | 100%
6 | Barlekha | LGED/RARIP/MOU/VR/18-19/W-76 | RHD-Bichrabond Road (Ch. 00 -1000m) under Baralekha Upazila, ID no: 658144028, Salvage Cost. 117208/= District: Moulvibazar. | 1 |  | 8232437 |  | 8232437 | 117208 | 24.10.18 | M/S Sharif Enterprise, Barlekha Moulvibazar. | 29.11.18 | 27.12.18 | 8200935 | 02.01.19 | 100% | 13.11.19 | 5985040 |  |  | 0.7298
7 | Juri | LGED/RARIP/MOU/VR/18-19/W-77 | Improvement of Bashirpur-Bazarchali Road (Ch. 00-1000m) under Juri Upazila, ID no: 658844008, District: Moulvibazar | 1 |  | 9082040 |  | 9082040 |  | 24.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) | 29.11.18 | 26.12.18 | 9076242.67 | 01.01.19 | 100% | 01.01.20 | 3975511
8 | Juri | LGED/RARIP/MOU/VR/18-19/W-78 | (a) Improvement of Ratna Bazar-Somai Bazar via Jalalpur (Jalalpur- Ratna ) Road (Ch. 1310 -2310m) under Juri Upazila, ID no: 658844010, District: Moulvibazar | 1.45 |  | 11096426 |  | 11096426 |  | 11.2.19 | M/S Mir Brothers-Lajowness International (JV),Tejgaon, Dhaka | 2019-09-22 | 17.10.19 | 11459812 | 23.10.19 | 20% | 22.10.20
|  |  | (b) Paschim Shilua-Borodohor road (Ch. 1250 -1700m) under Juri Upazila, ID no: 658845089 (New ID 658845106), District: Moulvibazar | [12 empty] | 0%
9 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-91 | (a) Improvement of Madhurbazar-Raktha-Amirpur road (Ch. 00 -550m) under Rajnagar Upazila, ID no: 658804051, District: Moulvibazar | 1.25 |  | 9167348 |  | 9167348 | 187891 | 24.10.18 | Shueb Ahmed Barlekha, Moulvibazar. 01910-821429 | 12.11.18 | 26.12.18 | 9122759 | 01.01.19 | 100% | 25.11.19 | 5517605
| Barlekha |  | (b) Barlekha Degree College- Mohammednagar via Gangerjal & Balichara road (Ch. 1500 -2200m) under Barlekha Upazila, ID no: 6658144093, District: Moulvibazar | [5 empty] | 28212 | [6 empty] | 100%
10 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-111 | Panchanandapur-Paulpur Rd (Ch. 1000-2000m) under Rajnagor Upazila, ID no:658804044, District: Moulvibazar | 1 |  | 7342509 |  | 7342509 |  | 24.10.18 | B. M Trade Center | 29.11.18 | 26.12.18 | 7332073 | 01.01.19 | 20% | 01.01.20 |  |  |  |  | ISG Ongoing
11 | Kulaura | LGED/RARIP/MOU/RHB/18-19/W-132 | (a) Rehabilitation of Tillagaon UP office -Fatikully Road (Ch. 00-1700 & 3260-3560m) under Kulaura Upazila, ID no:658653017, District: Moulvibazar | 5.4 |  | 11145183 |  | 11145183 |  | 25.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 29.11.18 | 24.12.18 | 11140205 | 30.12.18 | 100% | 31.12.19 | 11009480 |  |  | 0.98827
|  |  | (b) Rehabilitation ofChowdhuribazar-Milarmar Ghat Road (Ch. 00-2100m) under Kulaura Upazila, ID no:658654022 District: Moulvibazar | [12 empty] | 100%
|  |  | (c) Rehabilitation of Brahman bazar-Fenchugonj Road to Baramchal-Mohalal Road (Ch. 00-1300m) under Kulaura Upazila, ID no: 658654030, District: Moulvibazar. | [12 empty] | 100%
12 | Barlekha | LGED/RARIP/MOU/RHB/18-19/W-133 | a) Rehabilitation of Kalibari Bazar - Nijbahadurpur UP Office Road (Ch. 3000-5000m) under Baralekha Upazila, ID no: 658143003, District: Moulvibazar | 4.96 |  | 9159076 |  | 9159076 |  | 25.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 29.11.18 | 26.12.18 | 9254915.32 | 01.01.19 | 100% | 01.01.20 | 9180613 |  | 74302.32 | 99.2%
|  |  | (b) Rehabilitation of Chandgram RHD-Purba Maizgram Road (Ch. 00-2000m) under Baralekha Upazila, ID no: 658144005, District: Moulvibazar | [12 empty] | 100%
| Kulaura |  | (c) Rehabilitation of Pekurbazar-Koula rashi salehpur Road (Ch. 00-960m) under Kulaura Upazila, ID no:658654057 District: Moulvibazar. | [12 empty] | 100%
13 | Kamalgonj | LGED/RARIP/MOU/RHB/18-19/W-134 | (a) Patrokhola-Dholai BOP Road (Ch. 1600-3600m) under Kamalgonj Upazila, ID no: 658564041, District: Moulvibazar | 3 |  | 5281392 |  | 5281392 |  | 13.11.18 | B. M Trade Center Motojhil C/A, Dhaka . 01710-908083 | 26.12.18 | 22.01.19 | 5289024 | 28.01.19 | 100% | 28.01.20
| Rajnagar |  | (b) Highway Gayaspur-Indesswar T.E. Road (Ch. 00-1000m) under Rajnagor Upazila, ID no:658804013, District: Moulvibazar. | [12 empty] | 100%
14 | Rajnagar | LGED/RARIP/MOU/RHB/17-18/W-135 | a) Rehabilitation of Assain Highway-Bagajura Road (Ch. 00-500m) under Rajnagor Upazila, ID no:658804032, District: Moulvibazar | 2.5 |  | 6221514 |  | 6221514 |  | 25.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 29.11.18 | 24.12.18 | 6066815 | 30.12.18 | 100% | 29.12.19 | 5919991 |  | 146824 | 97.58%
| Sadar |  | (b) Rehabilitation of R&H (Mukambazar)-Premnagori Tea Garden Road (Ch. 80-2080m) under Sadar Upazila, ID no:658744115, District: Moulvibazar. | [12 empty] | 100%
15 | Sadar | LGED/RARIP/MOU/RHB/17-18/W-140 | Kazir Bazar-Manumukh Road (Ch. 00-2900m) under Sadar Upazila, ID no:658744061, District: Moulvibazar. | 2.9 |  | 10458481 |  | 10458481 |  | 25.10.18 | Tufaiel Ahmed Baharmordan Moulvibazar. | 29.11.18 | 26.12.18 | 9904825 | 01.01.19 | 100% | 01.01.20 | 7922189 |  |  | 0.79983
16 | Juri | LGED/RARIP/MOU/RHB/18-19/W-146 | a) Rehabilitation of Fultala - Konagaon Road (Ch. 00-1040m) under Juri Upazila, ID no: 658844047, District: Moulvibazar. . | 6 |  | 8847160 |  | 8847160 |  | 13.11.18 | M/S Mollah Enterprise, 257/A, Bara Mogbazar, Dhaka. 01711-473844 | 26.12.18 | 09.01.19 | 8836671 | 15.01.19 | 100% | 14.01.20 | 1748766 |  |  | 0.1979
|  |  | (b) Rehabilitation of Ratna Bazar-Shomai Bazar Via Jalalpur Road (Ch. 00-1310m) under Juri Upazila, ID no: 658844010, District: Moulvibazar. | [12 empty] | 100%
|  |  | (c) Rehabilitation of Shamai-Baraitali Road (Ch. 00-1650m) under Juri Upazila, ID no:65884030 District: Moulvibazar | [12 empty] | 40% | [5 empty] | Material on site for work & palasading ongoing
| Barlekha |  | (d) Rehabilitation of Satpur-Kazirbond Road (Ch. 810-2810m) under Baralekha Upazila, ID no:658144013 District: Moulvibazar. | [12 empty] | 0%
17 | Kulaura | LGED/RARIP/MOU/VR/18-19/W-72 | (a) Improvement of Amjuhub-Tilashijura-Bobanipur Road (Ch. 00-1901m) under Kulaura Upazila ID No. 658654119 District: Moulvibazar | 3.601 | 3 | 27572817 |  | 27572817 | 19055 | 19.12.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 24.2.19 | 20.3.19 | 27572348.65 | 26.3.19 | 35% | 26.3.20 | 2602102 |  |  |  | Sub-base complete
|  |  | (b) Improvement of Chowdhury bazar-Kality Road (Ch. 2000-2480 & 3292-4512m) under Kulaura Upazila ID No. 658654096 District: Moulvibazar. | [12 empty] | 70% | [5 empty] | WBM Complete
18 | Kulaura | LGED/RARIP/MOU/VR/18-19/W-73 | Improvement of R&H Polokuna-Hingazia Road (Ch. 1467-2877m) under Kulaura Upazila ID No. 658654036 District: Moulvibazar. | 1.41 | 0 | 10338308 |  | 10338308 |  | 19.12.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) | 27.1.19 | 14.2.19 | 10337830.36 | 20.02.19 | 70% | 20.02.20 | 7120612 |  |  | 0.68879 | WBM Complete
19 | Kamalgonj | LGED/RARIP/MOU/VR/18-19/W-74 | (a) Improvement of Shamshernagar -Daffolchara BDR Camp. Road via Chatlapur Road (Ch. 1000-2000m) under Kulaura Upazila ID No. 658564015 | 2 | 0 | 14770724 |  | 14770724 |  | 19.12.18 | M/S Suhag Enterprise Joypasa,Kulaura,Moulvibazar 01712-763155 | 24.2.19 | 20.03.19 | 14770076.6 | 27.03.19 | 75% | 27.03.20 | 3676458 |  |  |  | WBM Complete
|  |  | (b) Improvement of Choycut-Kalenga Road (Ch. 2600-3600m) under Kulaura Upazila ID No. 658564032 | [12 empty] | 60% | [5 empty] | WBM Complete
20 | Kamalgonj | LGED/RARIP/MOU/VR/18-19/W-79 | Vice-principal Abdus Shahid (Hospital) Road (Ch. 1850-2460 & 3810-4200m) under Kulaura Upazila ID No. 658564029 | 1 | 0 | 7182757 |  | 7182757 | 44608 | 19.12.18 | M/S Suhag Enterprise Joypasa,Kulaura, Moulvibazar. 01712-763155 | 27.01.19 | 2019-02-03 | 7182656.32 | 09.02.19 | 100% | 9.2.20 | 6027448 |  |  | 0.83917
21 | Sreemangal | LGED/RARIP/MOU/RHB/18-19/W-131 | (a) Rehabilitation of Beltuli-Madhya Road (Ch. 00-1695m) under Sreemangal Upazila ID No. 658834073 District: Moulvibazar | 6.081 | 0 | 12509918 |  | 12509918 |  | 19.12.18 | PD-JVCA (M/S Priti Enterprise & M/S Debangshu Sen) Sreemangal, Moulvibazar. 01711-467691 | 24.2.19 | 22.03.19 | 13398261.67 | 27.03.19 | 100% | 23.11.19 | 3986040 |  |  | 0.2975
|  |  | (b) Rehabilitation of Hajipurbazar-Hail haor Road (Ch. 00-2151m) under Sreemangal Upazila ID No. 658835055 District: Moulvibazar | [12 empty] | 100%
|  |  | (C) Rehabilitation of Satgaon UP (Lachna) to Mirzapur UP Via Makricharra Bazar Road (Ch. 00-2235m) under Sreemangal Upazila ID No. 658833004 District: Moulvibazar. | [12 empty] | 100%
22 | Barlekha | LGED/RARIP/MOU/UNR/18-19/W-06 | (a) Improvement of Talimpur UP Office-Edghabazar RHD via Kanchanpur Road (Ch. 1000-3000m) under Barlekha Upazila ID No. 658143011 District: Moulvibazar | 5.437 |  | 38670104 |  | 38670104 |  | 11.02.19 | M/S Mir Brothers-Lajowness International (JV),Tejgaon, Dhaka | 2019-05-12 | 2019-06-09 | 40479352.49 |  | 35% | 14.6.20 |  |  |  |  | Sub-base complete
| Kulaura |  | (b) Improvement of Purshai-Dewgoan-Rangichara Road (Ch. 3513-4950m) under Kulaura Upazila ID No. 658653025 District: Moulvibazar | [12 empty] | 65% | [5 empty] | WBM Complete
|  |  | (C) Improvement of Nawabgonj Batera via Berkuri [Nawabgonj UP office (Rasolgonj Bazar)- Batera via Berkuri] Road (Ch. 1500-3500m) under Kulaura Upazila ID No. 658653010 District: Moulvibazar Salvage Cost- 268537/- | [12 empty] | 0%
23 | Sadar | LGED/RARIP/MOU/UNR/18-19/W-07 | (a) Improvement of R&H -Sarkarbazar-Monumuk Bazar Road (Ch. 5000-5300m) under Sadar Upazila ID No. 658743007 District: Moulvibazar | 3.942 | 8.25 | 30049179 |  | 30049179 |  | 11.2.19 | ME & GU (JV)Motijhil, Dhaka | 12.5.16 | 9.6.19 | 29897420.85 |  | 25% | 14.6.20
|  |  | (b) Improvement of Chadnighat-Balikandi-Palpur Road (Ch. 4500-4800 & 4850-6550m) under Sadar Upazila ID No. 658743006 District: Moulvibazar | [12 empty] | 50% | [5 empty] | WBM ongoing
| Kamalgonj |  | (C) Improvement of Adampur-Adkanibazar Road via Kawargola Bazar Road (Ch. 3000-4180 & 4210-4672m) under Kamalgonj Upazila ID No. 658563003 District: Moulvibazar. | [12 empty] | 50% | [5 empty] | WBM ongoing
24 | Kamalgonj | LGED/RARIP/MOU/BDG(UNR)/19-20/W-16 | Construction of 25m long PC Girder Bridge on Adampur-Adkanibazar Road via Kawargola Bazar at Ch.2750m |  | 25 |  | 20276039 | 20276039 |  | 12.11.19 | [11 empty] | Evaluation send to PD Office
25 | Rajnagar | LGED/RARIP/MOU/BDG(VR)/19-20/W-71 | Construction of 46m long RCCC Girder Bridge on Holdigul-Kalabazar road to Bokshipur road at CH.250 |  | 46 |  | 34266286 | 34266286 |  | 12.11.19 | Dhrob-Mosarf(JV) Modhasheri | 9.02.20 | 2.3.20 | 35970219 | 9.3.20 | 10% | 8.3.21
26 | Barlekha | LGED/RARIP/MOU/BDG(VR)/19-20/W-117 | Construction of 20m long RCCC Girder Bridge onon Atuaborail-Kumarshail Road at Ch.3500m |  | 20 |  | 15755070 | 15755070 |  | 12.11.19 | Dhrob-Mosarf(JV) Modhasheri | 9.2.20 | 2.3.20 | 16544966 | 9.3.20 | 70% | 8.3.21
27 | Kulaura | LGED/RARIP/MOU/MAR/18-19/W-160 | a) Improvement of Rasulgonj Bazar under Kuraura Upazila, District: Moulvibazar |  |  |  |  | 7822237 |  | 8.12.19 | Md.Khaled Ahmed,Kulaura,Moulvibazar | 9.3.20 | 22.3.20 | 8199694 | 28.3.20 | 60% | 27.3.21
|  |  | b) Improvement of Pirer Bazar (Hajipur UP) under Kuraura Upazila, District: Moulvibazar | [12 empty] | 60%
28 | Sadar | LGED/RARIP/MOU/MAR/18-19/W-161 | a) Improvement of Sarkar Bazar under Sadar Upazila, District: Moulvibazar |  |  |  |  | 5385547 |  | 8.12.19 | Tufaiel Ahmed Baharmordan Moulvibazar. | 9.3.20 |  |  |  | 0%
|  |  | b) Improvement of Dighirpar Bazar under Sadar Upazila, District: Moulvibazar | [12 empty] | 20%
29 | Sreemangal | LGED/RARIP/MOU/MAR/18-19/W-162 | a) Improvement of Mirzapur Bazar under Sreemangal Upazila, District: Moulvibazar |  |  |  |  | 4161316 |  | 8.12.19 | Tufaiel Ahmed Baharmordan Moulvibazar. | 9.3.20 |  |  |  | 55%
|  |  | Grand Total = | 62.286 | 102.25 | 296553188 |  | 384219683 | [5 empty] | 358971185.73 |  |  |  | 111523103
|  | Accountant |  | Sub-Asstt-Engineer | [5 empty] | Asstt-Engineer | [5 empty] | Senior Asstt-Engineer |  |  |  | Executive Engineer
|  | LGED, Moulvibazar. |  | LGED, Moulvibazar. | [5 empty] | LGED, Moulvibazar. | [5 empty] | LGED, Moulvibazar. |  |  |  | LGED, Moulvibazar.
Note on S8: User: GoB=1034545.00 TK RPA= 4087392.00 TK (ISFD)
Note on S9: User: GoB=1309406.00 TK RPA(ISFD)=7581291.00 TK
Note on S15: User: GoB=475147.00 TK RPA(ISFD)=3940715.00 TK
Note on S22: User: GoB=8595101.00 TK
Note on S25: User: GoB=7167305 TK & RPA=1610646.00 TK
Note on S30: User: GoB= 4621737.00 TK RPA(Istisna'a)=1054767.00 TK
Note on S32: User: GoB=5156982.00 TK
Note on S33: User: GoB=1365262.00 TK
Note on S39: User: GoB=766178.00 TK
Note on S42: User: GoB=490289.00 TK
Note on S60: User: Total GoB Paid amount=32500000.00 TK Total RPA (Istisna'a & ISFD)=2665413+15609398.00=18274811.00 TK