## SchemeList (2)
Serial | District Name | District Code/ID | Upazila Name | Upazila Code/ID | Project ID | Package No | Scheme Name | Road ID | Length of Scheme(Km) - Road | Length of Scheme(m) - Bridge/Culverts | Building Quantity | Estimated Amount(LAC) | Contractor Name | Contract Amount(LAC) | Date of Contract (DD/MM/YYYY) | Date of commencement (DD/MM/YYYY) | Date of Completion (DD/MM/YYYY) | Physical Progress(%) | Financial Progress (Amount) (LAC) | Financial Progress(%) | Date of Progress Update (DD/MM/YYYY) | Remarks
1 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/GAI-S/UNR/18-19/W-06 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3600m-4150m & 4496m-7600m. including Costruction of 10 U- drain (.600mx0.625m) Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.3660m, 3984m, 4030m, 4073m, 5197m, 6115m, 6280m, 6695m, 7525m & 7591m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | 132243029 | 3.654 | 6 |  | 304.3582 | M/S Basundhara, Kurigram | 304.3 | 2019-05-05 | 2019-05-11 | 2020-12-31 | 100 | 303.9828 | 99.8958 | 2022-10-12 | Final bill paid
2 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/SAD/UNR/20-21/W-136 | Improvement of Bituminous carpeting Road on Pulbandhi Bazar-Ramchandrapur UP Office via Bloali UP office & Gonirjan Bridge Road at Ch.7627m-8057m Under Gaibandha Sadar Upazila, District Gaibandha. id 132243029 | 132243029 | 0.43 |  |  | 42.3891 | MD. SHAHID RANA JV | 33.5377 | 2020-11-24 | 2020-11-30 | 2021-11-29 | 100 | 33.3361 | 99.3987 | 2022-10-12 | Final bill paid
3 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-09 | Improvement of Bituminous Carpeting Road on khorda Rasulpur-Chandiapur Road at Ch.0.00m-2000m. including Costruction of 7 Nos U-Drain khorda Rasulpur-Chandiapur Road at Ch.85m, 526m, 880m, 925m, 1048m, 1343m, & 1835m. and 1Nos (2.00x2.00) m Cross Drainges Structure at Ch.710.0m. Under Shdullapur, District Gaibandha. | 132823001 | 2 | 6.2 |  | 186.3288 | Md.Khademul Islam Jewel, Gaibandha | 186.1307 | 2019-05-05 | 2019-05-11 | 2020-09-15 | 100 | 186.0636 | 99.9639 | 2022-10-12 | Final bill paid
4 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-10 | Improvement of Bituminous Carpeting Road on. Mohisbandi-Mirpur Road at Ch.1235m-3235. including Costruction of 1 Nos U-Drain 0.600mx0.625m Mohisbandi-Mirpur Road at Ch.2725.0m.Under Shdullapur, District Gaibandha. | 132823002 | 2 | 0.6 |  | 175.2451 | M/S SAJIN TRADERS JV | 175.1996 | 2019-05-08 | 2019-05-14 | 2020-03-21 | 100 | 175.1768 | 99.987 | 2022-10-12 | Final bill paid
5 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/20-21/RW- 185 | Rehabilitation of Moshbandhi-Mirpur Road at Ch: 4240m-5240m. Under Shadullapur upazila, District: Gaibandha | 132823002 | 1 |  |  | 19.1334 | H. S. Enterprise | 18 | 2021-05-11 | 2021-05-18 | 2022-05-17 | 100 | 15.8893 | 88.2737 | 2022-10-12
6 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/20-21/RW- 186 | Rehabilitation of Chandiapur bazar-Rahmatpur GC via Rasulpur bazar Road at Ch: 00m-1000m. Under Shadullapur upazila, District : Gaibandha | 132823006 | 1 |  |  | 22.7131 | H. S. Enterprise | 21.5 | 2021-05-11 | 2021-05-18 | 2022-05-17 | 100 | 19.4432 | 90.4336 | 2022-10-12
7 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/20-21/RW- 187 | Rehabilitation of Idilpur U.P.office-Dhaperhat U.P.office Road at Ch: 00m-1020m. Under Shadullapur upazila, District: Gaibandha | 132823008 | 1.02 |  |  | 17.0807 | H. S. Enterprise | 16 | 2021-05-11 | 2021-05-18 | 2022-05-17 | 100 | 14.2997 | 89.3733 | 2022-10-12
8 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/20-21/RW- 188 | Rehabilitation of Bhatgram U.P Office - Nagbari Bazar via Burir Bazar Road at Ch: 00m-1000m. Under Shadullapur upazila, District: Gaibandha | 132823017 | 1 |  |  | 14.5098 | H. S. Enterprise | 13.7 | 2021-05-11 | 2021-05-18 | 2022-05-17 | 100 | 12.1317 | 88.5525 | 2022-10-12
9 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/18-19/W-12 | Improvement of Bituminous Road on Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. Ch.2627m-3627m. including Costruction of 2 Nos U-Drain 0.600mx0.625m ,at Ch.2768m,3110m and Costruction of 1 Nos (2.00mx2.00m)Cross Drainges Structure and Bhatgram U.P office-Nagbari Bazar via Burir Bazar Road at Ch. 3260.0mUnder Shdullapur, District Gaibandha. | 132823017 | 1 | 3.6 |  | 87.7973 | Md. Mahomudun Nobi, Pirganj, Rangpur | 83.4074 | 2019-04-07 | 2019-04-13 | 2020-03-08 | 100 | 83.3532 | 99.935 | 2022-10-12 | Final Bill Paid
10 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/UNR/20-21/W-135 | Improvement of Bhangamora Bazar-School bazar – Padumshahor UP Road at Ch: 3526m-6386m Under Upazila:Saghata, District: Gaibandha. | 132883015 | 2.86 |  |  | 267.7326 | Md.Shamim Ahammed Mondal JV | 266.9 | 2020-11-23 | 2020-11-29 | 2021-11-28 | 100 | 236.83 | 88.7336 | 2022-10-12
11 | Gaibandha | 60 | Fulchori | 443 | 826 | PRO/GAI/FUL/UNR/21-22/W-279 | Improvement of Arandabari UP HQ -Algarchar bazar Ch: 1170-2250m under upazila: Fulchari, Dist: Gaibandha | 132213003 | 1.08 |  |  | 91.7466 | M/S S.Zaman Enterprise, Sabuj Songho Road, Pabla, Doulatpur, Khulna | 80 | 2021-12-13 |  | 2022-12-19 | 80 | 61.1818 | 76.4772 | 2022-10-12
12 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/19-20/W- 71 | Improvement of Bhatgram UP office –Jamalpur Bazar Road at Ch: 00m-2000m including Construction of 11 Nos (0.625x0.600) m U-Drain at Ch: 45m, 320m, 472m, 775m, 800m,1265m, 1360m, 1430m, 1550m, 1785m &1919m and 1x2.50mx2.00 m RCC Box Culvert on at Ch: 1275m Under Upazila:Sadullapur, District: Gaibandha | 132823004 | 2 | 14.3 |  | 191.6517 | M/S Mafi Construction JV, Sadullapur, Gaibandha | 162.9039 | 2020-05-18 | 2020-05-28 | 2021-05-28 | 100 | 162.8953 | 99.9947 | 2022-10-12 | Final bill paid
13 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/19-20/W- 68 | Improvement of Naldanga GC-Ramzibon UP officeRoad at Ch: 1500m-2500m including Construction of 1Nos (0.625x0.600) m U-Drain Under Upazila:Sadullapur, District:Gaibandha. | 132823009 | 1 | 1 |  | 97.5263 | Md.Shoeb Hossain Mona, Gaibandha | 81.2647 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 100 | 80.6083 | 99.1922 | 2022-10-12 | Final bill paid
14 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/UNR/19-20/W- 72 | Improvement of Dholvanga-Mohipur Bazar Road at Ch: 00m-1000m including Construction of 2 Nos (0.625x0.600) m U-Drain at Ch: 355m & 388m and 1x2.50mx2.00 m RCC Box Culvert at Ch: 330m Under Upazila:Sadullapur, District: Gaibandha. | 132823015 | 1 | 5.3 |  | 110.4923 | Md.Shoeb Hossain Mona, Gaibandha | 90.9552 | 2020-06-02 | 2020-06-09 | 2021-06-08 | 100 | 90.92 | 99.9613 | 2022-10-12 | Final bill paid
15 | Gaibandha | 60 | Sundargonj | 439 | 826 | PRO/GAI/SUN/VR/21-22/W-322 | Improvement by Bituminous Carpeting Road for Sarker Bazar –WAPDA Embankment Via Baraikandi road at Ch: 00-4254m under Upazila: Sundarganj, District: Gaibandha. | 132914077 | 4.254 |  |  | 420.9245 | M/S Tahity Enterprise, Purbo Shalbon, Rangpur | 400.0518 | 2022-04-13 | 2022-04-20 | 2023-04-19 | 0 | 0 | 0 | 2022-10-12
16 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/GAI-S/VR/18-19/W-07 | Improvement of Bituminous Carpeting Road on Fulbari-Badiakhali hat Road At Ch0.00m-1623m. &2300m-3100m. including Costruction of 10 U- drain (0.600mx0.625m) Fulbari-Badiakhali hat Road atCh0.00m-1623m. &2300m-3100m. Under Gaibandha Sadar Upazila, District Gaibandha. | 132244011 | 2.423 | 6 |  | 230.3237 | Md. Abdul Latif Hakkani, Gaibandha | 230.2791 | 2019-05-05 | 2019-05-11 | 2020-12-30 | 100 | 226.0099 | 98.1461 | 2022-10-12 | Final bill paid
17 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI /GAI-S/VR/18-19/W-08 | Improvement of Bituminous Carpeting Road on Ruper –Eslighat via Pramanik para Road at Ch.1500m-2980m including Costruction of 3 U- drain (0.600mX0.625m) at Ch.1280m,2300m,2640m. Under Gaibandha Sadar Upazila, District Gaibandha. | 132244021 | 1.48 | 1.8 |  | 168.3137 | RSL Enterprise, gaibandha | 168.2062 | 2019-05-05 | 2019-05-11 | 2020-04-21 | 100 | 168.2007 | 99.9967 | 2022-10-12 | Final Bill Paid
18 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/VR/18-19/W-11 | Improvement of Bituminous Road on Shdullapur Dhaperhat G.C road at Boxigonj Bazar toDhaperhat-Madarhat Road via Ambagan Road at Ch.0.00m-2480m. including Costruction of 11 Nos U-Drain 0.600mx0.625m at Ch.335m,720m,877m,1190m,1300m,1388m,1477m,1765m,1880m,1972m,&2226m. Under Shdullapur, District Gaibandha. | 132824014 | 2.48 | 6.6 |  | 218.4758 | Md. Abdul Latif Hakkani, Gaibandha | 219.25 | 2019-05-15 | 2019-05-21 | 2020-07-31 | 100 | 218.7433 | 99.7689 | 2022-10-12 | Final bill paid
19 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/VR/18-19/W-13 | Improvement of Bituminous Road on Gatia H/O Taibor Master-Chitholia H/O Mahatab Member Road at Ch.0.00m-800m. including Costruction of 4 Nos U-Drain 0.600mx0.625m at Ch20m,135m,290m,&700m Under Saghata, District Gaibandha. | 132885163 | 0.8 | 2.4 |  | 77.6445 | Md. Jakir Hossain, Gaibandha | 73.6928 | 2019-04-15 | 2019-04-21 | 2020-04-06 | 100 | 73.6557 | 99.9497 | 2022-10-12 | Final Bill Paid
20 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/VR/18-19/W-14 | Improvement of Bituminous Road on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Road at ch.600m-2930m. including Costruction of 10 Nos U-Drain 0.600mx0.625m at Ch.673m,735m,816m,925m,1387m,1760m,1920m,1987m,2150m,2493m.and Costruction of 3 Nos Slope Drain at Ch.1496m, 1745m, 2075m, and Costruction of 3 Nos (2.00mx2.00m) Cross Drainges Structure on Bonarpara H/O Mozammel Huq –BonarparaH/O akbar Ali Roadat Ch.2395m,2590m, 2787m. Under Saghata, District Gaibandha. | 132884002 | 2.33 | 22.5 |  | 215.6293 | M/S SAJIN TRADERS JV | 215.4817 | 2019-05-07 | 2019-05-13 | 2020-03-25 | 100 | 211.4652 | 98.136 | 2022-10-12 | Final bill paid
21 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/CUL/20-21/W-170 | Construction of 1Nos 3x4.50m x 4.50m RCC. Box Culvert on Bonarpara H/Q Mozammel Huq - Bonarpara H/Q Akbar Ali Road at Ch:1907m Under Upazila: Saghata , District: Gaibandha. | 132884002 |  | 14.85 |  | 39.506 | M/S B.B Traders | 29.505 | 2021-03-25 | 2021-03-31 | 2022-03-30 | 100 | 29.4971 | 99.9733 | 2022-10-12 | Final bill paid
22 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/GAI_S/RMP/19-20/ MW-114 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Salam bazar- Balata bazar via Mouja malibari Eidgah at ch. 00-2500m | 132245158 | 2.5 |  |  | 13.3122 | 1.Mst. Mousi akter 2.Mst. Aduri | 12.8122 | 2020-09-15 |  | 2022-09-14 | 98 | 11.853 | 92.5133 | 2022-10-12
23 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/GAI_S/RMP/19-20/ MW-115 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Naldanga G.C.-Ramzibon U.P. office. Road at ch. 00-780m. 2. Idilpur U.P. office-Dhaperhat U.P. office road at ch. 00-2000m. 3. Khorda Rasulpur-chandiapur roadat ch. 00-1020m. 4. Bhatgram U.P office-Jamalpur Bazar at ch.00-2000m. 5 Chandiapur bazar-Rahmatpur GC via Rasulpur bazar at ch.00-2000m. | 132823009 132823008 132823001 132823004 132823006 | 7.8 |  |  | 36.3933 | 1. Mst. Jobeda Begum & Mst. Sahada Begum Begum 2 Mst.Rony begum & Shoprati 3. bimoti rani & Mst .Rahima Begum. 4. Dulali begum & Mst. Salaha Begum 5. Mst. Aysa Begum & Mst. Lili Begum | 34.8333 | 2020-09-15 |  | 2022-09-14 | 98 | 32.4871 | 93.2646 | 2022-10-12
24 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/RMP/19-20/ MW-116 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Dighal Kandi- Digholkandi H/O Sonaullah Mirja at ch.00-2700m. 2. Chakili H/O Vikku sarker - Folia Bazar road at ch. 00-1900m. | 132885022 132885175 | 4.6 |  |  | 23.7418 | 1.Mst. Fatema Begum & Mst.Rausan Ara 2. Rozina & Mst.salina | 22.8218 | 2020-09-15 |  | 2022-09-14 | 98 | 21.2635 | 93.1719 | 2022-10-12
25 | Gaibandha | 60 | Fulchori | 443 | 826 | PRO/GAI/SAG/RMP/19-20/ MW-117 | 1. Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Erandabari U.P H/Q-Algarchar bazar at ch.1170-2250m. 2. Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S at ch.00-2500m. 3. Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram at ch.1170-2000m. 4. Pachim Khatiamary H/O Jalal Member-Gucha gram at ch.00-1000m. 5 Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary at ch.00-950m. | 132213003 132213011 132214050 132215025 132215037 | 6.36 |  |  | 32.1015 | 1. Mst. Diljan Begum & Mst. Forida Begum 2. Mst. Rajina & Mst. Kulsum 3. Mst. Balia Khatun & Mst. Anna Khatun 4. Mst. Amena Begum & Mst. Azima Khatun 5. Mst. Foyzan & Mst. Rasheda Begum | 29.2988 | 2020-09-15 |  | 2022-09-14 | 98 | 28.7575 | 98.1525 | 2022-10-12
26 | Gaibandha | 60 | Sundargonj | 439 | 826 | PRO/GAI/SUN/RMP/19-20/ MW-113 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Kapashia UP Office to Kashim Bazar- WAPDA Embankment via H/O Nesab Chairman (Kajir Char Ahammed Nagar Bazar) road, at Ch. 00-2300m. | 132915058 | 2.3 |  |  | 13.2722 | 1.Mst. Momata Begum & Mst Ismat Ara Begum | 12.8122 | 2020-09-15 |  | 2022-09-14 | 98 | 11.9668 | 93.4013 | 2022-10-12
27 | Gaibandha | 60 | Fulchori | 443 | 826 | PRO/GAI/FUL/LM/20-21/W-257 | Construction of Purbo Fulchari Bazar Upazila:Fulchori, Dist:Gaibandha (02 nos LCS group) |  |  |  |  | 52.7691 | Mst Nazma & Md.Dulal Hossen (LCS-1)/Mst.Helena Begum & Jahurul Islam (LCS-2) | 52.7691 | 2021-11-01 |  | 2022-10-31 | 40 | 25.694 | 48.6912 | 2022-10-12
28 | Gaibandha | 60 | Fulchori | 443 | 826 | PRO/GAI/FUL/WSM/21-22/W-276 | Development of Purbo Fulchari Bazar Womens Market Section Upazila:Fulchori, Dist:Gaibandha |  |  |  |  | 26.9273 | Md Mozibor & Mst.Tara(LCS-1) | 26.9273 | 2021-11-01 |  | 2023-04-30 | 50 | 13.4637 | 50 | 2022-10-12
29 | Gaibandha | 60 | Sadar | 442 | 826 | PRO/GAI/SAD/MM/20-21/ W-173 | Construction of Balua hat Upazila: Sadar, Dist:Gaibandha (02 nos LCS group) |  |  |  |  | 54.5572 | Mst Bely Begum & Mst.Ruzina Begum (LCS-1)/Mst.Lylee Begum & Mst.Morefa Begum(LCS-2) | 54.5572 | 2021-03-30 |  | 2022-03-30 | 100 | 47.3666 | 86.82 | 2022-10-12
30 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/MM/21-22/W-296 | Construction of Ullah Sonatola Bazar (2 nos LCS Group) |  |  |  |  | 60.0571 | Mst Kalpona Begum & Mst.Anguri Begum (LCS-1)/Mst.Shilpi Begum & Mst.Rahima Begum (LCS-2) | 60.0571 | 2021-12-22 |  | 2022-12-21 | 5 | 0 | 0 | 2022-10-12
31 | Gaibandha | 60 | Saghata | 440 | 826 | PRO/GAI/SAG/MM/21-22/W-297 | Construction of Nayabondar Hat (2 Nos LCS Group) |  |  |  |  | 46.8228 | Md.Bodrul Alam & Mst.Merina Begum (LCS-1)/Monzu Ahmad & Mst.Safia Akhtar (LCS-2) | 46.8228 | 2022-05-04 |  | 2023-04-13 | 25 | 11.7058 | 25.0001 | 2022-10-12
32 | Gaibandha | 60 | Sundargonj | 439 | 826 | PRO/GAI/SUN/MM/20-21/W-268 | Construction of Choroker Hat (2 nos LCS Group) |  |  |  |  | 44.7428 | Sufia Begum & Moina Begum (LCS-1)/Maleka Begum &Rosna Begum (LCS-2) | 44.7428 | 2021-07-11 |  | 2022-10-30 | 70 | 22.3715 | 50.0001 | 2022-10-12
33 | Gaibandha | 60 | Sundargonj | 439 | 826 | PRO/GAI/SUN/MM/21-22/W-288 | Construction of Jamaler Hat (2 nos LCS Group) |  |  |  |  | 50.055 | Mst Kajoli & Mst.Fatema (LCS-1)/Mst.Salma & Mst.Farida (LCS-2) | 50.055 | 2021-11-01 |  | 2023-05-02 | 45 | 18.1737 | 36.3075 | 2022-10-12
34 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/MM/20-21/ W-258 | Construction of Boxigonj Hat, Upazila: Sadullapur, Dist:Gaibandha (2 nos LCS group) |  |  |  |  | 60.6953 | Mst Santona & Mst.Soma (LCS-1)/Mst.Sahida & Mst.Momena (LCS-2) | 60.6953 | 2021-10-14 |  | 2022-12-15 | 65 | 37.1734 | 61.2459 | 2022-10-12
35 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/MM/20-21/ W-256 | Construction of Kantanagar Hat, Upazila: Sadullapur, Dist:Gaibandha (2 nos LCS group) |  |  |  |  | 51.6831 | Mst Kajoli & Mst.Fatema (LCS-1)/Mst.Salma & Mst.Farida (LCS-2) | 51.6831 | 2021-10-14 |  | 2022-12-15 | 60 | 25.8428 | 50.0025 | 2022-10-12
36 | Gaibandha | 60 | Shadullapur | 440 | 826 | PRO/GAI/SAD/FS/21-22/W-286 | Construction of Three storied Bashir Nagar Govt. Primary School cum Flood Shelter |  |  |  |  | 262.4026 | Md. Shamim Ahmed Mondol (JV), Planners Tower (16th floor), Suit no:8-11, 13/A, Sonargaon Road, Dhaka | 216.9934 | 2021-12-13 |  | 2023-06-19 | 20 | 27.32 | 12.5902 | 2022-10-12
37 | Gaibandha | 60 | Fulchori | 443 | 826 | PRO/GAI/FUL/FS/21-22/W-287 | Construction of Three storied South Burail Govt. Primary School cum Flood Shelter |  |  |  |  | 264.2861 | Md. Zahidul Islam | 218.7751 | 2021-12-19 |  | 2023-06-25 | 25 | 27.32 | 12.4877 | 2022-10-12
38 | Gaibandha | 60 | Sundargonj | 439 | 826 | PRO/GAI/SUN/FS/21-22/W-285 | Construction of Three storied Bakrir Char Govt. Primary School cum Flood Shelter |  |  |  |  | 261.8014 | M/S Tahity Enterprise & ZHD, Purbo Shalbon, Rnagpur | 212.9396 | 2021-12-13 |  | 2023-06-19 | 20 | 38.1539 | 17.9177 | 2022-10-12
39 | Kurigram | 56 | Chilmari | 407 | 826 | PRO/KUR/CHI/UNR/18-19/W-21 | Improvement of Bituminous Carpating Road On Thanahat up office – Balabarihat via Kajaldanga hat at Ch.2985m-3455m. Under Chilmari Upazila, District Kurigram. | 149093002 | 0.47 | 0 |  | 41.5907 | Nakshi Mobile Palace,Krishnopur, Kurigram | 39.5112 | 2019-05-28 | 2019-06-04 | 2020-02-25 | 100 | 39.4504 | 99.8463 | 2022-10-12 | Final bill paid
40 | Kurigram | 56 | Chilmari | 407 | 826 | PRO/KUR/CHIL/UNR/19-20/RW-79 | Improvement of Thanahat Up Office to Balabarihat via Kazaldanga Hat Road at Ch: 00m-1040m including Construction of 1Nos 1x3.00mx2.50mm RCC. Box Culvert at Ch: 15m and 1Nos 1x0.625mx0.600mm U-Drain at Ch: 760m and 1Nos 1x2.50mx2.00m m RCC. Box Culvert at Ch: 820m under Upazila:Chilmari, District:Kurigram | 149093002 | 1.04 | 7.5 |  | 64.0762 | Md.Abul Hossain, Shaheb Bazar,Groramara,Rajshahi. | 51.0263 | 2020-04-21 | 2020-05-15 | 2021-02-14 | 100 | 50.9618 | 99.8735 | 2022-10-12 | Final bill paid
41 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KUR/NAG/UNR/19-20/W-80 | Improvement of Ramkhana UP office to Sealkanda bazar Road at Ch: 1000m-2776m including Construction of 1Nos 1x2.00mx2.00m RCC. Box Culvert at Ch: 1727m and 4Nos 1x0.6250mx 0.625m m RCC. Box Culvert at Ch: 1080m,1390m,2022m & 2118.00m Under Upazila: Nageswari, District:Kurigram. | 149613039 | 1.776 | 6.5 |  | 174.548 | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 149.7823 | 2020-03-15 | 2020-05-23 | 2021-05-22 | 100 | 149.6222 | 99.8931 | 2022-10-12 | Final bill paid
42 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KUR/MAINT/19-20/W-1 | Maintenance work of LGED Office Building, Dist: Kurigram |  |  |  |  | 8.7461 | M/S Afiya Traders, Krishnopur, Chorupara, Sadar, Kurigram | 8.7461 | 2019-11-11 | 2019-11-11 | 2019-11-28 | 100 | 8.7461 | 100 | 2022-10-12 | Final bill paid
43 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/CHI/UNR/21-22/W-304 | Improvement of Bituminous Carpating Road on Burirhat-Gharialdanga UP office road at Ch: 963-1450m including 1 nos 0.90X0.90m RCC Cross drain at ch.1428m. | 149773010 | 0.487 | 1.4 |  | 49.9551 | M/S Zahurul haque Dulal, Sadar, Kurigram | 43.6259 | 2022-02-17 | 2022-02-24 | 2023-02-23 | 0 | 0 | 0 | 2022-10-12
44 | Kurigram | 56 | Chilmari | 407 | 826 | PRO/KUR/CHI/VR/18-19/W-20 | Improvement of Bituminous Carpating Road on Kutigram Madrasha Pacca Rd – Kachkol CARE Bridge via Eblus Chairman house Road Ch. 00m-790m. & Link Road 0.00-230.0m. Under Chilmari Upazila, District Kurigram. | 149095036 | 1.02 | 0 |  | 77.3506 | M/S. S. T Enterprise, Nageswari, Kurigram | 73.4831 | 2019-05-26 | 2019-06-03 | 2021-05-31 | 100 | 58.6643 | 79.8338 | 2022-10-12
45 | Kurigram | 56 | Chilmari | 407 | 826 | PRO/KUR/CHI/VR/20-21/W-190 | Improvement of Bituminous Carpating Road on Kutigram Madrasha Pacca Rd – Kachkol CARE Bridge via Eblus Chairman house Road Ch. 1290m-1650g & Link Road (112m, 20m, 50m) Under Chilmari Upazila, District Kurigram. | 149095036 | 0.36 |  |  | 35.7082 | M/S Bulbul construction, Sadar, Kurigram | 30.9 | 2021-09-20 | 2021-10-03 | 2022-12-30 | 35 | 0 | 0 | 2022-10-12
46 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KUR/KUR-S/VR/18-19/W-22 | Improvement of Bituminous Carpating Road on Paramali Dr. Sahabuddin Tepoti to Rajarhat Ch.000-1930m & at Ch.1585 Link Road Ch.0.00-264.0m including Contruction of 04 Nos. (0.625mx0.600m) U-Drain on Paramali Dr. Sahabuddin Tepoti to Rajarhat Road at Ch.90m,730m,1250m & 1770m . Kurigram Sader Upzila,District Kurigram | 149525128 | 2.19 | 2.5 |  | 167.4365 | Md. Mahmud Alam Liton, Fulbari Pourashova,Fulbari | 167.4247 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 100 | 167.3803 | 99.9735 | 2022-10-12 | Final bill paid
47 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BUR/VR/18-19/W-24 | Improvement of Bituminous Carpating Road on Milon Bazar – Baladfia Bazar (End point H/O Nasir Uddin) at Ch.00-2000.0m. including Contruction of 03 Nos. 0.625mx0.600m U-Drain at Ch.1003m, 1685m Under Bhurungamari Upazila, District Kurigram., | 149064036 | 2 | 1.88 |  | 147.4391 | M/S. Hamid Traders, Hospitalpara, Kurigram Sadar, Kurigram | 136.8945 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 100 | 136.8185 | 99.9444 | 2022-10-12 | Final bill paid
48 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KURI/NAW/VR/18-19/W-25 | Improvement of Bituminous Carpating Wabda Bazar – Berubari Abashon Road at Ch.00.0-1200.00m Under Nageswari Upazila, District Kurigram. ` | 149615083 | 1.2 | 0 |  | 91.1425 | M/S. Fahim Traders, RK Road, Sadar Kurigram | 86.5854 | 2019-05-28 | 2019-06-04 | 2020-02-27 | 100 | 86.5755 | 99.9886 | 2022-10-12 | Final bill paid
49 | Kurigram | 56 | Rajibpur | 406 | 826 | PRO/KURI/RJP/VR/18-19/W-26 | Improvement of Bituminous Carpating Road on By Tangalipara- Pakhiura road at Ch.0.00-2000.0m.Under Rajibpur Upzila, District Kurigram. | 149084053 | 2 | 0 |  | 150.1804 | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 142.1126 | 2019-05-30 | 2019-06-07 | 2020-05-30 | 100 | 136.3084 | 95.9158 | 2022-10-12 | Final bill paid
50 | Kurigram | 56 | Ulipur | 445 | 826 | PRO/KURI/ULP/VR/18-19/W-27 | Improvement of Bituminous Carpating Road on Ramramhat Mosque – Hatiar Mela WAPDA Embankment via Kokire para road at Ch.0.00-2080.0m including Contruction Of 2 Nos.0.600mx0.625m U-Drain at Ch.595, 786m. and Contruction Of 1 Nos.Cross Drainge Structure at Ch.1485.0m. Under Ulipur Upzila, District Kurigram. | 149944098 | 2.08 | 4.2 |  | 189.7723 | Milu Nowroj Abu Bakar, College Road, Kurigram Sadar, Kurigram | 168.4171 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 100 | 167.6276 | 99.5312 | 2022-10-12 | Final bill paid
51 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KURI/RAJ/VR/18-19/W-28 | Improvement of Bituminous Carpating Road on Mondir Mouja at H/O Nousher Ali- Khamar GPS Road at Ch.0.00m-2725.0m under Fulbari Upazila, District Kurigram. | 149775079 | 2.725 | 0 |  | 211.228 | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 184.2474 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 100 | 184.2126 | 99.9811 | 2022-10-12 | Final bill paid
52 | Kurigram | 56 | Fulbari | 408 | 826 | PRO/KUR/FUL/VR/18-19/W-39 | Improvement of Bituminous Carpating Road On Bokultola Bazar-H/O Nobiul Road at Ch. 00m – 1070.00m including Construction of U-drain (600mm X 0.625mm) at Ch.131m. Under Fulbari Upazila, District Kurigram. | 149185051 | 1.07 | 0.6 |  | 90.5008 | M/S. Milon Traders, Nilkhanto, Khalilgonj Bazar, Kurigram Sadar, Kurigram | 85.9758 | 2019-05-30 | 2019-06-06 | 2020-02-28 | 100 | 83.9667 | 97.6632 | 2022-10-12 | Final bill paid
53 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KUR/NAG/VR/18-19/W-40 | Improvement of Bituminous Carpating Road on Kherbari More UZR-Boitulah More via Taleberhat Road at Ch.1000-4070m including Construction Of 9 Nos. 0.600mx0.625mU-Drain at.Ch.1400m, 1780m, 1940m, 2220m, 3300m, 2244m, 3550m, 3680m & 3840m,Under Nageswari Upazila, District Kurigram. | 149614060 | 3.07 | 5.4 |  | 258.8477 | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 220.4684 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 100 | 215.2468 | 97.6316 | 2022-10-12 | Final bill paid
54 | Kurigram | 56 | Rajibpur | 406 | 826 | PRO/KUR/RAJI/VR/18-19/W-41 | Improvement of Bituminous Carpating Road on Tangalipara- Pakhiura road at Ch.2000-4000m.Under Rajibpur Upzila, District Kurigram. | 149084053 | 2 | 0 |  | 107.2306 | M/S. Aroshi Construction, Adorshopara, Nageswari, Kurigram | 98.2865 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 100 | 91.0029 | 92.5894 | 2022-10-12 | Final bill paid
55 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BHU/VR/18-19/W-42 | Improvement of Bituminous Carpating Road on R&H Trimohoni – Shingjhar Road at Ch.325.00-2685.00m. including Construction Of 1 Nos. (4x4.00x4.00) m Cross Drianges Structure at Ch 1702.00m. and Construction Of 1 Nos. (2.00x2.00) m Cross Drianges Structure and Construction Of 14 Nos.0.600mx0.625m U-Drain at Ch.636m,714m,935m,960m,1051m,1201m,1355m,1550m,2003m,2166m,2230m,2586m,2767m&3330m.Under Bhurungamari Upzila, District Kurigram. | 149064003 | 2.36 | 14.9 |  | 229.6112 | M/S. Zaharul Haque Dulal, Goshpara, Sadar, Kurigram | 212.0177 | 2019-06-16 | 2019-06-23 | 2020-06-16 | 100 | 211.9948 | 99.9892 | 2022-10-12 | Final bill paid
56 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BHUR/REHAB/VR/21-22/W-313 | Rehabilitation of R&H Trimohoni – Shingjhar Road at Ch.0.00-330.00m. including Construction Of 1 Nos. 0.60x0.60 m RCC Cross Drain Ch. 207.00m.Under Bhurungamari Upzila, District Kurigram. | 149064003 | 0.33 | 0.9 |  | 14.5253 | M/S.Mostafa Traders,Sadar,Kurigram. | 11.7402 | 2022-03-23 | 2022-03-30 | 2023-07-30 | 20 | 0 | 0 | 2022-10-12
57 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/18-19/W-43 | Improvement of Bituminous Carpating Road on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.0.00m-2000.0m Under Rajarhat Upzila, District Kurigram. including Construction Of 2 nos. 0.600mx0.625m U-Drain on Kalirhat Bazar – Dangrarhat BC (Rice Mill More) Road via Abul Kashem GPS Road at Ch.1667m, &1924m. under Rajarhat Upzila, District Kurigram. | 149775095 | 2 | 1.2 |  | 164.7747 | M/S. Khairul Enterprise, Trimohoni Bazar, Polashbari, Khalilgonj, Kurigram | 149.1041 | 2019-05-30 | 2019-06-06 | 2020-05-30 | 100 | 149.0359 | 99.9542 | 2022-10-12 | Final bill paid
58 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BUR/HBB/18-19/W-23 | Improvement of Bituminous Carpating Road on HBB from Pagla hat Bazar –Shangkose River Ghat at Ch.00-1390.0m. Under Bhurungamari Upazila, District Kurigram. | 149064016 | 1.39 | 0 |  | 73.8865 | M/S. Akram Traders, Porchim Nageswari, Kurigram | 70.1922 | 2019-05-28 | 2019-06-04 | 2020-02-27 | 100 | 68.9353 | 98.2094 | 2022-10-12 | Final bill paid
59 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KUR/KURI-S/VR/20-21/W-254 | Improvement of Shop of Abul at BWDB Embank.-Velurbazar Road at Ch: 0.00- 1000m including construction of 1 nos 1X0.600mX0.600m U-drain at ch. 695m and 2 nos 1X2.00mX2.00m Box culvert under Upazila Sadar, District: Kurigram. | 149525043 | 1 | 3.4 |  | 104.1916 | Mohammad Yunus & Brothers Pvt., Chattogram | 86.32 | 2021-11-10 | 2021-11-18 | 2022-11-17 | 0 | 0 | 0 | 2022-10-12
60 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KUR/NAG/VR/21/-22/W-329 | Improvement of Beparipara UNR more-Harirkuti via Sarkarpara Road at ch: 00-2340m Under Upazila: Nageswari, District:Kurigram. | 149615081 | 2.34 |  |  | 225.3736 | M/S Zahurul haque Dulal, Sadar, Kurigram | 220.855 | 2022-07-17 | 2022-07-24 | 2023-07-23 | 0 | 0 | 0 | 2022-10-12
61 | Kurigram | 56 | Fulbari | 408 | 826 | PRO/KUR/FUL/VR/19-20/W- 81 | Improvement of Uttar Kashipur Shenpara – Kashem Bazar Via Ghugurhat Road at Ch: 00m-2500m including Construction of 3Nos 1x0.600mx0.600m m RCC. Box Culvert at at Ch: 90m,270m,1437m Under Upazila: Fulbari, District:Kurigram. | 149185050 | 2.5 | 3 |  | 215.7094 | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 186.1683 | 2020-03-29 | 2020-05-15 | 2021-05-14 | 100 | 186.0659 | 99.945 | 2022-10-12 | Final bill paid
62 | Kurigram | 56 | Fulbari | 408 | 826 | PRO/KUR/FUL/VR/19-20/W- 82 | Improvement of H/O Shajamal – Bokultola Bazar Via Abder Tale House Road at Ch: 00m-545.00m including Construction of 2Nos U-Drain at Ch: 124m,375m Under Upazila: Fulbari, District:Kurigram. | 149185060 | 0.545 | 2 |  | 48.3291 | M/S Fahim Traders, Kurigram Sadar, Kurigram. | 42.399 | 2020-03-16 | 2020-05-02 | 2020-11-15 | 100 | 42.2725 | 99.7016 | 2022-10-12 | Final bill paid
63 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BHU/VR/20-21/W-165 | Improvement of Bituminous Carpating Road Thanaghat Bazar-Shahebganj Bazar Road at Ch. 0.00-3045m including construction of 1 nos 1X3.0mX3.0m RCC box culvert at 1435m and 2 nos 1X2.0mX2.0m RCC box culvert at Ch. 2540m, 2700m and 8 nos 0.900mX0.900m cross drainage at Ch. 330,715m,1080m,1595m,1725m,1960m,2010m,2307m under upazila: Bhurungamari, Dist: Kurigram | 149064020 | 3.045 | 17.2 |  | 273.3306 | M/S Hamid Traders. | 229.4624 | 2021-03-28 | 2021-04-04 | 2022-12-30 | 65 | 26.9247 | 11.7338 | 2022-10-12
64 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KUR/NAG/VR/21-22/W-291 | Improvement of Bituminous Carpating Road on Sadar Beparirghat - Momingonj bazar Ch. 470m-1700m including 1 nos 1X2.00X2.00m RCC box culvert & 2 nos 7X6.00mX0.60m RCC cross drainage Structure at ch. 1235m, 1700m under Nageswari upazila, Dist: Kurigram. | 149614012 | 1.23 | 4.2 |  | 106.9969 | M/S Hamid Traders | 94.3931 | 2022-01-10 | 2022-01-17 | 2023-01-18 | 20 | 0 | 0 | 2022-10-12
65 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/19-20/W-65 | Improvement of Bituminus carpeting road Chandamari-Shyom Narayan at Biddyananda road at Ch: 1000m-2235m including 1 Nos(0.625X0.625)m U-Drain under Upazila: Rajarhat, District: Kurigram | 149774012 | 1.235 | 1 |  | 69.2764 | M/S Khairul Enterprise | 60.0918 | 2020-02-17 | 2020-02-24 | 2020-08-23 | 100 | 60.0283 | 99.8942 | 2022-10-12 | Final Bill paid
66 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/19-20/RW-66 | Improvement of Bituminus carpeting road Chandamari-Shyom Narayan at Biddyananda road at Ch: 0-1000m including 1 Nos(0.625X0.625)m U-Drain under Upazila: Rajarhat, District: Kurigram | 149774012 | 1 |  |  | 24.7905 | M/S Khairul Enterprise | 20.3077 | 2020-02-17 | 2020-02-24 | 2020-08-23 | 100 | 20.278 | 99.8537 | 2022-10-12 | Final Bill paid
67 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/19-20/W-105 | Improvement of Rajmallir hat-Shakoa GPS road Ch: 00 m-1985.00m including Construction of 2x3.00mx3.00m Rcc.Box Culvert and 2 Nos0.925x0.925m U-Drain at Ch: 00 m-1985.00m Under Upazila: Razarhat, District:Kurigram. | 149774008 | 1.985 | 9.8 |  | 195.3136 | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 165.1294 | 2020-07-20 | 2020-07-27 | 2022-12-30 | 55 | 28.2291 | 17.0951 | 2022-10-12
68 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/21-22/W-305 | Improvement of Ramratan Mouza - Chinai UP ghat road at Ch. 325m-1325m including construction of 4 nos 0.750X0.750m RCC cross drain. | 149775058 | 1 | 4.6 |  | 96.2734 | M/S Nahid Enterprise. | 82.0349 | 2022-02-17 | 2022-02-24 | 2023-02-23 | 15 | 0 | 0 | 2022-10-12
69 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/19-20/W- 104 | Improvement of WAPDA Emb.at Chaturvuj Mouza-Makli Mouja at Brahmmon para road Ch: 00m-2000m Under Upazila: Razarhat, District:Kurigram. | 149775066 | 2 |  |  | 184.5759 | M/s Khairul Enter,Trimohoni Bazar,Polasbari, Khalilgonj, Kurigram Sadar, Kurigram. | 155.2877 | 2020-07-20 | 2020-07-27 | 2021-07-26 | 100 | 155.1372 | 99.9031 | 2022-10-12 | Final bill paid
70 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/VR/19-20/W-103 | Improvement of Nazimkhan -Forkerhat at Boroghat Madrasha More-Bottalahat road Ch: 00m-1000m including Construction of 3Nos 1x0.6250mx 0.625m m U-Drain at Ch: 630m,840m &982m Under Upazila: Razarhat, District:Kurigram | 149774067 | 1 | 3 |  | 93.1275 | Sheetal Construction,R.K Road,Khalilgong,Sadar, Kurigram | 79.0598 | 2020-07-20 | 2020-07-27 | 2021-11-30 | 100 | 79.0436 | 99.9795 | 2022-10-12 | Final bill paid
71 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KUR/ULI/RMP/19-20/MW-111 | Estimate of Wages for Rural road maintenance by LCS (Material & Wages) work on Panchgachi Bazer-Nayani Para Sarak at Kurigram Sadar Upazila, Kurigram District, under PROVATi³ Project, LGED, Dhaka. (Length 1.650Km) | 149525026 | 1.65 |  |  | 11.1403 | Beauti Begum / Santona Rani | 11.1403 | 2020-07-27 | 2020-09-01 | 2022-08-31 | 96 | 9.4365 | 84.7057 | 2022-10-12
72 | Kurigram | 56 | Ulipur | 445 | 826 | PRO/KURI/ULP/VR/20-21/W-152 | Improvement of Bituminous Carpating Road on Bozra U.P. office-Babur hat at ch. 0.00-1990m including 3nos 0.625mX0.625m at ch. 20m,168m,1850m and 1 nos 1X2.0mX2.0m at ch.510m under Ulipur upazila, Dist: Kurigram. | 149944136 | 1.99 | 5.4 |  | 181.052 | Sheetal Construction,Kurigram | 150.6172 | 2021-03-03 | 2021-03-10 | 2022-12-30 | 20 | 0 | 0 | 2022-10-12
73 | Kurigram | 56 | Rowmari | 437 | 826 | PRO/KUR/ROW/VR/19-20/W-106 | Improvement of Shaydabad to Shiber Dhangi FCD road Ch: 1000m-2000m Under Upazila: Rowmari, District:Kurigram. | 149795038 | 1 |  |  | 79.2392 | M/s K.M Abu Bakar, Collage Road,Kurigram Sadar,Kurigram | 68.8184 | 2020-07-20 | 2020-09-01 | 2021-02-28 | 100 | 68.7711 | 99.9313 | 2022-10-12 | Final bill paid
74 | Kurigram | 56 | Rowmari | 437 | 826 | PRO/KUR/ROW/VR/19-20/W-89 | Improvement of Boalmari Modho Mosque –Changtapara Via Danguapara Road at Ch: 1000m-3000m Under Upazila:Rowmari, District:Kurigram | 149794017 | 2 |  |  | 171.7045 | M/S Hamid Traders | 159.8038 | 2020-03-16 | 2020-05-15 | 2021-05-14 | 100 | 159.2923 | 99.6799 | 2022-10-12 | Final bill Paid
75 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BUR/VR/19-20/W- 98 | Improvement of Dhaldanga Bazar-Shilkhuri Kheya ghat road (HBB) Ch: 1200m-2250m including Construction of 1x2.00mx 2.00m RCC. Box Culvert on Ch: 1540m under Upazila:Bhurungamari, District:Kurigram. | 149064029 | 1.05 | 2.5 |  | 59.1901 | M/S. Belal Construction,Horiswor Kaloea,Khalilgonj,Kurigram sadar,Kurigram. | 51.7296 | 2020-04-21 | 2020-05-15 | 2021-09-14 | 100 | 51.7257 | 99.9925 | 2022-10-12 | Final bill paid
76 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BHUR/REHAB/VR/21-22/W-314 | Rehabilitation of Dhaldanga Bazar-Shilkhuri Kheya ghat road Ch:0.00- 1200m including Construction of 0.601x0.60m RCC. Cross drain on Ch: 510m under Upazila:Bhurungamari, District:Kurigram. | 149064029 | 1.2 | 0.9 |  | 31.4996 | M/S.Mostafa Traders,Sadar,Kurigram. | 25.9026 | 2022-03-23 | 2022-03-30 | 2023-07-30 | 0 | 0 | 0 | 2022-10-12
77 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KURI/RAJA/VR/19-20/W-130 | Improvement of Bazar Gate of Nazimkhan Union- Dangghat Kali Mondir via Ratiram Pathanpara GPS Road. road Ch: 0.0m-1580m including Construction of 1Nos 0.625m x 0.625m U-Drain at Ch: 427 m Under Upazila: Rajarhat, District:Kurigram. |  | 1.58 | 1 |  | 139.8979 | M/S S.S Enterprise Katamara, Aditpmari, Lalmonirhat | 114.9971 | 2020-12-17 | 2020-12-24 | 2022-10-30 | 60 | 56.7459 | 49.3455 | 2022-10-12
78 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KUR/NAG/REHAB/VR/21-22/W-315 | Rehabilitation of Momingonj School to Chilmari Road at Ch: 00 m-670 m. under Upazila: Nageswari, Dist: Kurigam | 149614030 | 0.67 |  |  | 16.0605 | M/S.Mostafa Traders,Sadar,Kurigram. | 13.085 | 2022-03-23 | 2022-03-30 | 2023-07-30 | 0 | 0 | 0 | 2022-10-12
79 | Kurigram | 56 | Chilmari | 407 | 826 | PRO/KURI/CHIL/LM/20-21/W-169 | Construction of Jorgach Hat Upazila: Chilmari, District: Kurigram (03 nos LCS group) |  |  |  |  | 68.8762 | 3 nos LCS group | 68.8762 | 2021-03-16 | 2021-12-09 | 2022-11-15 | 38 | 37.8721 | 54.9858 | 2022-10-12
80 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KURI/SAD/LM/19-20/W-110 | Construction of Jatiner Hat Upazila: Sadar, District: Kurigram (03 nos LCS group) |  |  |  |  | 98.0579 | (LCS-01) Shamoli Rani /Mst.Banecha Begum (LCS-02) Mst. Lubna Begum / Kalpona Begum (LCS-03) Arifa Khatun / Srimoti Sumi Muhonto | 98.0579 | 2020-06-30 | 2021-09-12 | 2022-10-30 | 36 | 44.75 | 45.6363 | 2022-10-12
81 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KURI/RAJA/MM/20-21/W-220 | Construction of Chowrahat Upazila: Rajarhat, District: Kurigram (02 nos LCS group) |  |  |  |  | 53.7291 | 2 nos LCS group | 53.7291 | 2021-12-28 | 2022-02-24 | 2022-12-20 | 15 | 16 | 29.779 | 2022-10-12
82 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KURI/NAG/MM/20-21/W-157 | Construction of Chilakhana Hat, Upazila: Nageswari Dist: Kurigram (2 nos LCS group) |  |  |  |  | 64.8158 | i) Rokeya Begum/ Laily Begum ii) Sufia Begum/ Monoara Begum | 64.8158 | 2021-03-10 | 2021-09-16 | 2022-06-30 | 100 | 53.5804 | 82.6657 | 2022-10-12
83 | Kurigram | 56 | Nageswari | 430 | 826 | PRO/KURI/NAG/MM/20-21/W-171 | Construction of Schooler Hat, Upazila: Nageswari Dist: Kurigram (2 nos LCS group) |  |  |  |  | 58.6145 | i) Momotaz Begum/Mst. Jannati ii) Aroti Rani/ Sahina Khatun | 58.6145 | 2021-06-28 | 2022-01-27 | 2022-11-30 | 21 | 28.3298 | 48.3324 | 2022-10-12
84 | Kurigram | 56 | Ulipur | 445 | 826 | PRO/KURI/ULI/MM/2019-20/W-61 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram |  |  |  |  | 25.775 | Gouribala and Bimala Rani | 25.775 | 2019-12-17 | 2019-12-29 | 2020-12-28 | 100 | 20.0542 | 77.805 | 2022-10-12
85 | Kurigram | 56 | Ulipur | 445 | 826 | PRO/KURI/ULI/MM/2019-20/W-62 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram |  |  |  |  | 25.7949 | Sagorika Bala and Anju Begum | 25.7949 | 2019-12-17 | 2019-12-29 | 2020-12-28 | 100 | 19.0899 | 74.0064 | 2022-10-12
86 | Kurigram | 56 | Ulipur | 445 | 826 | PRO/KURI/ULI/MM/2019-20/W-87 | Construction of Hatia Vobesh Hat Upazila: Ulipur, District: Kurigram |  |  |  |  | 5.3447 | Joymala begum and Beuty Begum | 5.3447 | 2020-01-12 | 2020-01-19 | 2020-07-18 | 100 | 4.5012 | 84.2181 | 2022-10-12
87 | Kurigram | 56 | Sadar | 409 | 826 | PRO/KUR/KUR_S/RMP/19-20/ MW-122 | i)Kawnia Ghat-Kaggipara G.P. School | 149525029 | 3 |  |  | 13.1167 | Mst Rashada Bebum / Mst Shanila Begum | 13.1167 | 2020-07-27 | 2020-09-01 | 2022-08-31 | 96 | 10.99 | 83.7861 | 2022-10-12
88 | Kurigram | 56 | Rajarhat | 444 | 826 | PRO/KUR/RAJA/RMP/19-20/ MW-123 | i)Amtoli Bazar to Sakhoa GPS road. ii)Dino Bazar rail line to Amtail Bazar via Narayam Nember House. | 149775054 149774065 | 2.8 |  |  | 15.8794 | i) Najma Begum / Sumi Begum ii) Anita Rani / Rasida Begum | 15.8794 | 2020-08-09 | 2020-09-01 | 2022-08-31 | 96 | 13.4365 | 84.6158 | 2022-10-12
89 | Kurigram | 56 | Rajibpur | 406 | 826 | PRO/KUR/RAJIRMP/19-20/ MW-124 | i) Boraidangi Collage Road. | 149084006 | 0.825 |  |  | 7.1399 | Mrs. Joynob / Mrs. Lutfa | 7.1399 | 2020-10-01 | 2020-11-01 | 2022-10-31 | 88 | 5.5911 | 78.3073 | 2022-10-12
90 | Kurigram | 56 | Rowmari | 437 | 826 | PRO/KURI/ULI/MM/2020-21/W-176 | Construction of Saydabad Hat under Upazila: Rowmari, District: Kurigram (2 nos LCS group) |  |  |  |  | 41.474 | i) Rokeya Khatun/ Johura Khatun ii) Rehana Khatun/ Asia Khatun | 41.474 | 2021-03-11 | 2021-08-25 | 2022-10-30 | 63 | 20.5 | 49.4286 | 2022-10-12
91 | Kurigram | 56 | Fulbari | 408 | 826 | PRO/KUR/FUL/MM/20-21/W- 155 | Construction of Shiberhat Bazar,Upazila: Fulbari Dist: Kurigram (2 nos LCS group) |  |  |  |  | 46.0578 | i) Anowara Khatun/ Monowara Begum ii) ProtimaRani/ Shefali Begum | 46.0578 | 2021-06-09 | 2021-09-16 | 2022-06-30 | 100 | 38.6046 | 83.8178 | 2022-10-12
92 | Kurigram | 56 | Fulbari | 408 | 826 | PRO/KUR/FUL/MM/20-21/W- 156 | Construction of Ghogurhat Bazar,Upazila: Fulbari Dist: Kurigram (2 nos LCS group) |  |  |  |  | 56.5201 | i) Hasina Begum/ Argina Begum ii) Hajera Begum/ Nurjahan Begum | 56.5201 | 2021-03-28 | 2021-09-16 | 2022-08-30 | 100 | 47.2235 | 83.5518 | 2022-10-12
93 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BUR/MM/20-21/W-153 | Construction of Boldia Hat, Upazila:Bhurungamari, Dist: Kurigram (2nos LCS Group) |  |  |  |  | 55.2261 | i) Shilpi Khatun/ Koriful Begum ii) Shahanaz Begum/ Aloka Rani | 55.2261 | 2021-02-08 | 2021-10-03 | 2022-06-30 | 100 | 45.5673 | 82.5105 | 2022-10-12
94 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BHUR/FS/21-22/W-312 | Construction of Three storied school cumflood shelter at Kochabari Govt. Primary School under Upazila: Bhurungamari, Dist: Kurigram. |  |  |  |  | 265.1864 | M/S.Shefat Traders,Kamarpara,Kurigram Sadar,Kurigram. | 228.9883 | 2022-02-23 | 2022-03-30 | 2023-10-29 | 10 | 0 | 0 | 2022-10-12
95 | Kurigram | 56 | Bhurungamari | 404 | 826 | PRO/KUR/BUR/SM/20-21/W-154 | Construction of Muktijoddha Hat, Upazila:Bhurungamari, Dist: Kurigram (2nos LCS Group) |  |  |  |  | 40.5196 | i) Arjina Khatun/ Josna Begum ii) Salma Begum/ Shefali Begum | 40.5196 | 2021-03-15 | 2022-01-25 | 2022-12-30 | 30 | 14 | 34.5512 | 2022-10-12
96 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/UNR/18-19/W-16 | Improvement of Bituminous Carpeting Road on Sarai Up office (Zahir) to Eakota Bazar Via Udaynarayon Machari Govt.Primary School at Ch.2375m-3055m. Under Kaunia Upazila, District Rangpur. | 185423012 | 0.68 | 0 |  | 54.3001 | M/S. Nila Enterprise, Shalbon, Rangpur | 51.5851 | 2019-04-09 | 2019-04-16 | 2020-12-30 | 100 | 50.7378 | 98.3574 | 2022-10-12 | Final Bill Paid
97 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/UNR/20-21/RW-189 | Improvement of Bituminous Carpeting Road on Sarai Up office (Zahir) to Eakota Bazar Via Udaynarayon Machari Govt.Primary School at Ch.0.00m-1400m. Under Kaunia Upazila, District Rangpur. | 185423012 | 1.4 | 0 |  | 21.108 | H. S Enterprise, Singghimari,Hatibandha,Lalmonirhat | 17.5 | 2021-05-16 | 2021-05-22 | 2021-11-18 | 100 | 17.1146 | 97.7977 | 2022-10-12
98 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RAN/GAN/UNR/18-19/W-17 | Improvement of Bituminous Carpeting Road on Kolkando UP (Binbina Ferrighat)-Abuliahat Upto Kaliganj Upazila Border (Tusvander UP) Road at Ch 00-2350m. including Costruction of 3 U- drain at Ch 00-2350m Under Gangachara Upazila, District Rangpur. | 185273020 | 2.35 | 4.8 |  | 215.4548 | M/S. Onto & Tahity (JV), Rangpur | 202.3945 | 2019-04-30 | 2019-05-06 | 2020-05-05 | 100 | 201.7014 | 99.6575 | 2022-10-12 | Final bill paid
99 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/UNR/19-20/W-74 | Improvement of Bituminous carpeting Road on Sarai UP- Bhahishwler More bazar via Naira Pry.School Road at Ch: 1412m-3412m including Construction of 1Nos (0.625x0.625) m U-Drain at Ch: 1775m,2247m, 2537m,2590m & 3155m and 1Nos 3x4.50mx4.00 m RCC Box Culvert at Ch: 2127m and 1Nos 1x2.00mx2.00 m RCC Box Culvert at Ch: 2901m Under Upazila:Kaunia, District: Rangpur | 185423013 | 2 | 22.5 |  | 248.1519 | KZ-AHC (JV) Kashimpur, Mithapukur, Rangpur | 221.9146 | 2020-03-25 | 2020-04-04 | 2022-11-30 | 75 | 157.583 | 71.0106 | 2022-10-12
100 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/VR/20-21/W-137 | Improvement of Bituminous carpeting on Jummarpar R&H - Mirbag Gramen Bank More Bazar. Road at Ch:00m-1482m including Construction of 2Nos 0.625x0.625 m U-Drain at Ch:315m & 465m Under Kaunia Upazila , District: Rangpur. | 185424058 | 1.482 | 2 |  | 132.7789 | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 114.1912 | 2020-11-15 | 2020-11-21 | 2021-10-05 | 100 | 111.9565 | 98.0429 | 2022-10-12 | Final bill paid
101 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/VR/20-21/W-138 | Improvement of Bituminous carpeting Road on Topical GC hat - Branter bazar via Gopidanga GPS. Road at Ch: 00m-2785m including Construction of 3Nos 0.625x0.625 m Drainage Structure at Ch:640m,1383m &1814m and 1Nos 1x1.500x1.50 m RCC Box Culvert at Ch: 551m and 1x2.00x2.00 m RCC Box Culvert at Ch: 128m 2x4.50x4.00 m RCC Box Culvert at Ch: 910m and 3x4.50x4.00 m RCC Box Culvert at Ch: 1607m Under Under Kaunia Upazila , District: Rangpur. | 185424060 | 2.785 | 32.8 |  | 339.6116 | Sinthia-Oishi & Jesmin (JV), Kamalkaccha, Rangpur | 284.4964 | 2020-11-15 | 2020-11-21 | 2022-12-31 | 70 | 156.18 | 54.897 | 2022-10-12
102 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RAN/GAN/VR/20-21/W-174 | Improvement of Bituminous carpeting on Balatary Chowpati – Joydeb Dolapara Road at Ch:00m-1916.00m including Construction of 3Nos 1x0.60m x 0.60m RCC. U-Drain at Ch:30m, 400m & 550m and 2Nos 2x3.00m x 2.50m RCC. Box Culvert | 185275107 | 1.916 | 16.5 |  | 203.3789 | M/S. Tahity Enterprise | 177.5859 | 2021-03-23 | 2021-03-30 | 2022-08-16 | 76 | 135.809 | 76.4751 | 2022-10-12
103 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RAN/GAN/VR/21-22/W-289 | Improvement of Bituminous carpeting road on Betgari Kachua UZR near Patakhowa more - Sudhuir Master's house road at Ch. 0.00-1075m including 1 nos 7.00mX0.600mX0.600m cross drain at Ch. 115m and 1 nos 3.00mX2.50m RCC box culvert at ch. 1052m under Gangachara Upazila, Dist: Rangpur | 185275134 | 1.075 | 3.06 |  | 107.1967 | M/S Ranga Construction, Dhap, Rnagpur | 91.8642 | 2021-12-18 |  | 2022-12-17 | 100 | 91.5405 | 99.6476 | 2022-10-12 | Final bill paid
104 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/VR/18-19/W-15 | Improvement of Bituminous carpeting Road on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 00-1715m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | 185424019 | 1.715 | 0.6 |  | 132.1205 | Md. Hafizur Rahman Burirhat, Rangpur. | 128.4981 | 2019-04-30 | 2019-05-05 | 2020-03-22 | 100 | 127.2664 | 99.0415 | 2022-10-12 | Final bill paid
105 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/VR/20-21/W-151 | Improvement of Bituminous carpeting Road on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 1715-2995m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | 185424019 | 1.28 |  |  | 108.8694 | M/S. Abu Taleb Milu, Tushbhandar, Kaliganj, Lalmonirhat. | 90.2884 | 2021-01-25 | 2021-01-31 | 2021-12-31 | 100 | 85.195 | 94.3588 | 2022-10-12
106 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/RMP/21-22/MW-270 | Road maintenance by LCS on Kutirghat Bazar-Sonaton Shaidar Darogar Chatal Road at Ch 00-1715m. including Costruction of 1 no U- drain (.600mx0.625m) at Ch 1120m. Under Kaunia Upazila, District Rangpur. | 185424019 | 1.715 |  |  | 7.643 | Mst. Tahsina & Mst. Nasrin begum | 7.643 | 2021-08-31 | 2021-08-31 | 2023-08-31 | 60 | 3.8827 | 50.8003 | 2022-10-12
107 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/MM/19-20/W- 107 | Construction of Ekoter Hat Upazila:Kaunia, District: Rangpur, Under PROVATi3 Project. |  |  |  |  | 50.3263 | Mst Sahida Khatun and Mst. Merina Begum (LCS-1)/Mst. Dolena and Mst. Sheuli Begum(LCS-2) | 50.3263 | 2020-07-21 | 2020-07-21 | 2021-07-21 | 100 | 46.3681 | 92.1349 | 2022-10-12 | Final bill paid
108 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RAN/GAN/RMP/19-20/MW-108 | (i) Rural road maintenance by LCS (Material & Wages) work on Char Nohali Bridger Bazar- Minar Bazar via Ashrayon Bazar (Bager hat) Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. (ii) Rural road maintenance by LCS (Material & Wages) work on Kutub hat(konabari) - Khamer mohona GPS via uttor kishamot Gonesh GPS Sarak at Gangachara Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | 185275228 185275241 | 9 |  |  | 36.6686 | Mst. Ayouli Begum & Mst. Anufa Begum (LCS-01) Mst. Monzila Begum & Mst. Rabeya Begum(LCS-02) | 36.6686 | 2020-06-01 | 2020-06-01 | 2022-09-30 | 100 | 31.2196 | 85.14 | 2022-10-12
109 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/RMP/19-20/MW-109 | Rural road maintenance by LCS (Material & Wages) work on Sarai UP-Bhahishwler more Bazar via Naira Pry. School Sarak at Kaunia Upazila, Rangpur District, under PROVATi³ Project, LGED, Dhaka. | 185423013 | 2.275 |  |  | 13.2672 | Mst. Rabeya Khatun & Mst. Rugina Begum | 13.2672 | 2020-06-01 | 2020-06-01 | 2022-05-31 | 100 | 12.3388 | 93.0022 | 2022-10-12
110 | Rangpur | 53 | Gangachara Kaunia | 424 | 826 | PRO/RAN/RMP/21-22/MW-334 | Maintenance of Kolkondo UP (Binbinia Ferrighat)- Abuliahat UP to Kaligonj Upazila Border (Tusvander UP) Road. Ch. 350m-2350m. ID:185273020 Maintenance of Sarai UP (Zahir)-Eakotar Bazar via Udoy Narayon Machari pry.school Road at ch. 2000m-1400 m. ID: 185423012 | 185273020 185423012 | 3.4 |  |  | 14.1579 | Mst. Moslema Khatun & Mst. Sufiya Khatun | 14.1579 | 15-06-2022 01-09-2022 |  | 2024-08-31 | 10 | 0.465 | 3.2844 | 2022-10-12
111 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/MM/20-21/W-164 | Construction of Bhaier Hat Upazila:Kaunia, District: Rangpur (2 nos LCS group) |  |  |  |  | 50.0877 | LCS-1 Chair Pertion Mst. Bilkis Begum, Seceretary Mst. Lovly Begum/ LCS-2 : Chairperson Most Rahima Begum, Sec: Mst. Asma Begum | 50.0877 | 2021-08-17 |  | 2022-08-17 | 0 | 0 | 0 | 2022-10-12
112 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/MM/20-21/W-162 | Construction of Bhutsora(Mirbag) Hat Upazila:Kaunia, District: Rangpur (2 nos LCS group) |  |  |  |  | 58.2568 | Group 1) Manika Rani Roy & Mst. Ayesha Khatun Gropu 2) Mst. Rajia Sultana & Taslima Khatun | 58.2568 | 2021-08-11 |  | 2022-08-11 | 80 | 38.3232 | 65.7833 | 2022-10-12
113 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/MM/20-21/W-163 | Construction of Haqueer hat Upazila:Kaunia, District: Rangpur (2 nos LCS group) |  |  |  |  | 42.1649 | Group 1) Mst. Sharifa Khatun & Most. Fancy Begum Group 2) Mst. Monoyara parvin & Mst. Anowara Begum | 42.1649 | 2021-03-09 |  | 2022-03-08 | 100 | 36.3958 | 86.3178 | 2022-10-12
114 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RAN/GAN/MM/20-21/W-175 | Construction of Abuliarhat upazila: Gangachara, District: Rangpur (2 nos LCS group) |  |  |  |  | 55.2731 | LCS-1 Chair Pertion Mst. Lakeja Khatun, Seceretary Mst. Sirina Begum/ LCS-2 : Chairperson Mst. Sarmin Aktar Boby Sec: Mst. Morsheda Begum | 55.2731 | 2021-03-18 |  | 2023-03-31 | 0 | 8 | 14.4736 | 2022-10-12
115 | Rangpur | 53 | Kaunia | 403 | 826 | PRO/RAN/KAU/FS/21-22/W-295 | Construction of three storied Pollimari Govt. Primary school cum Flood Shelter |  |  |  |  | 241.8399 | Md. Khairul Islam Roman, ThakurgoanG | 239.2863 | 2022-02-16 | 2021-02-22 | 2022-12-31 | 80 | 40.8418 | 17.0682 | 2022-10-12
116 | Rangpur | 53 | Gangachara | 424 | 826 | PRO/RANG/MAINT/19-20/MW-3 | Repair & maintenance work of LGED office building, Dist: Rangpur |  |  |  |  | 21.4164 | M/S Tahity Enterprise | 15.4791 | 2020-09-09 | 2020-09-15 | 2021-01-14 | 100 | 17.7999 | 100 | 2022-10-12 | Final bill paid
117 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/UNR/18-19/W-44 | Improvement of Bituminous carpeting Road of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164 km Under Dimla Upazila,District Nilphamari including Construction of 1Nos (2.00x2.00)m Cross Drainges Structure .at Ch.2287m and Construction of 2 Nos 7.00m Long.0.625mx0.625m U-Drain on Ch.2785,4011.0m of Dimla U.P (Petrol Pump)-Nizpara bazaar Rd.at Ch.2+255-4+164.00km Under Dimla Upazila,District Nilphamari | 173123002 | 1.909 | 3.25 |  | 179.9977 | M/S. Misuk Enterprise, Food Office Road, Nilphamari. | 177.2698 | 2019-07-08 | 2019-08-13 | 2020-09-25 | 100 | 177.1179 | 99.9143 | 2022-10-12 | Final bill paid
118 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/UNR/19-20/W-119 | Improvement of Bituminous carpeting Road of Naotara U.P Office-Motirbazar Rd. Ch: 950m-3250m including Construction of 1Nos 1x1.50mx 1.50 m U-Drain at Ch. 1159m and 2Nos 1mX0.6250mX 0.60m m U-Drain at Ch. 1389m under Upazila: Dimla, Dist: Nilphamari | 173123014 | 2.3 | 3 |  | 207.1749 | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 177.823 | 2020-11-19 | 2020-11-25 | 2021-11-24 | 100 | 177.7684 | 99.9693 | 2022-10-12 | Final bill paid
119 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/18-19/W-18 | Improvement of Bituminous carpeting Road on Ullarmore to Rahmangonj Bazar Road Under Gayabari Union at Ch.0.00m-2490m. including Construction of 2 Nos (1.50x1.50)m Box Culvert at Ch.142.00m & 630.0m and Construction of 1 Nos (2x3.00x3.00)m Box Culvert at Ch.197.00 m and Costruction of 1 Nos(1.500x1.00)m and Construction of 1 Nos (2x4.50x4.00) m Box Culvert at Ch.1922.00 m. and Costruction of 3 Nos(0.625x0.600) m U-Drain at Ch.50.0,480.0m&852m.Under Dimla Upazila,District Nilphamari. | 173124093 | 2.49 | 24.63 |  | 256.3798 | JV of SA FE Shahipara, Nilphamari. | 254.6916 | 2019-06-30 | 2019-07-06 | 2020-08-12 | 100 | 265.5226 | 99.9846 | 2022-10-12 | Final bill paid
120 | Nilphamari | 55 | Jaldhaka | 400 | 826 | PRO/NIL/JAL/VR/18-19/W-19 | Improvement of Bituminous Carpeting Road on Gabroli RNGPS-Tin Babul house via Rath Bazar Road at Ch 1000.0m-2650.0m including Costruction of 2 Nos (1.00x1.00) Box Culvert at Ch 1450.0m&1720.0m and Costruction of 1 Nos(2.00x2.00)m Box Culvert at Ch 2620.0m Under Jaldhaka Upazila,District Lilphamari. | 173365087 | 1.65 | 4.8 |  | 147.9967 | M/S. Mohsena Enterprise, Monshapara, Nilphamari. | 135.712 | 2019-07-09 | 2019-07-15 | 2021-06-30 | 100 | 133.1841 | 98.1373 | 2022-10-12 | Final bill paid
121 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/19-20/W-120 | Improvement of Bituminous Carpeting Road on Dakhin Sonakhuli-Dalia Taltola road Ch: 2150m-3650m including 2Nos 1x1.50mx 1.50 m U-Drain at Ch.Ch: 2388 m & 2630m and 2Nos 1x0.6250mx 0.60m m U-Drain at Ch: 2210 m & 2270m under Upazila: Dimla, Dist: Nilphamari | 173124012 | 1.5 | 5 |  | 148.6074 | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 128.7306 | 2020-11-19 | 2020-11-25 | 2022-10-30 | 64 | 81.9581 | 63.6664 | 2022-10-12
122 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/20-21/W-141 | Improvement of Kakina Chapani Madrasha-Tista Main Canal Road. Road Ch: 0.00m-1783.00m including Construction of 3Nos 1.50m x 1.50m RCCBox culvert at Ch: 625.0m,695.0m,1328.0m and 1Nos Single Vent2.00m x 2.00m RCCBox culvert at Ch: 1242.0m and 8Nos 7m longU-Drain 0.6250mm x 0.600m Drainage Culvert at Ch: 273.0m,362.0m, 467.0m, 540.0m, 727.0m,1347.0m,1475.0m, 1614.0m Under Upazila: Dimla, District:Nilphamari | 173125089 | 1.783 | 16.5 |  | 192.7822 | Babor Traders & Sons, Panchagarh road, Thakurgaon. | 161.9201 | 2020-12-28 | 2021-04-01 | 2022-03-01 | 100 | 159.8572 | 98.726 | 2022-10-12 | Final bill paid
123 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/20-21/W-140 | Improvement of Dokhin Sonakhuli -Vajonchur via Khamatpara. Road Ch: 1000.00m-3040.00m including Construction of 4Nos 1.50m x 1.50m RCC Box culvert at Ch: 1153.0m, 1186.0m, 2054.0m, 2480.0m and 1Nos 2vent 3.00m x 2.00m RCC Box culvert at Ch: 1991.00m and 3Nos U-Drain 7m Long 0.625.mm x 0.600mm Drainage Culvert at Ch: 1652.00m,2260.00m, 2290.00m Under Upazila: Dimla, District:Nilphamari | 173124082 | 2.04 | 17.5 |  | 231.8461 | MH Corporation & Mainuddin JVAC, Boda, Panchagarh. | 195.9028 | 2021-01-18 | 2021-01-24 | 2022-10-30 | 75 | 139.0313 | 70.9695 | 2022-10-12
124 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/19-20/W-125 | Improvement of Sonakhuli high School -Vendabari Road Ch: 00m-2155 m including 1Nos 1x3.00mx2.00m RCC. Box Culvert at Ch: 607m and 2Nos 1x1.50mx1.50m. RCC.Box Culvert at Ch: 720 m & 1167m and 1Nos 2x3.00mx2.00m RCC. Box Culvert at Ch: 206m Under Upazila: Dimla, District:Nilphamari. | 173124083 | 2.155 | 16 |  | 233.9402 | M/S. Zahurul Haque Dulal, Ghoshpara, Lalmonirhat | 200.6915 | 2020-11-19 | 2020-11-25 | 2022-09-15 | 100 | 103.7053 | 51.674 | 2022-10-12
125 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/VR/19-20/W-121 | Improvement of HBB Road on Sovangong Bazar- Astaf Ali House via Azgar rice mill road, under Balapara union Ch: 330m-1385 m Under Upazila: Dimla, District:Nilphamari. | 173125117 | 1.055 |  |  | 54.6815 | Rainbow Enterprise, Khaga Kharibarim Dimla, Nilphamari | 45.4891 | 2020-11-19 | 2020-11-25 | 2021-05-24 | 100 | 44.9863 | 98.8947 | 2022-10-12 | Final bill paid
126 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/RMP/20-21/ MW-128 | i)Naotara U.P. Office-Motirbazar RD at ch. 3200-6400 m. ii)DakhinSonakhuli-DaliaTaltola at ch. 1500-3750 m. iii)Kakina Chapani Madrasha-Tista Main Canal at ch. 2700-3500 m. iv)Dkhin Sonakhuli-Vajonchur via Khamatpara at ch. 2000-4500 m. v)Sonakhuli High School- Vendabari at ch. 2500-3800 m. | 173123014 173124012 173125089 173124082 173124083 | 10.05 |  |  | 50.7074 | LCS 1)Mst. Alena Akter & Srimati Golapi bala LCS 2)Mst. Hafezakhatun & Fozila Begum LCS 3) Mst Mamima Akter & Mst. Fozila Khatun LCS 4) Mst Lucky Begum & Homayra Begum LCS 5) Arzina Khatun & Nasima Begum | 50.7074 | 2020-10-29 | 2020-11-01 | 2022-10-31 | 80 | 40.3235 | 79.5219 | 2022-10-12
127 | Nilphamari | 55 | Jaldhaka | 400 | 826 | PRO/NIL/JAL/RMP/20-21/ MW-129 | i)WDB Bundh to WDB Bundh via Moratista Syphon at ch. 00-1215 m. ii)Moratista Syphon to WDB Bundh ch. 00-1506 m. | 173365064 173365066 | 2.721 |  |  | 15.8636 | LCS 1)Ambia Begum & Halima Khatun LCS 2)Mst.Ritta Begum & Most. Sayna Akter | 15.8636 | 2020-11-29 | 2020-12-01 | 2022-11-30 | 66 | 10.5142 | 66.2784 | 2022-10-12
128 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/RMP/21-22/MW-335 | Maintenance of Dimla U.P (Petrol Pump)-Nizpara bazar Road. Ch.2255m-4164m. ID:173123002 Maintenance of Uttarmore to Rahmangonj Bazar under Gayabari union Road at ch. 00m-2490 m. ID: 173124093 |  | 4.399 |  |  | 18.203 |  | 18.203 | 2022-06-26 | 2022-07-01 | 2024-06-30 | 8 | 1.5302 | 8.4065 | 2022-10-12
129 | Nilphamari | 55 | Dimla | 397 | 826 | PRO/NIL/DIM/FS/21-22/W-301 | Construction of Three Storied School cum Flood Shelter Dimla Bishpukur Tistar char Government Primary School |  |  |  |  | 234.1493 | M/S Keya Bakery & Confectionary,Munshipara,Nilphamari | 184.915 | 2022-02-16 | 2022-02-23 | 2023-02-22 | 10 | 0 | 0 | 2022-10-12
130 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/UNR/18-19/W-02 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Koborstan to Sarkarhat Jongra UP Road at Ch. 00-2185m. Under Patgram Upazila, District Lalmonirhat. | 152703010 | 2.19 | 0 |  | 161.4384 | M/S fahim Traders, Kurigram Sadar, Kurigram. | 139.6444 | 11-04-19 | 2019-04-18 | 2020-03-17 | 100 | 138.2827 | 99.0249 | 2022-10-12 | Final bill paid
131 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/UNR/19-20/W-78 | Improvement of Bituminous carpeting Road Sadhur Bazar-Guddimari Road at Ch: 1500m-3700m including Construction of 4Nos 1x 0.90mX0.900 m RCC Box Culvert at Ch: 2475m,2600m,3200m & 3640.00m and 1Nos 1x 2.0mX1.50 m RCC Box Culvert at Ch: 3030m Under Hatibandha Upazila ,District Lalmonirhat | 152333016 | 2.2 | 5.2 |  | 233.9955 | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 192.7611 | 2020-04-15 | 2020-04-22 | 2021-04-21 | 100 | 141.3582 | 73.3334 | 2022-10-12
132 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/UNR/20-21/W-143 | Improvement of Patikapara UP office – Dawabari UP Road. Ch: 1000.0m-3000.0m including Construction of 3 Nos 7.00x 0.900m x 0.900m Cross-Drain Ch: 1004.0m,1219.0m,1950.0m Under Upazila: Hatibandha, District:Lalmonirhat | 152333018 | 2 | 4.05 |  | 182.2611 | M/S Tahity Enterprise | 145.1985 | 2020-12-29 | 2021-05-01 | 2022-10-30 | 80 | 111.5861 | 76.8507 | 2022-10-12
133 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/REHAB/UNR/21-22/W-316 | Rehabilitation of Patikapara UP office -Dawabari UP Road at Ch: 00m-1000m. | 152333018 | 1 |  |  | 30.2128 | Ali Ahamed, Nursery Road, Rasulganj, Patgram, Lalmonirhat | 23.6556 | 2022-02-14 | 2022-02-21 | 2023-02-20 | 30 | 0 | 0 | 2022-10-12
134 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/UNR/19-20/W-57 | Improvement of Bituminous carpeting Road Jongra UP office (Futir Doba) to Sofinagadhat Road at Ch 00m-1000m. Under Patgram Upazila, District Lalmonirhat. | 152703020 | 1 | 0 |  | 82.1932 | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 73.9739 | 2020-02-18 | 2020-02-25 | 2021-02-24 | 100 | 72.1856 | 97.5826 | 2022-10-12 | Final bill paid
135 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/UNR/19-20/W-55 | Improvement of Bituminous carpeting Road on Patgram Zila Road at Kabarstanhat to Lalitarhat Kuchlibari UP Road at Ch: 1435m-3435m including Construction of 4Nos (1x2.00x1.50)m RCC.Box Culvert and 1 No (2x4.50x2.50)m RCC.Box Culvert Under Patgram Upazila ,District Lalmonirhat . | 152703019 | 2 | 20.5 |  | 208.9551 | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 188.0596 | 2020-02-18 | 2020-02-25 | 2021-02-24 | 100 | 187.6035 | 99.7575 | 2022-10-12 | Final bill paid
136 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/UNR/19-20/W-56 | Improvement of Bituminous carpeting Road on Kamerarhat Sreerampur UP via Dr.Hamidur Islam House Road at Ch: 900m-1995m Under Patgram Upazila ,District Lalmonirhat . | 152703007 | 1.095 | 0 |  | 98.4224 | M/S Zahurul Haque, Kurigram Sadar, Kurigram | 88.5802 | 2020-02-28 | 2020-02-25 | 2021-02-24 | 100 | 87.3119 | 98.5682 | 2022-10-12 | Final bill paid
137 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/19-20/W-127 | Improvement of Singimari Nebru House-Uttor Baraipara Masque Rd. Road Ch: 1150m -3260m including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch: 2122 m & 2952m Under Upazila: Hatibandha, District:Lalmonirhat. | 152334090 | 2.11 | 2.7 |  | 187.6976 | Ali Ahamed & M/S Hossain trading & Construction, Patgram, Lalmonirhat | 142.4997 | 2020-09-15 | 2020-09-21 | 2021-09-20 | 100 | 136.6414 | 95.8889 | 2022-10-12 | Final Bill Paid
138 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/20-21/W-148 | Improvement of Singimari UP-Goddimari UP Border Road Ch: 00m -3000m including Construction of 2Nos 1.50m x 1.50m RCC Box Culvert at Ch:530m & 1300m and 1 Nos 0.900m x 0.900m Cross-Drain at Ch: 2660.00m and 1Nos 3.00m x 3.00m RCC Box Culvert at Ch:90.00m Under Upazila: Hatibandha, District: Lalmonirhat. | 152335023 | 3 | 9.3 |  | 261.9134 | MPS & RT (JV), G.L. Roy Road, Rangpur | 199.2919 | 2021-02-17 | 2021-02-24 | 2022-10-30 | 75 | 123.9506 | 62.1955 | 2022-10-12
139 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/20-21/W-142 | Improvement of Hatibandha U.Z.R. at dhubni mauza to dhubni Madrasha Road Ch: 00m -1960m including Construction of 2Nos 0.900m x 0.900m Cross-Drain and 2Nos 1.50m x 1.50m Cross-Drain Under Upazila: Hatibandha, District: Lalmonirhat. | 152335059 | 1.96 | 5.4 |  | 183.2561 | ICL pvt. Ltd. Jessore | 142.1 | 2020-12-17 | 2020-12-23 | 2022-10-30 | 75 | 94.1458 | 66.2532 | 2022-10-12
140 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/19-20/W-77 | Improvement of Bituminous carpeting Road on Kasirdanga-Bazar to 3 no Vothatkhata GPS Road at Ch: 00m-2000m including Construction of 6Nos 1x1.50x1.00 m RCC Box Culvert at Ch: 830m, 870m,1120m, 1200m,1566m &1800m and 3Nos 1x3.00x2.00 m RCC Box Culvert under Patgram Upazila ,District Lalmonirhat | 152704084 | 2 | 15.5 |  | 236.5491 | Taheti & Shital (ZV), Kamal kachnu, Rangpur | 195.2021 | 15-04-2020 | 22-04-2020 | 2022-12-30 | 80 | 152.85 | 78.3035 | 2022-10-12
141 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/19-20/W-76 | Improvement of Bituminous carpeting Road on Nayerhat Mosque to Zero point of Dhagram UP Road at Ch: 1000m-4000m including construction of 1Nos 1x2.00x2.50 m RCC Box Culvert at Ch: 1310m Under Patgram Upazila ,District Lalmonirhat | 152705059 | 3 | 2.5 |  | 251.9885 | Md. Abdul Hossain, Ghoramara Rangpur. | 211.4183 | 30-04-20 | 2020-07-05 | 2021-06-02 | 100 | 209.6959 | 99.1853 | 2022-10-12 | Final Bill paid
142 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/19-20/W-75 | Improvement of Bituminous carpeting Road on Lolitarhat – Liakot Prodhan House Via Kolshirmuk BOP & Graipul Road at Ch: 4000m-4950m Under Patgram Upazila ,District Lalmonirhat | 152705121 | 0.95 |  |  | 82.4615 | GRP & RT (ZV), GL Roy Road, Rangpur. | 69.8203 | 15-04-20 | 22-04-20 | 21-04-21 | 100 | 69.6516 | 99.7584 | 2022-10-12 | Final Bill paid
143 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/21-22/W-293 | Improvement of Bituminous carpeting Road on Lolitarhat – Liakot Prodhan House Via Kolshirmuk BOP & Graipul Road at Ch: 4950m-6110m including 5 nos 2.00mX1.50m RCC box culvert at 5050m, 5294m, 5450m, 5685m, 5960m Under Patgram Upazila ,District Lalmonirhat | 152705121 | 1.16 | 17.5 |  | 127.3499 | Md. Mostafizur rahman | 116.8429 | 2021-11-30 | 2021-07-12 | 2022-12-30 | 35 | 9.69 | 8.2932 | 2022-10-12
144 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR-HBB/20-21/W-139 | Improvement of Karbalardighi R&H Road-Dakhalibandha Hat Road. Road Ch: 0.00m-2550.00m including Construction of 2Nos 2.00m x 1.50m Box culvert on Karbalardighi R&H Road-Dakhalibandha Hat Road. C/D st Ch: 1072 m & 2500m. Under Upazila: Hatibandha, District:Lalmonirhat. | 152334018 | 2.55 | 5 |  | 155.6061 | KHN & Sinthia (ZV) | 116.8429 | 2020-03-12 | 2020-10-12 | 2021-09-12 | 91 | 105.2532 | 90.0809 | 2022-10-12
145 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/21-22/W-292 | Improvement of Bituminous carpeting Road on Tangtindanga hat-H/O Khairul Islam via Belbariadanga GPS road at ch. 80-3410m including 1 nos 2.00mX1.50m RCC box culvert at ch. 1002m and 1 nos 3.00mX2.00m box culvert at ch. 570m under Patgram upazila, Dist: Lalmonirhat | 152704017 | 3.33 | 5.9 |  | 286.0725 | Md. Mostafizur rahman | 285.0009 | 2021-11-30 | 2021-07-12 | 2022-06-12 | 0 | 0 | 0 | 2022-10-12
146 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/MM/2019-20/W-67 | Construction of Shafinagar Hat, Upazila: Patgram, District: Lalmonirhat |  |  |  |  | 10.2531 | CPC Name- Mst.Luna Parvin . SPC Name- Mst.Provati Rani. LCS Member Nos- 10. | 10.2531 | 2020-08-23 |  | 2020-11-22 | 100 | 10.1804 | 99.2911 | 2022-10-12 | Final Bill paid
147 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/MM/2019-20/W-63 | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat |  |  |  |  | 17.609 | CPC Name- Mst.Lipi Begum . SPC Name- Mst.Merina Begum. LCS Member Nos- 15. | 17.609 | 2020-09-15 |  | 2021-03-14 | 100 | 15.2733 | 86.736 | 2022-10-12 | Final Bill paid
148 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/MM/2019-20/W-64 | Construction of Kamarer Hat Bazar, Upazila: Patgram, District: Lalmonirhat |  |  |  |  | 14.9443 | CPC Name- Mst.Nurzahan Begum . SPC Name- Mst.Laki Begum. LCS Member Nos- 10. | 14.9443 | 2020-09-15 |  | 2021-03-14 | 100 | 14.3752 | 96.192 | 2022-10-12 | Final Bill paid
149 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/MM/2020-21/W-184 | Construction of Cheatnai Hat (LCS-1,2) |  |  |  |  | 47.103 | LCS 1: Jharna Rani & Nomita Rani LCS 2: Rojufa Khatun & Rotna Rani | 47.103 | 2021-06-14 |  | 2021-12-13 | 40 | 15.12 | 32.0999 | 2022-10-12
150 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/PAT/MM/2020-21/W-149 | Construction of Dighirhat Bazar (LCS-1,2) |  |  |  |  | 57.6161 | LCS 1: Mst. Esmotara Begum & Mst. Maleka Khatun LCS 2: Mst. Shefali Khatun & Mst. Rahela Begum | 57.6161 | 2021-06-14 |  | 2021-12-13 | 5 | 12.96 | 22.4937 | 2022-10-12
151 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HAT/MM/20-21/W-133 | Construction of Nawdabash Hat (LCS-1,2,3) |  |  |  |  | 68.5579 | LCS 1 Sumitra Rani & Taproshi Rani barman, LCS 2: Santona rani & Kolpona Rani, LCS 3: Zosna Rani & Lavly Rani | 68.5579 | 2021-01-17 |  | 2021-07-16 | 15 | 10.8 | 15.7531 | 2022-10-12
152 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/RMP/20-21/ MW-131 | i) Jongra UP office (Futir Doba) to Shafinagar hat road. Ii) Aftab More to Shofinogorhat via Hosnabad Community Clinic & Mokbul Jahanara Hossain GPS road. iii) Olerpar to Dahagram Chairman bari road. | 152703020 152705151 152705098 | 3.17 |  |  | 19.4512 | LCS 1. Aklima khatun & Jhorna Begum LCS 2. Sheuli begum & Rohima khatun LCS 3. Morjina Begum & Nazma Khatun | 19.4512 | 2020-10-27 | 2021-01-11 | 2022-10-26 | 55 | 14.132 | 72.6537 | 2022-10-12
153 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/18-19/W-03 | Improvement of Bituminous Carpeting Road on Altab More to Safinagarhat via Hasnabad Community Clinik & Mokbul Jahanara Hossin GPS at Ch. 700-1700m. Under Patgram Upazila, District Lalmonirhat. | 152705151 | 1 | 0 |  | 69.7541 | M/S RML Enterprise, Hatibandha, Lalmonirhat. | 66.2664 | 2019-03-18 | 2019-03-25 | 2020-03-24 | 100 | 66.253 | 99.9797 | 2022-10-12 | Final Bill paid
154 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/REHAB/VR/21-22/W- 317 | Rehabilitation of Altab More to Safinagarhat via Hasnabad Community Clinik & Mokbul Jahanara Hossin GPS at Ch. 0-775m. Under Patgram Upazila, District Lalmonirhat. | 152705151 | 0.775 |  |  | 20.5201 | M/S Tahity Enterprise, Purba Shalbon, Rangpur | 15.7027 | 2022-02-14 | 2022-02-21 | 2023-02-20 | 100 | 15.3234 | 97.5848 | 2022-10-12 | Final bill paid
155 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-04 | Improvement of Niz Sheck Sundor Jameh Mosque - Applax Embankment road. Ch. 500m-1765m. including Construction of 7.00x0.900mx 0.900m Cross drain at Ch. 995m under Hatibandha Upazila, District Lalmonirhat. | 152335060 | 1.265 | 0.9 |  | 101.206 | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 88.3991 | 2019-04-11 | 2019-04-18 | 2020-03-17 | 100 | 88.3973 | 99.998 | 2022-10-12 | Final Bill paid
156 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/20/21/W-144 | Improvement of Niz Sheck Sundor Jameh Mosque - Applax Embankment road. Ch. 1765.0m-2365.0m. including Construction of 2Nos 7.00x 0.900m x 0.900m Cross-Drain at Ch. 1886.0m & 2115.0m and 1Nos 1x 2.00m x 1.50m Box Culvert at Ch: 1979.0m under Hatibandha Upazila, District Lalmonirhat. | 152335060 | 0.6 | 5.2 |  | 59.5297 | M/S Rifat Traders | 44.8075 | 2020-12-21 | 2020-12-27 | 2021-12-26 | 100 | 37.4421 | 83.562 | 2022-10-12 | Final bill paid
157 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-05 | Improvement of Bituminous Carpeting Road on WAPDA Pucea road to Dimla Bordar road at Ch.0.00m-3000.0m. including Construction of 2.00x 2.00 Cross drain at Ch. 2415.00m and Construction of 2 Nos 7x0.900mx0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | 152334015 | 3 | 4.2 |  | 276.1992 | M/S Islam Traders, Ghop Jossor, Lalmonirhat. | 244.0483 | 2019-04-10 | 2019-04-17 | 2020-09-01 | 100 | 241.5311 | 98.9686 | 2022-10-12 | Final bill paid
158 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-33 | Improvement of Bituminous carpeting Road on Patikapara Dowabari Up Boder To Kapil Member house Road at Ch. 00-1000m. including Construction of 2.00 Nos 0.900m x 0.900m Cross drain at Ch. 295.00m & 930.00m Under Hatibandha Upazila, District Lalmonirhat. | 152335034 | 1 | 1.8 |  | 77.6877 | Borsha Enterprise, Patgram, Lalmonirhat | 73.8033 | 2019-04-30 | 2019-06-10 | 2020-06-09 | 100 | 73.5575 | 99.667 | 2022-10-12 | Final bill paid
159 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-34 | Improvement of Bituminous carpeting Road on East Side Singimari Up Kalam Chatal to Goddimari Elahir Chatal at Ch. 0.00-2000.00m. Under Hatibanhda Upazila, District Lalmonirhat. including Construction of 2.00 Nos (2.50x2.50) m Cross Drainges Structure and Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch. 0.00-2000.00m. | 152334068 | 2 | 8 |  | 176.6935 | Anta & SH ZV, Patgram, Lalmonirhat | 156.3459 | 2019-06-09 | 2019-06-10 | 2019-11-09 | 100 | 156.0459 | 99.8081 | 2022-10-12 | Final bill paid
160 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-35 | Improvement of Bituminous carpeting Road R&H Nowabab Uddin House-Laxmi Kanto Chokider House at Ch.0.00m-1000.00m. including Construction of 1.00 Nos (3.00x2.50) m Cross Drainges Structure at Ch.661.00m. Under Hatibanhda Upazila, District Lalmonirhat. | 152334088 | 1 | 3 |  | 82.6468 | Nakshi Mobail Palace, Sadar, Kurigram | 78.5144 | 2019-05-14 | 2019-05-21 | 2020-03-01 | 100 | 78.4708 | 99.9445 | 2022-10-12 | Final bill paid
161 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-36 | Improvement of Bituminous carpeting Road Paschim Bisondai Mouza To Sattar Chairman House Road Ch 0.00m-2000.00m including Construction of 4.00 Nos 7.00x0.900x0.900 Cross drain At Ch.113m, 417m, 1280m, &2560m Under Hatibandha Upazila, District Lalmonirhat. | 152335033 | 2 | 3.6 |  | 150.0335 | M/S Alahi Box, Kaligonj, Lalmonirhat | 130.5193 | 19-06-19 | 2019-06-26 | 2020-05-25 | 100 | 128.9242 | 98.7779 | 2022-10-12 | Final bill paid
162 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/VR/18-19/W-45 | Improvement of Bituminous carpeting Road on Applax Badth to Dimla Border Road at Ch 0.00m-1800.0m including Construction of 3.00 Nos 0.900 X 0.900 Cross drain at Ch. 400.00m, 700.00m & 1000.00m on Applax Badth to Dimla Border Road. Under Hatibanhda Upazila, District Lalmonirhat. | 152335061 | 1.8 | 2.7 |  | 133.0841 | Ali Mostafiz ZV, Patgram, Lalmonirhat. | 115.7503 | 2019-07-24 | 2019-07-31 | 2020-06-16 | 100 | 115.676 | 99.9358 | 2022-10-12 | Final bill paid
163 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/18-19/W-46 | Improvement of Bituminous carpeting Road on Sarkarerhat Mosque to Borovita at Ch 0.00m-2500.0m. Under Patgram Upazila, District Lalmonirhat. | 152704023 | 2.5 |  |  | 188.4697 | Fahim Traders, Kurigram Sadar, Kurigram | 163.886 | 2019-07-24 | 2019-07-31 | 2020-06-16 | 100 | 163.7835 | 99.9374 | 2022-10-12 | Final bill paid
164 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/VR/18-19/W-47 | Improvement of Bituminous carpeting Road Dhobolsuti Mosque to Kamararhat Road at Ch 0.500m-3050.0m. Under Patgram Upazila, District Lalmonirhat. | 152704034 | 2.55 |  |  | 188.9541 | Fahim Traders, Kurigram Sadar, Kurigram | 164.0829 | 2019-07-24 | 2019-07-31 | 2020-06-16 | 100 | 164.3832 | 100.183 | 2022-10-12 | Final bill paid
165 | Lalmonirhat | 54 | Patgram | 389 | 826 | PRO/LAL/PAT/FS/21-22/W-300 | Construction of Three Storied School cum Flood Shelter at Jongra 3 No Battala Government Primary School |  |  |  |  | 262.3739 | M/S Ranga Construction, Dhap, Rangpur | 222.203 | 2022-01-02 | 2022-02-08 | 2023-02-07 | 15 | 0 | 0 | 2022-10-12
166 | Lalmonirhat | 54 | Hatibandha | 392 | 826 | PRO/LAL/HATI/FS/21-22/W-308 | Construction of Three Storied School cum Flood Shelter at Al-Haj Gohor Uddin Junior School |  |  |  |  | 256.418 | M/S M A Engineering, South Banasree, East Garden, khilgaon, Dhaka | 207.4574 | 2022-02-28 | 2022-03-07 | 2023-06-03 | 15 | 0 | 0 | 2022-10-12
167 | Lalmonirhat | 54 | Patgram Hatibandha | 389 | 826 | PRO/LAL/RMP/21-22/MW-332 | 1. Maintenance of Sharkarer hat Mousque to Borovita road at ch. 0.000-2.500 km. ID:152704023 2. Maintenance of Lolitarhat to Liakot Prodhan house via Kolshirmuk BOP & Greirpul road at ch. 2.580-4.950 km. ID: 152705121 3. Maintenance of Dhabolsuti Mosque to Kamarer hat road at ch. 0.000-3.100 km. ID: 152704034 4. Maintenance of Patgram ZR at Kabarstanhat-Sarker hat Jongra UP road at ch. 0.000-3.600 km. ID: 152703010 5. Maintenance of Kamererhat-Sreerampur UP via Dr. hamidul islam house road at ch. 0.900-2.000 km. ID: 152703007 6. Maintenance of R&H Nowabab Uddin House - Laxmi Kanto Chokider House road at ch. 0.000-1.000 km. ID: 152334088 7. Maintenance of East side Singimari Up Kalam Chatal to Goddimari Elahir Chatal road at ch. 0.000-2.000 km. ID: 152334068 | 152704023 152705121 152704034 152703010 152703007 152334088 152334068 | 15.67 |  |  | 62.6593 |  | 62.6593 | 2022-07-25 |  | 2022-07-31 | 0 | 2.1409 | 3.4168 | 2022-10-12
168 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/RMP/19-20/MW-99 | Rural road maintenance by LCS (Material & Wages) work on Chikajani UP Office to Chirmashuri Hat Sarak at Ch. 0.00-7500.00m Dewangonj Upazila, Jamalpur District (15 nos LCS worker) | 339153005 | 7.5 |  |  | 34.6698 | Chairperson- Anowara Khatun, Secretary- Most. Azma Khatun , LCS Group-02 | 34.6698 | 2020-09-01 |  | 2022-08-31 | 85 | 26.2125 | 75.606 | 2022-10-12
169 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/RMP/19-20/MW-100 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD-Tilokpur Mollapara Sarak at Ch. 0.00-2190.00m Dewangonj Upazila, Jamalpur district (4 nos LCS worker) | 339153016 | 2.19 |  |  | 8.4457 | Chairperson- Salma, Secretary- Safely Begum, LCS Group-03 | 8.4457 | 2020-09-01 |  | 2022-08-31 | 85 | 6.99 | 82.7645 | 2022-10-12
170 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/RCC/20-21/W-255 | Improvement of Ghoserpara UP (Beltoi Bazar)-Char shaguna Bazar Road. Ch: 2500-3480m including 1 nos 1X4.00X4.00m culvert and 1 nos 1X6.00X6.25m cross drain | 339613007 | 0.98 | 10 |  | 191.1288 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 137.6272 | 2021-08-24 | 2021-08-30 | 2022-07-03 | 100 | 92.3658 | 67.1131 | 2022-10-12
171 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/UNR/20-21/W-161 | Improvement of Bituminous carpeting on Merurchar UP Office- Jabbergonj GC via Chinarchar Gudharaghat Road at Ch.2900-4050m. Including 2Nos 2x4.0mx4.5m Cross-Drain Under bakshiganj Upazila, District Jamalpur. | 339073012 | 1.15 | 3 |  | 182.2144 | MMC AND M/S Omir Osman Traders (JV) Medical Road, Jamalpur | 148.154 | 2021-03-11 | 2021-03-17 | 2022-01-26 | 100 | 145.7896 | 98.4041 | 2022-10-12 | Final bill paid
172 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/VR/18-19/W-29 | Improvement of Bituminous carpeting Road on Airmari-Kamalerbarti Road at Ch.00.0-2850.0m including Contruction Of 1 Nos.(3.50x2.50) Cross Drainges Structure at Ch.1290.0m and Contruction Of 2 Nos.U-Drain at Ch.140m,1915m Under Bakshiganj Upazila, District Jamalpur. | 339075094 | 2.85 | 5.3 |  | 275.0043 | M/S. Lokman Hossain, 987, Choybaria, Gokornoghat, Brahmanbaria | 268.34 | 2019-05-27 | 2019-06-02 | 2020-06-01 | 100 | 273.1993 | 98.5016 | 2022-10-12 | Final bill paid
173 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/VR/18-19/W-30 | Improvement of Bituminous carpeting Road on Gazirpara-Derur Bill Road at Ch.00.0-2000.0m Under Bakshiganj Upazila, District Jamalpur. including Contruction Of 1 Nos. U-Drain on Gazirpara-Derur Bill Road at Ch.1640.0m Under Bakshiganj Upazila, District Jamalpur. | 339075012 | 2 | 0.6 |  | 176.2165 | M/S. Bilkis Enterprise Melandah, Jamalpur. | 158.0007 | 2019-06-27 | 2019-07-03 | 2020-07-02 | 100 | 177.7429 | 98.2346 | 2022-10-12 | Final bill paid
174 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ ISL/VR/18-19/W-31 | Improvement of Bituminous carpeting Road on Bulakipara-Goalaerchar Road at Ch.00.0-2800.0m Under Islampur Upazila, District Jamalpur. including Contruction Of 5 Nos.0.600x0.625 U-Drain on Bulakipara-Goalaerchar Road at 552m, 570m, 790m, 865m & 1350m Under Islampur Upazila, District Jamalpur. | 339294014 | 2.8 | 3 |  | 223.6757 | M/S. Bilkis Enterprise Melandah, Jamalpur. | 206.2548 | 2019-06-27 | 2019-07-03 | 2020-07-02 | 100 | 220.5619 | 98.3823 | 2022-10-12 | Final bill paid
175 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/VR/18-19/W-32 | Improvement of Bituminous carpeting Road on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.00.0-1560m including Contuction Of 1 Nos.( 2x3.50x3.00m ) Cross Drainges Structure at Ch.887.0m and Contuction Of 1 Nos. (2x4.5x4.00m) Cross Drainges Structure at Ch.1219.0m and Contruction Of 6 Nos.0.750x0.750 RCC U-Drain on Kangal Kursha RHD-Tarakandi Bazar UZR Road at Ch.279m,705m,1082m,1139m,1281m,1377m Under Melandah Upazila, District Jamalpur. | 339615037 | 1.56 | 22.6 |  | 222.2586 | M/S. Masum Constrution Chapatali, Sherpur Town, Sherpur. | 182.3514 | 2019-06-30 | 2019-07-06 | 2020-05-27 | 100 | 194.7167 | 99.6145 | 2022-10-12 | Final bill paid
176 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/VR/18-19/W-37 | Improvement of Bituminous carpeting Road on Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. including Construction Of 1 Nos.0.600mx0.625m U-Drain on Ch.1236.0m Tilokpur Mollapara Bazar-Utmarchar UNR Road at Ch.930-2880m Under Dewangonj Upazila, District Jamalpur. | 339154040 | 1.95 | 0.6 |  | 174.7195 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 146.7122 | 2019-06-12 | 2019-06-18 | 2020-05-13 | 100 | 144.2917 | 99.9779 | 2022-10-12 | Final bill paid
177 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/VR/18-19/W- 38 | Improvement of Bituminous carpeting Road on Bhatkhawa RHD-Amkhowa Bazar Road at Ch.0.00-3250.0m including Construction Of 1 Nos. 3.00x3.00 Cross Drainges Structure Bhatkhawa RHD-Amkhowa Bazar Road at Ch.512.0m Under Dewangonj Upazila, District Jamalpur. | 339154029 | 3.25 | 3 |  | 304.5161 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 256.9411 | 2019-06-12 | 2019-06-18 | 2020-05-13 | 100 | 262.1545 | 99.9622 | 2022-10-12 | Final bill paid
178 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/VR/21-22/W-330 | Improvement of Bituminous carpeting Road on Bhatkhawa RHD-Amkhowa Bazar Road at Ch.2700.00-3230.0m Under Dewangonj Upazila, District Jamalpur. | 339154029 | 0.53 |  |  | 84.5733 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 88.5889 | 2022-05-25 | 2022-06-01 | 2023-05-30 | 0 | 0 | 0 | 2022-10-12
179 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/VR/19-20/W-86 | Improvement of BC Road from Khorma naya Bazar via Vatipara Road from ch. 1300-2120.0m including 2Nos U-Drain (600X600mm) under Upazila Dewangonj, District- Jamalpur. | 339154027 | 0.82 | 2 |  | 78.4214 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 70.5793 | 2020-03-04 | 2020-03-10 | 2020-09-09 | 100 | 70.5562 | 99.9673 | 2022-10-12 | Final bill paid
180 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/RMP/19-20/MW-101 | Rural road maintenance by LCS (Material & Wages) work on Kharma Naya Bazar RHD- Molomgonj Bazar Vhatipara Sarak at Ch. 0.00-1500.00m Dewangonj Upazila, Jamalpur District (3 nos LCS worker) | 339154027 | 1.5 |  |  | 6.3047 | Chairperson- Rima, Secretary- Most. Rowsuna, LCS Group-04 | 6.3047 | 2020-09-01 |  | 2022-08-31 | 85 | 5.2425 | 83.1517 | 2022-10-12
181 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/RMP/19-20/MW-102 | Rural road maintenance by LCS (Material & Wages) work on Pathorerchar RHD - Sanandabari GC Road at Ch. 0.00-1000.00m Dewangonj Upazila, Jamalpur District (2 nos LCS worker) | 339152003 | 1 |  |  | 4.2038 | Chairperson- Most. Nazma Begum, Secretary- Most. Monowara Begum LCS Group-01 | 4.2038 | 2020-09-01 |  | 2022-08-31 | 85 | 3.495 | 83.1385 | 2022-10-12
182 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/VR/19-20/W-88 | Improvement of BC Road from Chakpara FRB - Sharkerpara FRB via Amkhowa Bazar road from ch. 700.00-3340.00m including Construction of 8 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-3-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert and 1 Nos-2-vent-4.50m X 5.00m RCC Box Culvert under Upazila Dewanganj, District- Jamalpur. | 339154032 | 2.64 | 43.22 |  | 434.4861 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 382.0219 | 2020-04-29 | 2020-05-05 | 2021-05-04 | 100 | 427.6704 | 99.9853 | 2022-10-12 | Final bill paid
183 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/VR/20-21/W-178 | Improvement of Bituminous carpeting Tegaria Bazar - Pakrul - Kolikandi Road at Ch.2300-5390m. Including Construction of 3 Nos 1x3.0x3.0m RCC. Box Culvert at Ch.2565m, 4015m,4330m and 1Nos 1x3.5x3.5m RCC. Box Culvert at Ch.5370m and 1Nos 1x0.60m x 0.60m RCC. U-Drain at Ch.2955m. | 339584061 | 3.09 | 16.025 |  | 337.6609 | M/S S R S Construction, Tamal Tola, Jamalpur | 270.1187 | 2021-05-05 | 2021-05-11 | 2022-04-03 | 80 | 189.452 | 70.1366 | 2022-10-12
184 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/VR/20-21/W-147 | Improvement of Nobbachar Bazar- Tegaria H/O Khalek via Hidagari road at Ch.0.00-3000m.Under Madarganj Upazila, District Jamalpur including Construction of 2 Nos 2x4.5x4.5m Cross-Drain at Ch.275, 835m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2350m and 3 Nos U-Drain at Ch.01280, 1775, 2050m. | 339585035 | 3 | 27.76 |  | 391.0075 | M/S Labony Enterprise, Madaganj, Jamalpur | 410.2112 | 2021-02-08 | 2021-02-14 | 2022-02-13 | 100 | 410.0091 | 99.9507 | 2022-10-12 | Final bill paid
185 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/VR/19-20/W-85 | Improvement of BC Road from Gabergram Bazar Embankment- Bafatuddin Talukder High School road from ch. 3150-6240.00m including Construction of 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 2Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 2 Nos U-Drain(600X 600mm)under Upazila Madarganj, District- Jamalpur | 339585030 | 3.09 | 21.37 |  | 487.8043 | M/S. Bilkis Enterprise & Md. Mizanur Rahman, Maderganj, Jamalpur. | 402.5001 | 2020-05-13 | 2020-05-19 | 2021-05-18 | 100 | 459.411 | 99.7361 | 2022-10-12 | Final Bill Paid
186 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/VR/20-21/W-177 | Improvement of Bituminous carpeting on Jonail-Koira UZR (Bow Bazar) - Khilkati via Purbo Shokhnagari at Ch.00-2125m including Construction of 1Nos 2x3.7mx3.7m RCC. Box Culvert at Ch.550m and 6Nos 0.625X 0.600m RCC. U-Drain at Ch.25m, 100m,160m, 540m, 590m, 1050m. | 339584060 | 2.125 | 15.11 |  | 285.4789 | M/S Durga Enterprise, Dewangonj, Jamalpur | 228.4131 | 2021-05-17 | 2021-05-23 | 2022-04-03 | 35 | 71.3131 | 31.2211 | 2022-10-12
187 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/VR/20-21/W-181 | Improvement of Bituminous carpeting on Battajure Nuton Bazar-Battajure Paschimpara via Shamolsaya road at Ch.00-1510m including Construction of 1 Nos 2x3.0x3.0m RCC. Box Culvert at Ch.380m and 2 Nos 2x4.0x3.50m RCC. Box Culvert at Ch.1294, 1428m | 339075096 | 1.51 | 15.7 |  | 200.402 | M/S Durga Enterprise, Dewangonj, Jamalpur | 160.2214 | 2021-05-02 | 2021-05-08 | 2022-04-03 | 100 | 160.1899 | 99.9803 | 2022-10-12 | Final bill paid
188 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/VR/20-21/W-160 | Improvement of Bituminous carpeting on Gazirpare- Kamalerbarti Road at Ch.00-1755m.including Construction of 1Nos 2x4.0m x3.5m Cross-Drain and 2Nos 1x0.60m x 0.60m U-Drain and 3x4.0mx4.50m RCC Box Culvert Under bakshiganj Upazila, District Jamalpur. | 339074011 | 1.755 | 24.409 |  | 230.9559 | Chowdhury Enterprise | 183.6918 | 2021-03-11 | 2021-03-17 | 2022-01-23 | 100 | 183.6886 | 99.9983 | 2022-10-12 | Final bill paid
189 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/RCC/20-21/W-180 | Improvement of RCC road on Mahmudpur bazar-Imampur H/O Shahjahan member Road at Ch.00-430m | 339614111 | 0.43 |  |  | 50.0242 | MDE-MAS (JV) Kacharipara, Jamalpur | 39.7692 | 2021-04-07 | 2021-04-13 | 2022-04-12 | 100 | 39.3261 | 98.8859 | 2022-10-12 | Final Bill paid
190 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/VR/20-21/W-179 | Improvement of Bituminous carpeting on Imampur UZR- Mahmudpur Bazer via Dharmpura UZR Road. at Ch.00-940m including Construction of 1 Nos 3x3.7x5.0m RCC. Box Culvert at Ch.120m and 1 Nos 3x3.0x3.0m RCC. Box Culvert at Ch.555m and 1Nos 0.75X 0.75m RCC. U-Drain at Ch.500m | 339615108 | 0.94 | 17.31 |  | 154.5107 | M/S Bilkis Enterprise Melandah, Jamalpur | 121.928 | 2021-04-11 | 2021-04-17 | 2022-03-12 | 100 | 106.4954 | 87.3429 | 2022-10-12
191 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/VR/20-21/W-159 | Improvement of Bituminous carpeting on Dakhin Khashimara-Uttar Khashimara GPS Road at Ch.00-1300m. Including Construction of 1Nos 1x3.0m x2.5m Cross-Drain and 1Nos 0.75X 0.75m U-Drain Under Melandah Upazila, District Jamalpur. | 339615107 | 1.3 | 3.75 |  | 136.0465 | Khan Enterprise | 118.36 | 2021-02-25 | 2021-03-03 | 2022-01-25 | 100 | 117.8546 | 99.5729 | 2022-10-12 | Final bill paid
192 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/MEL/REHAB/UZR/21-22/W-325 | Rehabilitation of Dewangonj GC-Sanandabari GC via Taratia bazar Road at Ch: 00m-10620m under Upazila:Dewanganj, District: Jamalpur. | 339152001 | 10.62 |  |  | 1114.3004 | M/S Belal Construction & M/S Hamid Traders (JV), Dadamor, Lohapati, Kurigram | 1012.4918 | 2022-04-28 | 2022-05-05 | 2023-03-28 | 45 | 40 | 3.9506 | 2022-10-12
193 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/REHAB/VR/21-22/W-318 | Rehabilitation of Bhaluka More UZR – Chinitola GPS Road at Ch: 00m-1175m under Melandah Upazila, Dist: Jamalpur. | 339615072 | 1.175 |  |  | 67.3837 | M/S Amin Enterprise | 50.707 | 2022-03-28 | 2022-04-03 | 2023-02-21 | 80 | 18.4819 | 36.4485 | 2022-10-12
194 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/VR/20-21/W-158 | Improvement of Bituminous carpeting on Kashimara Bazar- Purarchar(Shahin Bazar) Road at Ch.00-2680m.Under Melandah Upazila, District Jamalpur | 339614030 | 2.68 |  |  | 271.7655 | M/S Farhan Enterprise, Pathalia, Jamalpur | 225.5741 | 2021-03-15 | 2021-03-21 | 2022-02-01 | 100 | 225.3208 | 99.8877 | 2022-10-12 | Final bill paid
195 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/21-22/W-282 | Deghair - Bhangbari Road Ch.0.00-2500m including construction of 2 nos 2X4.50mX4.50m RCC box culvert at ch. 200m & 1750m and Construction of 2 nos 1X4.00mX4.00m RCC Box culvert and 1 nos 3X4.50mX5.00m RCC box culvert | 339295009 | 2.5 | 29.67 |  | 256.4796 | M/S Durga Enterprise, Dewangonj, Jamalpur | 268.6694 | 2021-11-29 | 2021-12-05 | 2022-10-19 | 0 | 0 | 0 | 2022-10-12
196 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/20-21/W-182 | Improvement of Bituminous carpeting on Char Dighair madrasha- Mohaz Mollah House at Dighair village road at Ch.00-1250m. Including Construction of 1Nos 1x4.00x4.00m RCC. Box Culvert at Ch.710.00m and 3Nos 2x4.25x4.25m RCC. Box Culvert at Ch. 390m, 600m, 1200m | 339295032 | 1.25 | 33.31 |  | 257.5636 | M/S Durga Enterprise, Dewangonj, Jamalpur | 241.3848 | 2021-05-02 | 2021-05-08 | 2022-05-07 | 95 | 185.7251 | 76.9415 | 2022-10-12
197 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/21-22/W-283 | Improvement of Bituminous carpeting on Char Dighair madrasha- Mohaz Mollah House at Dighair village road at Ch.1250-2375m. Including Construction of 2Nos 2x4.00x3.50m RCC. Box Culvert at Ch.1340,2230m and 1Nos 1x3.00mx3.00m RCC. Box Culvert at Ch. 1820m. | 339295032 | 1.125 | 12.45 |  | 190.2827 | KTQDE (JV), Islampur, Jamalpur | 199.3904 | 2021-12-01 | 2021-12-07 | 2023-01-06 | 35 | 47.8868 | 24.0166 | 2022-10-12
198 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/20-21/W-183 | Char Shisua GPS-Changania RNGPS via Deghair Road at Ch.0.00-3543.00m. Including Construction of 1 Nos 1x4.00x4.00mRCC. Box Culvert at Ch.235.00m and 1Nos 2x4.25x4.25m RCC. Box Culvert at Ch.1690.00m and 2Nos 3x4.00x4.50mRCC. U-Drain at Ch. 848.00m,1825.00m | 339295033 | 3.543 | 40.91 |  | 216.488 | M/S Durga Enterprise, Dewangonj, Jamalpur | 194.7264 | 2021-05-02 | 2021-05-08 | 2022-05-07 | 82 | 148.525 | 76.2737 | 2022-10-12
199 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/19-20/W-83 | Improvement of BC Road from Napiterchar High School-Chandanpur village via Dasani Ferry Ghat road at ch. 00- 3000m. Including Construction of 2 Nos 1x0.600mx0.600m m U-Drain and 2 Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-2-vent-4.50m X 4.00m RCC Box Culvert under Islampur Upazila, District Jamalpur. | 339294035 | 3 | 21.28 |  | 394.5401 | LE &ME (JV) Islampur, Jamalpur | 338.9661 | 2020-05-20 | 2020-05-26 | 2021-05-08 | 100 | 338.3453 | 99.8168 | 2022-10-12 | Final bill paid
200 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/19-20/W-84 | Improvement of BC Road from Dattapara R&H - Napiterchar Bazar via Adorsha Gramm road at ch. 00-3000.00m including Construction of 1 Nos 1x0.600mx0.600m m U-Drain and 1 Nos-2-vent-4.50m X 4.50m RCC Box Culvert and 1Nos-1-vent-4.00m X 4.00m RCC Box Culvert and 1Nos-3-vent-4.50m X 4.50m RCC Box Culvert under Upazila Islampur, District- Jamalpur | 339294067 | 3 | 30.56 |  | 438.2792 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 369.9779 | 2020-05-20 | 2020-05-26 | 2021-04-27 | 100 | 328.4052 | 88.7635 | 2022-10-12 | Final bill paid
201 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/21-22/W-280 | Improvement of BC Road from Kazla Bazar - Kathma Bazar road Ch.0.00-1370m including 1 nos 3X4.50mX3.50m RCC box culvert at Ch.730m. | 339294085 | 1.37 | 1.37 |  | 176.7591 | KTQDE (JV), Islampur, Jamalpur | 145.6495 | 2021-12-14 | 2021-12-20 | 2022-12-19 | 80 | 106.5447 | 73.1514 | 2022-10-12
202 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/21-22/W-281 | Improvement of BC Road from Kazla Kamar bari-Horindhora road from Ch. 0.00-1450m including construction of 1 nos 1X3.00mX3.00m RCC Box culvert at Ch. 20m. | 339295017 | 1.45 | 3.6 |  | 163.2562 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 171.0907 | 2021-11-29 | 2021-12-05 | 2022-10-19 | 80 | 124.3391 | 72.6744 | 2022-10-12
203 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/20-21/W-146 | Improvement of Malmara Bazar-Napiterchar Bazar via Khairdirrkanda road at Ch.0.00-2000m.Under Islampur Upazila, District Jamalpur including Construction of 2 Nos 1X4.00m x 4.00m Cross-Drain at Ch.1800m, 1900m3 Nos U-Drain at Ch.1400, 1530, 1600m. | 339294087 | 2 | 12.32 |  | 246.4863 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 217.6513 | 2021-02-11 | 2021-02-17 | 2022-01-31 | 100 | 217.4864 | 99.9242 | 2022-10-12 | Final bill paid
204 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/20-21/W-145 | Improvement of Malmara-Bolakipara road by BC at Ch.0.00-2500m.Under Islampur Upazila, District Jamalpur including Construction of 1 Nos 3X4.50m x 4.50m Cross-Drain at Ch.143m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2370m and 1 Nos 1x4.0x4.0m Cross-Drain at Ch.2140m and 3 Nos U-Drain at Ch.1500, 1900m | 339294008 | 2.5 | 25.97 |  | 333.9364 | Yunus & Brothes | 262.1374 | 2021-01-27 | 2021-01-02 | 2022-03-23 | 85 | 206.5956 | 78.8119 | 2022-10-12
205 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/VR/21-22/W-284 | Improvement of Malmara-Bolakipara road by BC at Ch. 2500m-3150m.under Islampur Upazila, District Jamalpur | 339294008 | 0.65 |  |  | 76.2837 | Talukder & Brothers Ltd. | 59.0656 | 2021-12-23 | 2021-12-29 | 2022-12-28 | 0 | 0 | 0 | 2022-10-12
206 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/ LM/19-20/W- 126 | Construction of Milon Bazar Upazila: Madarganj, Dist:Jamalpur (02 nos LCS group) |  |  |  |  | 60.1338 | LCS 01: Mst. Renura and Mst. Shikha & LCS 02: Mst. Ratna and Mst. Chanvanu | 60.1338 | 2021-06-15 | 2021-09-25 | 2021-12-24 | 100 | 44.8728 | 74.6216 | 2022-10-12
207 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/ LM/21-22/W-310 | Earth filling (Extra work) of Milon Bazar Upazila: Madarganj, Dist:Jamalpur (1 no LCS group) |  |  |  |  | 6.2038 |  | 6.2038 | 2021-06-15 | 2021-09-25 | 2021-12-24 | 100 | 6.161 | 99.3111 | 2022-10-12 | Final bill paid
208 | Jamalpur | 27 | Sadar | 204 | 826 | PRO/JAM/MAINT/19-20/MW-02 | Maintenance and repair work of LGED Office Building, Dist: Jamalpur |  |  |  |  | 1.8601 | SHABUZ ENTERPRISE | 1.8601 | 2019-12-17 | 2019-12-19 | 2020-01-13 | 100 | 1.8601 | 100 | 2022-10-12 | Final bill paid
209 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/LM/20-21/W-262 | Construction of Sanonda Bari Hat, Upazila: Dewanganj, Dist: Jamalpur (3 nos LCS Group) |  |  |  |  | 79.9755 | LCS 01: Mst. Piara Begum and Kohinur Begum, LCS 02: Mst. Jahanara Begumnd Sajeda Begum, LCS 03 Sabina Begum, Aleia Begum | 79.9755 | 2021-11-25 |  | 2022-11-24 | 45 | 25.2543 | 31.5776 | 2022-10-12
210 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/DEW/WSM/21-22/W-274 | Construction of Sanonda Bari Hat Womens Market Section, Upazila: Dewanganj, Dist: Jamalpur |  |  |  |  | 27.5833 | LCS 01: Mst. Jahanara Begum and Mst. Parvin Akter | 27.5833 | 2021-11-25 |  | 2022-11-24 | 0 | 0 | 0 | 2022-10-12
211 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/MM/20-21/W-202 | Construction of Talukpara Hat, Upazila: Melandah, Dist: Jamalpur (2 nos LCS Group) |  |  |  |  | 53.5796 | LCS 01: Mst. Kolpona Begum and Mst. Aklima Begum LCS 02: Mst. Hasina Begum and Asma Begum | 53.5796 | 2021-05-22 |  | 2021-11-21 | 95 | 40.96 | 76.447 | 2022-10-12
212 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/MM/21-22/W-303 | Earth filling work of Talukpara Hat, Upazila: Melandah, Dist: Jamalpur (1 no LCS Group) |  |  |  |  | 1.4567 |  | 1.4567 | 2021-05-22 |  | 2021-11-21 | 95 | 0 | 0 | 2022-10-12
213 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/MM/20-21/W-253 | Construction of Jhawgora Bazar, Upazila: Melandah, Dist: Jamalpur (2 nos LCS Group) |  |  |  |  | 64.2185 | LCS 01: . Jorna Rani and Purnima Rani LCS 02: Mst. Asma Begum and Kobita | 64.2185 | 2021-06-24 |  | 2021-12-23 | 100 | 43.1066 | 67.125 | 2022-10-12
214 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/WSM/21-22/W-275 | Development of Jhawgora Bazar Womens Market Section, Upazila: Melandah, Dist: Jamalpur |  |  |  |  | 29.8835 |  | 29.8835 | 2022-02-16 |  | 2023-02-15 | 60 | 15 | 50.1949 | 2022-10-12
215 | Jamalpur | 27 | Dewanganj | 202 | 826 | PRO/JAM/MEL/MM/21-22/W-299 | Construction of Gobindaganj Hat (02 nos LCS Group) |  |  |  |  | 41.145 | LCS 01: Mst. Shapla Begum and Mst.Momota LCS 02: Mst. Tanzila and Rashida Khatun | 41.145 | 2022-02-16 |  | 2023-02-15 | 60 | 16.5 | 40.1021 | 2022-10-12
216 | Jamalpur | 27 | Melandah | 206 | 826 | PRO/JAM/MEL/MM/20-21/W-210 | Construction of Nalsia bazar, Upazila: Melandah, Dist: Jamalpur (2 nos LCS Group) |  |  |  |  | 52.3626 | LCS 01: Mst. Renura Begum and Mst. Ambul Begum LCS 02: Mst. Suratul Jannat and Bina Rani | 52.3626 | 2021-04-26 |  | 2022-04-25 | 88 | 35.14 | 67.109 | 2022-10-12
217 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/MM/20-21/W-150 | Construction of Paschim kamaler barti Bazar |  |  |  |  | 65.7955 | LCS 01: Mst. Sahina Begum and Mst. Jabaful LCS 02: Mst. Sahana Begum and Sreemoti Parboti | 65.7955 | 2020-12-31 |  | 2021-06-30 | 0 | 0 | 0 | 2022-10-12
218 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/MM/20-21/W-259 | Construction of Nabbo Char Bazar (02 nos LCS group) |  |  |  |  | 56.1116 | LCS 01: Mst. Sahinur Begum and Mst. Jibon Begum LCS 02: Mst. Alema Begum and Morjina Khatun | 56.1116 | 2021-07-28 |  | 2021-12-27 | 0 | 0 | 0 | 2022-10-12
219 | Jamalpur | 27 | Islampur | 203 | 826 | PRO/JAM/ISL/SM/20-21/W-172 | Construction of Malmara Bazar, Upazila:Islampur, Dist: Jamalpur (2 nos LCS group) |  |  |  |  | 43.5563 | LCS 01: Mst. Mafuja Begum and Mst.Hashema LCS 02: Mst. Most. Najma and Most.Mafia Khatun | 43.5563 | 2021-10-06 |  | 2022-09-12 | 100 | 25.586 | 58.7423 | 2022-10-12
220 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/FS/20-21/W-261 | Construction of Three Storied School cum Flood Shelter at Chiner char Uttarpara Govt. Pri. School under Union: Merurchar, Upazila: Bakshiganj, Dist: Jamalpur |  |  |  |  | 255.2354 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 208.6466 | 2021-09-29 | 2021-10-05 | 2022-08-03 | 80 | 160.8747 | 77.1039 | 2022-10-12
221 | Jamalpur | 27 | Madargonj | 205 | 826 | PRO/JAM/MAD/FS/21-22/W-309 | Construction of Three Storied School cum Flood Shelter at Shuknogory Govt. Pri. School under Balijuri Union, Madarganj Upazila, Dist: Jamalpur |  |  |  |  | 282.1965 | M/S Laboni Enterprise, Madarganj, Jamalpur | 239.4576 | 2022-02-14 | 2022-02-20 | 2022-12-26 | 15 | 0 | 0 | 2022-10-12
222 | Jamalpur | 27 | Bakshigonj | 219 | 826 | PRO/JAM/BAK/FS/20-21/W-260 | Construction of Three Storied School cum Flood Shelter at Abdul Gani Govt. Pri. School under Union: Sadhurpara, Upazila: Bakshiganj, Dist: Jamalpur |  |  |  |  | 259.4639 | M/S. Durga Enterprise, Dewanganj, Jamalpur. | 212.0993 | 2021-09-29 | 2021-10-05 | 2022-08-03 | 56 | 107.003 | 50.4495 | 2022-10-12