## Both road (2)
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Boalkhali | 415123002 | Bengura D.C. Road | 2 | 5 | BC | 96.5
2 | Boalkhali | 415123006 | Kalurghat-Gomodondi-Bangura-Sakirapool road | 2 | 5 | BC | 96.5
3 | Boalkhali | 415123007 | Ahalla Village (Karal-Danga UP Montavi Bazar) Road | 2 | 7 | BC | 101.5
4 | Boalkhali | 415123014 | Monir Ahmed Road | 2 | 7 | BC | 101.5
5 | Boalkhali | 415123005 | Kalachand Takor Road | 2 | 7 | BC | 101.5
6 | Boalkhali | 415123012 | Shahid Dherandra-Amirul Haque Road | 2 | 5 | BC | 96.5
7 | Boalkhali | 415123019 | Okil Baidda Road | 2 | 5 | BC | 96.5
8 | Boalkhali | 415123018 | Amuchia Bura Masjid Road | 2 | 5 | BC | 96.5
9 | Boalkhali | 415123011 | Kanongo para Post office road | 2 | 7 | HBB | 77.5
10 | Boalkhali | 415123020 | Nazu shah road | 1.61 | 9 | BC | 90.12
11 | Boalkhali | 415123021 | Kazi road | 1 | 8 | HBB | 50
12 | Boalkhali | 415123016 | Ismait ali road | 1.5 | 8 | BC | 83
12 |  |  | Sub-Total | 22.11 | 78 |  | 1087.62 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Boalkhali | 415125035 | Shakpura UP Sabuj Sanggho Road | 1 |  | HBB | 25
2 | Boalkhali | 415125116 | Asgar Ali mazar road | 1 |  | HBB | 25
3 | Boalkhali | 415124083 | Dr. M A Mannan road (Anjumar tek to Kazibari Govt. Primary School) | 1.65 | 1.75 | BC | 57.125
3 |  |  | Sub - Total | 3.65 | 1.75 |  | 107.125 | 0 | 0 | 0 | 0 | 0 | 0
15 |  |  | Total | 25.76 | 79.75 |  | 1194.745 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Raozan | 415743001 | Anderson Road and Link Purba Aburkhil Jara Kallan Primary School & Mira para Repon Dr. House road | 3 | 10 | BC | 151
2 | Raozan | 415743002 | Akbar Shah Road | 2 | 10 | BC | 109
3 | Raozan | 415743003 | Chickdair Maddya palan para road & Kundeshari road. | 3 | 10 | HBB | 115
4 | Raozan | 415743004 | Hajrat Moulana Md. Shah Road | 1.23 | 4 | BC | 61.66
5 | Raozan | 415743005 | Ray Khishory road | 2 | 7.96 | BC | 103.9
6 | Raozan | 415743006 | Holadia Village road | 2 | 10 | BC | 109
7 | Raozan | 415743008 | Kehukhine Nowapara road | 2 | 8.2 | BC | 104.5
8 | Raozan | 415743010 | Ander Manik D.C (Chitta Rangan Chow. road & Natun bazar to Kadalpur road) road | 3 | 30 | BC | 201
9 | Raozan | 415743011 | Rawli DB road (Nutan Rughy nandan ro purbo dika Agrosar mondir) | 2 | 6 | BC | 99
10 | Raozan | 415743012 | Hafez bazuir Rahman road to Mohamani high School road | 2 | 8 | BC | 104
11 | Raozan | 415743013 | Parir Dighir par Poschim Barua para Sason to Sudmandir behor road | 2 | 4 | BC | 94
12 | Raozan | 415743014 | Urkirchar road (Muduna ghat to Kalifar ghona) | 4 | 65 | BC | 330.5
13 | Raozan | 415743015 | Abdul Manan road Eathenager | 1.5 | 3 | BC | 70.5
13 |  |  | Sub-Total | 29.73 | 176.16 |  | 1653.06 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Raozan | 415744085 | Moulana Dhiraj uddin road (Nona Hazi bari to Shuad alolia bari) | 1.5 | 4 | BC | 56.75
2 | Raozan | 415744086 | Rauli road (Hafez Bazlur Rahman road to Farirkul bazar) | 1 | 6 | BC | 44.5
3 | Raozan | 415744087 | Abdul Motlib Swdager road packhin | 1 | 5 | BC | 42.5
4 | Raozan | 415744088 | Kamali road (Sham-Maidar para Mosque to Harapara.) | 1 | 4 | BC | 40.5
5 | Raozan | 415744089 | Chanmolla Mosque road (Isamia School gate to Chanmolla Mosque road) | 1 | 5 | BC | 42.5
6 | Raozan | 415744090 | Poschim Barmmonhat to panchkhin via Ambolhat to ramgoti hat. | 1 | 5 | BC | 42.5
7 | Raozan | 415744091 | Waijmeah Chowdhury Road (Shaid Moti Lal Chowdhury Road) | 1 | 2 | BC | 36.5
8 | Raozan | 415744092 | Jamuine Kagatia road (Banijuri Jamuine Road) | 1 | 5 | BC | 42.5
9 | Raozan | 415744093 | Shama Chran road (West Guzara Jubail Ali master Shama Chran road) | 1 | 5 | BC | 42.5
10 | Raozan | 415744094 | Chickdair-Noajishpur road | 1.2 | 2 | BC | 43
11 | Raozan | 415744095 | Noajishpur Dabua road | 1 | 2 | BC | 36.5
12 | Raozan | 415744096 | Kantia Chand mech road | 1 | 4 | BC | 40.5
13 | Raozan | 415744097 | (Link) Abdul karim road (Uttar Sharta Damdama Madrasha, Durgachain and shide manan road | 1 | 5 | BC | 42.5
14 | Raozan | 415744098 | Maliek Munshi road | 1 | 4.8 | BC | 42.1
15 | Raozan | 415744099 | Moulana Rurul Amin road (Tafajul Hajur road) | 1 | 4 | BC | 40.5
16 | Raozan | 415744100 | Sam Pandit road | 1 | 3 | BC | 38.5
17 | Raozan | 415744101 | Kabir Ahamed Taluckder road | 1.46 | 3 | BC | 53.45
18 | Raozan | 415744102 | Student para road | 1 | 3 | BC | 38.5
19 | Raozan | 415744103 | Lal Mia tendal road | 1 | 3 | BC | 38.5
20 | Raozan | 415744104 | Purba Guzara Bebuban Behir road | 1 | 3 | BC | 38.5
21 | Raozan | 415744105 | Bama chrum road | 1 | 3 | BC | 38.5
22 | Raozan | 415744106 | Molla Miskin Road | 1 |  | BC | 32.5
23 | Raozan | 415744107 | Student Road | 1 |  | BC | 32.5
24 | Raozan | 415744108 | Amir para Road | 1 |  | BC | 32.5
25 | Raozan | 415744109 | Vomra para Road | 1 |  | BC | 32.5
26 | Raozan | 415744110 | Cittoranjon Chowdhory Road | 1 |  | BC | 32.5
27 | Raozan | 415744111 | Natun Chandro Chowdhory Road | 1 |  | BC | 32.5
28 | Raozan | 415744112 | Sancoy Kumar Chowdhory Road | 1 |  | HBB | 25
29 | Raozan | 415744113 | Shahid monoj Kumar Chowdhory Road. | 1 |  | HBB | 25
30 | Raozan | 415744114 | Shekh para School - Shekh para Mosjid road | 1 |  | HBB | 25
30 |  |  | Sub - Total | 31.16 | 80.8 |  | 1151.8 | 0 | 0 | 0 | 0 | 0 | 0
43 |  |  | Total | 60.89 | 256.96 |  | 2804.86 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Fatikchari | 415333011 | Kalumonshir Hat to Dawiat Monshir Hat ( Nanupur - Khiram Road) | 1.5 | 7.5 | BC | 81.75
2 | Fatikchari | 415333012 | Suabil UP H/Q to Shovanchari Bangiabazar Road | 1 | 7.5 | BC | 60.75
3 | Fatikchari | 415333019 | Nanupur UP H/Q to Samitirhat UP H/Q Road | 1 | 12 | HBB | 60
4 | Fatikchari | 415333006 | Paindong U.P HQ (Brindabonhat) to Kanchan Nagar U.P H.Q Road via Kanchurhat | 3.1 | 100 | BC | 380.2
5 | Fatikchari | 415333004 | Bhujpur U.P H.Q to Mirzerhat Road via Sandip para | 1.5 | 65 | BC | 225.5
6 | Fatikchari | 415333003 | Narayanhat to Mirzarhat Road | 1.5 | 20 | BC | 113
7 | Fatikchari | 415333010 | Bibirhat G.C to Harualchari Aman Bazar | 1 |  | BC | 42
8 | Fatikchari | 415333001 | Bagan bazar U.P HQ. to Natun bazar Road via Lalmai | 1.5 |  | BC | 63
9 | Fatikchari | 415333002 | Dantmara U.P HQ to Balutila Bazar via Ziltoli Bazar Road | 1.5 | 20 | BC | 113
10 | Fatikchari | 415333005 | Haruachari U.P H.Q to lalarhat Road via Harualchari Hospital & Santir hat | 1.5 | 15 | BC | 100.5
11 | Fatikchari | 415333009 | Bibirhat G.C to Dowlatpur Fakirhat Road via Aman Bazar (Nur Ali Chy.rd) | 1 |  | HBB | 30
12 | Fatikchari | 415333014 | Lelang U.P HQ to Cahraliahat Road via Shainnashirhat & Lelang Nayhat(Gopal Gatta rd ) | 1.5 | 40 | BC | 163
13 | Fatikchari | 415333015 | Roshangiri U.P HQ to nanupur U.P HQ Road | 1.5 | 5 | BC | 75.5
14 | Fatikchari | 415333017 | Dharmapur U.P HQ to Comitirhat Road | 1 |  | BC | 42
15 | Fatikchari | 415333018 | Mohammed Takirhat G.C to Abdullahpur U.P HQ Road | 1 |  | BC | 42
16 | Fatikchari | 415333020 | Mohammed Tokirhat G.C Samitirhat Up Office Rd | 1.35 |  | BC | 56.7
17 | Fatikchari | 415333016 | Shantirhat Agadi Bazar road under Bakhtapur-Dharmapur union. | 1.5 | 3 | BC | 70.5
17 |  |  | Sub-Total | 23.95 | 295 |  | 1719.4 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Fatikchari | 415335002 | North Shilkupa Road ( Fatikchari - Uttar/Eidilpur) | 1.5 |  | BC | 48.75
2 | Fatikchari | 415334051 | Chowmohoni Bazar - Anowar Aziz Atimkhana Road | 1 |  | BC | 32.5
3 | Fatikchari | 415334031 | Ramgar Section-1 (5 vent Regulator) Badyar hat Via East Suabil Brammon Hat Road | 1 |  | BC | 32.5
4 | Fatikchari | 415334009 | Fenua Tea Girden Road | 1 |  | BC | 32.5
5 | Fatikchari | 415335133 | Construction of RCC Box Culver on Raipur Dr. Jasim Uddin Road |  | 5 | Culvert | 10
6 | Fatikchari | 415334014 | Sadek Banu road under Bakhtapur | 1 |  | BC | 32.5
7 | Fatikchari | 415334015 | Shantirhat Motor road (Master Yousuf Ahmed road) under Bakhtapur-Dharmapur & Nanupur union Parishad | 1 |  | BC | 32.5
8 | Fatikchari | 415335078 | Dharmapur Kobbadia road | 1 |  | BC | 32.5
9 | Fatikchari | 415334025 | Gamaritola R.d | 1 | 5 | BC | 42.5
10 | Fatikchari | 415334042 | ABC Link Road (Mali Para Road ) | 1 | 5 | BC | 42.5
11 | Fatikchari | 415334110 | Hazrat Shah Ahmedullah Rd (Link Hazrat Shahan Shah Syed Ziaul Haque ( K) Maizbandari Internal Road) | 1 |  | BC | 32.5
12 | Fatikchari | 415334112 | Bura Bebe - Azimnagar via Gohira Heako Road. | 1 |  | BC | 32.5
13 | Fatikchari | 415335134 | Anowar Ali Chowdhury Road | 1 | 5 | HBB | 35
14 | Fatikchari | 415335135 | M.H. Chowdhury Road to Rafiqul Anowar Road (End Point) Via West Khiram to Gamari tola) | 1 | 20 | HBB | 65
15 | Fatikchari | 415335136 | Talukdar Bari Paca road to Cunnumiar Bari Road | 0.5 |  | HBB | 12.5
16 | Fatikchari | 415335137 | Barura para gram - Hait sakua road | 1 |  | HBB | 25
16 |  |  | Sub - Total | 15 | 40 |  | 541.25 | 0 | 0 | 0 | 0 | 0 | 0
33 |  |  | Total | 38.95 | 335 |  | 2260.65 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Hathazari | 415373001 | Hajee Yousuf Road | 3.5 | 40 | BC | 247
2 | Hathazari | 415373005 | Fatehpur Madrasha Road | 4 | 35 | BC | 255.5
3 | Hathazari | 415373006 | Noor Ahmed Chowdhury Road | 4.5 | 10 | BC | 214
4 | Hathazari | 415373007 | Chadgazi Road | 4 |  | BC | 168
5 | Hathazari | 415373010 | Murad road Rest portion & UP Road | 1 |  | BC | 42
6 | Hathazari | 415373004 | Gorduara Sarang road | 2.43 |  | HBB | 72.9
6 |  |  |  | 19.43 | 85 |  | 999.4 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Hathazari | 415374112 | 1 no. Pahartali Ashram Road | 1.7152 |  | HBB | 42.88
2 | Hathazari | 415375289 | Gorduara Abdul nobi sowdagor, Dr. nazir ahmed, kanter ali chowdhary & Amir ali sowdagor | 1.5 |  | HBB | 37.5
3 | Hathazari | 415374113 | Jafor Ali Talukdar Road | 1 |  | HBB | 25
3 |  |  | Sub - Total | 4.2152 | 0 |  | 105.38 | 0 | 0 | 0 | 0 | 0 | 0
9 |  |  | Total | 23.6452 | 85 |  | 1104.78 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Sandwip | 415783004 | Circular Road (Amanullah UP H/Q. Sontoshpur UP H/Q.) and Nowapara Ahasania Road. | 1.9 | 5 | BC | 92.3
2 | Sandwip | 415783005 | D.B. Road | 1 | 5 | HBB | 42.5
3 | Sandwip | 415783007 | Mir Abdullah Road (Amanullah U.P. H/Q-Kalapania UP H/Q) | 1 | 5 | HBB | 42.5
4 | Sandwip | 415783009 | Circular Road (Sarikat UP-Bangla Bazar) | 1.85 | 5 | BC | 90.2
5 | Sandwip | 415783010 | Harispur UP-Salam Bazar Road | 1.5 | 5 | BC | 75.5
6 | Sandwip | 415783002 | Tanashah Road Gouchuar Part | 1.5 |  | BC | 63
7 | Sandwip | 415783013 | North Sandwip college Road Tanashah Road to Akbar hat | 1.5 |  | BC | 63
8 | Sandwip | 415783018 | Abul Khair Khan Satghoriya Road Shiber hat to west bari | 1.5 |  | BC | 63
8 |  |  | Sub-Total | 11.75 | 25 |  | 532 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Sandwip | 415785105 | Kalapainia high school road. | 1 | 6 | HBB | 37
2 | Sandwip | 415784014 | Bauria feryghat road. | 1 | 5 | HBB | 35
3 | Sandwip | 415784045 | Gasua hasphal road. | 1 | 1.5 | HBB | 28
3 |  |  | Sub - Total | 3 | 12.5 |  | 100 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  | Total | 14.75 | 37.5 |  | 632 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Satkania | 415823029 | Sonakania UP-Satkania UP Road | 1 | 1.5 | BC | 45.75
2 | Satkania | 415823031 | Alur ghat Road | 1 |  | BC | 42
3 | Satkania | 415823024 | Cons. of 60m bridge over Dulukhal river on Alur ghat Road |  | 60 | Bridge | 150
4 | Satkania | 415823005 | Paschim Dhemsha Up - Chowdhury Hat road | 1 | 3.45 | BC | 50.625
5 | Satkania | 415823001 | Amilaish UP - Kanchana UP Via Hilimili road | 1 | 1.5 | HBB | 33.75
6 | Satkania | 415823025 | Sonakania UP-Madarsha UP Via Samity Road | 1.64 |  | BC | 68.88
7 | Satkania | 415823009 | Kaliais UP - Dharmapur UP - DasliderHat Road | 1 |  | HBB | 30
7 |  |  | Sub-Total | 6.64 | 66.45 |  | 421.005 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Satkania | 415825036 | Moulovir Dokan | 1 |  | BC | 32.5
2 | Satkania | 415824142 | Construction of RCC bridge on sikderpara Maijpara road. |  | 30 | Bridge | 60
3 | Satkania | 415824034 | Morhum Allama Fazlullah Road under Madarsa Union | 1 |  | BC | 32.5
4 | Satkania | 415824093 | Development of Ihore kewchni shah road | 1 |  | BC | 32.5
5 | Satkania | 415825052 | Netapakir para - Samatigor connecting road. | 1 |  | BC | 32.5
6 | Satkania | 415824038 | Rampur Madrasa Sikder para Road | 1 |  | BC | 32.5
7 | Satkania | 415824052 | Dhemsha H. School Road | 1 |  | BC | 32.5
8 | Satkania | 415824139 | Rampur Baitush Sharaf Road (Madrasa Dalu Embt. Road) | 1 |  | BC | 32.5
9 | Satkania | 415824092 | Shenar Hat Road | 1 |  | BC | 32.5
10 | Satkania | 415825018 | Morfola H. School Road | 0.75 |  | HBB | 18.75
11 | Satkania | 415825033 | Karaia Nagar Mahila Madrasa Road | 0.75 |  | HBB | 18.75
12 | Satkania | 415824009 | Kashai para Manu Fakir hat | 0.75 |  | HBB | 18.75
13 | Satkania | 415824049 | Chib Bari School Road | 0.75 |  | HBB | 18.75
13 |  |  | Sub - Total | 11 | 30 |  | 395 | 0 | 0 | 0 | 0 | 0 | 0
20 |  |  | Total | 17.64 | 96.45 |  | 816.005 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Sitakunda | 415863031 | Tarial Road | 2 | 10 | BC | 109
2 | Sitakunda | 415863008 | Sonaichari Raod | 1.3 | 15 | BC | 92.1
3 | Sitakunda | 415863040 | Ali Ahmed Road | 2 | 15 | BC | 121.5
4 | Sitakunda | 415863079 | Dhalipara Hasnabad Road | 2 | 15 | BC | 121.5
5 | Sitakunda | 405863004 | Lahanakha Sea Road | 2 | 5 | BC | 96.5
6 | Sitakunda | 405863083 | Bandari Road | 0.75 | 3 | BC | 39
7 | Sitakunda | 405863028 | Ambia Dhala Road | 2 | 5 | BC | 96.5
8 | Sitakunda | 405863001 | Ferihgat Road | 1.5 | 5 | BC | 75.5
9 | Sitakunda | 405863052 | Kheaghat Road | 0.9 | 7.5 | BC | 56.55
10 | Sitakunda | 415863082 | Seraj Road | 2.3 | 20 | BC | 146.6
11 | Sitakunda | 415863078 | Doajipara road shiraj road via doajipara | 1 |  | HBB | 30
12 | Sitakunda | 415863080 | Nunachara road, Jafor nagar hat high school to mirerhat via shams shanid road syedpur | 1.5 |  | BC | 63
13 | Sitakunda | 415863084 | Tarial Mohanagar or Mir Mohiuddin Road | 1.5 |  | BC | 63
14 | Sitakunda | 415863085 | Mandaritola Sea Road | 1 |  | HBB | 30
14 |  |  | Sub-Total | 21.75 | 100.5 |  | 1140.75 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Sitakunda | 415864133 | Sitakunda Bazar (Mandir) to 2 no. Baropul Road | 2 |  | BC | 65
2 | Sitakunda | 415864134 | Uttar Masjida Muhuri Road (Durgabari part) | 1 |  | BC | 32.5
3 | Sitakunda | 415864046 | Sitakunda sadar to Sandip Ghatghar(Golabari Sea road) road | 1.5 |  | BC | 48.75
4 | Sitakunda | 415864043 | Dokkhin Batiari Bazar to Mahtab bibi road ( St. from R&H Road) | 1 |  | BC | 32.5
5 | Sitakunda | 415865117 | Boro Dargar hat bazar to East Rail station road | 1.5 |  | HBB | 37.5
6 | Sitakunda | 415864128 | Sahid Nurul Islam road connecting road | 1 |  | BC | 32.5
7 | Sitakunda | 415864007 | Nilambor Talukder Road | 1 |  | BC | 32.5
8 | Sitakunda | 405864006 | Sadullaba Munshi Road | 1.5 |  | HBB | 37.5
9 | Sitakunda | 405864002 | Tarka Bagish Road | 1 |  | BC | 32.5
10 | Sitakunda | 405865103 | Hamid Ullah Mokter Road | 1 |  | BC | 32.5
11 | Sitakunda | 405864132 | Kalu Sha Mazar Road | 1 |  | BC | 32.5
11 |  |  | Sub - Total | 13.5 | 0 |  | 416.25 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  | Total | 35.25 | 100.5 |  | 1557 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Lohagara | 415473010 | Amirabad UP-Khalauzan Road | 1 | 5 | BC | 54.5
2 | Lohagara | 415473026 | Putivilla Sarail Ramvilla Road | 1 | 5 | BC | 54.5
3 | Lohagara | 415473013 | Padua Andhar Manik Road | 1 | 5 | BC | 54.5
4 | Lohagara | 415473002 | Uzirbita Road | 1 | 5 | BC | 54.5
5 | Lohagara | 415473007 | Kalauzan Niz Taluk Road | 1 | 5 | BC | 54.5
6 | Lohagara | 415473003 | Amirabad - Sukchari Khalauzan Road | 1 | 5 | BC | 54.5
7 | Lohagara | 415473006 | Barohatia Yeasinpara Road | 1 | 5 | BC | 54.5
8 | Lohagara | 415473012 | Charamba-Telibila Kalauzan Road. | 1 | 5 | HBB | 42.5
9 | Lohagara | 415473015 | Abdul Khaleque Shah Road. | 1 | 4.8 | HBB | 42
9 |  |  | Sub-Total | 9 | 44.8 |  | 466 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Lohagara | 415475043 | Charmba Masque Road | 1 |  | HBB | 25
2 | Lohagara | 415475123 | Charmba Rajghata Primary School Abul Oafah road | 1 |  | HBB | 25
3 | Lohagara | 415475283 | Charmba Sufiabad Road | 1 |  | HBB | 25
4 | Lohagara | 415475284 | Charmna Bibirbila - Maijbila Road | 1 |  | HBB | 25
5 | Lohagara | 415475285 | Kalachand Pukur Road | 1 |  | HBB | 25
6 | Lohagara | 415475286 | Nur Ahmed Chowdhury road. | 1 |  | HBB | 25
7 | Lohagara | 415475287 | Jalil Nagar Chowdhury para road. | 1.5 |  | HBB | 37.5
8 | Lohagara | 415475288 | Kalauzan - Sukchari Kamardhighi Charamba Road | 1 |  | BC | 32.5
9 | Lohagara | 415475067 | Kanuram BazarTo Harina Road | 1 |  | HBB | 25
10 | Lohagara | 415474047 | Asraf Ali Road | 0.75 |  | HBB | 18.75
11 | Lohagara | 415475016 | Bara Hatia Alur Ghat Road. | 0.75 |  | HBB | 18.75
12 | Lohagara | 415475246 | Bara Hatia Hat Khola Mura-Rasider Ghona School Road. | 0.75 |  | HBB | 18.75
13 | Lohagara | 415475282 | Amirabad Killer Ander Road. | 0.75 |  | HBB | 18.75
14 | Lohagara | 415475052 | Kalauzan Gabtali Phahor Chanda Road. | 0.75 |  | BC | 24.375
15 | Lohagara | 415475004 | Padua Ali Sikder Para Sagira Para Road. | 0.65 |  | BC | 21.125
16 | Lohagara | 415474019 | Tati para (putibila Union) Road. | 0.5 |  | BC | 16.25
17 | Lohagara | 415475165 | Putibila Saria Madrasha Road. | 0.5 |  | BC | 16.25
18 | Lohagara | 415475186 | Charamba Shah Majidia Road. | 0.5 |  | BC | 16.25
19 | Lohagara | 415475034 | Lahagara Majidia Para Road. | 0.5 |  | BC | 16.25
20 | Lohagara | 415474032 | Darbesh Hat maijbilla Road. | 1 |  | BC | 32.5
20 |  |  | Sub - Total | 16.9 | 0 |  | 463 | 0 | 0 | 0 | 0 | 0 | 0
29 |  |  | Total | 25.9 | 44.8 |  | 929 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Banshkhali | 415083041 | Baharchara UP Office Gondamara Bazar Road | 1 | 5 | BC | 54.5
2 | Banshkhali | 415083042 | Sarai UP to Silkup UP Office | 1.5 | 5 | BC | 75.5
3 | Banshkhali | 415083039 | Monswria Bazar to Silkup UP Office Road | 1 | 5 | BC | 54.5
4 | Banshkhali | 415083034 | Chachuria-Katharia Road | 1 | 5 | BC | 54.5
5 | Banshkhali | 415083003 | Upazila H/Q to Gondamara UP office Road (Dack Bangla - Gandamara upto Mattabar Para Road) | 1.5 |  | BC | 63
6 | Banshkhali | 415083004 | Puichari UP to Khudukkhali bazaar road (Prem bazaar – Chanua Emb) | 1.5 |  | BC | 63
7 | Banshkhali | 415083005 | Bhardar hat UP G.C to Chanua UP office road (Chanua Kadaria Road) | 1 |  | BC | 42
8 | Banshkhali | 415083006 | Elahi Box-huzur Road | 1.5 |  | BC | 63
9 | Banshkhali | 415083008 | Moulana Asraf Ali Road (Chanua UP to Khankhariabad UP VIA Gondamara,Saral,Katharia, Baharchara UP) | 1 |  | HBB | 30
10 | Banshkhali | 415083010 | Khankhariabad UP Shadanpur UP Road (Khankhariabad Abdul Hakim Road) | 1.5 |  | BC | 63
11 | Banshkhali | 415083011 | Chachuria - Katharia Road | 1.96 |  | BC | 82.32
12 | Banshkhali | 415083012 | Monsuria bazaar to Silkup UP office Road | 1.9 |  | BC | 79.8
13 | Banshkhali | 415083014 | Saral up to Silkup UP office Road | 1.77 |  | BC | 74.34
14 | Banshkhali | 415083015 | Napora to shaker khil UP office Road (Shekhakhil union parishad) | 1.5 |  | BC | 63
15 | Banshkhali | 415083016 | Moulana Ishaque shah Road | 1 |  | HBB | 30
16 | Banshkhali | 415083017 | Indra Narayon Road | 1.35 |  | BC | 56.7
17 | Banshkhali | 415083018 | Hajee Rafique Ahmed Chy. Road | 1.5 |  | BC | 63
18 | Banshkhali | 415083002 | Saral bazar to Joldi U.P Road (TC road). | 1.11 | 101.2 | BC | 299.62
19 | Banshkhali | 415083009 | Chamble Bangla bazar via LGED bridge (JAICA) Boro ghona Rahmania road. | 1.95 |  | BC | 81.9
20 | Banshkhali | 415083019 | Bara - Moulana Road | 1.5 |  | BC | 63
20 |  |  | Sub-Total | 28.04 | 121.2 |  | 1456.68 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Banshkhali | 415085177 | Chapachari Asraf Ali Road and Construction of RCC Girder Bridge | 1 | 10 | BC | 52.5
2 | Banshkhali | 415084108 | Omed Ali Munshi Road Ch. 00-1442 m | 1 |  | BC | 32.5
3 | Banshkhali | 415084095 | Pukuria Bazar - Paharia Road | 1.154 |  | BC | 37.505
4 | Banshkhali | 415084057 | Sarol Nadonno Road | 1 |  | BC | 32.5
5 | Banshkhali | 415084081 | Sarol Moulana Sikandar Shah Road | 1 |  | HBB | 25
6 | Banshkhali | 415084114 | Sarol Dorgha Road | 1 |  | HBB | 25
7 | Banshkhali | 415085181 | Chanpur Sayed Solaiman shah Road (Up to Jhinuk Poltree Unit -2). | 1 |  | HBB | 25
7 |  |  | Sub - Total | 7.154 | 10 |  | 230.005 | 0 | 0 | 0 | 0 | 0 | 0
27 |  |  | Total | 35.194 | 131.2 |  | 1686.685 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Mirsharai | 415533009 | Chotta Kamaldaha - Dhomdama Abotorab Bazar Road | 2 | 5 | BC | 96.5
2 | Mirsharai | 415533010 | Abutorab Hasimnagar charsarath road | 2 | 5 | BC | 96.5
3 | Mirsharai | 415533018 | Chinki Astana Ram sundari muhuri Road. | 2 | 2 | BC | 89
4 | Mirsharai | 415533021 | Jamalpur Kalibari road | 2 | 3.5 | BC | 92.75
5 | Mirsharai | 415533004 | Jogodispur Noarahat road | 2 | 2 | BC | 89
6 | Mirsharai | 415533024 | Mirsarai Station road | 2 | 2 | BC | 89
7 | Mirsharai | 415533023 | Abutorab Kheyar Hat Road | 2 | 5 | BC | 96.5
8 | Mirsharai | 415533005 | Abutorab Annerderhat Road | 2 | 5 | BC | 96.5
9 | Mirsharai | 415533012 | Abutorab - Sadur Hat Road | 2 | 5 | BC | 96.5
10 | Mirsharai | 415533020 | Samitire Hat - Saherkhali U.P. Road Via Gazaria | 2 | 3.4 | BC | 92.5
11 | Mirsharai | 415533022 | Mithanala UP - Bhorerbazar Road | 1.5 | 2 | BC | 68
12 | Mirsharai | 415533019 | Katachara UP to Taytoia Bazar Road | 2 | 2 | BC | 89
13 | Mirsharai | 415533014 | Jahabox -Banshkhali - Muhuri gate Bazar Road | 2 | 2 | BC | 89
14 | Mirsharai | 415533009 | Choto Komoldha Abu torab bazar road (St. Chandpur gobonia road) | 2 | 2 | BC | 89
15 | Mirsharai | 415533013 | Aburhat-Julonpul Osmania road | 2 | 2 | BC | 89
16 | Mirsharai | 415533003 | Hightkandi Gonria road | 2 | 2 | BC | 89
17 | Mirsharai | 415533007 | Bangla Bazar Osmanpur road | 2 | 2 | BC | 89
18 | Mirsharai | 415533016 | Bamonsundar-Bariakali-Julonpul road | 2 | 2 | HBB | 65
19 | Mirsharai | 415533006 | Gasbaria Shahebkhli Haspital road | 2 | 2 | BC | 89
19 |  |  | Sub-Total | 37.5 | 55.9 |  | 1690.75 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Mirsharai | 415534179 | Sheed Dr. Binoy Vushan Nah Road | 1 | 3 | BC | 38.5
2 | Mirsharai | 415534011 | Haiyatur Nesa Road | 1 |  | BC | 32.5
3 | Mirsharai | 415534109 | Shaheed Abu Basar Road | 1 | 5 | BC | 42.5
4 | Mirsharai | 415534166 | Ram Manikka Kar Road | 1 | 2 | BC | 36.5
5 | Mirsharai | 415535018 | Reju Muhuri Road | 1.4 | 2 | BC | 49.5
6 | Mirsharai | 415534160 | Abdul Munnaf Mastori Road | 1 | 2 | BC | 36.5
7 | Mirsharai | 415534177 | Shohid Jakir Hossain Road | 1 | 5 | BC | 42.5
8 | Mirsharai | 415534148 | Badshah Mia Road | 1 | 2 | BC | 36.5
9 | Mirsharai | 415534163 | Golam Akbar Khondakar Road (DT road to Lallichara) | 1.5 | 5 | BC | 58.75
10 | Mirsharai | 415534376 | Sattruya Obaidul Haque Road | 1 | 2 | BC | 36.5
11 | Mirsharai | 415534092 | Achia Khatun Road | 1.3 | 2 | BC | 46.25
12 | Mirsharai | 415534171 | Himmot Ali shah Road | 1.5 | 2 | BC | 52.75
13 | Mirsharai | 415534157 | Joypur purbo Joar Jame Mosjed Road | 1 | 2 | BC | 36.5
14 | Mirsharai | 415534166 | Jugi gram Road (DT road to Ram Manik Kar (east) | 1 | 2 | BC | 36.5
15 | Mirsharai | 415534192 | Mohajon Hat School College to Morhum F Rahman Bari via Santirhat Road | 1.5 | 5 | BC | 58.75
16 | Mirsharai | 415534139 | Jorarong high school Road | 1 | 2 | BC | 36.5
17 | Mirsharai | 415534193 | Old Dhaka to Chittagong Trank road to Mohajon Hat School via Mona Masque Road. | 1.25 |  | BC | 40.625
18 | Mirsharai | 415534044 | Kazi Taluk Shahid Dr. Bozle Shobahan road | 1.25 |  | BC | 40.625
19 | Mirsharai | 415535059 | Dr. Binay Vuson road | 1.5 |  | BC | 48.75
20 | Mirsharai | 415534151 | Choto komaldha - Pathuria road | 1 |  | HBB | 25
21 | Mirsharai | 415534010 | Mozzem Fakir Road | 1 |  | HBB | 25
22 | Mirsharai | 415534130 | Anu Chowdhary Monu Chowdhary road | 1 |  | BC | 32.5
23 | Mirsharai | 415535060 | Dom Khali bishnu mia Road. | 1 |  | BC | 32.5
24 | Mirsharai | 415535061 | Sundar Shaha Road (Uttar Talbari) | 1 |  | BC | 32.5
25 | Mirsharai | 415535062 | Abdur Rahman Road (Uttar Talbari) | 0.5 |  | BC | 16.25
26 | Mirsharai | 415535063 | Ali Nagar Bader Road. | 0.5 |  | BC | 16.25
27 | Mirsharai | 415535064 | Jogandar Mohajan Road. | 1 |  | BC | 32.5
28 | Mirsharai | 415535065 | Jamalpur Madrasa Road. | 1 |  | BC | 32.5
29 | Mirsharai | 415535066 | Hazi Sultan Ahmed Road. | 1 |  | BC | 32.5
30 | Mirsharai | 415535067 | Madan Mahajan Road. | 1 |  | BC | 32.5
31 | Mirsharai | 415535068 | Siddiq Chowdhiri Road. | 1 |  | BC | 32.5
31 |  |  | Sub - Total | 33.2 | 43 |  | 1150 | 0 | 0 | 0 | 0 | 0 | 0
50 |  |  | Total | 70.7 | 98.9 |  | 2840.75 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98) | 16 | 15 | BC | 709.5
2 | Rangunia | 415703052 | SagunBagicha-Hosnabad Rd. (From RHD #103) | 4.5 | 80 | BC | 389
3 | Rangunia | 415703006 | Chandragona U.P. Rd.(Kaptai road to Chandragona Union parishad Bhaban to Chandragona Ferigat. | 2 | 9 | BC | 106.5
4 | Rangunia | 415703007 | Ram Mohan Sikder Road(Rangunia UP - Tarachan Hat). | 1.5 | 5 | BC | 75.5
5 | Rangunia | 415703010 | Moyddha Parua (Parua UP HQ to Shoni chari Bazar). | 1.5 | 5 | BC | 75.5
6 | Rangunia | 415703002 | Marim nagar DC Rd-Razar hat ( Mogolhat to Razarhat ) | 1.5 | 5 | BC | 75.5
7 | Rangunia | 415703009 | RHD-Shilock UP-Bhuchakra Hat Road. | 1 | 3 | BC | 49.5
8 | Rangunia | 415703004 | Mahatipara Rd.-Maliarhat . | 1 | 3 | BC | 49.5
9 | Rangunia | 415703011 | S. D. O Road ( Padua bazer hat to Padua horihor School & Shilak rabar Dam to Kalindarani road) | 3 | 10 | BC | 151
10 | Rangunia | 415703012 | Darikop ( Padua Bramongat to Paschim Khurushia | 3 | 10 | BC | 151
11 | Rangunia | 415703013 | Firingir Khil Road ( Sarafvata - Shilak Connecting ) Road. | 3.1 | 15 | BC | 167.7
12 | Rangunia | 415703037 | Hajee para-Mizepara | 2 | 5 | BC | 96.5
13 | Rangunia | 415703014 | Jongol bogabili road (Rangamai road Tandachari tea bagan to Jongol bogabili) | 2 | 4 | BC | 94
14 | Rangunia | 415703015 | Hajee Nazim Jamir Uddin Shah connecting road ( Parua D.C road Dewan bazar to Damrai hat Moriom nagar D.C road | 2.17 | 4 | BC | 101.14
15 | Rangunia | 415703016 | Raisabili road ( Rangamati Road Gabtali to Raisabili Boddo Mondir) | 1.5 | 4 | BC | 73
16 | Rangunia | 415703018 | Mariam nagar DC Rd-Agunia Tea bagan road ( Dami hat to Marim nagar DC road to Agunia Tea bagan)(Magon Road). | 1.5 | 4 | BC | 73
17 | Rangunia | 415703019 | Nazarer tila Road ( Moriam nagar Union parishad babhan to Nazar tila) | 1.41 | 2 | BC | 64.22
18 | Rangunia | 415703020 | Hajee Raham Ali Road | 1.5 | 3 | BC | 70.5
19 | Rangunia | 415703024 | Raza miah Chy. Rd. | 1 | 3 | BC | 49.5
20 | Rangunia | 415703025 | Court Road Cum Amanullah Road | 1 | 3 | BC | 49.5
21 | Rangunia | 415703028 | Kalindi Rani connecting | 1.5 | 5 | BC | 75.5
22 | Rangunia | 415703029 | Kodala S.A. Chowdhury road | 1 | 4 | BC | 52
23 | Rangunia | 415703030 | Late Fazlul Kader Chowdhury (Sharafvata High School) Rd. | 1 | 3 | BC | 49.5
24 | Rangunia | 415703050 | Hajee Road | 1 | 4 | BC | 52
25 | Rangunia | 415703032 | Chandraghona High School Rd. | 0.85 | 2.8 | BC | 42.7
26 | Rangunia | 415703034 | Shahid saleh Ahmed | 1 | 3 | BC | 49.5
27 | Rangunia | 415703039 | Sonargaon High School Road | 1 | 3 | BC | 49.5
28 | Rangunia | 415703042 | Darikop Batapahar Tripura Sandari Rd. | 1 | 3 | BC | 49.5
29 | Rangunia | 415703043 | Killmogal Master Abdul Gani Village Road. | 1 | 3 | BC | 49.5
30 | Rangunia | 415703044 | East Shabdi Nagar Mohila Road | 1 | 5 | BC | 54.5
31 | Rangunia | 415703046 | Kha Mosjid Road | 1 | 5 | BC | 54.5
32 | Rangunia | 415703049 | Nasir Mohammad Road | 1 | 3 | BC | 49.5
33 | Rangunia | 415703017 | Bacha Shah Road | 1 | 2 | BC | 47
34 | Rangunia | 415703021 | Aman Ali Road - 1 | 1 | 10 | BC | 67
35 | Rangunia | 415703023 | Halimpur Darga Road | 1 | 5 | BC | 54.5
36 | Rangunia | 415703031 | Hazee Nurali | 0.87 | 3 | BC | 44.04
37 | Rangunia | 415703033 | Muradnagor west para | 1 | 3 | HBB | 37.5
38 | Rangunia | 415703038 | Tin Choqdia road | 1 | 3 | HBB | 37.5
39 | Rangunia | 415703035 | Uttar Parua | 1 | 3 | BC | 49.5
40 | Rangunia | 415703036 | Sailbukka Teknaf para Road | 1 | 3 | BC | 49.5
41 | Rangunia | 415703041 | Lakir Khil Road | 0.91 | 2.5 | BC | 44.47
42 | Rangunia | 415703053 | Kalurghat-Charandwip-Vandaljuri-Sarafvata Road | 1 | 20 | BC | 92
42 |  |  | Sub-Total | 74.31 | 290.3 |  | 3822.77 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Rangunia | 415704025 | Khurusia Abdul Hamid Rd.-Kamalchari Pry. School | 4 | 100 | BC | 330
2 | Rangunia | 415704026 | Minagazir Tila South Para Road | 0.6 | 3 | BC | 25.5
3 | Rangunia | 415704027 | Satgaria Para Road (From Padma Pukur) | 1 | 3 | BC | 38.5
4 | Rangunia | 415704028 | Korban Ali Rd. | 1 | 3 | BC | 38.5
5 | Rangunia | 415704029 | Chandraghona adur para Rd. | 0.79 | 3 | BC | 31.675
6 | Rangunia | 415704030 | Sarafvata Ashrayan Project Road. | 1.5 | 5 | BC | 58.75
7 | Rangunia | 415704031 | Kulal Para Rajanikanti Road | 1 | 3 | BC | 38.5
8 | Rangunia | 415704032 | Nazrupara Road | 1 | 3 | BC | 38.5
9 | Rangunia | 415704033 | Menagazir Tila - Sebakola Road | 0.65 | 2 | BC | 25.125
10 | Rangunia | 415704034 | Shilok - Hospital Road | 0.5 | 2 | BC | 20.25
11 | Rangunia | 415704035 | Sayed Ali Road Old Part (Dr. Bari to Donger Muk) | 0.75 | 5 | BC | 34.375
12 | Rangunia | 415704036 | 20 M Bridge on Dong Khal in Nuna Panir Road | 2 | 20 | BC | 105
13 | Rangunia | 415704037 | Noter Tila Road | 1 | 3 | BC | 38.5
14 | Rangunia | 415704038 | Talia Para Road | 1 | 3 | BC | 38.5
15 | Rangunia | 415704039 | 40 M Bridge on Varanchori khal in Jungle Bagabele Road |  | 40 | RCC | 80
16 | Rangunia | 415704040 | 30 M Bridge on Hizoltoli Mora Khal in Fultoli Road |  | 30 | RCC | 60
17 | Rangunia | 415704041 | Fultali Bazar Road | 1 | 3 | BC | 38.5
18 | Rangunia | 415704042 | Sayed Ahmed Road (Santir Hat - Olier Para via Barua Para) | 1 | 3 | BC | 38.5
19 | Rangunia | 415704043 | Ramgotir Hat - Mohajon Bari Road | 1 | 5 | BC | 42.5
20 | Rangunia | 415704044 | Modda Noagaon Road(Pry. School - Santir Hat) | 1 | 3 | BC | 38.5
21 | Rangunia | 415704045 | Magon Road | 1 | 5 | BC | 42.5
22 | Rangunia | 415704046 | Lalanagor Village Road | 1 | 3 | BC | 38.5
23 | Rangunia | 415704047 | Banagram Road | 1 | 3 | BC | 38.5
24 | Rangunia | 415704048 | Marium Nagor DC road to Rangunia College Road | 1 | 3 | BC | 38.5
25 | Rangunia | 415704049 | Pagla Mama | 1 | 3 | BC | 38.5
26 | Rangunia | 415704050 | Sahabdinagar Mosjid Road | 1 | 3 | BC | 38.5
27 | Rangunia | 415704051 | Kabir Mohammed Road | 1 | 3 | BC | 38.5
28 | Rangunia | 415704052 | Nazu Meah Taluck Road | 1 | 3 | BC | 38.5
29 | Rangunia | 415704053 | Abdul Wahed Talukder Road, Kodala | 1 | 3 | BC | 38.5
30 | Rangunia | 415704054 | Dr. Hafez Rahman Road , Padua | 0.45 | 3 | BC | 20.625
31 | Rangunia | 415704055 | Falharia Buddha Bihar Road | 1 | 3 | BC | 38.5
32 | Rangunia | 415704056 | Gazi Kalu Road,Padua | 1 | 3 | BC | 38.5
33 | Rangunia | 415704057 | Monitakur Para Road | 0.3 | 2 | BC | 13.75
34 | Rangunia | 415704058 | Moddam Para Buddha Mandir Road | 0.3 | 1 | BC | 11.75
35 | Rangunia | 415704059 | Goal Ghata - Khosailla Tila Road | 1 | 2 | HBB | 29
36 | Rangunia | 415704060 | Shahed Road, Padua | 1 | 3 | HBB | 31
37 | Rangunia | 415704061 | Rafique Road |  | 20 | RCC | 40
38 | Rangunia | 415704062 | Retaining Wall in Eunosia Azizul Ulum Madrasha |  | 15 | RCC | 30
39 | Rangunia | 415704063 | Sayed Bari East Para Sadar Ali Munse Road | 1 | 2 | HBB | 29
39 |  |  | Sub - Total | 35.84 | 325 |  | 1792.3 | 0 | 0 | 0 | 0 | 0 | 0
81 |  |  | Total | 110.15 | 615.3 |  | 5615.07 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Chandanish | 415183012 | Diakul-Chringhata-Dhopachari-Monglarmuk | 5 | 150 | BC | 585
2 | Chandanish | 415183003 | Noyarhat-Bhagabanhat-Mohankhali Bogertag Khoderhat GC Road |  | 25 | BC | 62.5
3 | Chandanish | 415183009 | Alhaz Ali Ahmed Road (Mehazangata-Khalirhat-Sabondi Bat tal-Syed bazar via Moulavi bazar | 3.5 |  | BC | 147
3 |  |  | Sub-Total | 8.5 | 175 |  | 794.5 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Chandanish | 415184046 | Purboshilpara to Barkal road under Suchigram | 0.5 |  | BC | 16.25
2 | Chandanish | 415184047 | Purbo Kashuya shah (R) Road. | 1 |  | BC | 32.5
3 | Chandanish | 415184048 | Bainnapukur - Forest office Arif shah mazar Road. | 1.5 |  | BC | 48.75
4 | Chandanish | 415184049 | West Boailtoli dokan to east Mostafij bari via east primary school road. | 1.5 |  | BC | 48.75
5 | Chandanish | 415184050 | Samukchora - Dhopachori road. | 1.5 |  | BC | 48.75
6 | Chandanish | 415184051 | West Boailtoli Daroga bari to west uttar Altaf master bari via Batajuri main road. | 1 |  | BC | 32.5
7 | Chandanish | 415184052 | West Boailtoli Majhpara Ahmed Hossain bari to Hindu para majh via Borhom para connecting road. | 1 |  | BC | 32.5
8 | Chandanish | 415184053 | Satbariya Dhonar para - Saliyar para road. | 1 |  | BC | 32.5
9 | Chandanish | 415184054 | Bhai Kholifa para - Hindupara Koirlamura road. | 1 |  | BC | 32.5
10 | Chandanish | 415184055 | Badamtol - Bodlagodha - Amtoli Road. | 1 |  | BC | 32.5
11 | Chandanish | 415184056 | Sikdarpara - Munshipara - Sonaichori kul road. | 1 |  | BC | 32.5
12 | Chandanish | 415184057 | Sayedabad Khuniyapara road. | 1 |  | BC | 32.5
13 | Chandanish | 415184058 | Boropara - Munshipara brick field road. | 1 |  | BC | 32.5
14 | Chandanish | 415184059 | Nagarpara - Adorshogram - Anshopara road. | 1 |  | HBB | 25
15 | Chandanish | 415184060 | Middle Bailtoli - Dipchoroti road. | 1 |  | HBB | 25
16 | Chandanish | 415184061 | Kanchonnagar nagarpara Arakan road to Purbo Elahabad Boruyapara road. | 1 |  | HBB | 25
17 | Chandanish | 415184062 | Khanhat GC - Hasimpur UP office (Morhum Abdul Kader road). | 1 |  | HBB | 25
18 | Chandanish | 415184063 | Kornel Oli Ahmed road. | 2.66 |  | BC | 86.45
19 | Chandanish | 415184064 | Deajee para - Seepoti Borua Road | 1 |  | HBB | 25
19 |  |  | Sub - Total | 21.66 | 0 |  | 666.45 | 0 | 0 | 0 | 0 | 0 | 0
22 |  |  | Total | 30.16 | 175 |  | 1460.95 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Anowara | 415043001 | Abdul Majid Chowdhury Road | 3.4 | 10 | BC | 167.8
2 | Anowara | 415043005 | Upazila Health Complex Peskarhat via Chotari UP Office | 4.38 | 10 | BC | 208.96
3 | Anowara | 415043023 | Anowara-Dhar Pura Hat Road (Hazi Abdul Jalil Road) | 5 | 15 | BC | 247.5
4 | Anowara | 415043014 | Mahata to Pathani Kotha High school Dattar hat to Gojra High School via Modon boidda bari road. | 5 |  | BC | 210
5 | Anowara | 415043015 | Porikora Lalanagar bazar Road (Up to Tangapul Bridge) | 4 |  | BC | 168
6 | Anowara | 415043024 | Alhaz Akhtaruzzaman Chowdhuri Road (Malghar Madrasha-Union Hospital (purano post office). | 4.47 |  | BC | 187.74
7 | Anowara | 415043017 | Construction of Kainpura vagno bridge. |  | 15 | BC | 37.5
8 | Anowara | 415043018 | Shinghara high school Road | 3 |  | BC | 126
9 | Anowara | 415043025 | Mahata Moulovi bari road. | 1 |  | BC | 42
10 | Anowara | 415043026 | Koinpura road including 85 m RCC Girder Bridge | 4.5 | 85 | BC | 401.5
11 | Anowara | 415043008 | Baroshoto UP office parkibazar Road (Amir Hossain Dovashi Road) | 2.5 |  | BC | 105
11 |  |  | Sub-Total | 37.25 | 135 |  | 1902 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Anowara | 415045051 | Dattar hat to Shilalia Road | 1 |  | BC | 32.5
2 | Anowara | 415045002 | Eakub Ali Road | 1 |  | BC | 32.5
3 | Anowara | 415045005 | Capatali Road | 1 |  | HBB | 25
4 | Anowara | 415045028 | Bariya Connecting Road | 2 |  | HBB | 50
5 | Anowara | 415045053 | Kaikhan Nayarasta Kodala Bridge to Kaligonga Road | 2 |  | HBB | 50
6 | Anowara | 415045054 | Kaikhan Camudia Connecting Road | 1 |  | BC | 32.5
7 | Anowara | 415044058 | Khashkhama Anowara Collage Connection road | 2 |  | BC | 65
8 | Anowara | 415045101 | Profesor Ahmed Hossain road (Purbo Haildhat) | 0.5 |  | BC | 16.25
9 | Anowara | 415044005 | Ali Ahmed Chowdhuary Dewtala Patny Cota road | 1.5 |  | BC | 48.75
10 | Anowara | 415045019 | Anowara college road | 2 |  | BC | 65
11 | Anowara | 415045125 | Tisori Road | 1 |  | BC | 32.5
12 | Anowara | 415045126 | Toladeep Barkan Circular road | 1.5 |  | BC | 48.75
13 | Anowara | 415045127 | Burungchara Samadia Road | 1.5 |  | BC | 48.75
13 |  |  | Sub - Total | 18 | 0 |  | 547.5 | 0 | 0 | 0 | 0 | 0 | 0
24 |  |  | Total | 55.25 | 135 |  | 2449.5 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Patiya | 415613009 | Juldha Danger Char Road | 2.8 | 20 | BC | 167.6
2 | Patiya | 415613014 | Abdul Jalil Chowdhury Road | 1.35 | 5 | BC | 69.2
3 | Patiya | 415613003 | Elahabad - Shovandandi Road | 2 | 10 | BC | 109
4 | Patiya | 415613002 | Shagadi Road | 2 | 15 | BC | 121.5
5 | Patiya | 415613017 | Khan Mohara Station - Bhattacharjee GC | 2 |  | BC | 84
6 | Patiya | 415613018 | Hidgou Union Parishad Road | 1 |  | BC | 42
7 | Patiya | 415613019 | Patiya Hidgou Akboria Mazar Road | 1 | 4 | BC | 52
8 | Patiya | 415613006 | Keranja Ghat Road | 1 | 4 | BC | 52
9 | Patiya | 415613021 | Abdul Malek Road | 1 |  | HBB | 30
10 | Patiya | 415613019 | Patiya Teker Fini Road | 1 |  | HBB | 30
10 |  |  | Sub-Total | 15.15 | 58 |  | 757.3 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Patiya | 415615130 | East Hidgou Ziayar para Hazi Bazlur Rahman Road | 1 | 22.14 | BC | 76.78
2 | Patiya | 415614088 | Akboria Road - Hazi Ahmadur Rahman master Road | 1 |  | BC | 32.5
3 | Patiya | 415614089 | Zolapara Kuilla mia khal box culvert |  | 20 | Bridge | 40
4 | Patiya | 415614067 | Annada datta road | 1 |  | BC | 32.5
5 | Patiya | 415614090 | Hidgou High school Road | 1 |  | BC | 32.5
6 | Patiya | 415614091 | Akboria Road (South) | 1 |  | BC | 32.5
7 | Patiya | 415614092 | Bodarpara road | 1 |  | BC | 32.5
8 | Patiya | 415614093 | Hazi Sayed Dilar road | 1 |  | BC | 32.5
9 | Patiya | 415614094 | Hazi Nuruccfa road | 1.5 |  | BC | 48.75
10 | Patiya | 415614044 | Kalibari Road connecting Abbas Ali Road, Mohira under Ziri Union | 1.5 | 10 | BC | 68.75
11 | Patiya | 415615047 | Hulain-Amirchar Primary school Road via Bonkmath | 1.5 | 30 | BC | 108.75
12 | Patiya | 415615059 | Budhpura to Mahira perpara connecting road under Kashiash union | 1 |  | BC | 32.5
13 | Patiya | 415614028 | Darok to Vandargou & bakkhain connecting road under Kashiash union | 1 |  | HBB | 25
14 | Patiya | 415614024 | Dhal ghat union Alampur-Union road | 1 |  | HBB | 25
15 | Patiya | 415614100 | Dhirin das Road ( Habilasdip Gram) | 1 |  | HBB | 25
15 |  |  | Sub - Total | 15.5 | 82.14 |  | 645.53 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  | Total | 30.65 | 140.14 |  | 1402.83 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Moheshkhali | 422493004 | Gorokghata-Ghatibhanga Sonadia Road | 2 | 130 | BC | 409
2 | Moheshkhali | 422493016 | Shipahipara-Modirchara Road | 1 |  | BC | 42
3 | Moheshkhali | 422493003 | Matarbari-Dhulghat Road | 1.25 |  | HBB | 37.5
4 | Moheshkhali | 422493002 | Lalmohammad Sikdarpara via Assaryon project | 1.3 | 6 | BC | 69.6
5 | Moheshkhali | 422493013 | KalaramarcharaJ M Ghat Dhala road | 1.5 |  | HBB | 45
6 | Moheshkhali | 422493017 | Younus khali Matabari - Uzantia road | 1.5 |  | HBB | 45
6 |  |  | Sub-Total | 8.55 | 136 |  | 648.1 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Moheshkhali | 422494001 | Zagiraghona - Fakiraghona Road | 1 |  | HBB | 25
1 |  |  | Sub - Total | 1 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
7 |  |  | Total | 9.55 | 136 |  | 673.1 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Teknaf | 422903002 | Hirla Baharchara Road | 1.5 |  | BC | 63
2 | Teknaf | 422903005 | Subrang UP Office-Panchari Para | 1.38 |  | BC | 57.96
3 | Teknaf | 422903006 | Subrang UP Office-Noa Para | 1.1 |  | BC | 46.2
4 | Teknaf | 422903010 | Notun palla para - beach Road | 2 | 1.05 | BC | 86.625
5 | Teknaf | 422903011 | Subrong union Moulovi para, Noya paraRoad | 1.5 |  | HBB | 45
6 | Teknaf | 422903012 | Subrong sea beach Road remaining part | 1 |  | BC | 42
7 | Teknaf | 422903013 | Howaikong road & Jonopath division road - Roikhom Road. | 1.5 |  | HBB | 45
7 |  |  | Sub-Total | 9.98 | 1.05 |  | 385.785 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Teknaf | 422904038 | Teknaf Waliabad Al-Haz Wali Hafsa Panjakhana gowdarbil Rd. | 2 | 10 | HBB | 70
1 |  |  | Sub - Total | 2 | 10 |  | 70 | 0 | 0 | 0 | 0 | 0 | 0
8 |  |  | Total | 11.98 | 11.05 |  | 455.785 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Chakaria | 422163004 | Badarkhali UP Office-Natun Bazar Road | 2 | 10 | HBB | 85
2 | Chakaria | 422163006 | Kakra Surazpur Manikpur Yangca Road | 2 | 10 | BC | 109
3 | Chakaria | 422163009 | Khutakhali Rubber Dam Road | 0.5 |  | BC | 21
4 | Chakaria | 422163008 | Dulahazara to Fashiakhali (Lama) Road | 1 | 20 | BC | 92
5 | Chakaria | 422163007 | Chiringa UP Office Mogbazar Palakata Jeti Road | 1 | 22 | BC | 97
6 | Chakaria | 422163002 | Harbang RSD/UP office to Shilkhali Road. | 1 |  | HBB | 30
6 |  |  | Sub-Total | 7.5 | 62 |  | 434 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Chakaria | 422165044 | Khutakhali R&HD- Sagun bagan road | 1 |  | BC | 32.5
2 | Chakaria | 422164006 | Purbung Magpara Road | 1 |  | BC | 32.5
3 | Chakaria | 422164013 | Illishia Mukbulabad Road | 1 |  | HBB | 25
4 | Chakaria | 422164054 | Demoshia Hetaliya para Road | 1 |  | HBB | 25
4 |  |  | Sub - Total | 4 | 0 |  | 115 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  | Total | 11.5 | 62 |  | 549 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Ramu | 422663005 | Eidgar Bazar-Rangachari Road | 1 |  | BC | 42
2 | Ramu | 422663007 | Chainda razarkul Road |  | 23 | Bridge | 57.5
3 | Ramu | 422663012 | Chakmarkul - Monthargoda Road | 1 | 8.5 | HBB | 51.25
4 | Ramu | 422663013 | Gorjonia bazar - Dochari Road | 1 | 7 | HBB | 47.5
5 | Ramu | 422663014 | Eidgar Bazar-Boughat Road | 1.5 | 68.5 | BC | 234.25
6 | Ramu | 422663011 | Ukhiar ghona-Gorjoniya road. | 2.5 |  | BC | 105
6 |  |  | Sub-Total | 7 | 107 |  | 537.5 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Ramu | 422665094 | Chakmar kul mithasari connecting road carpeting | 1 |  | BC | 32.5
2 | Ramu | 422665080 | Merin drive goalia teknaf connecting road carpeting | 2 |  | HBB | 50
3 | Ramu | 422664033 | Joaria nala to nonachar road carpeting | 2 |  | BC | 65
4 | Ramu | 422665074 | Khalikkamura - Kajorbil Road | 1 |  | HBB | 25
4 |  |  | Sub - Total | 6 | 0 |  | 172.5 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  | Total | 13 | 107 |  | 710 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Kutubdia | 422453001 | Kutubdia Upzila H/Q to Collage Road to Lemshikhali Road | 5 | 5.5 | BC | 223.75
2 | Kutubdia | 422453002 | Dhurung GC Uttar Uipi Via Assaraon Project Road | 1.82 | 3 | HBB | 62.1
2 |  |  | Sub-Total | 6.82 | 8.5 |  | 285.85 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Kutubdia | 422454001 | Uttar Dhurung UP-Bahingakata- Chandroghona connecting road | 1 | 5 | HBB | 35
2 | Kutubdia | 422454002 | Jummapara Road | 1 | 5 | HBB | 35
3 | Kutubdia | 422454031 | Bindapara Road | 1 |  | BC | 32.5
4 | Kutubdia | 422455016 | Puttinna para-Nasierpara Road | 1 | 3.87 | BC | 40.24
4 |  |  | Sub - Total | 4 | 13.87 |  | 142.74 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  | Total | 10.82 | 22.37 |  | 428.59 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Ukhia | 422943002 | Palongkhli Bazar-Palongkhli UP Office via Anguman para Road | 1.5 |  | BC | 63
2 | Ukhia | 422943006 | Holudiapalong UP Office to Patabari via Paglirbil Road | 2.5 | 6 | BC | 120
3 | Ukhia | 422943007 | Rotnopal UP Office - Chakboitha bazar Via Goalmara ( Yousuf Ali Rotnopalong Koroibonia) Road | 2 | 1.45 | HBB | 63.625
3 |  |  | Sub-Total | 6 | 7.45 |  | 246.625
Village Road
1 | Ukhia | 422944010 | Gilatoli Moskaria Road. | 1.2 | 0.63 | BC | 40.26
2 | Ukhia | 422944056 | Raja Palong Asrayon Road. | 1.65 | 7 | BC | 67.625
3 | Ukhia | 422944058 | Ukhiya Hatmura Road. | 1 |  | HBB | 25
4 | Ukhia | 422944051 | Rumkha Napitpara Road. | 0.55 | 1.35 | HBB | 16.45
5 | Ukhia | 422945067 | Falia Para Pry. School Road. | 1.1 | 1.875 | HBB | 31.25
5 |  |  | Sub - Total | 5.5 | 10.855 |  | 180.585
8 |  |  | Total | 11.5 | 18.305 |  | 427.21
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Sadar | 422243009 | Edgau UP Office - MeherGhona Forest Office bazar road | 3 |  | BC | 126
2 | Sadar | 422243005 | Piamkhali UP Office-Kuruschool UP Office(Xmilitari) Road | 1.5 | 7.5 | BC | 81.75
3 | Sadar | 422243004 | Islamabad UP Office-Islampur Bazar via Shawkat salt mill Road | 1.25 | 4 | BC | 62.5
4 | Sadar | 422243006 | Piamkhali UP Office-Kurulia Bazar via Mohasniapara Bazar Road | 1.25 | 10 | BC | 77.5
5 | Sadar | 422243008 | Islamabad Gohalia road carpeting | 1.25 |  | BC | 52.5
6 | Sadar | 422243001 | Rashid nagor UP office - Bharoakhali center bazar to West voroakhali Khuruskhul gat road carpeting | 1.25 |  | BC | 52.5
7 | Sadar | 422243017 | Edgau UP Office - Vomria Forest Office bazar Via Vaditola road | 1.5 |  | HBB | 45
8 | Sadar | 422243019 | Eidgon UP Office - Eidgon College Road | 1 |  | HBB | 30
8 |  |  | Sub-Total | 12 | 21.5 |  | 527.75 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Sadar | 422244025 | Maijpara Road (Dhakin Mazpara to ) | 1 | 3 | BC | 38.5
2 | Sadar | 422245138 | HAzi para Govrt. Primary School to Nabab Miar Bari Road | 1 |  | BC | 32.5
3 | Sadar | 422245012 | Banglabazar to Moulovhi para to Saitah gate Road | 1 |  | BC | 32.5
4 | Sadar | 422245063 | Bagla bazar to Mowlobi para carpeting road development | 1 |  | BC | 32.5
5 | Sadar | 422245011 | Mukterkul Churutia madrasa to meagi bari via Bakkali river side East Mukterkul jame mosque carpeting road dev. | 1 |  | BC | 32.5
6 | Sadar | 422245074 | PM khali union chankhola Khurskul carpeting | 1 |  | BC | 32.5
7 | Sadar | 422245132 | Chittagong Cox's bazar road to Islampur-Pokkhali Chowpol dondi upakulio road carpeting | 1 |  | BC | 32.5
8 | Sadar | 422244048 | Pokkhali muslim bazar road devlopment | 1 |  | BC | 32.5
9 | Sadar | 422245139 | P,M, khali Jumchari Bazar to Masuakhali Bazar Road | 1 |  | BC | 32.5
10 | Sadar | 422245140 | East Mosjid Road. | 1 |  | BC | 32.5
11 | Sadar | 422245141 | P,M, Khali High school to Kathaliamora Road | 1 |  | BC | 32.5
12 | Sadar | 422245046 | East Maize para - Ghonapara - Dolghata Road. | 1 |  | HBB | 25
13 | Sadar | 422244018 | Middle Maize para - Arakan Road. | 1 |  | HBB | 25
14 | Sadar | 422245051 | Azim Master Road under Edgau UP | 1 |  | HBB | 25
14 |  |  | Sub - Total | 14 | 3 |  | 438.5 | 0 | 0 | 0 | 0 | 0 | 0
22 |  |  | Total | 26 | 24.5 |  | 966.25 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Proposed Length |  | Type | Total Cost (in Lakh) | Allogation |  |  | Approval for Tender |  |  | Remarks
|  |  |  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka | (Km) | Span (m) | Taka
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Union Road
1 | Pekua | 422953008 | Shilkali Paharchad Mardasa via RHD Road | 1.5 | 3 | BC | 70.5
2 | Pekua | 422953010 | Mognama RHD via Mognama High School Road | 2.1 | 2 | BC | 93.2
3 | Pekua | 422953016 | Fatafari Sonali Bazar to Koida Bazar (Uzantia StimarGhat) Road | 2 | 2 | BC | 89
4 | Pekua | 422953018 | Razakhali UP Office to Amin Bazar Road | 1 | 2 | HBB | 35
5 | Pekua | 422953022 | Shilkali UP Office to Sakupara Road | 1 | 3 | HBB | 37.5
5 |  |  | Sub-Total | 7.6 | 12 |  | 325.2 | 0 | 0 | 0 | 0 | 0 | 0
Village Road
1 | Pekua | 422954026 | Mognama RHD to Sharatghona Kutubdia Upazila conneting Road. | 1 |  | BC | 32.5
2 | Pekua | 422955018 | Pekua North Nunna Chara Road. | 0.5 | 0.63 | BC | 17.51
3 | Pekua | 422955068 | Shondari Para-Ray Bapar Para Road. | 1 |  | BC | 32.5
4 | Pekua | 422955042 | Jaliakata Bridge-Toitong Rubber Dam Road. | 1 |  | BC | 32.5
5 | Pekua | 422955022 | Shilkhali Monshi Mura Village Road. | 1 |  | HBB | 25
6 | Pekua | 422954003 | Toitong Forest Office Road. | 1 |  | HBB | 25
6 |  |  | Sub - Total | 5.5 | 0.63 |  | 165.01 | 0 | 0 | 0 | 0 | 0 | 0
11 |  |  | Total | 13.1 | 12.63 |  | 490.21 | 0 | 0 | 0 | 0 | 0 | 0

## Progress
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong Date:24.11.2011
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Physical Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Boalkhali | 415123002 | Bengura D.C. Road | WD-UNR-CTG-BOAL-10/02 | 2 | 5 | BC | 96.5 | 2 | 5 | 96.5 |  | 0.84 | 4 | 22.79 | BC | 2010-05-08 | Rife Enterprise | 21.62 | 2010-10-10 | 23/2/10 | 100% | 21.62 | F/B Paid
2 | Boalkhali | 415123006 | Kalurghat-Gomodondi-Bangura-Sakirapool road | WD-UNR-CTG-BOAL-10/01 | 2 | 5 | BC | 96.5 | 2 | 5 | 96.5 |  | 2.635 |  | 92.23 | BC | 2010-10-05 | Khair & Son's | 92.19 | 25/07/10 | 8/12/2010 R30/04/11 | 100% | 69.42
3 | Boalkhali | 415123018 | Amuchia Bura Masjid Road | WD-UNR-CTG-BOAL-10/03 | 2 | 5 | BC | 96.5 | 2 | 5 | 93.6 | 2010-08-08 | 1.84 | 4.5 | 93.57 | BC | 2010-12-10 | m/s Iqubal H ssain | 102.92 | 2011-09-08 | 2012-02-03 | 25%
4 | Boalkhali | 415123014 | Monir Ahmed Road | WD-UNR-CTG-BOAL-11/05 | 2 | 7 | BC | 101.5 | 2 | 7 | 96.5 | 22/11/10 | 2.18 | 4.5 | 94.72 | BC | 2011-06-02 | M/S Aysha Construction | 89.98 | 05/048/11 | 25/04/12 | 50% | 20.29 | \
5 | Boalkhali | 415123012 | Shahid Dherandra-Amirul Haque Road | WD-UNR-CTG-BOAL-11/04 | 2 | 5 | BC | 96.5 | 2 | 1.5 | 35.85 | 27/12/10 | 1.88 | 1.5 | 35.85 | BC | 2011-06-02 | M/S Maha Associate | 35.85 | 2011-04-04 | 24/04/12 | 55% | 25.47 | Termination 02/01/13
5 | Boalkhali | 415123012 | Shahid Dherandra-Amirul Haque Road(Remaining) | WD-UNR-CTG-BOAL-13/09 | [6 empty] | 63.1 |  |  |  | 63.1 | BC | 30/06/13 | M/S Iqubal traders | 68.74 | 30/03/14
6 | Boalkhali | 415123005 | Kalachand Takor Road. | WD-UNR-CTG-BOAL-11/07 | 2 | 7 | BC | 101.5 | 1 |  | 42 | 2011-02-11 | 0.715 | 2.4 | 40.61 | BC | 2011-11-12 | M/S Abduj Salam | 42.64 | 31/05/12 | 22/12/12 R10/06/13
7 | Boalkhali | 415123005 | Kalachand Takor Road.(Remaining Part) | WD-UNR-CTG-BOAL-13/08 |  |  |  |  | 1.3 |  | 45 | 26/11/12 | 1.285 |  | 40.22 | HBB | 17/01/13 | M/S Abdul Salam | 44.99
8 | Boalkhali | 415124083 | Dr. M A Mannan road (Anjumar tek to Kazibari Govt. Primary School) | WD-UNR-CTG-BOAL-13/09 | 1.65 | 1.75 | BC | 57.125 | 1 |  | 28 | 2013-09-05 | 0.83 | 0.75 | 25.92 | HBB | 2013-01-10 | M/S Md. Ismail Chowdhury | 32.54
8 | Boalkhali | 415123001 | Murad Munsir Hat-Chowdhury Hat Via KadurkhilUP Road | WD-UNR-CTG-BOAL-14/10 | 1 |  | HBB | 33 | 1 |  | 31 | 2013-11-12 | 0.5 | 0.75 | 30 | HBB | 2014-02-02 | M/S Ferdous Enterpr. | 31.5
9 | Boalkhali | 415124070 | Shahid Rafique Road |  | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14
10 | Boalkhali | 415124075 | Boali Kalandar Sha Mazar Road | WD-UNR-CTG-BOAL-14/12 | 1 |  | BC | 56 | 1 |  | 45 | 31/03/14 | 1.2 |  | 41.58 | BC | 2014-10-07
10 |  |  | Sub - Total |  | 16.65 | 35.75 |  | 763.125 | 16.3 | 23.5 | 698.05 |  | 13.905 | 18.4 | 580.59 |  |  |  | 562.97 |  |  |  | 136.8
Village Road
1 | Boalkhali | 415125154 | Construction of One Vent 4mx4m Box Culvert & 4nos.0.75mx0.75m Box Culvert On Bishombar Road . | WD-UNR-CTG-BOAL-11/06 | Not In DPP |  |  |  | 2 |  | 60 | 17/01/11 |  | 7 | 20.75 |  | 25/05/11 | M/S Towakkul Enterprise | 19.71 | 27/07/11 | 17/02/12 | 100% | 12.87
2 | Boalkhali | 415124064 | Modon Sardar Road. |  | Not In DPP |  |  |  | 1 |  | 40 | 2013-03-09
3 | Boalkhali | 415124057 | Akub dondi Sayad Abdur Nur Road | WD-UNR-CTG-BOAL-14/11 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.9 |  | 25.1 | HBB | 2014-02-02
4 | Boalkhali | 415124069 | Dhorla Bodorsha Road |  | 1 |  | BC | 28 | 1 |  | 25 | 22/07/14
4 |  |  | Sub - Total | [5 empty] | 1 | 0 | 26 |  |  | 0 | 25.1 |  |  |  | 0 |  |  |  | 0
14 |  |  | Total |  | 16.65 | 35.75 |  | 763.125 | 17.3 | 23.5 | 724.05 |  | 13.905 | 18.4 | 605.69 |  |  |  | 562.97 |  |  |  | 136.8
Union Road
1 | Fatikchari | 415333011 | Kalumonshir Hat to Dawiat Monshir Hat ( Nanupur - Khiram Road) | WD-UNR-CTG-FATIK-10/01 | 2.4 | 1.2 | BC | 76.53 | 1.5 | 7.5 | 81.75 |  | 2.4 | 1.2 | 14.94 | BC | 2010-10-05 | M/S Salim & Brother's | 14.94 | 21/07/10 | 2010-04-12 | 100% | 14.94 | Termination R22/11/12
2 | Fatikchari | 415333012 | Suabil UP H/Q to Shovanchari Bangiabazar Road | WD-UNR-CTG-FATIK-10/02 | 1.05 | 4.5 | BC | 66.85 | 1 | 7.5 | 34.78 |  | 1.05 | 3.5 | 34.78 | BC | 2010-10-05 | M/S Alam Absar & Co. | 34.78 | 21/07/10 | 4/12/2010 RRR22/10/12 | 70% | 34.77
2 | Fatikchari | 415333012 | Suabil UP H/Q to Shovanchari Bangiabazar Road | WD-UNR-CTG-FATIK-13/39 | 1 |  | HBB | 33 | 1.05 |  | 25.97 |  |  |  | 25.97 | BC | 2013-07-11
3 | Fatikchari | 415333019 | Nanupur UP H/Q to Samitirhat UP H/Q Road | WD-UNR-CTG-FATIK-10/03 | 1.3 | 1.2 | BC | 65.12 | 1 | 12 | 60 |  | 1.3 | 1.2 | 59.51 | BC | 2010-10-05 | M/S Alif Enterprise | 59.2 | 2010-10-10 | 23/02/11 R30/11/11 | 65% | 30.05 | Termination R02/01//12
4 | Fatikchari | 415333006 | Paindong U.P HQ (Brindabonhat) to Kanchan Nagar U.P H.Q Road via Kanchurhat | WD-UNR-CTG-FATIK-10/05 | 2.82 | 108.25 | BC | 497.92 | 2.82 | - | 39.57 |  | 2.82 | 13.2 | 39.57 | BC | 2010-11-07 | M/S Chowdury Construction | 119 | 25/1/11 | 15/2/12 RR15/01/13 | 50% | 38.76 | Termination R4/4/13
|  |  | Paindong U.P HQ (Brindabonhat) to Kanchan Nagar U.P H.Q Road via Kanchurhat (Remaining Work) | WD-UNR-CTG-FATIK-13/36 | [9 empty] | 6 | 124.12 | BC | 2013-01-10 | M/S Fine Bricks Manu. | 130.32 | 2014-02-01 | 41920 | 85%
|  |  | Cont.Of 95.01 Long RCC Girder Bridge On Dhurang Khal. | WD-UNR-CTG-FATIK-10/10 | [5 empty] | 95.05 | 241.83 |  |  | 95.05 | 241.83 |  |  | M/S Regal Enterprise | 288.95 | 2011-09-08 | 30/08/12 RR20/11/13 | 95% | 259.93
5 | Fatikchari | 415333010 | Bibirhat G.C to Harualchari Aman Bazar. | WD-UNR-CTG-FATIK-11/13 | 2.13 | 0.6 | BC | 72.91 | 1.2 | - | 10.16 | 16/01/11 | 1.125 | 0.625 | 10.16 | BC | 20/03/11 | M/S Noor Enterprise | 10.15 | 2011-05-05 | 26/11/11 RR31/12/12 | 100% | 10.15 | Termination
5 | Fatikchari | 415333010 | Bibirhat G.C to Harualchari Aman Bazar. | WD-UNR-CTG-FATIK-13/41 | [5 empty] | - | 40.62 |  |  |  | 40.62 | BC | 2013-02-12 | M/S Fine Bricks Manu. | 42.65 | 21/04/14 | 29/09/14 | 0%
| Fatikchari | 415333010 | Bibirhat G.C to Harualchari Aman Bazar (Harualchari Part) Road | [5 empty] | 0.5 |  | 23 | 22/07/14
6 | Fatikchari | 415333016 | Shantirhat Azadia Road Under pul Baktapur UP H/Q -Dharmapur UP H/Q Road(Santirhat-Azadibazar) | WD-UNR-CTG-FATIK-11/14 | 1.64 | 2.4 | BC | 88.23 | 1.5 | 3 | 39.86 | 16/01/11 | 1.64 | 2.4 | 39.86 | BC | 20/03/12 | M/S Nurul Islam Traders | 39.83 | 16/05/11 | 2012-05-06 | 65% | 39.83 | Termination R12/08/12
7 | Fatikchari | 415333016 | Baktapur UP H/Q -Dharmapur UP H/Q Road(Santirhat-Azadibazar) | WD-UNR-CTG-FATIK-13/33 | [6 empty] | 37.97 |  |  |  | 37.97 | BC | 2013-08-04 | M/S L M Traders | 41.76 | 2013-03-11 | 2014-01-04 | 0%
8 | Fatikchari | 415333014 | Const. of 3nosRCC Box Culvert on Lelang UP HQ to Charaliahat via Sannasihat | WD-UNR-CTG-FATIK-13/12 | 1 | 10 | BC | 83.52 |  | 10.2 | 40.53 | 16/01/11 |  | 10.2 | 35.49 | RCC | 21/03/13 | M/STokier Enterprise | 37.57 | 2011-05-04 | 25/04/12 | 0.5 | 5
9 | Fatikchari | 415333004 | Const. of 66.05m Long RCC Girder over Halda khal on Bhujpur U.P H/Q to Mirzerhat Road. | WD-UNR-CTG-FATIK-11/11 |  | 66.05 | ST | 241.91 |  | 66.05 | 184.5 |  |  | 66.05 | 184.5 | BRIDGE |  | M/S Regal Enterprise | 219.92 | 2011-09-08 | 30/08/12 RR30/09/13 | 95% | 219.79
9 | Fatikchari | 415333002 | Dantmara UP HQ –Balutila Bazar Via Ziltoli Bazar Road | WD-UNR-CTG-FATIK-14/43 | 1 |  | HBB | 33 | 1 |  | 30 | 2013-11-12 | 1.115 |  | 29.51 | HBB | 20/01/14 | M/S Haque Brothers & co. | 32.41 | 2014-07-05 | 17/10/14 | 0%
11 |  |  | Sub-Total |  | 14.34 | 194.2 |  | 1258.99 | 10.57 | 201.3 | 890.54 |  | 11.45 | 199.425 | 918.83 |  |  |  | 1071.48 |  |  |  | 653.22
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Physical Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Village Road
1 | Fatikchari | 415334110 | Hazrat Shah Ahmedullah Rd (Link Hazrat Shahan Shah Syed Ziaul Haque ( K) Maizbandari Internal Road) | WD-VZR-CTG-FATIK-10/04 | 0.8 |  | BC | 30.61 | 1 |  | 32.5 |  | 0.8 |  | 32.27 | BC | 2010-11-07 | M/S Elias Brother's | 30.65 | 15/9/10 | 28/1/11 R30/12/11 | 100% | 30.61 | F.Bill Paid
2 | Fatikchari | 415334112 | Bura Bebe - Azimnagar via Gohira Heako Road | WD-VZR-CTG-FATIK-10/08 | 0.75 | 1.2 | BC | 66.68 | 1 |  | 32.5 | 2010-04-08 | 0.754 | 1.2 | 32.23 | BC | 27/12/10 | M/S Salem & sons | 30.61 | 13/03/11 | 2012-03-04 | 100% | 20.34 | Termination
3 | Fatikchari | 415335043 | Al-Jameatul Islamiatul Obaidia Madrasha Complex Roasd(Consturction of RCC U-Drain & Box/Culvert) | WD-VZR-CTG-FATIK-10/09 |  | 21 | B/C | 60.67 |  |  | 27.04 | 2010-05-08 |  | 203 | 27.04 | ST | 17/01/11 | M/S Elias Brother's | 47.26 | 2011-09-03 | 29/03/11 R28/12/12 | 60% | 10.76
3 | Fatikchari |  | Al-Jameatul Islamiatul Obaidia Madrasha Complex Roasd(Consturction of RCC U-Drain & Box/Culvert) | WD-VZR-CTG-FATIK-13/40 | [6 empty] | 23.52 |  |  |  | 23.52 | ST | 2013-07-11
4 | Fatikchari | 415335170 415335085 | Rosanggiri UP (S.M Faruk) Road | WD-VZR-CTG-FATIK-10/06 | 0.52 | 3.9 | BC | 18.84 | 0.52 |  | 18.03 |  | 0.52 |  | 18.03 | BC | 30/09/10 | Dider Enterprise | 17.13 | 2010-12-12 | 25/12/11 R31/03/13 | 65% | 2.54
5 | Fatikchari | 415335135 | M.H. Chodhury road to Rafiqul Anowar Road (End point) via west Khiram to Mogkata. | WD-VZR-CTG-FATIK-10/07 | 2.02 | 15.3 | BC | 65.97 | 1 | 20 | 61.75 | 11/10/10 | 2.018 | 10.8 | 61.55 | HBB | 08/12/10 | M/S Siddique Trading | 59.97 | 2011-09-03 | 29/03/12 | 40% | 12.25 | Termination D.16/11/13
6 | Fatikchari | 415334009 | Fenua Tea girden road | WD-VZR-CTG-FATIK-10/09 | 0.7 | 1.2 | BC | 30.57 | 1 |  | 30.85 | 11/10/10 | 0.7 | 1.2 | 30.64 | BC | 06/02/11 | M/S Monir Ahamed | 29.1 | 2011-04-04 | 24/04/12 | 60% | 14.97
7 | Fatikchari | 415335137 415335144 | Barura para gram - Haidchari road | WD-VZR-CTG-FATIK-11/20 | 0.75 | 0 | HBB | 22.57 | 1 |  | 23.75 | 03/11/10 | 0.753 |  | 23.75 | HBB | 2011-02-11 | M/S S.I Enterprise | 22.56 | 29/01/12 | 19/08/12 R30/07/13 | 100% | 21.45
8 | Fatikchari | 415334042 | ABC Link Road (Mali Para Road ) | WD-VZR-CTG-FATIK-10/12 | 1.14 | 1.8 | BC | 55.33 | 1 | 5 | 9.9 | 03/11/10 | 1.14 | 1.8 | 9.58 | BC | 2011-06-02 | M/S Maun Ahamed | 9.58 | 2011-05-04 | 25/04/12 | 100% | 9.58 | Termination
8 | Fatikchari | 415334042 | ABC Link Road (Mali Para Road ) | WD-VZR-CTG-FATIK-13/38 | [6 empty] | 40.39 |  |  |  | 40.39 | BC | 2013-07-11 | M/S Ovijit Pal | 42.41
9 | Fatikchari | 415335042 | Rosanggiri Union to Wahadia Jami Mosque to Sobhan Mollah Bari road | WD-VZR-CTG-FATIK-10/08 | 1.95 | 3.3 | BC | 67.62 | 1 |  | 2.9 | 03/11/10 | 0.95 |  | 2.9 | BC |  | M/S Taiyab Enterprise | 23.67 | 2011-09-03 | 29/03/13 | 30% | 2.34 | Termination
| Fatikchari | 415335043 | Rosanggiri Union to Wahadia Jami Mosque to Sobhan Mollah Bari road | WD-VZR-CTG-FATIK-14/47 | [9 empty] | 0.6 | 32.83 | BC | 2014-11-06
10 | Fatikchari | 415335136 | Talukdar Bari Paca road to Cunnumiar Bari Road | WD-VZR-CTG-FATIK-11/11 | 0.48 | 1.2 | HBB | 10.36 | 0.5 |  | 12.5 | 22/11/10 | 0.48 | 0.6 | 12.5 | HBB |  | M/S Monir Ahamed | 11.87 | 2011-05-04 | 25/04/12 | 100% | 10.35 | F.Bill Paid
11 | Fatikchari | 415334015 | Santirhat Motor road (Master Yousuf Ahmed road) under Bakhtapur-Dharmapur & Nanupur union Parishad | WD-VZR-CTG-FATIK-11/16 | 1.6 | 0.6 | BC | 49.62 | 1 |  | 25.38 | 25/01/11 | 0.855 |  | 25.38 | BC | 20/09/11 | M/S Haque Brothers | 25.38 | 27/11/11 | 18/06/12 | 46% | 11.9 | Termination
11 | Fatikchari | 415334015 | Santirhat Motor road (Master Yousuf Ahmed road) under Bakhtapur-Dharmapur & Nanupur union Parishad | WD-VZR-CTG-FATIK-13/37 | [6 empty] | 19.21 |  | 0.855 |  | 19.21 | BC | 2013-07-11
12 | Fatikchari | 514335170 | Bir Mukti Joddha Chowdhury Jafarullah Road (Ch. 00-710m) | WD-VZR-CTG-FATIK-11/15 | 0.59 | 3.9 | BC | 19.57 | 0.71 |  | 18.96 | 22/02/11 | 0.59 | 3.9 | 18.78 | BC | 2011-05-04 | M/S Arif Enterprise | 17.78 | 27/07/11 | 17/02/12 | 20% |  | Termination
13 | Fatikchari | 415335134 | Nanupur bazar Khiram Road To Rahmat Bari(Dr.Mahmud Hasan Road). | WD-VZR-CTG-FATIK-11/17 | 0.85 | 3 | BC | 46.5 | 1 | 5 | 35 | 24/04/11 | 0.85 | 3.6 | 38.54 | BC | 20/09/11 | M/S Daimond Enterprise | 40.62 | 27/11/11 | 18/06/12 | 60% | 17.99 | Termination
14 | Fatikchari | 415335187 | Badshamia Chowdhury Road(Barajali Badamtola To Kanchannnagar Rubber Bagan Conneting Road) | WD-VZR-CTG-FATIK-11/18 | 0.75 | 3 | BC | 35.19 | 1 |  | 32 | 24/04/12 | 0.75 | 3 | 31.98 | BC | 16/05/12 | M/Sayub Khan Azad | 31.98 | 27/07/11 | 17/02/12 R31/07/12 | 20% | 7.27 | Termination
15 | Fatikchari | 415335042 | Roshangri U.P Wahadia Jame Mosque To Subhan Mollah Bari Road | WD-VZR-CTG-FATIK-10/08 | 1.95 | 3.3 | BC | 67.62 | 0.95 | - | 2.9 |  | 0.95 |  | 2.9 | BC |  | M/S Tayab Enterprise | 23.67 | 2011-09-03 | 29/03/12 | 30% |  | Termination
| Fatikchari | 415335042 | Roshangri U.P Wahadia Jame Mosque To Subhan Mollah Bari Road(Remaining Work) | WD-VZR-CTG-FATIK-14/ | [10 empty] | 37.74
16 | Fatikchari | 415334011 415335187 | Lelang-Kanconnagar Road. | WD-VZR-CTG-FATIK-11/19 | 1.87 |  | HBB | 49.98 | 2 | - | 50 | 2011-01-08 | 1.86 |  | 50 | HBB | 24/08/11 | M/S Haque Brothers & co. | 49.97 | 27/11/11 | 18/06/12 | 100% | 50
17 | Fatikchari | 415335059 | Nanupur Tajul Islam Road. | WD-VZR-CTG-FATIK-13/22 | 1.55 | 2.4 | HBB | 47.16 | 1.5 |  | 40 | 28/09/11 | 1.55 | 2.4 | 43.23 | HBB | 2013-07-11 | M/S Nurul Ialam Trad | 45.4 | 26/02/12 | 18/09/12 | 0% |  | Termination
18 | Fatikchari | 415335112 | Hazi Saleh Ahammed road. | WD-VZR-CTG-FATIK-13/21 | 1.5 | 1.8 | HBB | 35.52 | 1 |  | 30 | 28/09/12 | 1.5 | 1.8 | 32.24 | HBB | 2013-07-11 | [6 empty] | Termination
19 | Fatikchari | 415334031 | Ramgor Section-1(5 Vent Regulator)To Badyarhat Via East Suabil Brammanhat Road | WD-VZR-CTG-FATIK-11/23 | 1.78 |  | BC | 61.47 | 1 |  | 30 | 28/09/13 | 0.78 |  | 29.74 | BC | 15/01/12 | M/S M Islam Brothers. | 35.69 | 30/10/12 | 20/05/13 | 100% | 25.43
20 | Fatikchari | 415334032 | Paindong Karan Sikdar Road. | WD-VZR-CTG-FATIK-12/25 | 0.14 | 7 | HBB | 20.76 |  | 8 | 16 | 28/09/14 | 0.136 | 8.2 | 15.45 | HBB | 28/03/12 | M/S M Islam Brothers. | 19.77 | 23/04/14 | 14/11/13 | 100% | 8.77
21 | Fatikchari | 415334025 | Gamaritola Road . | WD-VZR-CTG-FATIK-12/30 | 3.5 | 1.2 | HBB | 58.96 | 1 | 5 | 42.5 | 27/10/11 | 3.5 | 1.2 | 56.14 | HBB | 2012-08-12 | M/S Nurul Islam Tra. | 59.23 | 18/02/14 | 27/07/14 | 80%
22 | Fatikchari | 415334010 | East Forhadabad to Hazrat Matiur Rahman Shsh Magar (Abul Hossain Shah Road.). | WD-VZR-CTG-FATIK-12/24 | 0.85 | 7 | BC | 31.53 | 0.85 |  | 25 | 2011-04-12 | 0.85 |  | 24.02 | BC | 2012-04-03 | M/S Lacky Enterprise | 30.03 | 41610 | 41403 | 100% | 16.35
23 | Fatikchari | 415335270 | Mohammad Towkirhat -Isapur Via Mokbuler Baperhat road. | WD-VZR-CTG-FATIK-12/29 | 0.78 | 9 | HBB | 40.9 | 1.5 |  | 40 | 2011-04-12 | 0.782 | 9 | 38.95 | HBB | 28/03/12 | M/S Laky Enterprise | 42.46 | 18/02/14 | 27/09/14 | 0%
24 | Fatikchari | 415335108 | Shsh Golamur Rahman Road(Maizbhander-Charaliahat-Pathan Para )Road. | WD-VZR-CTG-FATIK-12/26 | 0.83 | 4 | HBB | 27.2 | 1 |  | 25 | 14/02/12 | 0.834 | 4 | 24.73 | HBB | 2012-05-04
25 | Fatikchari | 415334043 | Baktapur Sonagazi Road. | WD-VZR-CTG-FATIK-12/27 | 0.87 | 3 | HBB | 31.03 | 1 |  | 25 | 14/02/12 | 0.869 | 3.5 | 24.83 | HBB | 2012-05-04 | M/S Jam Jam Enterprise | 29.54 | 2012-09-12 | 30/06/13 | 0%
26 | Fatikchari | 415335272 | Gahira-Heakow Road-Dharmapur Center Road ViaJojbari,Kanabari,Gajibari,Abidbari road. | WD-VZR-CTG-FATIK-12/28 | 0.89 | 3 | HBB | 31.26 | 1 |  | 25 | 14/02/12 | 0.893 | 3 | 24.8 | HBB | 2012-05-04 | M/S R.M Enterprise | 29.77 | 2012-09-12 | 30/06/13 | 100% | 25.85
27 | Fatikchari | 415335190 | Malek Saha Via Setkua Para Road By HBB | WD-VZR-CTG-FATIK-13/31 | 1.38 | 1.2 | HBB | 36.62 | 1 |  | 35 | 20/12/12 |  | 1.2 | 33.29 | HBB | 13/03/13 | M/S Fain Bricks Manufacture | 36.62 | 2013-03-11 | 2014-01-04 | 60% | 26.77
28 | Fatikchari | 415335200 | Khan Mohammad Para Road By HBB. | WD-VZR-CTG-FATIK-13/32 | 1.05 | 3.6 | HBB | 29.82 | 1 |  | 35 | 20/12/12 |  | 3.6 | 27.11 | HBB | 13/03/13 | M/S Fain Bricks Manufacture | 32.49 | 2013-03-11 | 2014-01-04 | 60%
29 | Fatikchari | 415334113 | Tofail Ahamed Chowdhury Road | WD-VZR-CTG-FATIK-13/34 | 1 | 0.9 | HBB | 29.26 | 1 |  | 26.6 | 20/12/12 | 1 |  | 26.6 | HBB | 2013-08-04 | M/S Alif Enterprise | 29.26 | 2013-03-11 | 2013-01-04 | 80% | 0
30 | Fatikchari | 415334035 | Al-Haj Rafiqual Anower Road . | WD-VZR-CTG-FATIK-13/35 | 1.25 | 3.9 | HBB | 46.48 | 1.25 |  | 42.25 |  | 1.25 |  | 42.25 | HBB | 30/06/13 | M/S Nurul Islam Traders | 46.57 | 2013-03-11 | 2014-01-04 | 100% | 30.69
31 | Fatikchari | 415335158 | Purbo Nanupur (Dalkata) Morhum Hazi Korban Ali Mistry Road | WD-VZR-CTG-FATIK-14/42 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.643 | 3.5 | 24.67 | HBB | 20/01/14 | M/S Nurul Islam Tra.. | 26.96 | 2014-07-05 | 17/10/14 | 0%
32 | Fatikchari | 415335290 | Dantmara Santir Hat Rotnopur Road | WD-VZR-CTG-FATIK-14/44 | 1 |  | HBB | 33 | 1 |  | 30 | 2013-11-12 | 0.98 |  | 25.43 | HBB | 20/01/14 | M/S Haque Brothers & co. | 27.93 | 2014-07-05 | 17/10/14 | 60%
33 | Fatikchari | 415335292 415333002 | Datamara Balutila via ziltoly Bazar Road | WD-VZR-CTG-FATIK-14/48 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.835 |  | 25 | HBB | 23/07/14
34 | Fatikchari | 415335275 | Datmara Kanchana Nischinta Road | WD-VZR-CTG-FATIK-14/45 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.876 |  | 25 | HBB | 2014-11-06
35 | Fatikchari | 415335156 | Halda Velly Tea State Road | WD-VZR-CTG-FATIK-14/46 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.835 |  | 25 | HBB | 2014-11-06 | [6 empty] | F 2012-2013
35 |  |  | Sub - Total |  | 39.09 | 110.7 |  | 1370.67 | 33.78 | 43 | 1067.43 |  | 32.938 | 271.1 | 1140.24 |  |  |  | 1005.93 |  |  |  | 356.21
44 |  |  | Total |  | 53.43 | 304.9 | 0 | 2629.66 | 44.35 | 244.3 | 1957.97 |  | 44.388 | 470.525 | 2059.07 |  |  |  | 2077.41 |  |  |  | 1009.43
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Raozan | 415743001 | Anderson Road and Link Purba Aburkhil Jara Kallan Primary School & Mira para Repon Dr. House road 1780-3587 & 00-450 | WD-UNR-CTG-RAOZA-10/05 | 3 | 10 | BC | 151 | 1.5 | 10 | 88 |  | 1.807 |  | 84.86 | BC | 29/06/10 | Tanshi Associates | 84.84 | 16/8/10 | 29/2/11 R30/06/11 | 100% | 71.78
2 | Raozan | 415743004 | Hajrat Moulana Md. Shah Road 1590-3274 | WD-UNR-CTG-RAOZA-10/01 | 1.23 | 4 | BC | 61.66 | 1.23 | 4 | 61.66 |  | 1.685 |  | 57.4 | BC | 29/04/10 | Desh Unnyan | 57.07 | 21/7/10 | 4/12/2010 RR17/01/12 | 35% | 11.68
3 | Raozan | 415743005 | Ray Khishory road | WD-UNR-CTG-RAOZA-10/04 | 2 | 7.96 | BC | 103.9 | 1 | 7.96 | 61.9 |  | 2 | 7.96 | 61.19 | HBB | 24/05/10 | N.Z Associates | 61.18 | 16/8/10 | 29/2/11 | 60% | 35.38
4 | Raozan | 415743006 | Holadia Village road | WD-UNR-CTG-RAOZA-10/08 | 2 | 10 | BC | 109 | 1 | 10 | 67 |  | 1.87 | 3 | 59.61 | HBB | 2010-12-08 | N.Z Associates | 59.61 | 16/8/10 | 28/2/11 R11/05// | 100% | 57.5 | FinalBillPaid
5 | Raozan | 415743006 | Holadia Village road | WD-UNR-CTG-RAOZA-13/163 |  |  |  |  | 1 |  | 14.6 | 2013-05-12
6 | Raozan | 415743010 | Ander Manik D.C (Chitta Rangan Chow. road & Natun bazar to Kadalpur road) road | WD-UNR-CTG-RAOZA-10/11 | 3 | 30 | BC | 201 | 3 | 30 | 201 |  | 2.96 | 6 | 159.11 | BC | 22/08/10 | M/S Tanshi Associates | 159 | 2010-06-09 | 29/08/11 RRR30/12/13 | 45% | 47.05 | RE-Cast
7 | Raozan | DO | Contruction Of 20m Long RCC G.B | WD-UNR-CTG-RAOZA-10/30 | [9 empty] | 20 | 84.79 |  | 40696 | M/S Tanshi Associates | 89.85 | 2011-09-03 | 29/03/12 | 75% |  | Reveised 22/07/14
8 | Raozan | 415743014 | Urkirchar road (Muduna ghat to Kalifar ghona)800-2700 | WD-UNR-CTG-RAOZA-10/02 | 4 | 65 | BC | 330.5 | 2.6 | - | 109.2 |  | 4 |  | 100.25 | BC | 24/05/10 | Rabeya Enterprise | 100.24 | 16/8/10 | 29/8/11 R30/06/13 | 60% | 34.41
9 | Raozan | 415743002 | Akbar Shah Road | WD-UNR-CTG-RAOZA-10/17 | 2 | 10 | BC | 109 | 0.95 |  | 20 | 21/07/10 | 0.595 |  | 16.01 | HBB | 27/09/10 | Azmir Enterprise | 15.97 | 2010-12-12 | 25/12/11 | 100% | 15.96 | FinalBillPaid
10 | Raozan | 415743002 | Akbar Shah Road | WD-UNR-CTG-RAOZA-13/162 |  |  |  |  | 1 |  | 14 | 2013-05-12
11 | Raozan | 415743008 | Kachukhine Nowapara road 1400-2940 | WD-UNR-CTG-RAOZA-10/16 | 2 | 8.2 | BC | 104.5 | 1.54 | 0.9 | 90 | 21/07/10 | 1.54 | 0.9 | 59.14 | HBB | 27/09/10 | Bhai Bhai Construction | 59.13 | 2010-12-12 | 25/12/11 R310/05/13 | 20% | 5.19
12 | Raozan | GC | Bazar Shed At gohira Chowrasta Bazar. | WD-UNR-CTG-RAOZA-11/65 | [6 empty] | 12 | 27/12/10 |  |  | 11.99 |  | 19/04/11 | M/S J A Enterprise | 11.99 | 2011-07-06 | 28/12/11 | 100% | 11.99 | F/B Pament
13 | Raozan | GC | Lambur Hat Growth Center ,Market Shed&Cnnect.Road. | WD-UNR-CTG-RAOZA-11/66 |  |  |  | 30 |  |  | 18 | 27/10/11 |  |  | 18 |  | 27/10/11 | M/S S A B B Traders | 17.9 | 31/01/12 | 21/06/12
14 | Raozan | GC | Pahartali Gouri Shankar Hat | WD-UNR-CTG-RAOZA-12/152 | [6 empty] | 29.1 | 2012-01-10 |  |  | 29.1 | GC | 2012-01-10
15 | Raozan | GC | West Chikdair Kalachanda Hat | WD-UNR-CTG-RAOZA-12/153 | [6 empty] | 16.16 | 2012-01-10 |  |  | 16.16 | GC | 2012-01-10
16 | Raozan | GC | East Guzara Ander Manik Nutan Bazar Shed. | WD-UNR-CTG-RAOZA-12/154 |  | Not in DPP |  |  |  |  | 12.75 | 2012-01-10 |  |  | 12.75 | GC | 2012-01-10
17 | Raozan | GC | Dabua Jagannath Hat | WD-UNR-CTG-RAOZA-12/155 | [6 empty] | 5.89 | 2012-01-10 |  |  | 5.89 | GC | 2012-01-10
18 | Raozan | GC | Urkirchar Bazar | WD-UNR-CTG-RAOZA-12/156 | [6 empty] | 8.22 |  |  |  | 8.22 | GC | 18/11/12
19 | Raozan | GC | Purba Guzra Olimia Hat | WD-UNR-CTG-RAOZA-12/157 | [6 empty] | 9.47 |  |  |  | 9.47 | GC | 18/11/12
20 | Raozan | GC | Pachim Guzara Ragunandan Hat | WD-UNR-CTG-RAOZA-12/158 | [6 empty] | 6.59 |  |  |  | 6.59 | GC | 18/11/12
21 | Raozan | GC | Kadalpur Eishan Batta Hat | WD-UNR-CTG-RAOZA-12/159 | [6 empty] | 7.83 |  |  |  | 7.83 | GC | 18/11/12
22 | Raozan | 415743013 | Dharbari -Darga Road & Guide Wall. | WD-UNR-CTG-RAOZA-11/29 |  |  |  |  | 0.19 |  | 5.03 | 13/03/11 | 0.19 |  | 5.03 | HBB | 24/03/11 | M/S Runa Traders | 5.02 | 2011-08-05 | 29/11/11 | 100%
23 | Raozan | 415743010 | Kadalpur To Ray Chand Para Road. | WD-UNR-CTG-RAOZA-12/107 |  | Not in DPP |  |  | 1 |  | 22.57 | 20/02/12 | 1 |  | 22.57 | HBB | 20/02/12 | M/S GO Saha Metal | 21.75 |  |  | 100%
24 | Raozan | 415743008 | Uttor Kachukhain Inna Minna Road. | WD-UNR-CTG-RAOZA-12/129 |  | Not in DPP |  |  | 0.5 |  |  | 20/02/12 | 0.5 |  | 9.47 | HBB | 20/02/12
25 | Raozan | 415743012 | Gohira Parankrishno mohazon Road | WD-UNR-CTG-RAOZA-13/ | 0.5 |  | BC | 20 | 0.5 |  | 20 | 2013-05-12
26 | Raozan | 415743010 | Purbo Guzra Natun Bazar-Mongal khali Road | WD-UNR-CTG-RAOZA-13/ | 0.1 |  | HBB | 5 | 0.1 |  | 5 | 2013-05-12
27 | Raozan | 415743014 | Urkirchar Sharupa Nanda Road, Shadhu Mandir Road, MJinagazi Bridge Approach, Tegher Matha Road | WD-UNR-CTG-RAOZA-13/ | 0.1 |  | HBB | 5 | 0.1 |  | 26 | 2013-05-12
27 |  |  | Sub-Total |  | 19.93 | 145.16 |  | 1230.56 | 17.21 | 62.86 | 931.97 |  | 18.147 | 37.86 | 845.43 |  |  |  | 743.55 |  |  |  | 290.94
1 | Raozan | 415745210 415744085 | Moulana Dhiraj uddin road (Nona Hazi bari to Shuad alolia bari) 00-2255 | WD-VZR-CTG-RAOZA-10/08 | 1.5 | 4 | BC | 56.75 | 2.25 |  | 48.75 |  | 2.25 | 1.3 | 48.65 | BC | 2010-01-08 | M/S Munna Enterprise | 48.74 | 16/8/10 | 29/2/11 | 100% | 42.72
2 | Raozan | 415744092 415744039 | Jamuine Kagatia road (Banijuri Jamuine Road)00-1809 | WD-VZR-CTG-RAOZA-10/07 | 1 | 5 | BC | 42.5 | 1 |  | 32.5 |  | 1.75 |  | 32.49 | BC | 2010-01-08 | M/S M.A. Traders | 32.49 | 16/8/10 | 29/2/11 R30/08/12 | 50% | 16.13
3 | Raozan | 415744094 415745152 | Chickdair-Noajishpur road 00-1200 | WD-VZR-CTG-RAOZA-10/06 | 1.2 | 2 | BC | 43 | 1.2 |  | 39 |  | 1.2 |  | 38.7 | BC | 11/07/10 | Chowdhury Enterprise | 38.7 | 16/8/10 | 29/2/11 R30/12/11 | 100% | 38.66 | FinalBillPaid
4 | Raozan | 415744097 | (Link) Abdul karim road (Uttar Sharta Damdama Madrasha, Durgachain and shide manan road | WD-VZR-CTG-RAOZA-10/03 | 1 | 5 | BC | 42.5 | 1 | 5 | 32.5 |  | 1 | 5 | 32.5 | BC | 24/05/10 | S.M Trading | 32.49 | 16/8/10 | 29/2/11 | 100% | 32.24 | FinalBillPaid
5 | Raozan | 415744098 4157145173 | Maliek Munshi road 00-1250 | WD-VZR-CTG-RAOZA-10/09 | 1 | 4.8 | BC | 42.1 | 1 | 4.8 | 42.1 |  | 1.25 | 3 | 34.94 | HBB | 2010-12-08 | N.S Enterprise | 34.93 | 2010-10-10 | 23/10/11 R30/06/12 | 27% | 9.07
6 | Raozan | 415744100 4157145211 | Sam Pandit road 00-1050 | WD-VZR-CTG-RAOZA-10/10 | 1 | 3 | BC | 38.5 | 1 | 3 | 38.5 |  | 1.05 | 2 | 31.61 | HBB | 2010-12-08 | Saima Tithi Enterprise | 31.6 | 2010-10-10 | 23/10/11 RR30/06/13 | 40% | 8.5
7 | Raozan | 415744103 415745265 | Lal Mia tendal road | WD-VZR-CTG-RAOZA-10/23 | 1 | 3 | BC | 38.5 | 1.976 | 1.3 | 50 | 16/08/10 | 1.976 | 1.3 | 45.55 | HBB | 2010-04-10 | Bhai Bhai Construction | 45.54 | 2010-12-12 | 25/12/10 R30/06/13 | 70% | 29.77
8 | Raozan | 415744039 415745040 | Ali Khil Dout Khola road | WD-VZR-CTG-RAOZA-10/20 |  |  |  |  | 0.514 |  | 10 | 16/08/10 | 0.514 |  | 10 | HBB | 28/09/10 | Kashem Enterprise | 9.98 | 2010-12-12 | 25/12/11 | 100% | 9.91 | FinalBillPaid
9 | Raozan | 415745018 | Chickdair Shama Chran road | WD-VZR-CTG-RAOZA-10/19 |  |  |  |  | 1.1 | 1.3 | 30 | 16/08/10 | 1.1 | 1.3 | 27.37 | HBB | 28/09/10 | Anma Traders | 27.2 | 2010-12-12 | 25/12/11 | 100% | 26.98 | FinalBillPaid
10 | Raozan | 415744082 | Kabir Ahamed Taluckder road | WD-VZR-CTG-RAOZA-10/18 |  |  | not dpp |  | 1 |  | 40 | 16/08/10 | 1 |  | 39.49 | BC | 28/09/10 | Atik Trasers | 39.48 | 2010-12-12 | 25/12/11 | 100% | 39.43 | FinalBillPaid
11 | Raozan | 415745077 | West Gohira Ismail road | WD-VZR-CTG-RAOZA-10/21 |  |  |  |  | 0.975 | 3 | 40 | 16/08/10 | 0.975 | 3 | 37.91 | BC | 28/09/10 | M/S Zilani Traders | 37.88 | 2010-12-12 | 25/12/11 R30/05/12 | 40% | 5.55
12 | Raozan | 415745309 415745464 | Iqbal road | WD-VZR-CTG-RAOZA-10/24 |  |  |  |  | 1.27 | 1.3 | 40 | 16/08/10 | 1.27 | 1.3 | 39.44 | BC | 2010-04-10 | Hali FakirTraders | 39.49 | 2010-12-12 | 25/12/11 20/02/13 | 100% | 16.75
13 | Raozan | 415743015 415744062 | Abdul Mannan & FatheNager Road | WD-VZR-CTG-RAOZA-13/12 | 1.5 | 3 | BC | 70.5 | 1.1 |  | 27.97 | 14/07/13 | 1.1 |  | 27.97 | HBB | 14/07/13 | M/S Chowdhury Ent. | 29.36
14 | Raozan | 415743012 415744087 | Hafez bazuir Rahman road to Mohamani high School road 00-1460 | WD-VZR-CTG-RAOZA-10/13 | 2 | 8 | BC | 104 | 1.4 | 6.5 | 100 | 21/07/10 | 1.4 | 6.5 | 67.37 | BC | 2010-05-09 | Tanshi Associates | 67.36 | 2010-12-12 | 25/4/11 RR30/04/12 | 60% | 36.41
15 | Raozan | 415743013 415744011 | Kadalpur Parir Dighir par Poschim Barua para Sason to Sudmandir behor road | WD-VZR-CTG-RAOZA-10/14 | 2 | 4 | BC | 94 | 2.93 | 22.8 | 100.75 | 21/07/10 | 2.93 | 22.8 | 99.08 | BC | 2010-05-09 | Tanshi Associates | 99.02 | 2010-12-12 | 25/4/11 | 10%
16 | Raozan | 415743011 415744055 | Rawli DB road (Nutan Rughy nandan ro purbo dika Agrosar mondir) | WD-VZR-CTG-RAOZA-10/15 | 2 | 6 | BC | 99 | 3.768 | 14.5 | 160 | 21/07/10 | 3.768 | 14.5 | 154.13 | HBB | 27/09/10 | Tanshi Associates | 153.12 | 2010-12-12 | 25/12/11 | 50% | 52.88
17 | Raozan | 415744006 | Quran Monjil Road | WD-VZR-CTG-RAOZA-10/22 | Not in DPP |  |  |  | 1.9 |  | 37.03 |  | 1.9 |  | 37.03 | HBB | 30/09/10 | Zahanara Enterprise | 37.02 | 2010-12-12 | 25/12/11 | 100% | 31.24 | FinalBillPaid
18 | Raozan | 415744088 | Pahartali Mohamoni Mandir Road | WD-VZR-CTG-RAOZA-10/25 | Not in DPP |  |  |  | 0.856 | 0.9 |  |  | 0.856 | 0.9 | 32.62 | BC | 31/10/10 | Tanshi Associates | 32.61 | 25/01/11 | 15/2/12 | 60% | 11.6
19 | Raozan | 415745170 | Fatehnagar-Barua Parai road | WD-VZR-CTG-RAOZA-10/26 | Not in DPP |  |  |  | 0.715 |  | 18.18 | 14/07/13 | 0.715 |  | 18.18 | HBB | 14/07/13 | M/S Chowdhury Ent. | 19.09
20 | Raozan | 415745473 | Barua Para Road | WD-VZR-CTG-RAOZA-10/27 | Not in DPP |  |  |  | 0.316 |  |  |  | 0.316 |  | 6.14 | HBB | 31/10/10 | Shah Amanat | 6.14 | 18/1/11 | 1/2/2012 R25/08/12 | 100%
21 | Raozan | 415744114 | Shekh Para School-Shekh Para Mosjid Road | WD-VZR-CTG-RAOZA-11/47 | 1 |  | HBB | 25 | 1 |  | 23.75 | 16/01/11 | 0.734 |  | 19.02 | BC | 2011-05-04 | M/S A.H Enterprise | 19.02 | 27/07/11 | 17/02/12
22 | Raozan | 415745484 | Bagoan Chowdari bari road . | WD-VZR-CTG-RAOZA-11/46 | Not in DPP | [5 empty] | 10.15 | 15/02/11 | 0.33 |  | 10 | HBB | 2011-05-04 | M/S Arpon Construction | 9.99 | 2011-07-06 | 28/12/11 | 100%
23 | Raozan | 415744102 415745022 | Kodalpur Student Road in Kodalpur Union | WD-VZR-CTG-RAOZA-11/45 | 1 | 3 | BC | 38.5 | 1 |  | 30 | 15/02/11 | 1.212 | 3 | 29.99 | HBB | 2011-05-04 | M/S United Building | 29.99 | 2011-07-07 | 28/12/11 RR30/09/13 | 10%
24 | Raozan | 415745649 | 3x3x2.44m RCC Box Culvert On Romjan Ali Road | WD-UNR-CTG-RAOZA-11/44 |  | 9 | B | 6.37 |  | 3 | 6.49 | 13/03/11 |  | 9 | 6.49 |  | 24/03/11 | M/S Baized Corporation | 6.48 | 15/05/11 | 2011-05-12 | 100%
25 | Raozan | 415745638 | Gahira College road to gard wall (HBB) | WD-UNR-CTG-RAOZA-11/30 | 0.94 |  | BC | 5.01 | 0.94 |  | 4.99 | 13/03/11 | 0.94 |  | 4.99 | CC | 24/03/11 | M/S Runu Traders | 5 | 2011-08-05 | 29/11/11 | 100% | 5
26 | Raozan | 415744078 415745645 | Ichapur Road & Guard Wall And Saukat Bari Road & Guard Wall. | WD-UNR-CTG-RAOZA-11/31 | 0.17 |  | HBB | 5.54 | 0.17 |  | 5.54 | 13/03/11 | 0.17 |  | 5.55 | HBB | 24/03/11 | M/S Fabiha Enterprise | 5.53 | 2011-08-05 | 29/11/11 R07/06/12 | 100%
27 | Raozan | 415745647 | Gahira A.N.J.Y High School road to gard wall (HBB) | WD-UNR-CTG-RAOZA-11/32 |  |  |  |  | 0.15 |  | 9.99 | 13/03/11 | 0.15 |  | 9.99 | CC | 24/03/11 | M/S Anma Traders | 9.99 | 2011-08-06 | 29/11/11 | 70% | 2.9
28 | Raozan | 415745658 415745659 | Gahira Box Ali Chowdari bari to Iqbal bari road to gard wall | WD-UNR-CTG-RAOZA-11/33 |  |  |  |  | 0.191 |  | 12.36 | 13/03/11 | 0.191 |  | 12.36 | HBB | 24/03/11 | M/S Anma Traders | 12.36 | 2011-08-07 | 29/11/11 R15/04/12 | 70%
29 | Raozan | 415745652 | Binajuri Haripad Sharani Govt. Parimary school road to Lelengara connectin road (HBB) | WD-UNR-CTG-RAOZA-11/34 |  |  |  |  | 0.237 |  | 4.95 | 13/03/11 | 0.237 |  | 4.95 | HBB | 24/03/11 | M/S J,N. Enterprise | 4.94 | 15/05/11 | 2011-05-11 | 100%
30 | Raozan | 4157456401 | Raozan College road to grad wall (HBB) | WD-UNR-CTG-RAOZA-11/35 |  |  |  |  | 0.95 |  | 5.99 | 13/03/11 | 0.95 |  | 5.99 | HBB | 24/03/11 | M/S Runo Traders | 5.98 | 15/05/11 | 2011-05-11 | 100% | 5.98 | FinalBillPaid
31 | Raozan | 415745644 | Moulana Afzal road to grad wall (HBB) | WD-UNR-CTG-RAOZA-11/36 |  |  |  |  | 0.167 |  | 5.07 | 13/03/11 | 0.167 |  | 5.07 | HBB | 24/03/11 | M/S Shah Amanat Ent. | 5.05 | 15/05/11 | 2011-05-11 | 100% | 2.74
32 | Raozan | 415745657 | Raozan High School road to grad wall (HBB) | WD-UNR-CTG-RAOZA-11/37 |  |  |  |  | 0.94 |  | 4.99 | 13/03/11 | 0.94 |  | 4.99 | CC | 24/03/11 | M/S Runo Traders | 4.99 | 15/05/11 | 2011-05-15 | 100% | 4.99 | FinalBillPaid
33 | Raozan | 415745654 | Raozan Chad mia road to Gusho gramme road | WD-UNR-CTG-RAOZA-11/38 |  |  |  |  | 0.6 |  | 10.23 | 13/03/11 | 0.6 |  | 10.23 | HBB | 24/03/11 | M/S J,N. Enterprise | 10.22 | 15/05/11 | 2011-05-11 | 100% | 10.19 | FinalBillPaid
34 | Raozan | 415745054 | Sultanpur Banikpara road (HBB) | WD-UNR-CTG-RAOZA-11/39 |  |  |  |  | 0.767 |  | 15 | 13/03/11 | 0.767 |  | 14.93 | HBB | 18/12/11 | M/S Chowdhury Ent. | 17.83 | 2012-12-03 | 2012-02-11
35 | Raozan | 415745655 | Kadalpur Basir mahammad road to gird wall (HBB) | WD-UNR-CTG-RAOZA-11/40 |  |  |  |  | 0.3 |  | 8.19 | 13/03/11 | 0.3 |  | 8.19 | HBB | 24/03/11 | M/S United Builders. | 8.17 | 15/05/11 | 2011-05-12 | 100% | 3
36 | Raozan | 415745660 | Pahartali Emam Garjali college road to gird wall (HBB) | WD-UNR-CTG-RAOZA-11/41 |  |  |  |  | 0.122 |  | 5.97 | 13/03/11 | 0.122 |  | 5.97 | HBB | 24/03/11 | M/S Sonali Traders | 5.97 | 15/05/11 | 2011-05-11 | 100% | 4
37 | Raozan | 415745106 | Ukhir char Aburkhil Amitar high school road to gird wall (HBB) | WD-UNR-CTG-RAOZA-11/42 |  |  |  |  | 0.105 |  | 10.49 | 13/03/11 | 0.105 |  | 10.49 | HBB | 24/03/11 | M/S Tansi Associates | 10.48 | 15/05/11 | 5/14/2011 R15/07/13 | 0%
38 | Raozan | 415745643 415745669 415745662 | Noapara Govt.parimary school road gird wall (HBB) & Noapara college road to gird wall (HBB) & Noapara High school road to gird wall (HBB) | WD-UNR-CTG-RAOZA-11/43 |  |  |  |  | 0.255 |  | 12.99 | 13/03/11 | 0.255 |  | 12.99 | HBB | 24/03/11 | M/S bhai Bhai Construction | 12.96 | 15/05/11 | 2011-05-11
39 | Raozan |  | 12m Long Bridge on South Gahira Ashraf Ali Sarang Bari Road | WD-UNR-CTG-RAOZA-11/58 | [5 empty] | 12 | 9.04 | 13/03/11 |  | 12 | 9.4 | RCC | 2011-03-04 | M/S.S.M.Trading | 9.39 | 18/05/11 | 2011-08-10 | 0%
40 | Raozan | 415745650 | 10m Long RCC Bridge On Samsar Nagar Tila Road. | WD-UNR-CTG-RAOZA-11/62 | [5 empty] | 7.9 | 7.9 | 13/03/11 |  | 10 | 7.9 | RCC | 2011-03-05 | M/S.Baizad Corporation | 7.9 | 18/05/11 | 2011-08-11 | 45%
41 | Raozan | 415745656 415745663 | 2mx2mx2.26m Long RCC Box culvert OnRashider Para Kewtila Para Road & Jaldas Para Road & Retaining Wall | WD-UNR-CTG-RAOZA-11/63 |  | Not in DPP |  |  | 0.1 | 2 | 8.18 | 13/03/11 | 0.1 |  | 8.18 | HBB | 2011-03-06 | M/S.Riyadh Trade Com. | 8.18 | 18/05/11 | 8/12/11 R30/05/13 | 60%
42 | Raozan | 415745098 | Tonar Para,Bura Thakur Para Seba Sharam & Chitapara kali Mondir Road. | WD-UNR-CTG-RAOZA-11/64 |  |  |  |  | 0.585 |  | 9.42 | 13/03/11 | 0.585 |  | 9.42 | BC & HBB | 2011-03-07 | M/S.Baizad Corporation | 9.42 | 18/05/11 | 8/13/2011 RR25/08/13 | 0%
43 | Raozan | 415745098 | 2mx2mx4.26m Long RCC Box Culvert On Sultanpur Sattarpara cnnecting Road | WD-UNR-CTG-RAOZA-11/57 | [5 empty] | 2 | 3.24 | 13/03/11 |  | 4 | 3.24 |  | 2011-03-04 | M/S.Baizad Corporation | 3.24 | 18/05/11 | 8/14/2011 R20/09/13 | 0%
44 | Raozan |  | West Guzara Ismail Road. | WD-UNR-CTG-RAOZA-11/60 |  |  |  |  | 0.62 |  | 10.86 | 13/03/11 | 0.62 |  | 10.86 | HBB | 2011-03-05 | M/S.Saima Tithi | 10.86 | 18/05/11 | 8/15/2011 R30/07/12 | 80%
45 | Raozan | 415745611 415745612 | Baguna Fousdarpara Road & Sahid Muktijuddha Ezahar Road | WD-VZR-CTG-RAOZA-11/59 |  |  |  |  | 0.6 |  | 8.82 | 13/03/11 | 0.6 |  | 8.83 | Hbb | 2011-03-04 | M/S.Arpan Construction | 8.8 | 18/05/11 | 2011-08-16 | 100% | 4.84
46 | Raozan | 415745642 415744007 | Dabua - Girls Highool Road & Guard Wall And Dabura Amir Chowdhury Road. | WD-VZR-CTG-RAOZA-11/48 |  |  |  |  | 0.42 |  | 7.48 | 13/03/11 | 0.42 |  | 7.48 | HBB | 2011-03-04 | M/S. Master Traders | 7.44 | 18/05/11 | 8/17/2011 R30/06/12 | 85%
47 | Raozan | 415745646 415745651 | Chickdair Sonali Hechari road to grad wall | WD-VZR-CTG-RAOZA-11/61 |  |  |  |  | 0.119 |  | 5.97 | 13/03/11 | 0.119 |  | 5.97 | HBB | 2011-03-05 | M/S. Shah Amanat Ent. | 5.97 | 18/05/11 | 2011-08-18 | 100% | 3.28
48 | Raozan | 415745639 | Gahira girls High School road to grad wall (HBB) | WD-VZR-CTG-RAOZA-11/49 |  |  |  |  | 0.185 |  | 7.99 | 13/03/11 | 0.185 |  | 7.99 | BC | 2011-03-04 | M/S. Fabiha Enterpriset. | 7.98 | 18/05/11 | 8/19/2011R25/12/12 | 70%
49 | Raozan | 41574 | Gahira Kotoalighona magem bari road to gard wall | WD-VZR-CTG-RAOZA-11/50 |  |  |  |  | 0.125 |  | 6.01 | 13/03/11 | 0.125 |  | 6.01 | HBB | 2011-03-05 | M/S. Fabiha Enterpriset. | 6 | 18/05/11 | 2011-08-20 | 100%
50 | Raozan | 415745671 | Gahira Nasir mohammad bari road & gard wall (HBB) | WD-VZR-CTG-RAOZA-11/51 |  |  |  |  | 0.299 |  | 7.49 | 13/03/11 | 0.299 |  | 7.49 | HBB | 2011-03-06 | M/S. AnjumanaraEnterpriset. | 7.49 | 18/05/11 | 8/10/2011 R30/04/12 | 100%
51 | Raozan | 415715641 | Raozan Fakhir Takia road to grad wall (HBB) | WD-VZR-CTG-RAOZA-11/52 |  |  |  |  | 0.3 |  | 17.53 | 13/03/11 | 0.3 |  | 17.53 | HBB | 2011-03-07 | M/S Kashem Enterprise | 17.53 | 18/05/11 | 8/10/2011 R30/07/12 | 90% | 7.38
52 | Raozan | 415745637 415745648 | Raozan Police Station road &guard wall (HBB) | WD-VZR-CTG-RAOZA-11/53 |  |  |  |  | 0.252 |  | 5.93 | 13/03/11 | 0.252 |  | 5.93 | HBB | 2011-03-08 | M/S Riton Enterprise | 5.93 | 18/05/12 | 2011-08-11 | 100% | 2.99
53 | Raozan | 415745613 | Ukil Mohammad Chowdari road to grad wall (HBB) | WD-VZR-CTG-RAOZA-11/54 |  |  |  |  | 0.3 |  | 5.4 | 13/03/13 | 0.3 |  | 5.4 | HBB | 2011-03-09 | M/S J.N Enterprise | 5.4 | 18/05/13 | 2011-08-12 | 100%
54 | Raozan | 415745654 | Ramkrishno road to Gusho gramme road (HBB) | WD-VZR-CTG-RAOZA-11/55 | [6 empty] | 9.32 | 13/03/11 |  |  | 9.32 |  | 2011-03-10 | M/S Gaosia Enterprise | 9.32 | 18/05/11 | 2011-08-10 | 100% | 9.32
55 | Raozan |  | Aparajita sheba Asram road (HBB) | WD-VZR-CTG-RAOZA-11/56 |  |  |  |  | 0.3 |  | 4.95 | 13/03/11 | 0.3 |  | 4.95 | HBB | 2011-03-11 | M/S Iqubal & Brothers | 4.95 | 18/05/12 | 2011-08-11 | 90%
56 | Raozan | 415744078 | Ichapur Road. | WD-VZR-CTG-RAOZA-11/67 |  |  |  |  | 0.6 |  | 15 | 2011-07-12 | 0.62 |  | 15 | HBB | 15/01/12
57 | Raozan | 415745082 | Internal Road(CUET campus,New Hall Road,Main Road To New Hall Connecting Road,Primary school Road,darmatory Road,play ground North side.) | WD-VZR-CTG-RAOZA-12/149 |  |  |  |  | 4.4 |  | 66 | 16/01/12 | 1.281 |  | 56.39 | BC | 2012-07-05 | M/S I.S Trading | 72.22
58 | Raozan | 415745097 | Kadalpur West Barua Para Road | WD-VZR-CTG-RAOZA-12/68 |  |  |  |  | 1 |  | 22.29 | 20/02/12 | 1 |  | 22.29 | HBB | 20/02/12 | M/S Rahman Enterprise | 22.29 | 25/05/12 | 14/12/12 | 0%
59 | Raozan | 415745114 | South Dewanpur Badra Sanpara Road. | WD-VZR-CTG-RAOZA-12/69 |  | Not in DPP |  |  | 1 |  | 19.33 | 20/02/12 | 1 |  | 19.33 | HBB | 20/02/12 | M/S Arpon Construction | 19.33 | 25/05/12 | 14/12/12
60 | Raozan | 415745091 | Bagon R/D Mohamida Road | WD-VZR-CTG-RAOZA-12/70 |  |  |  |  | 1 |  | 19.33 | 20/02/12 | 1 |  | 19.33 | HBB | 20/02/12 | M/S SABB Traders | 19.33 | 25/05/12 | 14/12/12
61 | Raozan | 415744054 | Noajish Pur Natun Bazar Road | WD-VZR-CTG-RAOZA-12/71 |  |  |  |  | 0.83 |  | 26.1 | 20/02/12 | 0.83 |  | 26.1 | BC | 20/02/12
62 | Raozan | 415745013 | Holudia Bricca Banupur Road. | WD-VZR-CTG-RAOZA-12/72 |  |  |  |  | 0.5 |  | 11.26 | 20/02/12 | 0.5 |  | 11.26 | HBB | 20/02/12 | M/S Chowdhury Ent. | 11.25 | 14/06/12 | 14/12/12
63 | Raozan | 415745411 | Holudia Molubi Ramjan Ali Road. | WD-VZR-CTG-RAOZA-12/73 |  |  |  |  | 0.156 |  | 2.96 | 20/02/12 | 0.156 |  | 2.96 | HBB | 20/02/12 | M/S kohinoor Enterprise | 2.95 | 23/05/12 | 14/09/12 R30/09/13
64 | Raozan | 415745412 | Holudia Karigor Barii Road. | WD-VZR-CTG-RAOZA-12/74 |  |  |  |  | 0.207 |  | 3.92 | 20/02/12 | 0.207 |  | 3.92 | HBB | 20/02/12 | M/S kohinoor Enterprise | 3.92 | 23/05/12 | 14/09/12
65 | Raozan | 415745142 | Holudia Rustom Fakia Road. | WD-VZR-CTG-RAOZA-12/75 |  |  |  |  | 0.156 |  | 2.95 | 20/02/12 | 0.156 |  | 2.95 | HBB | 20/02/12 | M/S kohinoor Enterprise | 2.95 | 23/05/12 | 14/09/12
66 | Raozan | 415745413 | Goda Moulobi Bari Road | WD-VZR-CTG-RAOZA-12/76 |  |  |  |  | 0.104 |  | 1.97 | 20/02/12 | 0.104 |  | 1.97 | HBB | 20/02/12 | M/S S A Enterprise | 1.97 | 23/05/12 | 14/09/12
67 | Raozan | 415745414 | Tita Gazi Bari Road | WD-VZR-CTG-RAOZA-12/77 |  |  |  |  | 0.104 |  | 1.97 | 20/02/12 | 0.104 |  | 1.97 | HBB | 20/02/12 | M/S S A Enterprise | 1.97 | 23/05/12 | 14/09/12
68 | Raozan | 415745415 | Abu Talukder Bari Mosque To Contructor Bari Road | WD-VZR-CTG-RAOZA-12/78 |  |  |  |  | 0.104 |  | 1.97 | 20/02/12 | 0.104 |  | 1.97 | HBB | 20/02/12 | M/S S A Enterprise | 1.97 | 23/05/12 | 14/09/12
69 | Raozan | 415745142 | Holudia Uttar Shatta ali Hossain Shah Road. | WD-VZR-CTG-RAOZA-12/79 |  |  |  |  | 0.26 |  | 4.92 | 20/02/12 | 0.26 |  | 4.92 | HBB | 20/02/12 | M/S Fabiha Enterprise | 4.92 | 23/05/12 | 14/09/12 R28/03/13
70 | Raozan | 415745416 | Mohettar Bari Road. | WD-VZR-CTG-RAOZA-12/80 |  |  |  |  | 0.104 |  | 1.97 | 20/02/12 | 0.104 |  | 1.97 | HBB | 20/02/12 | M/S S A Enterprise | 1.97 | 23/05/12 | 14/09/12
71 | Raozan | 415745410 | Shahib Bari Road. | WD-VZR-CTG-RAOZA-12/81 |  |  |  |  | 0.258 |  | 4.89 | 20/02/12 | 0.258 |  | 4.89 | HBB | 20/02/12 | M/S Fabiha Enterprise | 4.88 | 23/05/12 | 14/09/12 28/03/13 R28/03/13
72 | Raozan | 415745417 | Manu Patan Road. | WD-VZR-CTG-RAOZA-12/82 |  |  |  |  | 0.65 |  | 1.23 | 20/02/12 | 0.65 |  | 1.23 | HBB | 20/02/12 | M/S S M Trading | 1.23 | 23/05/12 | 14/09/12 R30/04/13
73 | Raozan | 415745418 | Tata Gazi Road. | WD-VZR-CTG-RAOZA-12/83 |  |  |  |  | 0.65 |  | 1.23 | 20/02/12 | 0.65 |  | 1.23 | HBB | 20/02/12 | M/S S M Trading | 1.23 | 23/05/12 | 14/09/12
74 | Raozan | 415745419 | Sonali Talukder Road. | WD-VZR-CTG-RAOZA-12/84 |  |  |  |  | 0.65 |  | 1.23 | 20/02/12 | 0.65 |  | 1.23 | HBB | 20/02/12 | M/S S M Trading | 1.23 | 23/05/12 | 14/09/12 R30/04/13
75 | Raozan | 415745419 | WD-VZR-CTG-RAOZA-12/86 | WD-VZR-CTG-RAOZA-12/85 |  |  |  |  | 0.122 |  | 2.31 | 20/02/12 | 0.122 |  | 2.31 | HBB | 20/02/12 | M/S Fahim Enterprise | 2.31 | 23/05/12 | 14/09/12
76 | Raozan | 415745425 | Shalauddin Bari Road | WD-VZR-CTG-RAOZA-12/86 |  |  |  |  | 0.122 |  | 2.31 | 20/02/12 | 0.122 |  | 2.31 | HBB | 20/02/12 | M/S S A Enterprise | 2.31 | 23/05/12 | 14/09/12
77 | Raozan | 415745426 | Haji Abul Kashem Road. | WD-VZR-CTG-RAOZA-12/87 |  |  |  |  | 0.122 |  | 2.31 | 20/02/12 | 0.122 |  | 2.31 | HBB | 20/02/12 | M/S S A Enterprise | 2.31 | 23/05/12 | 14/09/12
78 | Raozan | 415745034 | Dabua Jaganath Hat Yasin Shah Road. | WD-VZR-CTG-RAOZA-12/88 |  |  |  |  | 1 |  | 18.95 | 20/02/12 | 1 |  | 18.95 | HBB | 20/02/12 | M/S S A Enterprise | 18.95 | 23/05/12 | 14/09/12
79 | Raozan | 415745115 | Dabua Ramnath Para Road. | WD-VZR-CTG-RAOZA-12/89 |  |  |  |  | 0.26 |  | 4.92 | 20/02/12 | 0.26 |  | 4.92 | HBB | 20/02/12 | M/S Master traders | 4.92 | 23/05/12 | 14/09/12
80 | Raozan | 415745432 | Dabua Shuranga Road. | WD-VZR-CTG-RAOZA-12/90 |  |  |  |  | 1 |  | 18.95 | 20/02/12 | 1 |  | 18.95 | HBB | 20/02/12 | M/S Garib ullah Ent. | 18.76 | 23/05/12 | 14/09/12
81 | Raozan | 415745296 R415745541 | Chikdair Haji Abdul Jalil Sharang Bari Road.Chikdair Haji Kalamia Dabua Road. | WD-VZR-CTG-RAOZA-12/91 |  |  |  |  | 0.3 |  | 4.93 | 2012-07-05 | 0.3 |  | 4.93 | HBB | 2012-07-05
82 | Raozan | 415745434 | Chikdair Afiuddin Road. | WD-VZR-CTG-RAOZA-12/92 |  |  |  |  | 0.515 |  | 9.33 | 20/02/12 | 0.515 |  | 9.33 | HBB | 20/02/12 | M/S J. S Trading | 9.33 | 23/05/12 | 14/12/12
83 | Raozan | 415745154 | Chikdair Dolilur Rahaman Road. | WD-VZR-CTG-RAOZA-12/93 |  |  |  |  | 0.2 |  | 3.79 | 20/02/12 | 0.2 |  | 3.79 | HBB | 20/02/12 | M/S sayam traders | 3.79 | 23/05/12 | 14/12/12
84 | Raozan | 415745435 | Chikdair Chairman Bari Road. | WD-VZR-CTG-RAOZA-12/94 |  |  |  |  | 0.3 |  | 5.43 | 20/02/12 | 0.3 |  | 5.43 | HBB | 20/02/12 | M/S sayam traders | 5.43 | 23/05/12 | 14/12/12
85 | Raozan | 415745436 | Gohira Mojam Bari Road. | WD-VZR-CTG-RAOZA-12/95 |  |  |  |  | 0.15 |  | 6.48 | 20/02/12 | 0.15 |  | 6.48 | HBB | 20/02/12 | M/S structural Corpora. | 6.48 | 23/05/12 | 14/12/12
86 | Raozan | 415745105 | Gohira Madrasha Bari Road. | WD-VZR-CTG-RAOZA-12/96 |  |  |  |  | 0.45 |  | 15.48 | 20/02/12 | 0.45 |  | 15.48 | HBB | 20/02/12 | M/S J N Enterprise. | 15.48 | 23/05/12 | 14/12/12
87 | Raozan | 415745442 | Gohira Mmofijol Ahammed Chowdhuryi Road. | WD-VZR-CTG-RAOZA-12/97 |  |  |  |  | 0.104 |  | 1.97 | 20/02/12 | 0.104 |  | 1.97 | HBB | 20/02/12 | M/S S M Trading. | 1.97 | 23/05/12 | 14/12/12
88 | Raozan | 415745443 | Nur Ahammad Mistry Bari Road. | WD-VZR-CTG-RAOZA-12/98 |  |  |  |  | 0.208 |  | 3.94 | 20/02/12 | 0.208 |  | 3.94 | HBB | 20/02/12 | M/S A Zaman Trading. | 3.94 | 23/05/12 | 14/12/12 R25/03/13
89 | Raozan | 415745445 | Gohira Jala Bari Road. | WD-VZR-CTG-RAOZA-12/99 |  |  |  |  | 0.26 |  | 4.93 | 20/02/12 | 0.26 |  | 4.93 | HBB | 20/02/13 | M/S A Zaman Trading. | 4.92 | 23/05/12 | 14/12/12 R25/03/13
90 | Raozan | 415745041 | Gohira Santir Dip South Srtt. Road. | WD-VZR-CTG-RAOZA-12/100 |  |  |  |  | 0.36 |  | 14.59 | 20/02/12 | 0.36 |  | 14.59 | HBB | 20/02/12 | M/S S M Trading. | 14.59 | 23/05/12 | 14/12/12
91 | Raozan | 415745198 | Middle Binajuri Darmankur Bari Road. | WD-VZR-CTG-RAOZA-12/101 |  |  |  |  | 0.258 |  | 4.89 | 20/02/12 | 0.258 |  | 4.89 | HBB | 20/02/12 | M/S J N Enterprise. | 4.88 | 23/05/12 | 14/12/12
92 | Raozan | 415745451 | East Binajuri Darmankur Beher To Budda Shasam Road | WD-VZR-CTG-RAOZA-12/102 |  |  |  |  | 0.258 |  | 4.89 | 20/02/12 | 0.258 |  | 4.89 | HBB | 20/02/12 | M/S Samiun Enterprise | 4.88 | 23/05/12 | 14/12/12
93 | Raozan | 415745452 | East Binajuri Chulla BaydyaRoad | WD-VZR-CTG-RAOZA-12/103 |  |  |  |  | 0.258 |  | 4.89 | 20/02/12 | 0.258 |  | 4.89 | HBB | 20/02/12 | M/S Reyadh Trade Com. | 4.88 | 23/05/12 | 14/12/12 R30/05/13
94 | Raozan | 415745492 | Binajuri Purna Chandra Road. | WD-VZR-CTG-RAOZA-12/104 |  |  |  |  | 0.62 |  | 11.75 | 20/02/12 | 0.62 |  | 11.75 | HBB | 20/02/12 | M/S Pubali Traders. | 11.75 | 23/05/12 | 14/12/12 |  |  | RE-Cast
95 | Raozan | 415744039 | Binajuri Nabin Mohajon Road. | WD-VZR-CTG-RAOZA-12/105 |  |  |  |  | 0.675 |  | 12.8 | 20/02/12 | 0.675 |  | 12.8 | HBB | 20/02/12 | M/S M A Traders. | 12.79 | 23/05/12 | 14/12/12
96 | Raozan | 415745456 | Roazan Fakir Mohamd Chow.House Road. | WD-VZR-CTG-RAOZA-12/106 |  |  |  |  | 0.52 |  | 9.86 | 20/02/12 | 0.52 |  | 9.86 | HBB | 20/02/12 | M/S Bayzid Corporation. | 9.84 | 23/05/12 | 14/12/12
97 | Raozan | 415745458 | Kadalpur Chikdair Para Natun para Road. | WD-VZR-CTG-RAOZA-12/108 |  |  |  |  | 0.7 |  | 13.49 | 20/02/12 | 0.7 |  | 13.49 | HBB | 20/02/12 | M/S Bayzid Corporation. | 13.49 | 23/05/12 | 14/12/12
98 | Raozan | 415745050 | Kadalpur DhakinJoynagor Barua Para Road. | WD-VZR-CTG-RAOZA-12/109 |  |  |  |  | 0.515 |  | 9.76 | 20/02/12 | 0.515 |  | 9.76 | HBB | 20/02/12 | M/S Rahman Enterprise. | 9.76 | 23/05/12 | 14/12/12
99 | Raozan | 415745096 | Pahartoli R.D Mohamidia Road, | WD-VZR-CTG-RAOZA-12/110 |  |  |  |  | 0.49 |  | 15.53 | 20/02/12 | 0.49 |  | 15.53 | HBB | 20/02/12 | M/S I S trading. | 15.53 | 23/05/12 | 14/12/12 R20/07/13
100 | Raozan | 415745460 | Pahartoli Al-Haj Gara Mia Najir Road. | WD-VZR-CTG-RAOZA-12/111 |  |  |  |  | 0.606 |  | 11.48 | 20/02/12 | 0.606 |  | 11.48 | HBB | 20/02/12 | M/S Alam & Brothers. | 11.47 | 23/05/12 | 14/12/12
101 | Raozan | 415745237 | Pahartoli Billa Braman Para Road. | WD-VZR-CTG-RAOZA-12/112 |  |  |  |  | 0.278 |  | 5.26 | 20/02/12 | 0.278 |  | 5.26 | HBB | 20/02/12 | M/S I S trading. | 5.26 | 23/05/12 | 14/12/12
102 | Raozan | 415745461 | Pahartoli Dewan Pur Jala Dass Para Road. | WD-VZR-CTG-RAOZA-12/113 |  |  |  |  | 0.46 |  | 8.71 | 20/02/12 | 0.46 |  | 8.71 | HBB | 20/02/12 | M/S I S trading. | 8.71 | 23/05/12 | 14/12/12
103 | Raozan | 415745462 | Pahartoli Bashir Md.Cnnecting Road. | WD-VZR-CTG-RAOZA-12/114 | Not in DPP |  |  |  | 0.46 |  | 8.71 | 20/02/12 | 0.46 |  | 8.71 | HBB | 20/02/12 | M/S Hachi Fakir Traders. | 8.71 | 23/05/12 | 14/12/12
104 | Raozan | 415745219 | East Guzara Rada Mohan Road. | WD-VZR-CTG-RAOZA-12/115 |  |  |  |  | 1 |  | 18.95 | 20/02/12 | 1 |  | 18.95 | HBB | 20/02/12 | M/S Shah Amanat Ent.. | 18.94 | 23/05/12 | 14/12/12 R25/05/13
105 | Raozan | 415745464 | Purba Gugra Jor Pakur To Baruathakur Para Road. | WD-VZR-CTG-RAOZA-12/116 |  |  |  |  | 0.45 |  | 8.52 | 20/02/12 | 0.45 |  | 8.52 | HBB | 20/02/12 | M/S Zahanara Ent.. | 8.5 | 23/05/12 | 14/12/12
106 | Raozan | 415745465 | Purba Gugra Moulovi Bosharot Ulla Road. | WD-VZR-CTG-RAOZA-12/117 |  |  |  |  | 0.533 |  | 9.34 | 20/02/12 | 0.533 |  | 9.34 | HBB | 20/02/12 | M/S Munna Enterprise.. | 11.98 | 23/05/12 | 14/12/12
107 | Raozan | 415745004 | Pachim Guzra Hazi Badu Mia Road. | WD-VZR-CTG-RAOZA-12/118 |  |  |  |  | 0.415 |  | 7.86 | 20/02/12 | 0.415 |  | 7.86 | HBB | 20/02/12 | M/S Saima tithi Enterprise.. | 7.86 | 23/05/12 | 14/12/12
108 | Raozan | 415745470 | Pachim Guzra Sarkar Para Road. | WD-VZR-CTG-RAOZA-12/119 |  |  |  |  | 0.78 |  | 14.78 | 20/02/12 | 0.78 |  | 14.78 | HBB | 20/02/12 | M/S Saima tithi Enterprise.. | 14.78 | 23/05/12 | 14/12/12
109 | Raozan | 415745500 | Taki Shikder Road To Mohajon Hose Road. | WD-VZR-CTG-RAOZA-12/120 |  |  |  |  | 0.415 |  | 7.86 | 20/02/12 | 0.415 |  | 7.86 | HBB | 20/02/12 | M/S Saima tithi Enterprise.. | 7.86 | 23/05/12 | 14/12/12
110 | Raozan | 415745471 | Pachim Guzra Bashi-Mohajan Road. | WD-VZR-CTG-RAOZA-12/121 |  |  |  |  | 0.415 |  | 7.86 | 20/02/12 | 0.415 |  | 7.86 | HBB | 20/02/12 | M/S Bayzid Corporation. | 7.85 | 23/05/12 | 14/12/12
111 | Raozan | 415745520 | Har Para Sheikh Ahammad Bari Road. | WD-VZR-CTG-RAOZA-12/122 |  |  |  |  | 0.1 |  | 2.83 | 20/02/12 | 0.1 |  | 2.83 | HBB | 20/02/12 | M/S Swapan Constructi. | 3.16 | 23/05/12 | 14/12/12 R30/06/13
112 | Raozan | 415745521 | Mia Para Monsur Bari&Bipin Doctor bari Road. | WD-VZR-CTG-RAOZA-12/123 |  |  |  |  | 0.25 |  | 3.38 | 20/02/12 | 0.25 |  | 3.38 | HBB | 20/02/12 | M/S Kohinoor Enterprise. | 4.22 | 23/05/12 | 14/12/12
113 | Raozan | 415745522 | Sheikh Para Md. Ahammad Hossain Road. | WD-VZR-CTG-RAOZA-12/124 |  |  |  |  | 0.95 |  | 1.28 | 20/02/12 | 0.95 |  | 1.28 | HBB | 20/02/12 | M/S Kohinoor Enterprise. | 1.6 | 23/05/12 | 14/12/12
114 | Raozan | 415745523 | Sheikh Para Mollah Bari Road. | WD-VZR-CTG-RAOZA-12/125 |  |  |  |  | 0.31 |  | 4.92 | 20/02/12 | 0.31 |  | 4.92 | HBB | 20/02/12 | M/S Kohinoor Enterprise. | 6.02 | 23/05/12 | 14/12/12
115 | Raozan | 415745524 | Moishkaram Primary School Link Road. | WD-VZR-CTG-RAOZA-12/126 |  |  |  |  | 0.21 |  | 4.96 | 20/02/12 | 0.21 |  | 4.96 | HBB | 20/02/12 | M/S S S Enterprise. | 4.96 | 23/05/12 | 14/12/12
116 | Raozan | 415745525 | Ala Mia Bazar To Chowdhury Bari Road. | WD-VZR-CTG-RAOZA-12/127 |  |  |  |  | 0.3 |  | 1.47 | 20/02/12 | 0.3 |  | 1.47 | HBB | 20/02/12 | M/S Swapan Constructi. | 1.47 | 23/05/12 | 14/12/12
117 | Raozan | 415745264 | Sheil Para Road. | WD-VZR-CTG-RAOZA-12/128 |  |  |  |  | 0.363 |  | 6.87 | 20/02/12 | 0.363 |  | 6.87 | HBB | 20/02/12 | M/S A H Enterprisei. | 6.87 | 23/05/12 | 14/12/12
118 | Raozan | 415745478 | Ghatkul Karam Ali Road. | WD-VZR-CTG-RAOZA-12/130 |  |  |  |  | 0.4 |  | 7.58 | 20/02/12 | 0.4 |  | 7.58 | HBB | 20/02/12 | M/S A H Enterprisei. | 7.58 | 23/05/12 | 14/12/12
119 | Raozan | 415745479 | Shambolir Bari Road. | WD-VZR-CTG-RAOZA-12/131 |  |  |  |  | 0.6 |  | 11.37 | 20/02/12 | 0.6 |  | 11.37 | HBB | 20/02/12 | M/S A H Enterprisei. | 11.37 | 23/05/12 | 14/12/12
120 | Raozan | 415745482 | Bagon Narayan Prashad Nath Road. | WD-VZR-CTG-RAOZA-12/132 |  |  |  |  | 0.6 |  | 10.25 | 20/02/12 | 0.6 |  | 10.25 | HBB | 20/02/12 | M/S S s Enterprisei. | 11.54 | 23/05/12 | 14/12/12
121 | Raozan | 415745483 | Bagon Panchkhan Meharjaman Chairman House Road. | WD-VZR-CTG-RAOZA-12/133 |  |  |  |  | 0.425 |  | 7.14 | 20/02/12 | 0.425 |  | 7.14 | HBB | 20/02/12 | M/S Bayzad Enterprisei. | 7.87 | 23/05/12 | 14/12/12
122 | Raozan | 415745485 | Bagan Goran Fakir Bari Road. | WD-VZR-CTG-RAOZA-12/134 |  |  |  |  | 0.4 |  | 6.02 | 20/02/12 | 0.4 |  | 6.02 | HBB | 20/02/12 | M/S Gorun Fakir Tradersi. | 7.31 | 23/05/12 | 14/12/12
123 | Raozan | 415745486 | Vopash Borura Bari Road. | WD-VZR-CTG-RAOZA-12/135 |  |  |  |  | 0.3 |  | 5.68 | 20/02/12 | 0.3 |  | 5.68 | HBB | 20/02/12 | M/S SA BB Tradersi. | 5.68 | 23/05/12 | 14/12/12
124 | Raozan | 415745499 | Noajish Pur Nadim Pur Road. | WD-VZR-CTG-RAOZA-12/136 |  |  |  |  | 0.364 |  | 6.89 | 20/02/12 | 0.364 |  | 6.89 | HBB | 20/02/12 | M/S Aziz mnower ent.. | 6.89 | 23/05/12 | 14/12/12 R25/06/13
125 | Raozan | 415745170 | Noajish Pur Uttar Fate Nagar Road. | WD-VZR-CTG-RAOZA-12/137 |  |  |  |  | 0.51 |  | 15.4 | 20/02/12 | 0.51 |  | 15.4 | BC | 20/02/12
126 | Raozan | 415745000 | Noajish Pur Siddique Bazar Road. | WD-VZR-CTG-RAOZA-12/138 |  |  |  |  | 0.515 |  | 9.76 | 20/02/12 | 0.515 |  | 9.76 | HBB | 20/02/12 | M/S Aziz mnower ent.. | 9.76 | 23/05/12 | 14/12/12
127 | Raozan | 415745526 | Moishkaram Munshi Bari Road. | WD-VZR-CTG-RAOZA-12/139 |  |  |  |  | 0.125 |  | 2.11 | 20/02/12 | 0.125 |  | 2.11 | HBB | 20/02/12 | M/S swapan Construction. | 2.11 | 23/05/12 | 14/12/12
128 | Raozan | 415745527 | Urkir Cfhar Zabbar Saodagor Bari Road. | WD-VZR-CTG-RAOZA-12/140 |  |  |  |  | 0.155 |  | 2.54 | 20/02/12 | 0.155 |  | 2.54 | HBB | 20/02/12 | M/S S S Enterprise. | 2.54 | 23/05/12 | 14/12/12 30/06/13
129 | Raozan | 415745495 | Urkir Cfhar Minnat Ali Road. | WD-VZR-CTG-RAOZA-12/141 |  |  |  |  | 0.24 |  | 4.62 | 20/02/12 | 0.24 |  | 4.62 | HBB | 20/02/12 | M/S S S Enterprise. | 4.62 | 23/05/12 | 14/12/12 R30/06/13
130 | Raozan | 415745496 | Urkir Cfhar HarparaTo Dewangee Bari Road. | WD-VZR-CTG-RAOZA-12/142 |  |  |  |  | 0.18 |  | 3.01 | 20/02/12 | 0.18 |  | 3.01 | HBB | 20/02/12 | M/S swapan Construction. | 3.01 | 23/05/12 | 14/12/12 R30/06/13
131 | Raozan | 415745501 | Gohira Hanif Bari Road. | WD-VZR-CTG-RAOZA-12/143 |  |  |  |  | 0.188 |  | 4.94 | 20/02/12 | 0.188 |  | 4.94 | HBB | 20/02/12 | M/S Anjumanara Enterp. | 4.94 | 23/05/12 | 14/12/12
132 | Raozan | 415745502 | Gohira Salamat Khan Road. | WD-VZR-CTG-RAOZA-12/144 |  |  |  |  | 0.24 |  | 5.26 | 20/02/12 | 0.24 |  | 5.26 | HBB | 20/02/12 | M/S Fabiha Enterp. | 5.26 | 23/05/12 | 14/12/12
133 | Raozan | 415745503 | Eidal Pur Barua Para Road. | WD-VZR-CTG-RAOZA-12/145 |  |  |  |  | 0.3 |  | 4.85 | 20/02/12 | 0.3 |  | 4.85 | HBB | 20/02/12 | M/S S M Trading. | 5.62 | 23/05/12 | 14/12/12
134 | Raozan | 415745504 | Raozan Fulbari Road & Dewan Ali Talukder Bari Road | WD-VZR-CTG-RAOZA-12/146 |  |  |  |  | 0.273 |  | 4.97 | 20/02/12 | 0.273 |  | 4.97 | HBB | 20/02/12 | M/S Sanjita Enterprise. | 4.97 | 23/05/12 | 14/09/12 R25/04/13
135 | Raozan | 415745506 | Nandi Para Road to Nabin Road. | WD-VZR-CTG-RAOZA-12/147 |  |  |  |  | 0.36 |  | 4.63 | 20/02/12 | 0.36 |  | 4.63 | HBB | 20/02/12 | M/S Riyadh Trade com. | 4.63 | 23/05/12 | 14/12/12 R30/05/13 |  |  | Re-Cast
136 | Raozan | 415745512 | Gohira Biswas House Road. | WD-VZR-CTG-RAOZA-12/148 |  |  |  |  | 0.327 |  | 4.94 | 20/02/12 | 0.327 |  | 4.94 | HBB | 20/02/12 | M/S K P Enterprise. | 4.94 | 23/05/12 | 14/12/12
137 | Raozan | 415745540 | Chickdair Kamal Showdagar Bari Road. | WD-VZR-CTG-RAOZA-12/150 |  |  |  |  | 0.3 |  | 4.93 | 2012-07-05 | 0.3 |  | 4.93 | HBB | 2012-07-05
138 | Raozan | 415745655 | Kadalpur Bashair Mosammad Road. | WD-VZR-CTG-RAOZA-12/151 |  |  |  |  | 0.825 |  | 32 | 15/05/12 | 0.78 | 1.3 | 26.03 | HBB | 14/06/12 | M/S Modina Enterprise | 31.24
139 | Raozan | 415745082 | Development Of CUET Campas Primary School Road. | WD-VZR-CTG-RAOZA-13/160 |  |  |  |  | 0.12 | 0.6 | 15.78 | 14/02/13 | 0.12 | 0.6 | 15.78 | BC | 14/02/13
140 | Raozan | 415745035 | 54.00m Long RCC Bridge on Dabua Khal | WD-VZR-CTG-RAOZA-13/161 | [5 empty] | 54 | 144.79 |  |  | 54 | 144.79 | ST | 22/05/13
141 | Raozan | 415744077 | Chikdair Md Tokye Road(Pathan para) | WD-VZR-CTG-RAOZA-13/167 | 1.1 |  | BC | 30 | 1.1 |  | 30 | 2014-02-01 | 1.1 |  | 27.13 | BC/HBB |  | M/S Chowdhury Ent. | 28.48 | 31/03/14
142 | Raozan | 415745264 | Binajuri Milonram Bihar Road | WD-VZR-CTG-RAOZA-13/168 | 0.5 |  | HBB | 11 | 0.5 |  | 11 | 2013-02-01
143 | Raozan | 415745096 | Noapara Patiapara Road | WD-VZR-CTG-RAOZA-13/169 | 0.5 |  | BC | 11 | 0.5 |  | 11 | 2013-02-01
144 | Raozan | 415744007 | Kodolpur Amirpara Road | WD-VZR-CTG-RAOZA-13/170 | 0.5 |  | HBB | 14 | 0.5 |  | 14 | 2013-02-01
145 | Raozan | 415745241 | Shekh para Mohamoni Road of Pahartoli Chueat South side | WD-VZR-CTG-RAOZA-13/171 | 0.8 |  | HBB | 15 | 0.8 |  | 15 | 2013-02-01 | 0.66 |  | 14.27 | HBB |  | M/S KRB Enterprise | 14.56 | 31/03/14
146 | Raozan | 415744001 | Purbo Guzra Boro Thaqour para Road(Oli mia hat link road) | WD-VZR-CTG-RAOZA-13/172 | 0.7 |  | HBB | 14 | 0.7 |  | 14 | 2013-02-01
147 | Raozan | 415745219 | Paschim Guzra Bama Charan Road | WD-VZR-CTG-RAOZA-13/173 | 1 |  | HBB | 25 | 1 |  | 25 | 2013-02-01
148 | Raozan | 415744086 | Boyjokhali bazar-Dhakakhali Kholifarghona Road | WD-VZR-CTG-RAOZA-13/174 | 1 |  | BC | 30 | 1 |  | 30 | 2013-02-01
149 | Raozan | 415745266 | Noapara School-Uvolong Road | WD-VZR-CTG-RAOZA-13/175 | 0.5 |  | BC | 30 | 0.5 |  | 30 | 2013-02-01
150 | Raozan | 415745247 | Bagoan Nasim Jongol Road | WD-VZR-CTG-RAOZA-13/176 | 1 |  | HBB | 20 | 1 |  | 20 | 2013-02-01
151 | Raozan | 415745160 | Noazishpur Rahamat Ali Sikdar bari, Fothehnagar Monu Mia Road, Uttar Horua Para Road, Hore Krishno Mohazon Road, Nadimpur Azizur Rahman Road, Sonagazi Chowdhuri Road | WD-VZR-CTG-RAOZA-13/177 | 1.3 |  | BC | 28.6 | 1.3 |  | 28.6 | 2013-02-01
152 | Raozan | 415745131 | Shap Longa (Shah Nagor) 1no. Road | WD-VZR-CTG-RAOZA-13/178 | 0.45 |  | HBB | 11.35 | 0.45 |  | 11.35 | 2013-02-01
153 | Raozan | 415745302 | Shah Nagor-Fakhirhat bazar Road | WD-VZR-CTG-RAOZA-13/179 | 0.5 |  | HBB | 11 | 0.5 |  | 11 | 2013-02-01
154 | Raozan | 415745615 | East Rauzan Saha Sundar Aulia Road | WD-VZR-CTG-RAOZA-13/180 | 0.7 |  | HBB | 14 | 0.7 |  | 14
155 | Raozan | 415745099 | Rauzan Ramdhon Road | WD-VZR-CTG-RAOZA-13/181 | 0.7 |  | HBB | 14 | 0.7 |  | 14
156 | Raozan | 415745616 | G O Sha Mazar Road guid wall | WD-VZR-CTG-RAOZA-13/182 | 0.1 |  | HBB | 2.5 | 0.1 |  | 2.5
157 | Raozan | 415745036 | Oheder khil Rustom Saha Road, Sayed Ahmed Fakir Road, Nazir Ahmad Road, Paschim Rauzan Zan Box Raod, Kazipara Road, Paschim Rauzan Kulal bari Road, Paschim Rauzan Md.Sultan Chowdhuri bari Road | WD-VZR-CTG-RAOZA-13/183 | 2.452 |  | HBB | 45 | 2.452 |  | 45
158 | Raozan | 415745619 | Dewanpur School Road | WD-VZR-CTG-RAOZA-13/184 | 0.3 |  | HBB | 3 | 0.3 |  | 3
159 | Raozan | 415745620 | Mobarakkhil Hakim Ullah Fakir bari Road | WD-VZR-CTG-RAOZA-13/185 | 0.15 |  | HBB | 3 | 0.15 |  | 3
160 | Raozan | 415745621 | West Rouzan Fate Ali Chowdhury Bari Road guid wall | WD-VZR-CTG-RAOZA-13/186 | 0.1 |  | HBB | 2.5 | 0.1 |  | 2.5
161 | Raozan | 415745037 | Holdia Durga Charan Road | WD-VZR-CTG-RAOZA-13/187 | 1 |  | HBB | 17 | 1 |  | 17
162 | Raozan | 415745291 | Dabua Khosal Talukder bari Road | WD-VZR-CTG-RAOZA-13/188 | 0.675 |  | HBB | 14 | 0.675 |  | 14 |  | 1.255 |  | 13.51 |  |  | M/S Chowdhury Ent. | 14.19 | 31/03/14
163 | Raozan | 415745018 | Moddho Chikdhair Shama charan & Purbo Chikdhair Road | WD-VZR-CTG-RAOZA-13/189 | 0.5 |  | HBB | 12 | 0.5 |  | 12
164 | Raozan | 415744078 | Gohira Echapur Road from Nashrat Digiher Pashchim Para | WD-VZR-CTG-RAOZA-13/190 | 0.122 |  | HBB | 3.05 | 0.122 |  | 3.05
165 | Raozan | 415745574 | Binazori Gobindho Thaqore Road | WD-VZR-CTG-RAOZA-13/191 | 0.3 |  | HBB | 6.6 | 0.3 |  | 6.6
166 | Raozan | 415745180 | Rauzan ShamserNagar Gozali Shah Mazar Road | WD-VZR-CTG-RAOZA-13/192 | 0.125 |  | HBB | 12.88 | 0.125 |  | 12.88
167 | Raozan | 415744011 | Kadalpur Paschim Baroa para Road | WD-VZR-CTG-RAOZA-13/193 | 0.5 |  | HBB | 11 | 0.5 |  | 11
168 | Raozan | 415745622 | Purbo Guzra Surendra Baydha bari Road | WD-VZR-CTG-RAOZA-13/194 | 0.2 |  | HBB | 4 | 0.2 |  | 4
169 | Raozan | 415745030 | Paschim Guzra Kobi Nobin Sen Road | WD-VZR-CTG-RAOZA-13/195 | 1 |  | HBB | 20 | 1 |  | 20
170 | Raozan | 415745160 | Urkirchar Aburkhil Dhutango Khutir Road | WD-VZR-CTG-RAOZA-13/196 | 0.245 |  | HBB | 3.39 | 0.245 |  | 3.39
171 | Raozan | 415744083 | Noapara Mozumdar bari Road, Moduna Jonzol Road | WD-VZR-CTG-RAOZA-13/197 | 0.7 |  | HBB | 14 | 0.7 |  | 14
172 | Raozan | 415745123 | Bagoan Pachkhain Comred Mothear Rahman Road | WD-VZR-CTG-RAOZA-13/198 | 0.6 |  | HBB | 13.2 | 0.6 |  | 13.2
173 | Raozan | 415744083 | Noazishpur Abu Hanif Road | WD-VZR-CTG-RAOZA-13/199 | 0.8 |  | HBB | 14 | 0.8 |  | 14
174 | Raozan | 415745420 | Holdia Barua Road | WD-VZR-CTG-RAOZA-13/200 | 0.4 |  | HBB | 8.8 | 0.4 |  | 8.8
175 | Raozan | 415745127 | Dabua Hingla Village Road(from Musa Sha road) | WD-VZR-CTG-RAOZA-13/201 | 0.5 |  | HBB | 11 | 0.5 |  | 11
176 | Raozan | 415745624 | Chikdahir Mohendro Master Road | WD-VZR-CTG-RAOZA-13/202 | 0.25 |  | HBB | 5.5 | 0.25 |  | 5.5
177 | Raozan | 415745625 | Gohira Doloi Nagor Kanu Meazir Road | WD-VZR-CTG-RAOZA-13/203 | 0.215 |  | HBB | 4.7 | 0.215 |  | 4.7
178 | Raozan | 415745450 | Binazuri BB Road | WD-VZR-CTG-RAOZA-13/204 | 0.5 |  | HBB | 11 | 0.5 |  | 11
179 | Raozan | 415745192 | Kadalpur Khamar bari Road | WD-VZR-CTG-RAOZA-13/205 | 0.5 |  | HBB | 11 | 0.5 |  | 11
180 | Raozan | 415745461 | Pahartoli Uttar Deawanpur Bipin Mohazan Road | WD-VZR-CTG-RAOZA-13/206 | 0.135 |  | HBB | 3 | 0.135 |  | 3
181 | Raozan | 415744011 | Purbo Guzra Notun Bazar kadalpur Road | WD-VZR-CTG-RAOZA-13/207 | 1 |  | HBB | 22 | 1 |  | 22
182 | Raozan | 415744002 | Paschim Guzra Kagotia Myazpara Soru Priya Road | WD-VZR-CTG-RAOZA-13/208 | 0.3 |  | HBB | 6.6 | 0.3 |  | 6.6 |  |  |  | 6.55
183 | Raozan | 415745524 | Urkirchar Moeskrom Munshi bari, Mira para, Abul Bashar, Mir bari Road | WD-VZR-CTG-RAOZA-13/209 | 0.28 |  | HBB | 10 | 0.28 |  | 10 |  |  |  | 11.26 | HBB |  | M/S N K Enterprise | 11.82
184 | Raozan | 415745580 | Noapara Mokami Para Road | WD-VZR-CTG-RAOZA-13/210 | 0.3 |  | HBB | 6.6 | 0.3 |  | 6.6 |  |  |  | 6.33 | HBB
185 | Raozan | 415745483 | Bagoan Pachkhain Chairman Bari Road | WD-VZR-CTG-RAOZA-13/211 | 0.2 |  | HBB | 5.5 | 0.2 |  | 5.5 |  |  |  | 5.33 | HBB
186 | Raozan | 415744054 | Noazishpur Notun Bazar Road | WD-VZR-CTG-RAOZA-13/212 | 0.75 |  | HBB | 20 | 0.75 |  | 20 |  |  |  | 14.51 | HBB
187 | Raozan | 415745053 | Holdia-Brikkhovanupur Road | WD-VZR-CTG-RAOZA-13/213 | 0.46 |  | HBB | 10.12 | 0.46 |  | 10.12 |  |  |  | 9.72 | HBB
188 | Raozan | 415745283 | Dabua Hingla kazirkhill Road | WD-VZR-CTG-RAOZA-13/214 | 0.4 |  | HBB | 8.8 | 0.4 |  | 8.8 |  |  |  | 8.5 | HBB
189 | Raozan | 415745627 | Chikdahir Raghu Nandan Road, Moulana Rohim Ullah Road. | WD-VZR-CTG-RAOZA-13/215 | 0.36 |  | HBB | 9.08 | 0.36 |  | 9.08 |  |  |  | 8.78 | HBB
190 | Raozan | 415745628 | Gahiradoloi Nagar Village Road | WD-VZR-CTG-RAOZA-13/216 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.82 | HBB
191 | Raozan | 415745629 | Binajuri Ratnangkul Behar Road | WD-VZR-CTG-RAOZA-13/217 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.96 | HBB
192 | Raozan | 415745630 | Rouzan Babul Mozumder Bari Road | WD-VZR-CTG-RAOZA-13/218 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.96 | HBB
193 | Raozan | 415745085 | Pahartoli Khiyakhali 69 para Road | WD-VZR-CTG-RAOZA-13/219 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.84 | HBB
194 | Raozan | 415745104 | Paschim Guzra Shikder Para Hossain Shikder Road, Mozidar Para Abdul Motin Road, Dr. Ali Ahmed Road | WD-VZR-CTG-RAOZA-13/220 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
195 | Raozan | 415745496 | Urkirchar Harpara Biur Muktijuddha Serazul Islam Road | WD-VZR-CTG-RAOZA-13/221 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.56 | HBB |  | M/S N K Enterprise | 4.79
196 | Raozan | 415745021 | Noapara Surjo Sheen Road, Neramish Road | WD-VZR-CTG-RAOZA-13/222 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
197 | Raozan | 415745248 | Bagoan Koeapara-Perdapara Road | WD-VZR-CTG-RAOZA-13/223 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
198 | Raozan | 415745538 | Holdia Hazrat Ali Hossain Road | WD-VZR-CTG-RAOZA-13/224 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
199 | Raozan | 415744008 | Dabua Kalampoti Road | WD-VZR-CTG-RAOZA-13/225 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
200 | Raozan | 415745631 | Binajuri Bashu Mitro Barua bari Road | WD-VZR-CTG-RAOZA-13/226 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
201 | Raozan | 415745085 | Pahartoli RD Mohammadia Road | WD-VZR-CTG-RAOZA-13/227 | 0.2 |  | HBB | 9 | 0.2 |  | 9 |  |  |  |  | HBB
202 | Raozan | 415744001 | Purbo Guzra Boro Tagoure Para Jorpukur Road, Hafizea Madrasha Road, Oli Mia Hat Notun bazar Road | WD-VZR-CTG-RAOZA-13/228 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
203 | Raozan | 415745058 | Urkirchar Joy Nagar Baruapara Road | WD-VZR-CTG-RAOZA-13/229 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
204 | Raozan | 415745632 | Bagoan Ahamodur Rahman Mistri Road | WD-VZR-CTG-RAOZA-13/230 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  |  | HBB
205 | Raozan | 415745136 | Holdia Yeasine nagar baghmara Tila Road | WD-VZR-CTG-RAOZA-13/231 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.58 | HBB |  | M/S Chowdhury Ent | 4.81
206 | Raozan | 415745279 | Dabua Kalompoti Gopendro Sarkar bari Road | WD-VZR-CTG-RAOZA-13/232 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.82 | HBB
207 | Raozan | 415745577 | Binajuri Monmohon Driver bari Road | WD-VZR-CTG-RAOZA-13/233 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.82 | HBB
208 | Raozan | 415745633 | Purbo Guzra Khatipara Road, Bollar Dighirpara Road, Maulana Answr Ali House Road | WD-VZR-CTG-RAOZA-13/234 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.96 | HBB
209 | Raozan | 415745135 | Holdia Yasin Nagar Guman Ali Road | WD-VZR-CTG-RAOZA-13/235 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.58 | HBB |  | M/S Chowdhury Ent | 4.81
210 | Raozan | 415745033 | Binazuri Edilpur Shakkomoni Behar-Kundeshore Road, Romep Chandra Muhuri Road, Purbo Lelenggara Road | WD-VZR-CTG-RAOZA-13/236 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.96
211 | Raozan | 415745087 | Urkirchar Oli Fakir Road, Suzarpara Road, Mea Shah Road | WD-VZR-CTG-RAOZA-13/237 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.99
212 | Raozan | 415745624 | Bagoan Fouzodar para Road | WD-VZR-CTG-RAOZA-13/238 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.84
213 | Raozan | 415744070 | Dabua Nagesshor Guard Road | WD-VZR-CTG-RAOZA-13/ | 0.2 |  | HBB | 5 | 0.2 |  | 5
214 | Raozan | 415745544 | Dabua Santinagar Road Kalampoti Uttarpara Road, Paschim Dabua Monu Hazi House Road | WD-VZR-CTG-RAOZA-13/239 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.81
215 | Raozan | 415745512 | Gohera Choitanna Charan Road – Kundesshori Barua Para-Biswash House Road | WD-VZR-CTG-RAOZA-13/240 | 0.2 |  | HBB | 5 | 0.2 |  | 5 |  |  |  | 4.86
216 | Raozan | 415744075 | Pach-khine Dharer Tack Road | WD-VZR-CTG-RAOZA-14/241 | 1 |  | HBB | 28 | 1 |  | 23.36 |  | 1 |  | 23.36 | HBB | 30/06/14
215 |  |  | Sub - Total |  | 32.869 | 0 |  | 767.77 | 111.78 | 145.9 | 2874.58 |  | 79.108 | 156.8 | 2258.79 |  |  |  | 1927.45 |  |  |  | 0
242 |  |  | Total |  | 52.799 | 145.16 |  | 1998.33 | 128.99 | 208.76 | 3806.55 |  | 97.255 | 194.66 | 3104.22 |  |  |  | 2671 |  |  |  | 290.94
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Hathazari | 415373001 | Hajee Yousuf Road 00-950 | WD-UNR-CTG-HATHA-10/01 | 3.5 | 40 | BC | 247 | 1.5 | - | 63 |  | 0.95 | 5 | 62.41 | BC | 2010-05-08 | Haque & Brother's | 55.69 | 2010-01-11 | 01/04/11 RC08/05/11 | 90% | 20.38
2 | Hathazari | 415373005 | Fatehpur Madrasha Road | WD-UNR-CTG-HATHA-10/02 | 4 | 35 | BC | 255.5 | 1.5 | - | 31.98 |  | 1.56 | 3.6 | 31.98 | BC | 16/05/10 | Islam & Brother's | 56.51 | 16/08/10 | 28/2/11 R30/05/11 | 75% | 25.62 | Termination 02/01/13
| Hathazari | 415373005 | Fatehpur Madrasha Road (Remaining) | WD-UNR-CTG-HATHA-13/25 | [5 empty] | - | 26.06 |  |  |  | 26.06 | BC | 2013-02-12 | M/S Shafi & Brothers | 12.95 |  |  |  |  | Reveised
3 | Hathazari | 415373006 | Noor Ahmed Chowdhury Road 00-2255 | WD-UNR-CTG-HATHA-10/03 | 4.5 | 10 | BC | 214 | 1.5 | - | 63 |  | 1.38 | 10 | 62.95 | BC | 16/05/10 | Shah Latif Enterprise | 54.86 | 16/08/10 | 29/2/11 | 100% | 54.85 | FinalbilPaid
4 | Hathazari | 415373004 | Gorduara Sarang road 00-1750 | WD-UNR-CTG-HATHA-10/04 | 2.43 |  | HBB | 72.9 | 2.43 | - | 32.81 |  | 1.75 |  | 32.81 | HBB | 2010-01-08 | Chowdury Enterprise | 32.5 | 2010-10-10 | 23/2/11 R20/02/12 | 70% | 8.48
5 | Hathazari | 415375310 | Ashaba Jame Masque Road (Nazirpur East Dayan Nagar) | WD-UNR-CTG-HATHA-10/14 | Not DPP |  |  |  | 0.35 |  | 14.98 |  | 0.35 |  | 14.98 | BC | 09/11/10 | Build Tech Associates | 14.2 | 18/12/11 | 2012-01-02 | 100% | 14.02 | FinalbilPaid
6 | Hathazari | 415373011 | Romesh Mohazan Road | WD-UNR-CTG-HATHA-10/16 | Not DPP |  |  |  | 1 | 3 | 16.69 |  | 1 | 3 | 16.69 | BC | 09/11/10 | M.A Chowdury & Sons. | 31.35 | 18/12/11 | 2012-01-02 | 70% | 13.11
6 | Hathazari | 415373011 | Romesh Mohazan Road | WD-UNR-CTG-HATHA-13/26 | Not DPP | [5 empty] | 19.09 |  |  |  | 19.09 | BC | 2013-08-04
7 | Hathazari | 415373007 | Chadgazi Road. | WD-UNR-CTG-HATHA-11/21 | 4 |  | BC | 168 | 1 | - | 15.33 | 2011-04-08 | 0.8 |  | 15.33 | BC | 2011-02-11 | M/S Hasan & Brothers | 48.5
7 | Hathazari | 415373007 | Chadgazi Road. | WD-UNR-CTG-HATHA-13/28 | [5 empty] | - | 35.71 |  |  |  | 35.71 | BC | 2013-07-11
8 | Hathazari | 415373001 | Cont.Of 30.05 Long RCC Girder Bridge On Hazee Yusuf Road Over Boalia Khal. | WD-UNR-CTG-HATHA-12/22 | [5 empty] | 30.05 | 164.4 | 2012-10-06 |  | 30.05 | 164.4 | RCC | 2012-10-06 | M/S Bengal Trading Ege | 213.2 | 2012-06-12
9 | Hathazari | 415373007 | Cont. Of 30.05m Long RCC Girder On Chand Gazi Road | WD-UNR-CTG-HATHA-12/23 | [5 empty] | 30.05 | 164.55 | 2012-10-07 |  | 30.05 | 164.55 | RCC | 2012-10-07 | M/S Bengal Trading Ege | 213.39 | 2012-06-12
10 | Hathazari | 415373005 | Cont. Of 27.05m Long RCC Girder On Fatehpur Madrasha Road | WD-UNR-CTG-HATHA-12/24 | [5 empty] | 27.05 | 162.72 | 2012-10-06 |  | 27.05 | 162.72 | RCC | 2012-10-06 | M/S Bengal Trading Ege | 211.21 | 2012-06-12
11 | Hathazari | 415373006 | Noor Ahamed Chowdhury (Remaining Part) Road | WD-UNR-CTG-HATHA-13/29 | 2.38 | 1.5 | HBB | 82.86 | 1 |  | 28 | 29/08/13 | 0.678 |  | 24.34 | BC | 18/12/13 | M/S Ali & Brothers | 25.56
12 | Hathazari | 415373001 | Hazi Yosuf (Remaining Part) Road | WD-UNR-CTG-HATHA-13/30 |  |  |  |  | 1 |  | 42 | 29/08/13 | 1.07 |  | 36.92 | BC | 18/12/13
| Hathazari | 415372008 | Mehaenega Road By Bc | WD-UNR-CTG-HATHA-14/31 | 1 |  | BC | 70.67 | 2 |  | 60 |  | 2 |  | 59.99 | BC | 2014-11-06
12 |  |  | Sub-Total |  | 20.81 | 86.5 |  | 1040.26 | 11.28 | 90.15 | 940.32 |  | 9.538 | 108.75 | 930.93 |  |  |  | 969.92 |  |  |  | 136.46
21.81
Village Road
1 | Hathazari | 415375289 | Gorduara Abdul nobi sowdagor, Dr. nazir ahmed, kanter ali chowdhary & Amir ali sowdagor |  | 1.5 |  | HBB | 37.5 | 1.5 | - | 37.5 | [10 empty] | 0
2 | Hathazari | 415375306 | Fuzlul Hoque Chowdhary road 00-1300 | WD-VZR-CTG-HATHA-10/05 | Not in DPP |  | HBB |  | 1.3 |  | 24.78 |  | 1.3 |  | 27.94 | HBB | 2012-01-03 | M/S Saha Amanat Ent | 23.54 |  |  |  |  | W/O.Cancell
3 | Hathazari | 415375307 | Abdul Kader Ukil road 00-1200 | WD-VZR-CTG-HATHA-10/06 |  |  | HBB |  | 1.2 |  | 21.01 |  | 1.2 | 21.01 | 21.01 | HBB | 2010-01-08 | Tuhin Enterprise | 20.84 | 2010-10-10 | 23/2/11 R30/12/11 | 50%
4 | Hathazari | 415375308 | West Gorduara east mekhal road 00-1050 | WD-VZR-CTG-HATHA-10/07 |  |  | HBB |  | 1.05 |  | 18.7 |  | 1.05 |  | 18.7 | HBB | 2010-01-08 | Tuhin Enterprise | 18.7 | 2010-10-10 | 23/2/11 R22/02/12 | 90% | 6.71
5 | Hathazari | 415375327 | Uttor Mekhol Dosh Mohammad Abdul Goni road 00-80 | WD-VZR-CTG-HATHA-10/08 |  |  | HBB |  | 0.75 |  | 1.34 |  | 0.75 |  | 1.34 | HBB | 2010-01-08 | Chowdury Enterprise | 1.34 | 2010-10-10 | 23/2/11 | 100% | 1.06 | FinalBillPaid
6 | Hathazari | 415375328 | Mirza Ali road 00-70 | WD-VZR-CTG-HATHA-10/09 |  |  | HBB |  | 0.7 |  | 1.22 |  | 0.7 |  | 1.22 | HBB | 2010-01-08 | Tuhin Enterprise | 1.22 | 2010-10-10 | 23/2/11 | 100% | 1.15 | Completed
7 | Hathazari | 415375019 | Rahmania (North Madrasha) road. 00-750 | WD-VZR-CTG-HATHA-10/10 |  |  |  |  | 1.5 |  | 32.65 | 2010-08-08 | 0.75 | 7.2 | 32.65 | HBB | 27/09/10 | Ifaque Traders | 30.25 | 2010-12-12 | 25/12/11 R05/12/12 | 100% | 18.45
8 | Hathazari | 415375311 | North Mekal Dosto Mohammad Abdul Goni connecting road.00-825 | WD-VZR-CTG-HATHA-10/11 |  |  |  |  | 0.825 |  | 9.45 |  | 0.825 |  | 9.45 | BC & HBB | 30/09/10 | Alam & Brother's | 26.89 | 2010-12-12 | 25/12/11 | 100% | 9.24
8 | Hathazari | 415375311 | North Mekal Dosto Mohammad Abdul Goni connecting road.00-825 | WD-VZR-CTG-HATHA-13/27 | [10 empty] | 18.21 | BC & HBB | 2013-07-11
9 | Hathazari | 415375082 | Jan Ali Chowdhury Road 00-617 | WD-VZR-CTG-HATCA-10/12 | Not DPP |  |  |  | 0.577 |  | 8.8 |  | 0.577 |  | 8.8 | BC | 19/10/10 | Gulzan Traders | 8.79 | 18/12/11 | 2012-01-02 | 100% | 4.39
10 | Hathazari | 415374004 | Daimunddin Shah Bashirulla Miazi Kala Khan road 00-600 | WD-VZR-CTG-HATCA-10/13 | Not DPP |  |  |  | 0.6 | 1.8 | 25.76 |  | 0.6 | 1.8 | 25.76 | BC | 19/10/10 | Gulzan Traders | 25.75 | 18/12/11 | 2012-01-02 | 100% | 20.74 | Finalbillpaid
11 | Hathazari | 415375291 | Hazee Abdul Barik Mistry Road | WD-VZR-CTG-HATHA-10/15 | Not DPP |  |  |  | 0.35 | 11.2 | 41.06 |  | 0.35 | 11.2 | 41.06 | BC | 09/11/10 | Milton Entertprise | 38.86 | 18/12/11 | 2012-01-02 | 85% | 23.44
12 | Hathazari | 415375275 | Jinnat Ali Minnat Ali-Zinnat Ali Road. 00-1000 | WD-VZR-CTG-HATHA-10/17 | Not DPP |  |  |  | 1 | 12 | 17.43 |  | 1 | 12 | 18.07 | HBB | 2012-01-03 | M/S United Tradind Co. | 16.55 | 18/01/11 | 2012-01-02 |  |  | W/O.Cancell
13 | Hathazari | 415375311 | Chowhuri Bari Road. | WD-VZR-CTG-HATHA-10/18 | Not DPP |  |  |  | 0.3 |  | 6.74 |  | 0.3 |  | 6.74 | HBB | 09/11/10 | Sagor Enterprise | 6.4 | 18/12/11 | 2012-01-02 | 15%
14 | Hathazari | 415374124 | Construction of 3x4x4m RCC Box Culvert | WD-VZR-CTG-HATHA-10/19 | Not DPP |  |  |  |  | 12 | 15.46 |  |  | 13.26 | 19.08 | Culvert | 14/03/13 | M/S S.M Trading | 20.03
15 | Hathazari | 415375031 415375021 | Jibon Chowdhury Road. | WD-VZR-CTG-HATHA-11/20 | Not DPP |  |  |  | 1 |  | 25 | 2011-04-08 | 0.65 |  | 23.7 | HBB | 2011-02-11 | M/S Rangdhonu | 24.96 | 24/01/12 | 14/08/12 RR30/06/13 | 50%
16 | Hathazari | 415375330 | Ahammad Sowdagar Bari Road |  | Not DPP |  |  |  | 0.5 |  | 13 | 14/05/12
17 | Hathazari | 415374097 | Dr.Sanaullah Berister Road | WD-UNR-CTG-HATHA-14/32 | 1 |  | HBB | 28 | 1 |  | 25 |  | 0.8 |  | 24.99 | BC | 2014-10-07
17 |  |  | Sub - Total |  | 1.5 | 0 |  | 37.5 | 14.152 | 37 | 324.9 |  | 10.852 | 66.47 | 298.72 |  |  |  | 264.12 |  |  |  | 85.18
29 |  |  | Total |  | 22.31 | 86.5 |  | 1077.76 | 25.432 | 127.15 | 1265.22 |  | 20.39 | 175.22 | 1229.65 |  |  |  | 1234.04 |  |  |  | 221.64
Union Road
1 | Sandwip | 415783004 | Circular Road (Amanullah UP H/Q. Sontoshpur UP H/Q.) and Nowapara Ahasania Road. | WD-UNR-CTG-SAND-10/01 | 1.9 | 5 | BC | 92.3 | 1.9 | 5 | 92.3 |  | 1.52 |  | 67.45 | BC | 2010-04-05 | Dabor Traders | 67.4 | 2010-09-12 | 22/4/11 | 100% | 67.3 | FinalBillPaid
2 | Sandwip | 415783005 | D.B. Road | WD-UNR-CTG-SAND-10/02 | 1 | 5 | HBB | 42.5 | 1 | 5 | 42.5 |  | 1 |  | 42.5 | HBB | 2010-04-05 | Manna Enterprise | 42.5 | 2011-09-12 | 22/4/11 | 100% | 42.48 | FinalBillPaid
3 | Sandwip | 415784003 | Gasua-Bauria Border Road By Bc(Via Zamalul Mawla House) | WD-UNR-CTG-SAND-12/03 |  |  |  |  | 1.25 |  | 48 | 17/09/12 | 1.25
4 | Sandwip | 415784073 | Bauria Cross Road. | [5 empty] | 1 |  | 40 | 2012-11-12
5 | Sandwip | 415784066 | Shekh Hasina Road. | WD-UNR-CTG-SAND-13/04 |  |  |  |  | 1 |  | 40 | 2012-11-12 | 1 | 0.625 | 39.34 | RCC | 17/04/13
| Sandwip | 415784069 | Sarafat Ali Road in Bouria Union |  | 1 |  | HBB | 28 | 1 |  | 25 | 22/07/14
5 |  |  | Total |  | 2.9 | 10 |  | 134.8 | 7.15 | 10 | 287.8 |  | 4.77 | 0.625 | 149.29 |  |  |  | 109.9 |  |  |  | 109.78
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Satkania | 415823029 415823022 | Sonakania UP-Satkania UP Road | WD-UNR-CTG-SATKA-10/01 | 1 | 1.5 | BC | 45.75 | 1 | 1.5 | 45.75 |  | 0.892 |  | 45 | BC | 29/04/10 | Islam Construction | 44.95 | 25/7/10 | 8/12/2010 R30/04/11 | 65% | 21.71
2 | Satkania | 415823031 415533024 | Alur ghat Road | WD-UNR-CTG-SATKA-10/02 | 1 |  | BC | 42 | 1 |  | 42 |  | 0.97 |  | 41.72 | BC | 29/04/10 | A. Ananta Bikash | 41.7 | 25/7/10 | 8/12/2010 R30/05/11 | 100% | 41.69
3 | Satkania | 415823005 | Paschim Dhemsha Up - Chowdhury Hat road | WD-UNR-CTG-SATKA-10/06 | 1 | 3.45 | BC | 50.63 | 1 | 1 | 18.51 |  | 1.55 | 0.6 | 18.51 | BC | 27/12/10 | Bul Bul Construction | 43.49 | 2011-04-04 | 3/4/2012 R30/12/12 | 65%
4 | Satkania | 415823005 | Paschim Dhemsha Up - Chowdhury Hat road | WD-UNR-CTG-SATKA-13/19 | [6 empty] | 38.26 |  |  |  | 38.26 | BC | 2013-08-04
5 | Satkania | 415823001 | Amilaish UP - Kanchana UP Via Hilimili road | WD-UNR-CTG-SATKA-10/03 | 1 | 1.5 | HBB | 33.75 | 1 | 1.5 | 33.75 |  | 1.25 |  | 33.75 | HBB | 28/09/10 | Hazee Enterprise | 31.95 | 2010-12-12 | 25/12/11 | 100% | 31.76 | FinalBillPaid
6 | Satkania | GC | Karani Hat GC | WD-UNR-CTG-SA-GC-11/09 |  |  |  | 30 |  |  | 30 |  |  |  | 30.08 |  | 2011-05-04 | M/S Haque Construction | 28.57 | 2011-07-06 | 28/12/11 RRR30/05/13 | 65% | 10.79
6 | Satkania | GC | Chadaha Fakirhat Bazar Shed. | WD-UNR-CTG-SA-GC-14/22 |  |  |  | 40 |  |  | 35 | 2013-11-12 |  |  | 35 |  | 2014-11-06
7 | Satkania | 415822007 | Nolua-Satkania Road(Nolua Hyderkhal Bridge Road). | WD-UNR-CTG-SA-GC-11/11 |  |  |  |  | 1.5 |  | 50.02 | 20/09/11 | 1.5 |  | 66.7 |  |  | M/S Islam Construction | 66.68 | 27/11/11 | 18/06/12 | 50% |  | Termination R13/12/12
8 | Satkania | 415822007 | Nolua-Satkania Via Gatiadanga Highschool Road. | WD-UNR-CTG-SA-GC-12/17 | 1 |  | BC |  | 1.2 |  | 16.68 | 22/03/12 | 0.94 |  | 16.68 | BC | 2012-03-06 | M/S Subarno Enterpr | 35.94
| Satkania | 415822007 | Nolua-Satkania Via Gatiadanga Highschool Road. | WD-UNR-CTG-SA-GC-14/23 |  |  | BC |  |  |  | 26.43 |  |  |  | 26.43 | BC | 2014-11-06
9 | Satkania | 415823014 | Bomang hat Mahalia via Chadaha UP(Abul Hossain Chowdhory) Road | WD-VZR-CTG-SATKA-14/21 | 0.5 |  | HBB | 16 | 0.5 |  | 15 | 2013-02-01 | 0.553 |  | 14.74 | HBB | 31/03/14
9 |  |  | Sub-Total |  | 5.5 | 6.45 |  | 258.13 | 7.2 | 4 | 351.4 |  | 7.655 | 0.6 | 366.87 |  |  |  | 293.28 |  |  |  | 105.95
Village Road
1 | Satkania | 415825052 415825032 | Netapakir para - Samatigor connecting road. | WD-VNR-CTG-SATKA-10/04 | 1 |  | BC | 32.5 | 1 |  | 32.5 |  | 0.923 |  | 32.49 | HBB | 2010-01-08 | Tohid & Brother's | 30.86 | 2010-10-10 | 23/02/11 | 100% | 30.77 | FinalBillPaid
2 | Satkania |  | Barodona-Chibbarichora Bottola-Koryeanagar Khalaque shop (Deilar shop-Akbar bari Mosque) Road | WD-VNR-CTG-SATKA-10/07 | [6 empty] | 27 | 16/08/10 | [9 empty] | 0%
3 | Satkania | 415824076 | Barodona Chib Bari Chara Bottal-Kararia Nagar Khalaker Dokan (Daillar Dokan-Akbar Bari Jama Mosque) Road (Ch. 00.00-500m)& Brick Reatining Wall (Ch. 60-270m) | WD-VZR-CTG-SATKN-10/05 | Not DPP |  |  |  | 0.5 |  | 20.61 |  | 0.5 |  | 20.61 | BC | 09/11/10 | Bul Bul Construction | 19.58 | 18/1/11 | 2012-01-02 | 65%
4 | Satkania | 415825052 | Chituapara Kashem Bari Road | WD-VZR-CTG-SATKN-11/08 | Not DPP |  |  |  | 0.16 |  | 9.7 | 25/01/11 | 0.16 |  | 9.62 | RCC | 20/03/11 | M/S Haque Construction | 9.14 | 05/0/11 | 26/11/11 R30/06/12 | 100%
5 | Satkania | 415824112 | Sadaha Keochia High School Road(Hamid Ali Road). | WD-VZR-CTG-SATKN-11/10 | Not DPP |  |  |  | 1.4 |  | 48 | 18/08/11 | 1.415 |  | 45.94 | BC | 20/09/11 | M/S The Engg.Syndicate | 55.15 | 21/11/11 | 18/06/12 | 65%
6 | Satkania | 415824034 415824085 | Morhum Allama Fazlullah Road Under Madrasa | WD-VZR-CTG-SATKN-11/13 | 1 |  | BC | 32.5 | 1 |  | 32.5 | 2011-12-05 | 1 |  | 35.53 | BC | 2011-11-12 | M/S Nishan Traders | 35.52 | 2012-09-02 | 1/9/2012 R22/01/13
|  |  | Morhum Allama Fazlullah Road Under Madrasa (Remaining Work) | WD-UNR-CTG-SA-GC-14/24 |  |  | BC |  | 1 |  | 38 | 31/03/14 | 0.72 | 2.5 | 36.68 | BC | 23/07/14
7 | Satkania | 415824052 | Dhemsha H.School Road. | WD-VZR-CTG-SATKN-11/14 | 1 |  | BC | 32.5 | 1 |  | 32.5 | 2011-08-09 | 0.75 |  | 32.32 | BC | 2011-02-11 | M/S Ahanf Associate | 33.8 | 2012-03-05 | 24/11/12 |  |  | F-11-12 Above
8 | Satkania | 415824139 | Rampur Baitush Sharaf Road(Madrasha Dalu Embt.Road) | WD-VZR-CTG-SATKN-11/15 | 1 |  | BC | 32.5 | 1 |  | 32.5 | 27/10/11 | 1.533 |  | 32.32 | HBB | 18/12/11 | M/S Ahanf Associate | 32.19 | 2012-12-03 | 2012-02-10 | 1
9 | Satkania | 415823024 415824141 | Construction Of 36.05m Long RCC Girder Bridge Over Dalu Khal On Sikder Para-Maij Para Road . | WD-VZR-CTG-SATKN-11/12 |  | 30 |  | 60 |  | 36.05 | 121.32 | 17/11/11 |  | 36.05 | 121.32 | RCC | 17/11/11 | The Engineers Sindikate | 121.32
10 | Satkania | 415823024 415824141 | Construction Of 60.05m Long RCC Girder Bridge Over Dalu Khal On AlurghatvRoad . | WD-VZR-CTG-SATKN-11/16 |  | 60 |  | 150 |  | 60.05 | 161.89 | 18/12/11 |  | 60.05 | 161.89 | RCC | 1906-01-30 | M/S Chowdhury Syndic. | 1900-06-24 23:02 | 29/05/12 | 20/12/12 R30/05/13
11 | Satkania | 415824028 | Demsha Kanchana (Bokshirkhil) | WD-VZR-CTG-SATKA-12/18 |  |  |  |  | 1 |  | 42 | 22/10/12 | 1 |  | 40.06 | BC | 2012-08-12 | [6 empty] | Termination 08/04/14
12 | Satkania | 415824029 415824012 | Kutubpara Road-Choto Hatia Hazi Nur Ahamed Road –Miapara Mosque-Achartali Road | WD-VZR-CTG-SATKA-14/20 | 1.5 |  | BC | 42 | 1.5 |  | 40 | 2013-11-12 | 1.38 |  | 38.29 | BC | 2014-02-02
13 | Satkania | 415475298 | Garangia Safar Ali Road |  | 1 |  | HBB | 28 | 1 |  | 25 | 22/07/14
13 |  |  | Sub - Total |  | 5.5 | 90 |  | 382 | 10.56 | 96.1 | 663.52 |  | 9.381 | 98.6 | 607.07 |  |  |  | 514.52 |  |  |  | 30.77
20 |  |  | Total |  | 11 | 96.45 |  | 640.13 | 17.76 | 100.1 | 1014.92 |  | 17.036 | 99.2 | 973.94 |  |  |  | 807.8 |  |  |  | 136.72
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Sitakunda | 415863031 | Tarial Road | WD-UNR-CTG-SITAKU-10/03 | 1.75 |  | BC | 202.17 | 2 | - | 84 |  | 0.75 |  | 94.94 | BC | 24/04/12 | M/S Momtaz Building | 78.19 | 22/11/12 |  | 15% |  | Terminatio
2 | Sitakunda | 415863006 | Terial Road (ch. 1550m-2550m). | WD-UNR-CTG-SITAKU-13/10 |  |  |  |  | 1 |  | 94.93 | 2013-04-07 | 1 |  | 118.44 | BC | 2013-04-07 | M/S AssociateBuilde | 118.44 | 13/10/13 | 25/03/14 | 0.93 | 110.24
3 | Sitakunda | 415863008 | Sonaichari Raod | WD-UNR-CTG-SITAKU-10/01 | 0.88 |  | BC | 31.99 | 1.3 | - | 9.41 |  | 0.875 |  | 9.41 | BC | 2010-11-07 | Shahin Construction | 9.41 | 15/9/10 | 28/1/10 R15/05/11 | 39% | 9.41 | Terminatio
4 | Sitakunda | 415863009 | Sonaichari Raod | WD-UNR-CTG-SITAKU-13/14 | [5 empty] | - | 19.26 |  |  |  | 19.26 | BC | 13/02/13 | M/S R.F Traders | 20.22 | 2013-02-06 | 23/10/13 | 80%
5 | Sitakunda | 405863028 415863004 | Ambia Dhala Road | WD-UNR-CTG-SITAKU-11/06 | 0.64 |  | BC | 45.55 | 0.642 | 5 | 91.5 | 22/11/10 | 0.64 |  | 33.16 | BC | 24/04/12 | M/S Bismillah Enterprise | 41.41 | 28/11/12 | 19/12/12 | 0.24 | 10.03
5 |  |  | Sub-Total |  | 3.27 | 0 |  | 279.71 | 4.942 | 5 | 299.1 |  | 3.265 | 0 | 275.21 |  |  |  | 267.67 |  |  |  | 129.68
Village Road
1 | Sitakunda | 415863009 415864133 | Sitakunda Bazar (Mandir) to 2 no. Baropul Road | WD-VZR-CTG-SITAKU-10/02 | 1.407 |  | BC | 58.75 | 1.5 | - | 20.46 |  | 1.407 |  | 20.46 | BC | 2010-11-07 | Shahin Construction | 20.46 | 15/9/10 | 28/1/11 R10/05/11 | 50% | 20.46
2 | Sitakunda | 415864133 | Sitakunda Bazar (Mandir) to 2 no. Baropul Road(Remaining) | WD-VZR-CTG-SITAKU-13/13 | [5 empty] | - | 29.93 |  |  |  | 29.93 | BC | 13/02/13 | M/S Saha Amanat Tra. | 34.32 | 2013-09-01 | 20/03/14 | 40% |  | Revised
3 | Sitakunda | 415864134 | Uttar Masjida MuhuriRoad(Durjabari Part) |  | 1 |  | BC | 32.5 | 1 | - | 32.5
4 | Sitakunda | 415864043 415864036 | Dokkhin Batiari Bazar to Mahtab bibi road ( St. from R&H Road) | WD-VZR-CTG-SITAKU-10/04 | 0.45 | 0.6 | BC | 16.25 | 1 | - | 32.5 |  | 0.45 | 0.9 | 15.55 | BC | 25/10/10 | M/S Faruk Builders & Trading Agency | 14.77 | 18/1/11 | 2012-01-12 | 100% | 14.15
5 | Sitakunda | 415865042 | Napitarchara Road. | WD-VZR-CTG-SITAKU-11/05 | 0.26 |  | HBB | 47.3 | 1 | - | 30 | 17/01/11 | 0.255 |  | 33.49 | HBB | 24/04/12 | M/S Assosicts Buillders | 43 | 28/11/12 | 19/06/13 | 0
6 | Sitakunda | 415864101 | Korban Ali Road | WD-VZR-CTG-SITAKU-13/07 | Not in DPP |  |  |  | 0.6 |  | 25.95 |  | 0.6 |  | 25.95 | BC | 22/05/13
7 | Sitakunda | 415865174 | Mir Awlia Mazar Road | WD-VZR-CTG-SITAKU-13/08 | Not in DPP |  |  |  | 1.05 |  | 40.34 |  | 1.05 |  | 40.34 |  |  | M/S Murad & Sons | 42.35
8 | Sitakunda | 415864039 | Jane Alom Munshi Road | WD-VZR-CTG-SITAKU-13/09 | Not in DPP |  |  |  | 0.707 |  | 33.73 | 2013-04-07 | 0.707 |  | 33.73 | BC | 2013-04-07
9 | Sitakunda | 415864073 | Modha Mahmudabad Road | WD-VZR-CTG-SITAKU-13/11 | Not in DPP |  |  |  | 2.5 | 1.8 | 65.8 | 2013-04-07 | 2.5 | 1.8 | 65.8 | BC | 2013-04-07
10 | Sitakunda | 415864046 | Darbesh Eyusuf Ali Road | WD-VZR-CTG-SITAKU-13/12 | Not in DPP |  |  |  | 0.225 |  | 7.8 | 2013-04-07 | 0.225 |  | 7.8 | BC | 2013-04-07
11 | Sitakunda | 415864117 | Madham Bibir Hat-Sithakundu Navy Camp Road | WD-VZR-CTG-SITAKU-13/15 | 2 |  | BC | 80 | 2 |  | 80 | 14/07/13 | 1.034 |  | 61.71 | BC | 2013-02-12 | M/S Yaquab & Brothe. | 104.53
12 | Sitakunda | 415864118 | Zoghi Para Road In Sonaichari Union | WD-VZR-CTG-SITAKU-13/16 | Not in DPP |  |  |  | 1.5 |  | 60 | 14/07/13 | 0.59 |  | 45.96 | BC | 2013-02-12
13 | Sitakunda | 415865015 | Kotpara Alekdia Road | WD-VZR-CTG-SITAKU-13/17 | Not in DPP |  |  |  | 0.7 |  | 30 | 14/07/13 | 0.997 |  | 26.36 | BC | 2013-02-12
14 | Sitakunda | 415864119 | Chittagong Cantonment Road from Batiary Baraddighirpar Road at 4no. MP Checkpost via 1no. MP Checkpost to Baizid Bustami Road By BC | WD-VZR-CTG-SITAKU-14/18 | 1.75 |  | BC | 100 | 3.137 |  | 97.73 |  | 3.14 |  | 97.73 | BC | 2014-02-02
14 |  |  | Sub - Total |  | 6.867 | 0.6 |  | 334.8 | 16.919 | 1.8 | 586.74 |  | 12.955 | 2.7 | 504.81 |  |  |  | 259.43 |  |  |  | 34.61
19 |  |  | Total |  | 10.137 | 0.6 |  | 614.51 | 21.861 | 6.8 | 885.84 |  | 16.22 | 2.7 | 780.02 |  |  |  | 527.1 |  |  |  | 164.29
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Lohagara | 415473010 415473003 | Amirabad UP-Khalauzan Road | WD-UNR-CTG-LOHA-10/01 | 1 | 5 | BC | 54.5 | 1 | 5 | 54.5 |  | 1 | 5 | 54.19 | BC | 16/05/10 | Tilhi Association | 54.18 | 16/8/10 | 29/2/11 R15/05/11 | 100% | 32.36
2 | Lohagara | 415473009 415473026 | Putivilla Sarail Ramvilla Road | WD-UNR-CTG-LOHA-10/02 | 1 | 5 | BC | 54.5 | 1 | 5 | 54.5 |  | 1 | 5 | 53.76 | BC | 16/05/10 | Zan Zan AutoRice Mills | 53.57 | 16/8/10 | 29/09/11 RR30/06/11 | 100% | 53.27
3 | Lohagara | 415473007 | Kalauzan Niz Taluk Road | WD-UNR-CTG-LOHA-11/08 | 1 | 5 | BC | 54.5 | 1 | 5 | 51.7 | 27/12/10 | 1.508 |  | 50.76 | BC | 2011-05-04 | M/S Dipu Kanti Pal | 51.41 | 2011-07-06 | 28/12/11 | 100% | 27.86 | Variati App.
4 | Lohagara | GC | Tewari Hat GC/Hat Bazar. | WD-UNR-CTG-LOHA/GC-12/11 |  |  |  | 30 |  |  | 30 | 2011-08-09 |  |  | 29.28 |  | 28/03/12
5 | Lohagara | 415475043 415475031 | Chramba Majider Para Road | WD-UNR-CTG-LOHA-12/12 | 1 |  | HBB | 25 | 1 |  | 25 | 2012-01-13 | 1.118 | 2.5 | 24.78 | HBB | 2012-07-05 | M/S Alam Enterprise | 28.37
6 | Lohagara | 415473015 | Abdul Khalique Sha Road. | WD-UNR-CTG-LOHA-13/16 | 1 | 4.8 | HBB | 42 | 1 |  | 40 | 2012-11-12 | 1.332 |  | 39.3 | HBB | 13/02/13 | M/S Shilpy Construction | 41.26
7 | Lohagara | 415473013 | Padua Andhar Manik Road | WD-UNR-CTG-LOHA-12/13 | 1 | 5 | BC | 54.5 | 1 |  | 30 | 2012-01-03 | 1.028 |  | 29.37 | HBB | 2012-03-06
8 | Lohagara | 415473005 | Chunti Satgar Sha Ataullah Road(Borua Para Dokan) Road. | WD-UNR-CTG-LOHA-13/14 |  | Not DPP |  |  | 1 |  | 40 | 26/11/12 | 1 |  | 41.31 | BC | 17/01/13
9 | Lohagara | 415473006 | Construction of 2vent-4.00mx3.00m Long RCC Box Culvert on Barahatia Yasin Para Road | WD-UNR-CTG-LOHA-13/28 |  | Not DPP |  |  |  | 8 | 15.32 |  |  | 8 | 15.54 | ST |  | M/S Harun & Brothers | 16.31
9 | Lohagara |  | Sub-Total |  | 6 | 24.8 |  | 315 | 7 | 23 | 341.02 |  | 7.986 | 20.5 | 338.29 |  |  |  | 245.1 |  |  |  | 113.49
Village Road
1 | Lohagara | 415475287 415475291 | Jalil Nagar Chowdhury para road. | WD-VZR-CTG-LOHA-10/03 | 1.5 |  | HBB | 37.5 | 1.5 | - | 37.5 |  | 1.5 |  | 33.61 | HBB | 16/05/10 | DOT Enterprise | 33.58 | 16/8/10 | 29/2/11 | 100% | 33.57 | FinalBillPaid
2 | Lohagara | 415475123 415475292 | Charmba Rajghata Primary School Abul Wafa road | WD-VZR-CTG-LOHA-10/04 | 1 |  | HBB | 25 | 1 |  | 23.75 | 11/10/10 | 1.212 |  | 23.75 | HBB | 27/12/10 | M/S Nishan traders | 22.56 | 30/03/11 | 29/03/12 | 100% | 22.53 | FinalBillPaid
3 | Lohagara | 415474032 | Darbesh Hat maijbilla Road | WD-VZR-CTG-LOHA-10/05 | 1 |  | BC | 32.5 | 1 |  | 30.85 | 03/11/10 | 0.807 |  | 30.47 | BC | 27/12/10 | M/S Md. Faruk | 28.94 | 2011-09-03 | 29/03/12 | 100% | 28.72 | FinalBillPaid
4 | Lohagara | 415475282 415475278 | Amirabad Kamar Digi Road. | WD-VZR-CTG-LOHA-10/06 |  | NOT DPP |  |  | 1.1 | - | 15.33 | 22/11/10 | 1.04 |  | 15.33 | BC | 17/01/11 | M/S TazinEnterprise | 28.75 | 2011-09-04 | 29/03/12 | 70% | 12.86 | Terminatio
5 | Lohagara | 415475278 | Amirabad Kamar Digi Road. | WD-VZR-CTG-LOHA-13/22 | [5 empty] | - | 19.41 | 17/04/13 |  |  | 19.41 | BC | 17/04/13
6 | Lohagara | 415475284 415475025 | Charamba Maizbila Bibirbila Road | WD-VZR-CTG-LOHA-11/07 | 1 |  | HBB | 25 | 1 | - | 23.75 | 27/12/10 | 1.499 |  | 23.65 | HBB | 2011-05-04 | M/S Nurul Absar Chowd. | 23.65 | 2011-07-06 | 28/12/11 | 100% | 23.65 | FinalBillPaid
7 | Lohagara | 415474024 415474024 | Kalauzan-Sukchari Kalibari Road | WD-VZR-CTG-LOHA-11/09 | 1 | 5 | BC | 54.5 | 1.1 | 5 | 41.06 | 17/01/11 | 1.1 |  | 41.06 | BC | 2011-05-04 | M/S Dipu Kanti Pal | 50.48 | 2011-07-07 | 28/12/11 | 100% | 24.16 | Terminatio 02/01/13
7 | Lohagara | 415474024 415474024 | Kalauzan-Sukchari Kalibari Road(Remaining Work) | WD-VZR-CTG-LOHA-13/27 |  |  |  |  | 1.1 |  | 21.86 |  | 1.1 |  | 19.88 | BC | 2013-01-10 | M/S Shilpy Constru. | 21.86
8 | Lohagara | 415445067 415475050 | Kanuram Bazar To Harina Road. | WD-VZR-CTG-LOHA-11/10 | 1 |  | HBB | 25 | 1 |  | 25 | 2011-04-08 | 0.962 |  | 24.92 | HBB | 2011-02-11 | M/S Alam Enterprise | 23.68 | 24/01/12 | 14/08/12 | 1
9 | Lohagara | 415472004 | Padua Chibbari Road. | WD-VZR-CTG-LOHA-13/15 |  |  | HBB |  | 1 |  | 40 | 2012-11-12 | 0.963 | 1.25 | 38.1 | BC | 13/02/13 | M/S Anower Constr. | 54.69
10 | Lohagara |  | Borohatia Dany Shikderpara Road. |  |  | NOT DPP | HBB |  | 1 |  | 40 | 2012-11-12 | 0.965 |  | 38.96 | BC | 20/02/13
11 | Lohagara |  | Amirabad Muktizuddha Saifur Rahman Road. | WD-VZR-CTG-LOHA-13/18 |  |  | HBB |  | 1 |  | 40 | 2012-11-12 | 1.769 |  | 39.12 | HBB | 20/02/13 | M/S Kabir Ahammed | 41.08
12 | Lohagara | 415474030 | Lohagara Rashider Para Road By BC. | WD-VZR-CTG-LOHA-13/23 |  |  | BC |  | 1 |  | 35 | 23/01/13 | 0.75 |  | 26.78 | BC | 25/04/13 | M/S Alam Enterprise | 43.22 | 31/03/14
13 | Lohagara | 415475297 | Construction of 3 Vent 5mx5m RCC Box Culvert On Amir Baper Para Rampur DC Road Over Thomthomia Khal | WD-VZR-CTG-LOHA-13/21 |  | NOT DPP | BC |  |  | 16.6 | 33.17 | 23/01/13 |  | 16.6 | 33.18 | RCC | 17/04/13 | M/S Md. Faruk | 34.83
14 | Lohagara | 415473011 | Padua Saha Mozidia(Tewari Hat GC) Road | WD-VZR-CTG-LOHA-13/20 |  |  | BC |  | 1.5 |  | 30 | 23/01/13 | 1.5 |  | 33.92 | BC | 17/04/13 | M/S Md. Faruk | 35.62
15 | Lohagara | 415474026 | Construction Of 20.00m Long RCC Girder Bridge On Ratar Khal Chunati Serrat Mahaffil Road | WD-VZR-CTG-LOHA-13/19 |  |  | BRIDGE |  |  | 20 | 104.34 | 2013-03-03 |  | 20 | 104.34 |  | 2013-03-03 | M/S Mazid Corporation JV Aslam & Co.
16 | Lohagara | 415474011 | Padua Madrasha Road(Part-2) | WD-VZR-CTG-LOHA-13/25 |  |  | NOT DPP |  | 1 |  | 22 | 2013-09-05
17 | Lohagara | 415475069 | Construction of 2vent 4.00mx3.6m RCC Box-Culvert on Darbar Sharif Road Over Sonaichari Chara(Ch.150m). | WD-VZR-CTG-LOHA-13/24 |  |  | NOT DPP |  |  | 8 | 16.99 | 13/06/13 |  | 8 | 16.99 | ST |  | M/S M Rahman Tra. | 17.84
17 | Lohagara | 415474028 | Barahatia Esataul Ulom Road.(Band---BAND) ********* | WD-VZR-CTG-LOHA-13/26 |  |  | NOT DPP |  | 1 |  | 35.23 | 15/09/13
18 | Lohagara | 415475306 | Amir Baper Para Road | WD-VZR-CTG-LOHA-14/29 |  |  |  |  | 0.386 | 13.6 | 29.52
19 | Lohagara | 415475227 | Barahatia Durga Pukur Maizb Para Road | WD-VZR-CTG-LOHA-14/29 |  |  |  |  | 0.786 |  | 19.58 |  | 0.786 |  | 19.58 | HBB | 31/03/14
20 | Lohagara | 415475257 | Amirbad Kabir Mohammad Para Road | WD-VZR-CTG-LOHA-14/30 |  |  |  |  | 0.7 |  | 18.18 |  | 0.7 |  | 18.18 | HBB | 31/03/14
21 | Lohagara | 415474055 | Amirabad Joynab Kabir Academy Road in Amirabad Union |  | 0.5 |  | HBB | 14 | 0.5 |  | 12 | 31/03/14
22 | Lohagara | 415475298 | Charamba Nasir Mohammad Para-Majid Master Road |  | 0.7 |  | HBB | 20 | 0.7 |  | 17 | 31/03/14
23 | Lohagara | 415475300 | South Adhunagar Rustomer para Road |  | 0.7 |  | HBB | 20 | 0.7 |  | 17 | 31/03/14
24 | Lohagara | 415475308 | Amir Baper Para Rampur DC Asraon Prokolpo Connecting Road | WD-VZR-CTG-LOHA-14/31 | 0.7 |  | HBB | 20 | 0.4 | 1.6 | 18.02 | 2014-11-06 | 0.4 | 1.6 | 18.02 | HBB | 11/.6/14
25 | Lohagara | 415475305 | Hazrat Chingi Shah Road | WD-VZR-CTG-LOHA-14/32 | 0.7 |  | HBB | 20 | 0.8 |  | 17.69 | 2014-11-06 | 0.8 |  | 17.69 | HBB | 2014-11-06
26 | Lohagara | 415475306 | Boro Hatia Amir Baper Para Road. | WD-VZR-CTG-LOHA-14/33 | 1 | 12 | HBB | 36 | 0.386 | 4 | 29.52 | 2014-11-06 | 0.386 | 4 | 29.52 | HBB | 2014-11-06
27 | Lohagara | 41574055 415475321 | Amirabad Joynab Kabir Academy Road in Amirabad Union | WD-VZR-CTG-LOHA-14/34 | 0.5 |  | HBB | 14 | 0.5 |  | 12 |  | 0.496 |  | 11.73 | HBB | 2014-10-07
28 | Lohagara | 415475298 | Charamba Nasir Mohammad Para-Majid Master Road | WD-VZR-CTG-LOHA-14/35 | 0.7 |  | HBB | 20 | 0.7 |  | 17 |  | 0.717 |  | 16.63 | HBB | 2014-10-07
29 | Lohagara | 415475300 415475215 | South Adhunagar Rustomer para Road | WD-VZR-CTG-LOHA-14/36 | 0.7 |  | HBB | 20 | 0.617 |  | 17 |  | 0.617 |  | 16.65 | HBB | 2014-10-07
30 | Lohagara | 415474066 | Const. of 2 vent 5.0mX3.6m RCC Box-Culvert on Natun Miaji Para & Solir Bor Para Conecting Road over Ratar Chara Khal. |  |  | 10 | ST | 35 |  | 10 | 30 | 22/07/14
30 |  |  | Sub - Total |  | 9.1 | 5 | 0 | 273.5 | 23.475 | 63.2 | 889.75 | 247174 | 16.653 | 45.85 | 601.23 |  |  |  | 460.78 |  |  |  | 145.49
39 |  |  | Total |  | 15.1 | 29.8 | 0 | 588.5 | 30.475 | 86.2 | 1230.77 | 247174 | 24.639 | 66.35 | 939.52 |  |  |  | 705.88 |  |  |  | 258.98
Union Road
1 | Banshkhali | 415083041 | Baharchara UP Office Gondamara Bazar Road | WD-UNR-CTG-BANSH-10/01 | 1 | 5 | BC | 54.5 | 1 | 5 | 54.5 |  | 1.8 |  | 54.21 | BC | 2010-04-05 | Gangchil Association | 54.15 | 25/7/10 | 8/12/2010 RR31/05/12 | 100% | 27.4
2 | Banshkhali | 415083042 | Sarai UP to Silkup UP Office | WD-UNR-CTG-BANSH-10/02 | 1.5 | 5 | BC | 75.5 | 1.5 | 5 | 75.5 |  | 1.765 |  | 75.23 | BC | 2010-04-05 | Aysha Construction | 75.17 | 25/7/10 | 8/12/2010 RR30/04/11 | 20% |  | Terminatio 05/06/12
3 | Banshkhali | 415083009 | Chamble Bangla bazar via LGED bridge (JAICA) Boro ghona Rahmania road. | WD-UNR-CTG-BANSH-10/03 | 1.95 |  | BC | 81.9 | 1.1 | - | 46.2 |  | 1.14 |  | 45.72 | BC | 2010-04-05 | Aysha Construction | 45.67 | 25/7/10 | 8/12/2010 R30/04/11 | 20%
4 | Banshkhali | 415083019 | Bara - Moulana Road | WD-UNR-CTG-BANSH-10/04 | 1.5 |  | BC | 63 | 1.5 | - | 63 |  | 1.88 |  | 60.92 | BC | 2010-04-05 | Aysha Construction | 60.9 | 25/7/10 | 8/12/2010 R30/04/11 | 60% | 22.58
5 | Banshkhali | 415083017 | Indra Narayon Road | WD-UNR-CTG-BANSH-10/05 | 1.35 |  | BC | 56.7 | 1.35 |  | 55 | 2010-08-08 | 0.825 |  | 50.23 | BC | 27/09/10 | Maysha Trading Co. | 50.2 | 2011-09-01 | 2/2/2012 R30/06/13 | 70% | 25.79 | Terminatio 11/03/14
6 | Banshkhali | 415083041 415083018 | Baharchara UP Office To Gandamara Bazar Via Katharia And Saral Union Road(saral Bridge To Amiruzzaman fakir Mazar). | WD-UNR-CTG-BANSH-11/12 | 1 | 5 | BC | 54.5 | 1.96 |  | 80 | 13/03/11 | 1.65 | 10.97 | 61.7 | HBB
7 | Banshkhali | 415083003 | Upazila H/Q To Gondamara UP Office Road(Dack Bangla-Gandamara Up to Mattabar Para Road) | WD-UNR-CTG-BANSH-11/08 | 1.5 |  | BC | 63 | 1 |  | 42 | 21/12/11 | 0.9 |  | 41.24 | BC | 19/01/12 | M/S ShakeInternational | 50.72 | 2012-06-12 |  |  |  | Terminatio 11/06/14
8 | Banshkhali | 415083012 | Monsuria Bazar to Silkup UP Office Road. | WD-UNR-CTG-BANSH-11/09 | 1.9 |  | BC | 79.8 | 1 |  | 42 | 21/12/11 | 0.897 |  | 41.15 | BC | 19/01/12 | M/S Romana Enterprise | 43.21 |  | R30/06/13
9 | Banshkhali | 415083021 | Chunti Bazar to Basirullah Miazir Bazar To Mosharaf Miazi BazarUp To Upokulio College Road(West Side Of Jalkadar Khal) | WD-UNR-CTG-BANSH-11/10 |  | NOT DPP |  |  | 2 |  | 50 | 21/12/11 | 1.89 |  | 50 | HBB | 19/01/12 | M/S Jonosaba Enterpr. | 57.45 |  | R30/05/13
10 | Banshkhali | 415083001 | Kalipur UP To Khankhanabad Bazar Road(Advocate Abdus Sobur Chowdhury) | WD-UNR-CTG-BANSH-12/14 |  | NOT DPP |  |  | 1 | 1.2 | 40.81 | 2012-10-09 | 1 | 1.2 | 40.81 | BC | 13/9/2012
11 | Banshkhali | 415083019 | Moulana mosharaf Ali Hat To Baharchara UP Road. | WD-UNR-CTG-BANSH-11/11 |  | NOT DPP |  |  | 0.52 |  | 24 | 21/12/11 | 0.52 |  | 24.07 | BC | 19/01/12 | M/S Shake Enterprise | 30.41 | 41072
12 | Banshkhali | 415083015 | Napora-Sekherkhil Union Parisad(Sekherkhil Union Parisad) |  | 1.5 |  | BC | 63 | 1 |  | 42 | 2012-01-03
13 | Banshkhali | 415083008 | Moulana Asraf Ali Road(Chanua UP to Khankha-nabab up via Gondamara,Saral,Kathara, Baharchara) | WD-VZR-CTG-BANSH-13/16 | 1 |  | HBB | 30 | 1 |  | 40 | 26/11/12 | 0.94 | 2.4 | 31.72 | HBB | 13/02/13
14 | Banshkhali | 415083020 | Pairang Jaliaghata (Banshkhsli Main Road-Baraithali)Road | WD-VZR-CTG-BANSH-13/24 | 1 | 8 | HBB | 30.8 |  | 8 | 28 | 28/02/13 |  | 8 | 15.06 | ST | 2013-02-12 | M/S Suvassa Corpo. | 15.81
15 | Banshkhali | 415083021 | Mosarof Ali Bazar-Bashirullah Bazar Paschim Kull Conecting Road | WD-VZR-CTG-BANSH-13/34 | 1 |  | HBB | 33 | 1 |  | 3 | 19/11/13 | 0.999 |  | 27.82 | HBB | 2014-09-02
15 |  |  | Sub Total |  | 16.2 | 23 |  | 685.7 | 16.93 | 19.2 | 686.01 |  | 16.206 | 22.57 | 619.88 |  |  |  | 483.69 |  |  |  | 75.77
Village Road
1 | Banshkhali | 415085181 415085131 | Chandpur Sayed Solaiman shah Road (Up to Jhinuk Poltree Unit-2) | WD-VZR-CTG-BANSH-12/07 | 1 | - | HBB | 25 | 1 |  | 23.75 | 27/12/10 | 1.273 |  | 27.59 | HBB | 22/03/12 | M/S Banshkhali Floor Mil | 33.58
2 | Banshkhali | 415085118 | Const. of 2 vent 4.3x3.6m RCC Box Culvert on Chapachari - Asraf Ali Road | WD-VZR-CTG-BANSH-12/06 | 1 | 10 | BC | 52.5 |  | 8.6 | 14.28 |  |  | 8 | 14.65 | RCC | 22/03/12 | M/S Alamgir Store | 18.45
3 | Banshkhali | 415084108 415085079 | Omed Ali Munshi Road |  | 1 |  | BC | 32.5 | 1 |  | 32.5 | 2012-01-03
4 | Banshkhali | 415084089 | Shah-Jahan Chowdhury Road | WD-VZR-CTG-BANSH-12/13 |  |  |  |  | 1 |  | 32.5 | 2012-01-03 | 1.035 |  | 32.42 | BC | 2012-03-06
5 | Banshkhali | 415085078 | Const. of 3vent. 4.5x4.5m RCC Box Culvert on Minzirtala Abdul Karim Mattabar to Sahar Ali Mattabar Road. | WD-VZR-CTG-BANSH-12/15 | [5 empty] | 13.5 | 16 | 17/07/12 |  | 13.5 | 25.35 | Bridge
6 | Banshkhali | 415085078 | Gandamara Union Hatkhali - Saral Union Naya Bazar Road. | WD-VZR-CTG-BANSH-13/17 | 1.27 |  |  | 41.12 | 1 |  | 40 | 2012-06-11 | 1.27 |  | 37.37 | HBB | 13/02/13 | M/S Hamid Enterprise | 39.99
7 | Banshkhali |  | Chamble Union East Chamble Dullahghiri Road | [5 empty] | 1 |  | 40 | 2012-06-11
8 | Banshkhali |  | khan mohammad Fakir Saha Road. | WD-VZR-CTG-BANSH-13/18 |  |  |  |  | 1 |  | 35 | 17/01/13 | 1.3 | 0.6 | 32.96 | HBB | 21/03/13
9 | Banshkhali | 415085065 | Napura Mira Para Sama Sang-guna Road | [5 empty] | 1 |  | 28 | 2013-11-06
10 | Banshkhali | 415085094 | East Manik Pathan to Chort Para Road | WD-VZR-CTG-BANSH-13/19 |  |  |  |  | 1 |  | 28 | 2013-11-06 | 1.045 | 1.8 | 26.52 | HBB | 2013-01-10 | M/S Friends Marketing co & Dipu Kanti Pal | 28.16
11 | Banshkhali | 415085252 | Hamid Ali Road | WD-VZR-CTG-BANSH-13/21 |  |  |  |  | 1 |  | 28 | 14/07/13 | 1.067 |  | 27.42 | HBB | 2013-01-10 | M/S Friends Marketing co & Dipu Kanti Pal | 28.79
12 | Banshkhali | 415085253 | Hazi Ismail Munshi Bari Road | WD-VZR-CTG-BANSH-13/20 |  |  |  |  | 1 |  | 28 | 14/07/13 | 0.818 | 1.8 | 21.91 | HBB | 2013-01-10 | M/S Friends Marketing co & Dipu Kanti Pal | 23.48
13 | Banshkhali | 415085032 | Khankhanabad Nayan Tara Road . | WD-VZR-CTG-BANSH-13/22 |  |  |  |  | 1 |  | 28 | 17/07/13 | 0.884 | 1.8 | 23.29 | HBB | 2013-01-10 |  | 24.45
14 | Banshkhali | 415084033 | Abdul Ohab Road | WD-VZR-CTG-BANSH-13/23 |  |  |  |  | 2 |  | 56 | 29/08/13 | 0.737 | 18.6 | 54.25 | HBB | 29/10/13 | M/S Friends Marketing co & Dipu Kanti Pal | 56.96
15 | Banshkhali | 415085258 | Kotpara-Katharia to Halipara Road(Sonaichari Bridge – Hazrat Oli Sha Market –Dhopabari Katharia Main Road) | WD-VZR-CTG-BANSH-14/31 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-12 | 1.1 |  | 25.34 | HBB | 1900-01-24 08:10 | M/S Al Modina Cons. | 26.55
16 | Banshkhali | 415085254 415085262 | Asraf Ali Road(Mostafizur Rahman Chowdhury Road) | WD-VZR-CTG-BANSH-14/29 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-12 | 0.682 |  | 19.99 | HBB | 20/01/14 | M/S Gihan Enterprise | 20.99
17 | Banshkhali | 415084067 415085260 | Tara Kinkor Road | WD-VZR-CTG-BANSH-14/25 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-12 | 1 |  | 25.52 | HBB | 20/01/14
18 | Banshkhali | 415084068 | Napora Miradul Alom (Murid Alam –Jangle Napor Road) | WD-VZR-CTG-BANSH-14/26 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-12 | 1 |  | 25.52 | HBB | 20/01/14
19 | Banshkhali | 415085256 | Gondamara Dhupi Road | WD-VZR-CTG-BANSH-14/32 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.99 |  | 25.55 | HBB | 20/01/14
20 | Banshkhali | 415085257 | Sha Chanmollo Road | WD-VZR-CTG-BANSH-14/30 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.52 |  | 16.14 | HBB | 20/01/14 | M/S Gihan Enterprise | 16.11
21 | Banshkhali | 415085048 | Master Nazir Ahamed College Road | WD-VZR-CTG-BANSH-14/27 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.995 |  | 25.47 | HBB | 20/01/14
22 | Banshkhali | 415084066 | Naporar Dhalar Road | WD-VZR-CTG-BANSH-14/28 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.935 |  | 24.95 | HBB | 20/01/14
23 | Banshkhali | 415085256 | South Barumchara Morhum Moulovi Wise Uddin Road | WD-VZR-CTG-BANSH-14/33 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-01 | 0.5 |  | 11.37 | HBB | 2014-09-02 | M/S Abdul Gaffar | 11.95
24 | Banshkhali | 415085384 | Shekher Khil Moulovi Bazar-Rezaul Karim Master Road | WD-VZR-CTG-BANSH-14/36 | 0.5 |  | BC | 28 | 0.5 |  | 26 | 2013-02-01 | 0.68 |  | 19.64 | BC | 2014-11-06
25 | Banshkhali | 415085259 | West Chechuria (Ghonapara) Modhom Road | WD-VZR-CTG-BANSH-14/35 | 1 |  | HBB | 28 | 1 |  | 26 | 19/11/13 | 1.03 | 0.9 | 25.38 | HBB | 2014-09-02
26 | Banshkhali | 415085385 | Khuduk Ali Mia jan Road |  | 0.5 |  | BC | 28 | 0.5 |  | 25 | 31/03/14
26 |  |  | Sub Total |  | 15.27 | 10 |  | 487.12 | 24 | 22.1 | 741.03 |  | 18.861 | 47 | 568.6 |  |  |  | 329.46 |  |  |  | 0
41 |  |  | Total |  | 31.47 | 33 |  | 1172.82 | 40.93 | 41.3 | 1427.04 |  | 35.067 | 69.57 | 1188.48 |  |  |  | 813.15 |  |  |  | 75.77
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Mirsharai | 415533009 | Chotta Komoldho - Dhomdoma Abutorab Bazar Road | WD-UNR-CTG-MIRSH-10/01 | 5.64 | 1.875 | BC | 214.75 | 2 | 5 | 34.63 |  | 3.1 |  | 96.57 | BC | 29/04/10 | M/S Aggrajatra Traders | 24.63 | 25/7/10 |  | 100% | 34.63 | Terminati
2 | Mirsharai | 415533009 | Chotta Komoldho - Dhomdoma Abutorab Bazar Road(Remaining Work) | WD-UNR-CTG-MIRSH-12/18 | [6 empty] | 76.91 |  | 3.1 |  | 76.91 | BC | 27/09/12 | M/S Anowarul Islam | 80.75 | 29/01/13 | 19/06/13 | 34% | 27.42
3 | Mirsharai | 415533009 | Chotta Komoldho - Dhomdoma Abutorab Bazar Road(Remaining Work) | WD-UNR-CTG-MIRSH-13/19 |  |  |  |  | 1 |  | 50 | 13/12/12 | 1.04 | 0.625 | 48.43 | BC | 29/01/13 | M/S Onik Traders | 50.82 | 22/09/13 | 13/02/14 | 60% | 15
4 | Mirsharai | 415533009 | Choto Kamaldaha Damdama Abutorab Road North Side (Remaining Part) | WD-UNR-CTG-MIRSH-13/41 |  |  |  |  | 1 |  | 56 | 2013-01-10 | 1.3 |  | 54 | BC | 17/11/13
5 | Mirsharai | 415533010 | Abutorab Hasimnagar charsarath road | WD-UNR-CTG-MIRSH-10/06 | 3.55 | 17.225 | BC | 193.66 | 2 | 5 | 96.5 |  | 2.215 | 2.225 | 96.18 | BC | 2010-11-07 | M/S Ali Traders | 96.18 | 2010-10-10 | 23/4/11 R30/12/11 | 100% | 95.98 | F.B..Paid
6 | Mirsharai | 415533010 | Construction Of 2nos.4.5mx4.5m & 5mx5m RCC Box Culvert on Abutorab – Hashim Nagar -Char Sharat Road . | WD-UNR-CTG-MIRSH-13/45 | [5 empty] | 15 | 50 | 2013-01-10 |  | 9.5 | 36.12 | ST. | 2014-01-01 |  | 37.74 | 29/04/14 | 2014-04-09 | 0%
7 | Mirsharai | 415533011 | Abutorab Hasimnagar charsarath road(Remaining Part) | WD-UNR-CTG-MIRSH-13/35 |  |  |  |  | 1 |  | 50 | 13/12/12 | 1.3 |  | 47.67 | BC | 22/08/13 | M/S Arafat Steel & Engineering | 50 | 17/12/13 | 25/05/14 | 40%
8 | Mirsharai | 415533021 | Jamalpur Kalibari road | WD-UNR-CTG-MIRSH-10/02 | 2.18 | 4.625 | BC | 92.49 | 2.2 | 3.5 | 92.75 |  | 2.18 | 4 | 92.75 | BC | 29/04/10 | Shahajan Construction | 92.62 | 25/7/10 | 8/12/2010 R30/04/11 | 100% | 92.48 | F.B..Paid
9 | Mirsharai | 415533023 | Abutorab Kheyar Hat Road | WD-UNR-CTG-MIRSH-10/08 | 2.85 | 1 | BC | 104.21 | 2.85 | 5 | 22.96 | 18/10/10 | 2.85 | 1 | 22.96 | BC | 28/11/10 | M/S Mithu Enterprise | 22.95 | 25/1/11 | 2012-11-02 | 100% | 22.95 | Termina 22/01/13
10 | Mirsharai | 415533023 | Abutorab Kheyar Hat Road(Remaining Part) | WD-UNR-CTG-MIRSH-13/33 | [6 empty] | 77.38 | 2011-08-09 |  |  | 77.38 | BC | 2013-04-07 | M/S Haque Traders | 81.24 | 13/10/13 | 25/03/14 | 80% | 35.3
11 | Mirsharai | 415533020 | Samitir Hat To Saherkhali UP Road Via Gagaria. | WD-UNR-CTG-MIRSH-11/11 | 1.95 | 4.125 | BC | 110.8 | 1.95 |  | 84 | 13/03/11 | 1.95 |  | 94.58 | BC |  | M/S Ra Enterpeise | 110.79 | 23/07/12 | 13/02/13 | 40% | 14.14
12 | Mirsharai | 415534240 | Tatuiya Nathpara Road. | WD-UNR-CTG-MIRSH-11/10 | 1.65 | 1.25 | BC | 74.51 | 1.65 |  | 65 | 13/03/12 | 1.65 | 1.25 | 74.62 | BC | 24/10/12 | M/S Ali Traders | 74.5 | 2011-11-12 | 30/06/12 RRR30/06/13 | 100% | 74.14
13 | Mirsharai | 415533007 | Bangla Bazar Osmanpur Road. | WD-UNR-CTG-MIRSH-11/17 | 3.5 |  | HBB | 103.26 | 1.75 |  | 47 | 2011-08-09 | 1.75 |  | 46.39 | HBB | 13/02/12 | M/S Ali Traders | 48.72 | 18/06/12 | 2013-09-01 |  |  | Termina
15 | Mirsharai | 415533007 | Bangla Bazar Osmanpur road | WD-UNR-CTG-MIRSH-13/21 |  |  | BC |  | 1.75 |  | 54.56 | 2013-04-07 | 1.75 |  | 54.56 | BC | 2013-04-07 | M/S Ali Enterprise | 65.42 | 13/04/14 | 22/09/14 | 0
14 | Mirsharai | 415533024 41553302 | Mirsarai Station road | WD-UNR-CTG-MIRSH-13/36 | 1.115 |  | BC | 38.87 | 1 |  | 40 | 13/12/12 | 1.5 |  | 38.87 | BC | 22/08/13 | M/S Santoi Enterprise | 40.77 | 17/12/14 | 25/05/14 | 100% | 13.79
16 | Mirsharai | 415533015 | Bamonsundar-Yasak Driver Sawgi Bazar Road | WD-UNR-CTG-MIRSH-13/43 | 2 | 2 | HBB | 65 | 1 |  | 28 | 2013-09-07 | 0.7 |  | 24.12 | BC | 2013-02-12 | M/S Pavia Traders | 25.3 | 21/04/14 | 29/09/14 | 0
17 | Mirsharai | 415533005 | Abutorab Annerderhat Road | WD-UNR-CTG-MIRSH-13/37 | 0.75 |  | BC | 50 | 1 |  | 28 | 2013-09-07 | 1 | 0.625 | 26.96 | HBB | 2013-10-10
18 | Mirsharai | 415533017 | Bari Badth-Takerhat Road | WD-UNR-CTG-MIRSH-13/42 | 0.75 |  | BC | 50 | 1 |  | 28 | 2013-09-07 | 0.9 |  | 24.18 | BC | 2013-02-12 | M/S Chowdhury & Co. | 25.35 | 21/04/14 | 29/09/14 | 0.1
19 | Mirsharai | 415533003 | Gagaria-Hait Kandi -Ghagaria Road | WD-UNR-CTG-MIRSH-13/40 | 0.75 |  | BC | 50 | 1.5 |  | 50 | 2013-04-08 | 0.8 |  | 22.93 | BC | 2013-02-12
19 |  |  | Sub-Total |  | 26.685 | 32.1 |  | 1147.55 | 24.65 | 33.5 | 1031.69 |  | 29.085 | 19.225 | 1056.18 |  |  |  | 927.78 |  |  |  | 425.83
Village Road
1 | Mirsharai | 415534192 415534193 | Mohajon Hat School College to Morhum F Rahman Bari via Santirhat Road | WD-VZR-CTG-MIRSH-10/03 | 2.05 | 2.225 | BC | 75.69 | 2.05 | 5 | 37.25 |  | 2.05 | 5 | 37.25 | BC | 16/05/10 | M/S Evergreen Enterprise | 37.25 | 16/8/10 | 28/2/11 RR30/12/11 | 100% | 37.25 | Termination
2 | Mirsharai | 415534192 415534193 | Mohajon Hat School College to Morhum F Rahman Bari via Santirhat Road(Remaining Part) | WD-VZR-CTG-MIRSH-13/26 | [6 empty] | 37.56 |  |  |  | 36.6 | BC | 21/03/13 | M/S Ali Enterprise | 38.43 | 2013-08-06 | 2013-09-11 | 100% | 31.5
3 | Mirsharai | 415534139 | Jorarong high school Road | WD-VZR-CTG-MIRSH-10/04 | 1 | 2 | BC | 33.97 | 1 | 2 | 36.5 |  | 1 | 2 | 35.71 | BC | 16/05/10 | M/S Ali Traders | 35.96 | 2010-12-08 | 25/2/11 R30/09/11 | 100% | 33.97 | F.B.Paid
4 | Mirsharai | 415534190 | Old Dhaka to Chittagong Trank road to Mohajon Hat School via Mona Masque Road. | WD-VZR-CTG-MIRSH-10/05 | 1.25 | 1.6 | BC | 40.53 | 1.25 | - | 40.63 |  | 1.25 |  | 40.57 | BC | 16/05/10 | M/S Shahajan Construction | 40.55 | 16/8/10 | 28/2/11 | 100% | 40.52 | F.B.Paid
5 | Mirsharai | 415534088 | Protap Narayan Road | WD-VZR-CTG-MIRSH-10/06 | 1 | 7.2 | BC | 50.48 |  |  | 29.73 |  | 1 | 7.2 | 29.73 | BC | 17/01/11 | M/S Haq traders | 43.56 | 13/03/11 | 2012-03-04 | 65% | 28.37 | Termination
5 | Mirsharai | 415534088 | Protap Narayan Road | WD-VZR-CTG-MIRSH-13/34 | [6 empty] | 20.74 |  | 1 | 7.2 | 20.74 | BC | 41372 | M/S S.M Cons. | 21.76 | 19/11/13 | 26/04/14 | 0%
6 | Mirsharai | 415535059 | Dr. Binay Vuson road | WD-VZR-CTG-MIRSH-10/07 | 1.3 | 1.25 | BC | 46.07 | 1.5 |  | 46.3 | 11/10/10 | 1.3 | 1.25 | 46.09 | BC | 28/11/10 | M/S Haq traders | 46.06 | 2010-09-03 | 29/03/11 | 100% | 46.06 | F.B.Paid
7 | Mirsharai | 415534153 | Mohalonka-Baliyadi Road | WD-VZR-CTG-MIRSH-11/09 | 1 |  | BC | 34 | 1 |  | 34.56 | 25/01/11 | 1 |  | 34.03 | BC | 20/03/11 | M/S Anowarul Islam | 40 | 2011-08-05 | 29/11/11 | 100% | 33.99 | F.B.Paid
8 | Mirsharai | 415534177 | Cont.Of 16.00m Long RCC G.B On shahid Jakir hossain Road At Ch.820m. | WD-VZR-CTG-MIRSH-11/13 |  | 48 | STR | 189.89 |  | 16 | 60.19 | 18/10/11 |  | 60.19 |  |  | 18/10/11 | M/Sshahjahan Construc | 62.41 | 2011-11-12 | 30/06/12 R30/12/12 | 100% | 62.39 | REVEISED
9 | Mirsharai | 415534177 | Cont.Of 16.00m Long RCC G.B On shahid Jakir hossain Road At Ch.820m. | WD-VZR-CTG-MIRSH-11/14 | [5 empty] | 16 | 60.98 | 18/10/11 |  | 60.98 |  |  | 18/10/11 | M/Sshahjahan Construc | 62.82 | 2011-11-12 | 30/06/12 R31/10/12 | 100% | 62.81 | REVEISED
10 | Mirsharai | 415534177 | Cont.Of 16.00m Long RCC G.B On shahid Jakir hossain Road At Ch 2590m. | WD-VZR-CTG-MIRSH-11/15 | [5 empty] | 16 | 64.74 | 18/10/11 |  | 64.74 |  |  | 18/10/11 | M/Sshahjahan Consc | 64.74 | 2011-11-14 | 30/06/12 | 0% |  | Termination 02/01/13
11 | Mirsharai | 415534257 | Mithanala Rhamatabad Center Road(Sufia Mithanala Connecting Road) | WD-VZR-CTG-MIRSH-11/16 | 0.77 | 1.25 | BC | 37.65 | 1 |  | 32 | 2011-11-12 | 0.77 | 1.25 | 31.69 | BC | 15/01/12 | M/S Sohan Enter Prise | 37.64 | 17/12/12 | 2013-07-07 | 60% | 15.63
12 | Mirsharai | 415534069 | Muradpur Road. | WD-VZR-CTG-MIRSH-13/20 | 1.81 |  | BC | 91.67 | 1 |  | 40 | 13/12/12 | 0.91 |  | 39.7 | BC | 29/01/13 | M/S R A EnterPrise | 41.66 | 22/09/13 | 13/02/14 | 0%
13 | Mirsharai | 415534012 | Istern Circular Road. | WD-VZR-CTG-MIRSH-13/22 | 1.425 |  | HBB | 38.63 | 1 |  | 40 | 13/12/12 | 1.425 |  | 38.63 | HBB | 29/01/13
14 | Mirsharai | 415534111 | Khaiyachara Highschool Road | WD-VZR-CTG-MIRSH-13/30 | 1.42 |  | BC | 45.63 | 1.5 |  | 50 | 14/01/13 | 1.42 |  | 45.63 | HBB | 41522 | M/S S M Constructio | 47.92 | 23/10/13 | 28/03/14 | 30% | 14
15 | Mirsharai | 415534011 | Haiyatur Nesa Chowdhury Road | WD-VZR-CTG-MIRSH-13/31 | 1.88 |  | HBB | 47.88 | 1.5 |  | 50 | 14/01/13 | 1.88 |  | 47.85 | HBB | 41522
16 | Mirsharai | 415534115 | Sahid Mahabub Alam Road | WD-VZR-CTG-MIRSH-13/29 | 1.27 |  | HBB | 32.73 | 1 |  | 35 | 14/01/13 | 1.27 |  | 32.73 | HBB | 41522
17 | Mirsharai | 415534044 415534130 | Anu Chowdhury (Monu Bhuyan Road)Road | WD-VZR-CTG-MIRSH-13/23 | 0.85 |  | BC | 36.06 | 1 |  | 35 | 14/01/13 | 0.845 |  | 34.37 | BC | 14/03/13 | M/S Onik Traders | 36.05 | 22/09/13 | 13/02/14 | 60% | 10
18 | Mirsharai | 415534103 | Bosrot Ali Road(Sodmara Dighi-Naherpur Chowdhury House) Road | WD-VZR-CTG-MIRSH-13/25 | 1.37 |  | BC | 32.24 | 1 |  | 35 | 14/01/13 | 1.37 |  | 29.92 | BC | 14/03/13 | M/S Saiful Enterprise | 32.92 | 2014-07-05 | 17/10/14 | 0%
19 | Mirsharai | 415534192 | Santirhat Pacca Road-Mohajonhat Road Via Chitto Dr. Bari Road(Mohajonhat High School) Road | WD-VZR-CTG-MIRSH-13/24 | 0.95 | 0.625 | HBB | 26.74 | 1 |  | 35 | 14/01/13 | 0.95 | 0.625 | 26.73 | HBB | 14/03/13
20 | Mirsharai | 415534131 | Santirhat Grave West Side to Mirja Ali Hazibari(Santirhat -Doulat Bibi) Road. | WD-VZR-CTG-MIRSH-13/28 | 1.11 |  | HBB | 33.47 | 1 |  | 35 | 14/01/13 | 1.11 |  | 33.46 | HBB | 2013-09-05 | M/S Sohan Enterprise | 33.46 | 2013-09-07 | 31/11/13
21 | Mirsharai | 415535052 | Joytara Road | WD-VZR-CTG-MIRSH-13/27 | 1 |  | BC | 42.88 | 1 |  | 42.88 |  | 1 |  | 37.65 | HBB | 2013-08-04 | M/S Mahin Assosiate | 42.88 | 2014-07-05 | 17/10/14 | 0%
22 | Mirsharai | 415534157 & 415535062 | Joypur Pachim Joar Jame Mosjid Road(Dom Khali Bishu Mia Road) & Joypur Pachim Joar Cornel Mohasin Bary Road | WD-VZR-CTG-MIRSH-13/32 | 1.6 | 2.225 | HBB | 43.8 | 1.6 | 2.225 | 43.8 |  | 1.6 | 2.225 | 39.81 | HBB | 2013-09-05 | M/S Saiful Enterprise | 43.8 | 2014-08-05 | 18/10/14 | 30%
23 | Mirsharai | 415534109 | Const. Of 2vent 5mx5m Long RCC Box Culvert Shaheed Abu Basar Road on Shair Khali Khal | WD-VZR-CTG-MIRSH-13/38 | 1 | 5 |  | 42.5 |  | 15 | 35 | 2013-09-07 |  | 10 | 24.98 | St. | 2013-10-10 | M/S Ali Enterprise | 27.67 | 2014-07-05 | 17/10/14 | 0%
24 | Mirsharai | 415534044 | Kazi Taluk Shahid Dr. Bozle Shobahan Road | WD-VZR-CTG-MIRSH-13/39 | 0.9 |  | BC | 50 | 1 |  | 27.35
25 | Mirsharai | 415534257 | Gagaria –Haitkandi old Oli Ahammad Abdur Ragman Road | WD-VZR-CTG-MIRSH-13/ | Not in DPP |  |  |  | 1 |  | 28 | 2013-09-07 | [5 empty] | 333333333333333
26 | Mirsharai | 415534204 | Rokon Banu Road | WD-VZR-CTG-MIRSH-13/44 | Not in DPP |  |  |  | 1.5 |  | 50 | 2013-04-08 | 1.1 |  | 45.09 | BC | 41640 | 33333333333
27 | Mirsharai | 415534195 | Migi Gram Eidgaoh –Let.Suja Member House Road | WD-VZR-CTG-MIRSH-13/41 | 1.5 |  | HBB | 42 | 1.5 |  | 42 | 2013-04-08 | 1.5 | 1.25 | 39.09 | HBB | 2013-02-12 | M/S Pavia Traders | 41.05 | 21/04/14 | 20/09/14 | 70% | 5
28 | Mirsharai | 415534243 | Norendro Ukil Road | WD-VZR-CTG-MIRSH-13/ | 2.5 |  | HBB | 43 | 1 |  | 28 | 2013-04-08 | [5 empty] | 33333333333
29 | Mirsharai | 415534128 | Lolito Roudhro Road | WD-VZR-CTG-MIRSH-13/44 | 0.9 |  |  | 50 | 1.5 |  | 50 | 2013-04-08 | 1.65 | 1.25 | 44.34 | BC | 17/11/13 | M/S Haque Traders | 47.21 | 21/04/14 | 20/09/14 | 0%
30 | Mirsharai | 415534084 | Roghunath Road | WD-VZR-CTG-MIRSH-13/ | Not in DPP |  |  |  | 1.5 |  | 50 | 2013-04-08 | [5 empty] | 33333333333
31 | Mirsharai | 415534293 | DT Road – DT Wabidullah Road | WD-VZR-CTG-MIRSH-13/43 | 1 |  | HBB | 28 | 1 |  | 28 | 2013-01-10 | 1.1 |  | 25.63 | BC | 17/11/13 | M/S SM Construction | 26.92 | 21/04/14 | 29/09/14 | 0%
32 | Mirsharai | 415534375 415534275 | Khore-Moula Bhuiyar Taluk Road | WD-VZR-CTG-MIRSH-13/40 | 1 |  | HBB | 28 | 1 |  | 28 | 2013-01-10 | 1 |  | 25.57 | HBB | 17/11/13 | M/S Shimul Enterprise | 26.82 | 21/04/14 | 29/09/14 | 0%
33 | Mirsharai | 415534048 415534375 | South Moghadia Hazi Nazir Ahammad Road | WD-VZR-CTG-MIRSH-13/42 | 2 |  | HBB | 28 | 1 |  | 28 | 2013-01-10 | 1 | 0.9 | 27.08 | HBB | 17/11/13
33 | Mirsharai | 415534018 415534375 | Approach Road of Sachiram Kar-Ahmed Ullah Vuya Road | WD-VZR-CTG-MIRSH-14/46 | 1 |  | BC | 56 | 1 |  | 42 | 2013-11-12 | 0.42 |  | 21.25 | HBB | 31/03/13
33 |  |  | Sub - Total |  | 34.855 | 71.375 |  | 1347.51 | 33.4 | 72.225 | 1379.21 |  | 30.92 | 226.06 | 971.92 |  |  |  | 979.54 |  |  |  | 421.49
52 |  |  | Total |  | 61.54 | 103.475 |  | 2495.06 | 58.05 | 105.725 | 2410.9 |  | 60.005 | 245.285 | 2028.1 |  |  |  | 1907.32 |  |  |  | 847.32
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Chandanish | 415183012 415183006 | Diakul-Chringhata-Dhopachari-Monglarmuk | WD-UNR-CTG-CHAND-10/02 | 5 | 150 | BC | 585 | 2 | - | 84 |  | 2.19 | 12.5 | 69.84 | BC | 2010-10-05 | ARM Engineers | 75.04 | 25/7/10 | 8/12/2010 R30/04/11 | 100% | 73.68
2 | Chandanish | DO | Diakul-Chringhata-Dhopachari-Monglarmuk | WD-UNR-CTG-CHAND-10/05 | Do |  |  |  |  | - | 69.84 |  | 2.19 | 12.4 | 69.84 | HBB | 08/12/10 | M/S Nurul Anowar | 69.65 | 30/03/11 | 29/03/12 | 35% | 10.23 | TERMINA R10/06/13
2 |  |  | Sub-Total |  | 5 | 150 |  | 585 | 2 | 0 | 153.84 |  | 4.38 | 24.9 | 139.68
Village Road
1 | Chandanish | 415184046 | Kulain DangaRoad(Barkal Satbari)Purbo-shilpara to Barkal road. | WD-VZR-CTG-CHAND-10/03 | 0.5 |  | BC | 16.25 | 0.5 | - | 16.25 |  | 0.492 |  | 16.23 | BC | 2010-10-05 | S.M Yousuf Brothers | 14.87 | 21/7/10 | 4/12/2010 RR30/3/13 | 65% | 6.98
2 | Chandanish | 415184063 | Kornel Oli Ahmed road. | WD-VZR-CTG-CHAND-10/04 | 2.66 |  | BC | 86.45 | 2.66 | - | 55.16 |  | 2 |  | 55.16 | BC | 2010-10-05 | Nipa Enterprise | 55.16 | 25/7/10 | 8/12/2010 RR30/06/12 | 65% | 38.18 | TERMINA R02/04/13
3 | Chandanish | 415184063 | Kornel Oli Ahmed road. | WD-VZR-CTG-CHAND-13/13 | [5 empty] | - | 46.55 |  | 2 |  | 46.55 | BC | 2013-04-08 | M/S Mazad Enterpri | 48.85
4 | Chandanish | 415184007 | South Harala (Bashirullah Nizam Uddin) road (remaining partion) road. | WD-VZR-CTG-CHAND-10/01 | Not in DPP |  |  |  | 1 | - | 27.32 |  | 1 |  | 27.33 | BC | 2010-10-05 | Islam Construction | 27.26 | 25/7/10 | 8/12/2010 R30/04/11 | 100% | 21.23
5 | Chandanish | 415184047 415185114 | Purbo Kashuya shah (R) Road. | WD-VZR-CTG-CHAND-10/06 | 1 |  | BC | 32.5 | 1 | - | 30.85 | 11/10/10 | 0.63 | 1 | 25.29 | BC | 28/11/10 | M/S Ajmir Engineers | 24.02 | 18/1/11 | 1/2/2012 R30/12/12 | 60% | 8.45
6 | Chandanish | 415184048 415184018 | Hashimpur U.P Off.(Bainnapukur)Bagicharhat Via Forest- Off.Alisha Mazar Road. | WD-VZR-CTG-CHAND-10/07 | 1.5 |  | BC | 48.75 | 1.5 | - | 18.8 | 03/11/10 | 1.49 |  | 18.8 | BC | 27/12/10 | M/S islam Construction | 42.99 | 40789 | 29/03/12 | 45% | 5
7 | Chandanish | 415184048 415184018 | Hashimpur U.P Off.(Bainnapukur)Bagicharhat Via Forest- Off.Alisha Mazar Road.(Remaining Part) | WD-VZR-CTG-CHAND-13/11 | [5 empty] | - | 36.63 | 03/11/10 | 1.49 |  | 36.63 | BC | 19/02/13
8 | Chandanis | 415185124 | Dakhin Harala GPS-Mygatha-Borama Road. | WD-VZR-CTG-CHAND-12/08 | Not in DPP |  |  |  | 1.43 | 3 | 45 | 22/02/12 | 1.43 | 3 | 44.97 | BC | 2012-01-04 | M/S Al-Modina traders | 47.19
9 | Chandanis | 415185132 | Nagar Para Adrasha Gram-Alisha Mazar Road. | WD-VZR-CTG-CHAND-13/09 | Not in DPP |  |  |  | 1 |  | 45 | 13/12/12 | 1.582 |  | 44.35 | HBB | 17/01/13
10 | Chandanis | 415184011 | Patia Tea Garden Road. | WD-VZR-CTG-CHAND-13/10 | Not in DPP |  |  |  | 1 |  | 45 | 2013-03-01 | 0.91 |  | 43.7 | BC | 13/02/13
11 | Chandanis | 415185130 | Roushan Hat- Muradabad-Azigia Road | WD-VZR-CTG-CHAND-13/12 | Not in DPP |  |  |  | 1 |  | 42 | 2013-01-04 | 1.09 | 1 | 40.93 | BC | 24/07/13 | M/S Saima Anam | 42.98
12 | Chandanis | 415185078 | R & H Uttar Jurara Nagar Para Jurara Hindu Para Road. | WD-VZR-CTG-CHAND-13/14 | Not in DPP |  |  |  | 1 |  | 28 | 21/05/13 | 0.672 |  | 28 | HBB | 2013-01-10
13 | Chandanis | 415185026 | Hashim Vandari Para Road . | WD-VZR-CTG-CHAND-13/15 | Not in DPP |  |  |  | 1 |  | 28 | 21/05/13 | 0.551 |  | 25.84 | BC | 2013-01-10 | M/S Harun Cons. | 27.1
13 | Chandanis | 415185087 | Ledu Member House –Bhuia Bari Connecting Road |  | 1 |  | BC | 56 | 1 |  | 50 | 2013-11-12
| Chandanis | 415185035 | Hazrat Mosta Ali Shah Road Road | WD-VZR-CTG-CHAND-14/17 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-01 | 0.75 |  | 25.4 | BC | 2014-11-06
13 | Chandanis | 415184036 | Purbo Hashimpur M.K High School-Sikder para Road | WD-VZR-CTG-CHAND-14/16 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-01 | 0.505 | 1 | 24.74 | BC | 2014-11-06
14 | Chandanis | 415184022 | Putunnabari (Gullapara Sluice Gate) Road (End of Bodur para Road) |  | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14
13 |  |  | Sub - Total |  | 9.66 | 0 |  | 323.95 | 17.09 | 3 | 591.56 |  | 16.592 | 6 | 503.92 |  |  |  | 330.42 |  |  |  | 79.84
16 |  |  | Total |  | 14.66 | 150 |  | 908.95 | 19.09 | 3 | 745.4 |  | 20.972 | 30.9 | 643.6 |  |  |  | 330.42 |  |  |  | 79.84
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98) | WD-UNR-CTG-RANGU-10/08 | 16 | 15 | BC | 709.5 | 8 | 15 | 373.5 |  | 6.614 |  | 370.79 | BC | 2010-04-05 | Karnafully Enterprise | 190.83 | 2010-03-08 | 16/2/11 RR31/01/12 | 45% | 15.51 | Terminated 02/09/12
2 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98)(Remaining Part) | WD-UNR-CTG-RANGU-12/53 | [13 empty] | M/S B-Alam Talukdh | 144.68
3 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98)(Remaining Part) | WD-UNR-CTG-RANGU-12/54 | [13 empty] | M/S B-Alam Talukdh | 64.76
4 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98)(Remaining Part) | WD-UNR-CTG-RANGU-12/55 | [13 empty] | M/S B-Alam Talukdh | 66.52 | 28/02/13
5 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98) | [5 empty] | 2 |  | 84 | 20/10/11 | [11 empty] | F-2011-2012
6 | Rangunia | 415703051 | Hazee Sayed Ali Road (From RHD #98) | [5 empty] | 2 |  | 84 | 2011-04-12 | [11 empty] | F-2011-2012
7 | Rangunia | 415703052 | SagunBagicha-Hosnabad Rd. (From RHD #103) | WD-UNR-CTG-RANGU-10/13 | 4.5 | 80 | BC | 389 | 2 |  | 84 |  | 0.48 | 2 | 1.78 | BC | 27/09/10 | M/S K.R Traders | 33.7 | 2010-12-12 | 25/12/11 | 20%
8 | Rangunia | 415703052 | SagunBagicha-Hosnabad Rd. (From RHD #103) | WD-UNR-CTG-RANGU-12/52 | [10 empty] | 47.65 | BC | 41071 | M/S Bappa Enterprise | 50.03
9 | Rangunia | 415703011 | S. D. O Road ( Padua bazer hat to Padua horihor School & Shilak rabar Dam to Kalindarani road) | WD-UNR-CTG-RANGU-10/05 | 3 | 10 | BC | 151 | 2.64 |  | 78.24 |  | 2.64 | 1.2 | 78.24 | BC | 10/10/10 | M/S Talukder Const. | 124.21 | 25/1/11 | 15/2/12 RR30/09/12 | 70% | 85.15 | Terminated 02/09/12
10 | Rangunia | 415703011 | S. D. O Road ( Padua bazer hat to Padua horihor School & Shilak rabar Dam to Kalindarani road) | WD-UNR-CTG-RANGU-12/46 | [6 empty] | 67 |  |  |  | 67 | BC | 22/10/12 | M/S Rangamati traders | 70.35
11 | Rangunia | 415703013 | Firingir Khil Road ( Sarafvata - Shilak Connecting ) Road. | WD-UNR-CTG-RANGU-10/06 | 3.1 | 15 | BC | 167.7 | 3.1 | [5 empty] | 154.12 | BC | 2010-04-05 | Shah Abdul Jubben Association | 154.06 | 25/7/10 | 8/12/2010 R30/04/11 | 35% | 49.56 | Terminated
12 | Rangunia | 415703014 | Firingir Khil Road ( Sarafvata - Shilak Connecting ) Road. | WD-UNR-CTG-RANGU-11/26 | [6 empty] | 128.02 |  | 2.35 | 8.7 | 128.02 | BC | 29/11/11
13 | Rangunia | 415703037 | Hajee para-Mizepara | WD-UNR-CTG-RANGU-10/07 | 2 | 5 | BC | 96.5 | 2 | 5 | 96.5 |  | 1.82 |  | 54.12 | BC | 2010-04-05 | Shah Abdul Jubben Association | 54.12 | 21/7/10 | 4/12/2010 R30/04/11 | 60% | 21.93 | Terminated 20/02/12
14 | Rangunia | 415703037 | Hajee para-Mizepara(Termination Part)(Termination Part) | WD-UNR-CTG-RANGU-12/34 | [8 empty] | 1.82 |  | 52.25 | BC | 23/05/12
15 | Rangunia | 415703019 | Nazarer tila Road ( Moriam nagar Union parishad babhan to Nazar tila) | WD-UNR-CTG-RANGU-10/01 | 1.41 | 2 | BC | 64.22 | 1.41 | 2 | 25.98 |  | 0.6 |  | 25.98 | BC | 2010-04-05 | Jahan Enterprise | 63.47 | 25/7/10 | 8/12/2010 RR30/10/11 | 65% | 26.19 | Terminated 12/08/12
16 | Rangunia | 415703019 | Nazarer tila Road ( Moriam nagar Union parishad babhan to Nazar tila) | WD-UNR-CTG-RANGU-12/47 | [6 empty] | 48.58 |  |  |  | 48.58 | BC | 22/10/12 | M/S F.R Traders | 51.02
17 | Rangunia | 415703032 | Chandraghona High School Rd. | WD-UNR-CTG-RANGU-10/02 | 0.85 | 2.8 | BC | 42.7 | 0.865 | 2 | 17.86 |  |  |  | 17.86 | BC | 2010-04-05 | Islam Construction | 32.79 | 25/7/10 | 8/12/2010 R30/04/11 | 65% | 17.34
18 | Rangunia | 415703032 | Chandraghona High School Rd. | WD-UNR-CTG-RANGU-12/44 | [6 empty] | 20.31 |  | 2 |  | 20.31 | BC |  | M/S Bappa Enterprise | 21.33
19 | Rangunia | 415703033 | Muradnagor west para | WD-UNR-CTG-RANGU-10/03 | 1 | 3 | HBB | 37.5 | 1 | 3 | 37.5 |  | 1.07 |  | 51.97 | HBB | 2010-04-05 | Hasan Enterprise | 51.97 | 2010-03-08 | 16/12/10 | 100% | 51.92
20 | Rangunia | 415703016 | Raisabili road (Rangamati Road Gabtali to Raisabili Boddo Mondir) | WD-UNR-CTG-RANGU-10/13 | 1.5 | 4 | BC | 74 | 1.5 | 4 | 39.06 | 2010-08-08 | 1.45 | 7 | 39.06 | BC | 25/10/10 | The five star | 70.44 | 25/1/11 | 15/2/12 R31/10/12 | 60% | 24.03
21 | Rangunia | 415703016 | Raisabili road (Rangamati Road Gabtali to Raisabili Boddo Mondir) | WD-UNR-CTG-RANGU-12/50 | [6 empty] | 45.41 | 22/10/12 |  |  | 45.41 | BC | 22/10/12 | M/S Alam Traders | 47.69
22 | Rangunia | 415703044 415713004 | East Shabdi Nagar Mohila Road | WD-UNR-CTG-RANGU-10/14 | 1 | 5 | BC | 54.5 | 1 | 5 | 52.85 | 2010-08-08 | 1.25 | 2.25 | 57.91 | BC | 25/10/10 | Rony Enterprise | 54.91 | 25/1/11 | 15/2/12 | 100% | 54.87
23 | Rangunia | 415703039 | Sonargaon High School Road | WD-UNR-CTG-RANGU-10/18 | 1 | 3 | BC | 49.5 | 1 | 3 | 25.69 | 2010-08-08 | 1.14 | 2.4 | 25.69 | BC | 2010-09-11 | Jahan Enterprise | 45.56 | 16/1/11 | 2012-05-02 | 60% | 16.27
24 | Rangunia | 415703039 | Sonargaon High School Road (Remaining Part) | WD-UNR-CTG-RANGU-13/51 | [6 empty] | 28.76 | 14/03/13 |  |  | 28.76 | BC | 14/03/13 | M/S Alamgir Enterpe | 30.2
25 | Rangunia | 415703004 | Mahatipara Rd.-Maliarhat | WD-UNR-CTG-RANGU-10/20 | 1 | 3 | BC | 49.5 | 1 | 3 | 57.55 | 2010-11-10 | 1.62 | 1.62 | 57.55 | BC | 08/12/10 | M/S Limu Enterprise | 57.55 | 2011-09-03 | 29/03/12 | 45% | 13.9 | Terminated 14/08/12
26 | Rangunia | 415703004 | Mahatipara Rd.-Maliarhat | WD-UNR-CTG-RANGU-12/49 | [6 empty] | 37.78 | 22/10/12 |  |  | 37.78 | BC | 22/10/12 | M/S Khaza Gariba Newas Enterorise | 39.67
27 | Rangunia | 415703049 | Nasir Mohammad Road | WD-UNR-CTG-RANGU-10/21 | 1 | 3 | BC | 49.5 | 1 | 3 | 47 | 2010-11-10 | 0.84 | 1.95 | 46.75 | BC | 2011-06-02 | M/S Prama Trading | 46.52 | 2011-04-04 | 24/04/12 | 40% | 18.64
28 | Rangunia | 415703036 | Sailbukka Teknaf para Road | WD-UNR-CTG-RANGU-10/19 | 1 | 3 | BC | 49.5 | 1 | 5.15 | 28.66 | 18/10/10 | 1 | 5.15 | 28.66 | BC | 08/12/10 | M/S Rony Enterprise | 28.66 | 13/03/11 | 2012-03-05 | 60% | 22.78
29 | Rangunia | 415703036 | Sailbukka Teknaf para Road | WD-UNR-CTG-RANGU-12/42 | [6 empty] | 27.32 | 22/10/12 |  |  | 27.32 | BC | 22/10/12 | M/S Hasan Entwerprise | 28.68 | 17/01/13
30 | Rangunia | 415703007 | Ram Mohan Sikder Road(Rangunia UP - Tarachan Hat). | WD-UNR-CTG-RANGU-11/25 | 1.5 | 5 | BC | 75.5 | 1.5 | 5 | 71.7 | 27/12/10 | 2.48 | 4 | 70.66 | HBB | 2011-08-05 | M/S Nurallah enterprise | 70.47 | 27/07/11 | 17/02/12 RR30/08/12 | 90% | 10.32
31 | Rangunia | 415703012 | Darikop Road | WD-UNR-CTG-RANGU-11/23 | 3 | 10 | BC | 151 | 2.8 | 11.75 | 14.04 | 27/12/10 | 2.8 | 11.75 | 14.04 | BC | 20/03/11 | M/S talukder construction | 140.82 | 15/05/11 | 2012-04-06 | 35% |  | Terminated 02/09/12
32 | Rangunia | 415703012 | Darikop Road | WD-UNR-CTG-RANGU-12/48 | [6 empty] | 176.54 | 22/10/12 |  |  | 176.54 | BC | 22/10/12 | M/s Rangamati traders | 185.4
33 | Rangunia | GC | Rajar Hat Growth Center | WD-UNR-CTG-RANGU-11/24 |  |  |  | 30 |  |  | 30 | 27/12/10 |  |  | 30.06 |  | 13/04/11 | M/S Jewel Enterprise | 30.05 | 2011-07-06 | 28/12/11 RRR30/8/13 | 40% | 5.5
34 | Rangunia | 415703009 | RHD-Shilock UP-Bhuchakra Hat Road. |  | 1 | 3 | BC | 49.5 | 1 | 3 | 49 | 2011-04-08
35 | Rangunia | 415703029 | Kodala S.A Chowdhury Road. | WD-UNR-CTG-RANGU-11/26 | 1 | 4 | BC | 52 | 1 | 4 | 52 | 2011-04-08 | 1.277 | 6.75 | 51.58 | HBB | 24/10/11 | M/S S0hel Enterprise | 59.16 | 23/06/12 | 22/12/12 | 0
36 | Rangunia | 415703006 | Chandragona U.P.Rd(Kaptali Road To Chandragona Union Parisad Bhaban To Chandragona Ferighat) |  | 2 | 9 | BC | 106.5 | 1 | 9 | 64 | 2011-08-09
37 | Rangunia | 415703038 | Tin Chowdia Road. | WD-UNR-CTG-RANGU-12/37 | 1 | 3 | HBB | 37.5 | 1 |  | 30 | 2012-10-01 | 1.65 | 5.75 | 28.84 | HBB | 2012-03-06 | M/S Kornofully Ent. | 36.66
38 | Rangunia | 415703021 | Aman Ali Road-1. | WD-UNR-CTG-RANGU-13/57 | 1 | 10 | BC | 67 | 1 |  | 42 | 2012-10-02 | 0.91 | 1.75 | 38.99 | BC | 29/01/13
39 | Rangunia | 415703043 4154704015 | killmogal Master Abdul Gani Village Road. | WD-UNR-CTG-RANGU-12/41 | 1 | 3 | BC | 49.5 | 1 |  | 30 | 2012-06-03 | 0.965 | 4.25 | 29.33 | HBB | 14/06/12 | M/S Nurallah enterprise | 36.9
40 | Rangunia | 415703053 415702005 | Kalurghat Charandwip-Vandalijuri-Sarafvata Road. | WD-UNR-CTG-RANGU-12/40 | 1 | 20 | BC | 92 | 1 |  | 42 | 2012-06-04 | 1.09 | 4.5 | 41.9 | HBB | 2012-03-06 | M/S Moulovy enterprise | 49.69
41 | Rangunia | 415703010 | Mayddah Parua Rd(Parua H/Q-Sonai Chari Bazar)Road. | WD-UNR-CTG-RANGU-13/58 | 1.5 | 5 | BC | 75.5 | 1.64 | 7.5 | 69.56 |  | 1.64 | 7.5 | 69.56 | BC | 17/04/13 | M/S Jahanara & Sons | 72.98
42 | Rangunia | 415703025 | Court Road Cum Amanullah Road | WD-UNR-CTG-RANGU-13/70 | 1 | 3 | BC | 49.5 | 1 |  | 28 | 2013-04-07 | 0.24 | 4.75 | 22.59 | HBB | 2013-02-12 | M/S Kornofult Enterprise | 24.28
43 | Rangunia | 415703006 | Chandragona U.P. Road. | WD-UNR-CTG-RANGU-13/71 | 2 | 9 | BC | 106 | 2 |  | 56 | 2013-04-07 | 1.7 | 1 | 43.69 | HBB | 18/12/13
44 | Rangunia | 415703024 415705094 | Raza Mia Chowdhury Road | WD-UNR-CTG-RANGU-13/73 | 1 | 3 | BC | 49.5 | 1 |  | 28 | 2013-04-07 | 0.6 |  | 25.44 | HBB | 2014-01-01
45 | Rangunia | 415703030 | Sharafvata High School Road | WD-UNR-CTG-RANGU-14/76 | 1 |  | BC | 67 | 1 |  | 45 | 2013-02-12 | 1.035 | 0.75 | 38.21 | BC | 2014-10-07
46 | Rangunia | 415703023 415705279 | Halimpur Darga Road | WD-UNR-CTG-RANGU-14/75 | 1 |  | BC | 50 | 1 |  | 45 | 2013-02-12 | 0.6 | 4.1 | 38.45 | BC | 2014-10-07
46 |  |  | Sub-Total |  | 58.36 | 240.8 |  | 3092.62 | 50.455 | 90.4 | 2408.41 |  | 43.681 | 89.12 | 2233.44 |  |  |  | 2330.13 |  |  |  | 433.91
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Village Road
1 | Rangunia | 415704026 | Minagazir Tila South Para Road | WD-VNR-CTG-RANGU-10/10 | 0.6 | 3 | BC | 25.5 | 0.6 | 3 | 25.5 |  | 0.585 | 3 | 24.88 | BC | 2010-11-07 | Aziz & Brothers | 24.81 | 15/9/10 | 28/1/11 RR30/04/12 | 100% | 11
2 | Rangunia | 415704027 | Satgaria Para Road (From Padma Pukur) | WD-VNR-CTG-RANGU-10/04 | 1 | 3 | BC | 38.5 | 1 | 3 | 38.5 |  | 0.48 |  | 30.49 | BC | 2010-04-05 | The five star | 28.56 | 25/7/10 | 2010-08-12 | 100% | 30.03
3 | Rangunia | 415704028 415704001 | Korban Ali Rd. | WD-VNR-CTG-RANGU-10/09 | 1 | 3 | BC | 38.5 | 1 | 3 | 38.5 |  | 1 | 3 | 36.94 | BC | 24/05/10 | Nurullah Enterprise | 36.15 | 2010-10-10 | 23/2/11 | 100% | 36.03
4 | Rangunia | 415704029 | Chandraghona adur para Rd. | WD-VNR-CTG-RANGU-10/11 | 0.79 | 3 | BC | 31.675 | 0.65 | 3 | 19.71 |  | 0.65 | 5 | 19.71 | BC | 2010-11-07 | Kamrul Kawshik | 19.71 | 15/9/10 | 28/1/11 RR30/10/11 | 75% | 18.18
5 | Rangunia | 415704029 | Chandraghona adur para Rd. | WD-VNR-CTG-RANGU-12/45 | [6 empty] | 17.07 |  |  |  | 17.24 | BC | 22/10/12 | M/S Raju Traders | 17.24
6 | Rangunia | 415704036 | 20 M Bridge on Dong Khal in Nuna Panir Road |  | 2 | 20 | BC | 105 | 2 | 20 | 105
7 | Rangunia | 415704045 | Magon Road | WD-VNR-CTG-RANGU-10/12 | 1 | 5 | BC | 42.5 | 1 | 5 | 42.5 |  | 1.2 |  | 42.13 | BC | 2010-12-08 | Alamgir Enterprise | 42.12 | 15/9/10 | 28/1/11 | 100% | 42.02
8 | Rangunia | 415704059 | Goal Ghata - Khosailla Tila Road |  | 1 | 2 | HBB | 29 | 1 | 2 | 29
9 | Rangunia | 415704031 | Kulal Para Rajanikanti Road | WD-VZR-CTG-RANGU-10/15 | 1 | 3 | BC | 38.5 | 1 | 3 | 13.29 | 2010-08-08 | 0.685 | 7.25 | 13.29 | BC | 25/10/10 | Karnafully Enterprise | 13.29 | 2012-05-02 | 2012-05-02 | 40% | 13.29
10 | Rangunia | 415704031 | Kulal Para Rajanikanti Road | WD-VZR-CTG-RANGU-12/43 | [6 empty] | 32.64 | 22/10/12 | 0.685 |  | 32.64 | BC | 22/10/12 | M/S B.Alam Talukther | 34.28
11 | Rangunia | 415705129 | Golam Ali Chowdhury road. | WD-VZR-CTG-RANGU-10/17 | Not DPP |  |  |  | 0.6 | 1 | 33.3 |  | 0.6 | 1 | 33.3 | BC | 18/10/10 | Jaman brothers | 31.64 | 13/02/11 | 13/02/12 R30/08/12 | 65% | 11.28
12 | Rangunia | 415704051 | Kabir Mohammed Road | WD-VZR-CTG-RANGU-11/22 | 1 | 3 | BC | 38.5 | 1 | 3 | 36.5 | 27/12/10 | 1.7 | 2.25 | 36.24 | HBB | 20/03/11 | M/S Alamgir Enterprise | 34.27 | 2011-05-05 | 26/11/11 | 100% | 34.18
13 | Rangunia | 415704004 | Betaghi Court Road Cum Amaullah Road. | WD-VZR-CTG-RANGU-12/29 | 1 | 3 | BC | 49.5 | 2 | 3 | 60 | 2011-08-09 | 1.241 | 4 | 58.63 | HBB | 2012-05-04 | M/S Kornifully Enterprise | 74.09
14 | Rangunia | 415705274 | Agunia Cha Bagan road(Start Mariamnagar DC Road) | WD-VzR-CTG-RANGU-12/27 | 1.5 | 4 |  | 73 | 1.5 | 4 | 52 | 28/09/11 | 1.309 | 9 | 51.75 | HBB | 2012-06-03 | M/S Alamgir Enterprise | 54.34 | 18/06/12 | 09/01/13 R14/04/13
15 | Rangunia | 415705274 | Agunia Cha Bagan road(Start Mariamnagar DC Road) | WD-VzR-CTG-RANGU-13/69 |  |  |  |  | 1.5 |  | 42 | 19/09/13 | 1.58 |  | 39.54 | HBB | 13/11/13
16 | Rangunia | 415704025 415704013 | Khurusla Abdul Hamid Road-Kanatchari Primary School. | WD-VZR-CTG-RANGU-12/32 | 4 | 100 | BC | 330 | 1 |  | 32 | 2011-04-12 | 1.49 | 6.25 | 30.72 | HBB | 24/04/12 | M/S Moulovi Enterprise | 37.61
17 | Rangunia | 415704054 | Dr.Hafez Rahman Road. | WD-VZR-CTG-RANGU-12/31 | 0.45 | 3 | BC | 20.63 | 0.45 | 3 | 20 | 2011-04-12 | 0.636 | 0.45 | 19.45 | HBB | 24/04/12 | M/S Moulovi Enterprise | 24.13
18 | Rangunia | 415704041 | Fultali Bazar Road. | WD-VZR-CTG-RANGU-12/33 | 1 | 3 | BC | 38.5 | 1 | 3 | 38 | 2011-04-12 | 1.37 |  | 31.21 |  | 23/05/12 | M/S A.k.M Corporation | 38.79
19 | Rangunia | 415704047 | Banagram Road. | WD-VZR-CTG-RANGU-12/30 | 1 | 3 | BC | 38.5 | 1 |  | 32 | 2011-11-12 | 0.8 |  | 31.31 | HBB | 24/04/12 | M/S Khaza Ahammad Noor Enterprise | 38.15
20 | Rangunia | 415705038 | Old Abdul Hamid Road-Tripura Sundari Road. | WD-VZR-CTG-RANGU-12/28 | Not DPP |  |  |  | 1 |  | 25 | 21/12/11 | 0.41 | 9.5 | 24.07 | HBB | 22/03/12 | M/s Talukder Cons. | 31.03 | 31/03/14
21 | Rangunia | 415704055 | Falharia Buddha Bihar Road. |  | 1 | 3 | BC | 38.5 | 1 | 3 | 37 | 21/12/12
22 | Rangunia | 415704046 | Lalanagar village Road. | WD-VZR-CTG-RANGU-12/38 | 1 | 3 | BC | 38.5 | 1 |  | 32 | 2012-10-01 | 0.62 | 2.25 | 31.52 | BC | 2012-03-06 | M/S Nurallah enterprise | 40.4
23 | Rangunia | 415705388 | Hazee Ansur Ali Sowdagar Bari & Khorsed Master Ghata Road. | WD-VZR-CTG-RANGU-12/35 | Not DPP |  |  |  | 0.3 |  | 8 | 2012-06-03 | 0.25 |  | 7.86 | HBB | 23/05/12
24 | Rangunia | 415704050 | Sahabdinagar Mosjid Road. | WD-VZR-CTG-RANGU-12/39 | 1 | 3 | BC | 38.5 | 1 |  | 32 | 2012-06-03 | 0.8 | 0.75 | 31.01 | BC | 2012-03-06 | M/S Hassan Ent. | 39.25
25 | Rangunia | 415703046 415705317 | Kha Mosjid Road. | WD-VZR-CTG-RANGU-12/36 | 1 | 5 | BC | 54.5 | 1 |  | 42 | 2012-10-01 | 0.57 |  | 40.93 | HBB | 23/05/12
26 | Rangunia | 415705024 | Construction of 2vent-4.5mx4.5mRCC Box Culvert on Fultali Bazar Road Over Hizoltali Morakhal | WD-VZR-CTG-RANGU-13/59 |  | 30 | RCC | 60 |  | 10.2 | 17.52 |  |  | 10.2 | 17.52 | ST |  | M/S Fihima Enterprise | 19.72
27 | Rangunia | 415705144 | Nobo- Chandro Road By HBB. | WD-VZR-CTG-RANGU-13/60 |  |  |  |  | 1 |  | 35 | 18/02/13 | 1.186 | 1.5 | 31.81 | HBB | 22/05/13 | M/S Nuralla Enterpr. | 40.04
28 | Rangunia | 415705141 | Karmakar Para Road By HBB | WD-VZR-CTG-RANGU-13/61 |  |  |  |  | 1 |  | 35 | 18/02/13 | 1.186 | 2.25 | 32.5 | HBB | 22/05/13 | M/S Nuralla Enterpr. | 38.82
29 | Rangunia | 415705013 | Kokania Road | WD-VZR-CTG-RANGU-13/62 |  |  |  |  | 1.2 |  | 38.53 |  | 1.2 |  | 38.53 | HBB | 22/05/13 | M/S Nuralla Enterpr. | 40.46
30 | Rangunia | 415705420 | Raham Ali Road. | WD-VZR-CTG-RANGU-13/63 |  |  |  |  | 0.35 | 1.5 | 14 |  | 0.315 | 1.5 | 12.24 | HBB | 30/06/13
31 | Rangunia | 415705413 | Shanti Nikaton Ramkrishno Road | WD-VZR-CTG-RANGU-13/72 |  |  |  |  | 0.6 |  | 18 | 2013-04-07 | 0.585 |  | 17.95 | HBB | 2014-01-01
32 | Rangunia | 415704028 | Construction of 2vent-4.5mx5m RCC Box Culvert On Majumdarkhil Road. | WD-VZR-CTG-RANGU-13/74 | [5 empty] | 10 | 25 | 2013-04-07 |  | 9 | 20.8 | ST. | 2014-01-01
33 | Rangunia |  | Ahammad Rahman Road | WD-VZR-CTG-RANGU-13/67 |  |  |  |  | 1 |  | 28 | 17/07/13 | 0.8 | 1.6 | 16.87 | HBB | 29/10/13 | M/S K R Traders | 24.84
34 | Rangunia | 415705187 | Jan Mohammad Road | WD-VZR-CTG-RANGU-13/68 |  |  |  |  | 1 |  | 28 | 17/07/13 | 0.65 | 1.6 | 20.78 | HBB | 29/10/13 | M/S K R Traders | 24.65
35 | Rangunia | 415705010 | Construction of 1vent 2.00mx2.00m RCC Box Culvert on South Nichintupur Godarper S.Alam Road | WD-VZR-CTG-RANGU-13/64 | [5 empty] | 2 | 2.32 | 24/07/13
36 | Rangunia | 415705419 | Late Hazi Abdul Goni Road. | WD-VZR-CTG-RANGU-13/65 |  |  |  |  | 0.4 |  | 4.11 | 2013-10-10 | 0.4 | 1 | 4.11 | HBB | 2013-10-10
37 | Rangunia | 415704039 | Construction of 42.00m Long RCC Girder Bridge on Jangle Bagabele Road | WD-VZR-CTG-RANGU-STRU-13/66 |  | 42 | ST | 267.47 |  | 42 | 211.52 |  |  | 42 | 211.52 | ST | 2013-12-10 | M/S Consonance Enterprise | 260.96
38 | Rangunia | 415704053 415705163 | Abdul Wahed Talukder Road | WD-VZR-CTG-RANGU-14/79 | 0.7 |  | BC | 40 | 0.7 |  | 35 | 2013-02-12 | 0.6 | 1.6 | 33.09 | BC | 23/07/14
39 | Rangunia | 415705417 415705188 | Abdul Motaleb Chowdhury Road | WD-VZR-CTG-RANGU-14/80 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.75 | 4.8 | 23.04 | HBB | 23/07/14
40 | Rangunia | 415704028 | Mozumderkhi Road | WD-VZR-CTG-RANGU-14/77 | 2 |  | HBB | 56 | 1.5 |  | 39 | 2013-11-12 | 1.4 | 1.1 | 33.26 | HBB | 2014-10-07
41 | Rangunia | 415705416 | Pear Mohammad Para Road | WD-VZR-CTG-RANGU-14/78 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.74 | 0.6 | 21.62 | HBB | 2014-10-07
41 |  |  | Sub - Total |  | 27.04 | 247 |  | 1587.275 | 34.35 | 127.7 | 1465.51 |  | 28.473 | 132.45 | 1220.5 |  |  |  | 1109.35 |  |  |  | 196.01
85 |  |  | Total |  | 85.4 | 487.8 |  | 4679.895 | 84.805 | 218.1 | 3873.92 |  | 72.154 | 221.57 | 3453.94 |  |  |  | 3439.48 |  |  |  | 629.92
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Anowara | 415043001 | Abdul Majid Chowdhury Road | WD-UNR-CTG-ANOWA-10/03 | 3.4 | 10 | BC | 167.8 | 2 | - | 84 |  | 1.175 | 10 | 80.83 | BC | 24/5/10 | Azad Enterprise | 80.59 | 15/9/10 | 28/03/11 RR28/04/12 | 100% | 61.99
2 | Anowara | 415043023 | Anowara-Dhar Pura Hat Road (Hazi Abdul Jalil Road) | WD-UNR-CTG-ANOWA-10/07 | 5 | 15 | BC | 247.5 | 2 | - | 84 |  | 1.26 | 1.5 | 83.68 | BC | 1q | Saived Enterprise | 81.65 | 2010-12-12 | 25/04/11 | 85% | 69.49
3 | Anowara | 415043023 | Anowara-Dhar Pura Hat Road (Hazi Abdul Jalil Road)Remaining Part. | WD-UNR-CTG-ANOWA-11/13 |  |  |  |  | 1 |  | 45 | 28/09/11 | 0.675 |  | 40.68 | BC | 18/12/11 | M/S Ridwanul Haque & Brothers | 40.68 | 13/03/12 | 2012-02-10 | 805% | 6.5
4 | Anowara | 415043023 | Anowara-Dhar Pura Hat Road (Hazi Abdul Jalil Road)Remaining Part. | WD-UNR-CTG-ANOWA-12/19 | [5 empty] | 20 | 106.78 |  |  | 20 | 106.78 | BRIDE | 41133
5 | Anowara | 415043014 | Mahata to Pathani Kotha High school Dattar hat to Gojra High School via Modon boidda bari road. | WD-UNR-CTG-ANOWA-10/01 | 5 |  | BC | 210 | 2.7 | - | 105 |  | 2.7 |  | 101.98 | BC | 2010-04-05 | Saived Enterprise | 101.64 | 15/7/10 | 8/12/2010 R28/02/12 | 100% | 89.39
6 |  |  |  | WD-UNR-CTG-ANOWA-10/10 |  |  |  |  | 2.15 | 12.5 | 96.38 |  | 2.15 | 12.5 | 96.38 | BC | 27/12/10 | M/S Azad Enterprise | 94.43 | 2011-09-03 | 29/03/12 RRR30/06/13 | 60% | 20.55 | Variation
7 | Anowara | 415043015 | Porikora Lalanagar bazar Road (Up to Tangapul Bridge) | WD-UNR-CTG-ANOWA-10/02 | 4 |  | BC | 168 | 1.5 | - | 63 |  | 1.05 |  | 61.2 | BC | 2010-04-05 | Saired Enterprise | 62.94 | 25/7/10 | 08/12/10 RR30/12/11 | 70% | 36.18
8 | Anowara | 415043024 | Alhaz Akhtaruzzaman Chowdhuri Road (Malghar Madrasha-Union Hospital (purano post office). | WD-UNR-CTG-ANOWA-10/14 | 4.47 |  | BC | 187.74 | 1 | - | 21.55 |  | 0.89 |  | 21.55 | BC | 24/5/10 | Karhem Construction | 40.42 | 23/8/10 | 2010-06-03 | 60% | 22.77
9 | Anowara | 415043024 | Alhaz Akhtaruzzaman Chowdhuri Road (Malghar Madrasha-Union Hospital (purano post office). | WD-UNR-CTG-ANOWA-13/24 | [6 empty] | 28.91 |  |  |  | 28.91 | BC | 25/04/13
10 | Anowara | 415043026 | Koinpura road including 85 m RCC Girder Bridge | WD-UNR-CTG-ANOWA-10/09 | 4.5 | 85 | BC | 401.5 | 4.5 | - | 189 |  | 0.715 |  | 23.1 | BC | 28/11/10 | M/S Bappa Enterprise | 21.82 | 18/01/11 | 2012-01-02 | 75% | 8.58
|  |  |  | WD-UNR-CTG-ANOWA-10/11 | [5 empty] | 30.05 | 125.54 |  |  | 30.05 | 125.54 | RCC | 2011-08-05 | Consonance Enterprise | 150.92 | 2011-10-05 | 30/05/12 | 90% | 124.49 | Revised 01/07/12
|  |  |  | WD-UNR-CTG-ANOWA-10/12 | [5 empty] | 36.05 | 115.02 |  |  | 36.05 | 115.02 | RCC | 2011-08-06 | Consonance Enterprise | 139.48 | 2011-10-06 | 30/05/13 | 100% | 84.85 | Revised
|  |  |  | WD-UNR-CTG-ANOWA-13/20 |  |  |  |  | 1 |  | 45 | 13/12/12 | 1.215 |  | 44.61 | HBB | 27/02/13 | M/S Sairad Enterprise | 48.59 |  |  |  |  | 2013-12-01
11 | Anowara | 415045028 415043002 | Bariya Connecting Road | WD-UNR-CTG-ANOWA-10/09 | 2 |  | HBB | 50 | 2 |  | 47.5 | 03/11/10 | 1.355 |  | 22.07 | BC | 08/12/10 | M/S Tazin Enterprise | 41.99 | 13/03/11 | 3/4/2012 R30/12/12 | 60%
11 | Anowara | 415045028 415043002 | Bariya Connecting Road(Remaining Work) | WD-UNR-CTG-ANOWA-13/29 | [10 empty] | 36.5 | BC | 29/10/13 | M/S Zafor & Brother | 32.32
12 | Anowara | GC | Halidhar Fakirhat Bazar,Kanumazir Hat Bazar,Hazirhat Bazar,Dhan-purhat Bazar,Juidandi Sultan Ahamed Chowdhury Bazar,Dattar Hat Bazar&Mamun Khair Bangla Bazar. | WD-UNR-CTG-ANOWA-11/11 |  |  |  | 30 |  |  | 30 | 27/12/10 |  |  | 29.92 |  | 2011-05-04 | M/S N.Huda Enterprise | 28.42 | 2011-07-06 | 28/12/11 | 80% | 12.31
13 | Anowara | 415043024 | Alhaz Akhtaruzzaman Chowdhuri Road (Malghar Madrasha-Union Hospital (purano post office).Remaining Part SL.7&11 | WD-UNR-CTG-ANOWA-11/14 | 4.47 |  | BC | 187.74 | 1 |  | 42 | 2011-05-04 | 0.6 |  | 40.81 | BC | 13/02/12 | M/S Rewdadan Hq & Bro. | 48.96
14 | Anowara | 415043013 | Kantirhat-Barasat U.P Office(Baktiar Road). | WD-UNR-CTG-ANOWA-11/06 | NOT |  | DPP |  | 1.02 |  | 37.6 |  | 1.02 |  | 37.6 | BC | 13/04/11 | M/S Nobi Hossain | 35.71 | 2011-07-06 | 28/12/11 | 100% | 20.27
15 | Anowara | 415043005 | Upazila health Complex Peskarhat Via Chotari UP Off. By HBB. | WD-UNR-CTG-ANOWA-11/17 | 4.38 | 10 | BC | 208.96 | 1 |  | 42 | 27/10/11 | 0.98 |  | 38.55 | BC | 18/12/11 | M/S Saired Enterprise | 46.25
16 | Anowara | 415043008 | Barasat UP office parkibazar Road (Amir Hossain Dovashi Road) | WD-UNR-CTG-ANOWA-13/27 | 2.5 |  | BC | 105 | 1 |  | 28 | 2013-01-04 | 0.875 |  | 27.52 | BC | 22/05/13 | M/S Md.Nurul Aziz Cg. & Brother | 28.89
16 |  |  | Sub-Total |  | 39.72 | 120 |  | 1964.24 | 23.87 | 98.6 | 1336.28 |  | 16.66 | 110.1 | 1163.23 |  |  |  | 1125.7 |  |  |  | 557.37
Village Road
1 | Anowara | 415045005 | Capatali Road | WD-VNR-CTG-ANOWA-10/05 | 1 |  | HBB | 25 | 1 | - | 25 |  | 1 |  | 24.97 | HBB | 24/05/10 | M/S Zahed & Brother's | 23.72 | 15/9/10 | 28/01/11 | 100% | 23.67 | Copleted
2 | Anowara | 415044058 | Khashkhama Anowara Collage Connection road | WD-VNR-CTG-ANOWA-10/06 | 2 |  | BC | 65 | 2 | - | 65 |  | 2 |  | 63.22 | BC | 24/05/10 | Zafar & Brother's | 62.99 | 2010-12-12 | 25/04/11 R10/07/12 | 100% | 38.62
3 | Anowara | 415044005 | Ali Ahmed Chowdhuary Dewtala Patny Cota road | WD-VNR-CTG-ANOWA-10/07 | 1.5 |  | BC | 48.75 | 1.5 |  | 47.25 | 2010-08-08 | 1 |  | 32.79 | BC | 12/10/10 | M/S Kazi Enterprise | 44.27 | 18/01/11 | 2012-01-02 | 70% | 18.25
3 | Anowara | 415044005 | Ali Ahmed Chowdhuary Dewtala Patny Cota road(Remaining Work) | WD-VNR-CTG-ANOWA-13/30 | [10 empty] | 22.08 | BC | 19/10/13 | M/S Nipa Enterprise | 23.18
4 | Anowara | 415045126 | Tairdeep Barokhain Circular road | WD-VNR-CTG-ANOWA-11/15 | 1.5 |  | BC | 48.75 | 1.5 |  | 46.25 | 2010-11-10 | 1.16 | 1.8 | 32.49 | BC | 13/02/12 | M/S Nurul Hossain | 40.45
5 | Anowara | 415044015 | Basiuzaman Road. | WD-VNR-CTG-ANOWA-11/16 | Not Dpp |  |  |  | 1 |  | 30 | 28/09/11 | 0.77 | 1.8 | 28.2 | HBB | 18/12/11 | M/S Ahanaf Enterprise | 33.72
6 | Anowara | 415045128 | Tekota Ali Mohammad Chowdhury Road | WD-VNR-CTG-ANOWA-13/21 |  | NOT DPP |  |  | 1 |  | 40 | 2012-11-12 | 0.57 |  | 22.5 | BC | 27/02/13 | M/s Azad Enterprise | 23.63
7 | Anowara | 415045125 | Tisori Road. | WD-VNR-CTG-ANOWA-13/22 | 1 |  | BC | 32.5 | 1 |  | 35 | 13/12/12 | 1.166 | 0.6 | 30.69 | HBB | 27/02/13 | M/S Saired Enterprise | 32.12 |  |  |  |  | Re-Cast 10/02/14
8 | Anowara | 415045051 | Dattar hat to Shilalia Road | WD-VNR-CTG-ANOWA-13/28 | 1 |  | BC | 32.5 | 1 |  | 28 | 2013-01-04 | 1.15 |  | 27.22 | HBB | 22/05/13 | M/S N Hudah Enterp. | 29.89
9 | Anowara | 415045127 | Bak-Khain Roy Mohon Mollick Road | WD-VNR-CTG-ANOWA-13/23 |  | NOT DPP |  |  | 1 |  | 28 | 28/02/13 | 0.714 |  | 26.43 | HBB | 17/04/13 | M/S Saired Enterprise | 26.14 | 31/03/14
10 | Anowara | 415043010 | Hassan Ali Munsi Road | WD-VNR-CTG-ANOWA-13/ |  | NOT DPP |  |  | 1 |  | 28 | 2013-04-07
11 | Anowara | 415045009 | Anowara Khaikhine Dumuria – Rudura Road By HBB. | WD-VNR-CTG-ANOWA-13/25 |  |  |  |  | 1 |  | 28 | 2013-01-04 | 0.85 |  | 27.56 | BC | 22/05/13 | M/S Jashim & Brother | 28.94
12 | Anowara | 415045024 | Samadia Road By HBB. | WD-VNR-CTG-ANOWA-13/26 |  |  |  |  | 1 |  | 28 | 2013-01-04 | 0.8 |  | 27.43 | BC | 22/05/13 | M/S Tangim Enterprise | 28.8
12 | Anowara | 415045029 | Ram Krishna Road (Boalia Nimtoli Road) | WD-VNR-CTG-ANOWA-14/31 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.93 | 0.75 | 23.81 | HBB | 31/03/14
12 | Anowara | 415045027 | Saleh Ahamed Road | WD-VNR-CTG-ANOWA-14/32 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-01 | 0.8 |  | 24.97 | BC | 31/03/14
13 | Anowara | 415045027 | Saleh Ahamed Road |  | 2 |  | HBB | 29 | 1 |  | 25 | 31/03/14
13 |  |  | Sub - Total |  | 12 | 0 |  | 337.5 | 17 | 0 | 505.5 |  | 12.91 | 4.95 | 414.36 |  |  |  | 397.85 |  |  |  | 80.54
29 |  |  | Total |  | 51.72 | 120 |  | 2301.74 | 40.87 | 98.6 | 1841.78 |  | 29.57 | 115.05 | 1577.59 |  |  |  | 1523.55 |  |  |  | 637.91
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Chittagong
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Patiya | 415613009 | Juldha Danger Char Road | WD-UNR-CTG-PATIYA-10/04 | 2.8 | 20 | BC | 167.6 | 2.8 | - | 51.67 |  | 2.8 | 5 | 51.67 | BC | 2010-12-08 | M/S Syred Enterprise | 96.41 | 2010-10-11 | 1/4/2011 R30/12/11 | 70% | 54.2 | Termination
2 | Patiya | 415613009 | Juldha Danger Char Road | WD-UNR-CTG-PATIYA-10/12 |  |  |  | 0 | 3 | - | 70 | 19/06/11 | 1.58 | 4.05 | 69.78 | BC | 20/07/11 | M/S Bangladesh Constr. | 77.69 | 22/09/11 | 13/04/12 R30/09/12 | 60% | 18.93 | Termination
2 | Patiya | 415613009 | Juldha Danger Char Road | WD-UNR-CTG-PATIYA-13/36 | [5 empty] | - | 75.38 |  |  |  | 75.38 | BC | 2013-07-11
3 | Patiya | 415613021 415613017 | Khan Mohana Station(Abdul Malek) Road | WD-UNR-CTG-PATIYA-10/03 | 1 |  | HBB | 30 | 1 | - | 15.82 |  | 1 |  | 15.82 | BC | 16/05/10 | M/S Haque & Enterprise | 25.67 | 29/8/10 | 2011-12-03 | 80% | 17.5
4 | Patiya | 415613021 415613017 | Khan Mohana Station(Abdul Malek) Road | WD-UNR-CTG-PATIYA-13/34 | [6 empty] | 16.9 |  |  |  | 16.9 | BC | 25/04/13 | M/s Saima Enam | 17.73
5 | Patiya | 415613019 | Patiya Hidgoo Akboria Mazar Road | WD-UNR-CTG-PATIYA-10/01 | 1 | 4 | BC | 52 | 1 |  | 42 |  | 0.95 |  | 29.4 | BC | 16/05/10 | A.S Chowdury | 33.38 | 29/7/10 | 12/12/10 R27/09/11 | 100% | 28.82
6 | Patiya | 415613006 | Keranja Ghat Road. | WD-UNR-CTG-PATIYA-10/07 | 1 | 4 | BC | 52 | 1 | 4 | 49.4 | 03/11/10 | 1.1 | 2.75 | 49.36 | BC | 27/12/10 | M/S Tajin Enterprise | 46.89 | 40789 | 29/03/12 | 45%
7 | Patiya | 415613003 | Elahabad-Shovandardi Road | WD-UNR-CTG-PATIYA-10/08 | 2 | 10 | BC | 109 | 2 | 10 | 35.58 | 22/11/10 | 2 | 1 | 35.58 | Bc | 23/02/11 | M/S Royal Associate | 62.82 | 15/05/11 | 2012-04-06 | 60% | 6.1 | Terminati
7 | Patiya | 415613003 | Elahabad-Shovandardi Road | WD-UNR-CTG-PATIYA-13/35 | [6 empty] | 39.67 | 22/11/10 | 2 | 1 | 39.67 | Bc | 2013-04-08 | M/S Pavel Enterprise | 41.66
8 | Patiya | 415613003 | Elahabad-Shovandardi Road | WD-UNR-CTG-PATIYA-11/11 |  |  | BC |  | 1.8 |  | 23.65 |  | 1.8 |  | 23.65 | Bc | 18/10/11 | M/S Shsh Godi Enterpr | 22.46 | 24/01/12 | 14/08/12 | 80%
9 | Patiya | GC | Budpura GC/Hat Bazar | WD-UNR-CTG-PATIYA-11/09 |  |  |  | 30 |  |  | 30 | 27/12/10 |  |  | 29.49 |  | 20/03/11 | M/S Pavel Enterprise | 29.47 | 2011-05-05 | 26/11/11 RR31/08/12 | 70% | 10.33
10 | Patiya | 415612017 | Uzirpur Road (From kaiagram Ghat Jiri Union to Existitng BC Road of shah Mirpur of Barouthan Union (Ch. 10430-11260n) | WD-UNR-CTG-PATIYA-11/10 | Not DPP |  |  |  | 0.83 | 4 | 14.68 |  | 0.83 |  | 14.68 | BC | 20/12/10 | M/S Tajin Enterprise | 32.96 | 13/03/11 | 2012-03-03 | 70%
10 | Patiya | 415612017 | Uzirpur Road (From kaiagram Ghat Jiri Union to Existitng BC Road of shah Mirpur of Barouthan Union (Ch. 10430-11260n) | WD-UNR-CTG-PATIYA-13/37 | Not DPP | [5 empty] | 19.12 |  |  | 4 | 19.12 | BC | 2013-07-11
11 | Patiya | 415613019 | Patiya Tegarpuni Road. | WD-UNR-CTG-PATIYA-11/16 | 1 |  | HBB | 30 | 1 |  | 30 | 2011-04-08 | 1 |  | 28.97 | HBB | 20/09/11 | M/S M.K Enterprise | 28.96 | 24/01/12 | 14/08/12 | 80%
12 | Patiya | 422663008 | Construction Of 30.05m Lopng RCC Girder bridge On Asia Bathua Road (Ch.350m) | WD-UNR-CTG-PATIYA-STRU-12/24 |  | NOT DPP |  |  |  | 30.05 | 150.04 |  |  | 30.05 | 150.04 | RCC | 2012-02-05 | M/S Salim & Brothers | 150.04 | 2012-09-09 | 30/03/13 R30/06/13 | 0.3
13 | Patiya | 422663008 | Cons.Of 45.00m Long RCC Girder Bridge On Alakananda Road. | WD-UNR-CTG-PATIYA-STRU-12/26 |  | NOT DPP |  |  |  | 45 | 217.89 |  |  | 45 | 217.89 | BRIDG | 23/05/12 |  | 248.16 |  |  |  |  | Reveised 12/02/14
13 |  |  | Sub-Total |  | 8.8 | 38 |  | 470.6 | 14.43 | 93.05 | 881.8 |  | 15.06 | 92.85 | 867.4 |  |  |  | 914.3 |  |  |  | 135.88
1 | Patiya | 415614028 | Darok to Vandargou & bakkhain connecting road under Kashiash union | WD-VZR-CTG-PATIYA-10/02 | 1 |  | HBB | 25 | 1 |  | 25 |  | 1.05 |  | 25 | HBB |  | Nipa Enterprise | 24.95 | 25/7/10 | 2010-08-12 | 100% | 24.84
2 | Patiya | 415614100 415615384 | Dhirin das Road ( Habilasdip Gram) | WD-VZR-CTG-PATIYA-10/05 | 1 |  | HBB | 25 | 1 |  | 24.25 | 2010-08-08 | 1 |  | 24.25 | HBB | 25/10/10 | M/S Tajin Enterprise | 23.03 | 18/01/11 | 2012-01-02 | 100% | 13.48
3 | Patiya | 415614085 | Oli Pathar via Manik Ghola road | WD-VZR-CTG-PATIYA-10/06 | Not DPP |  |  |  | 1 |  | 44.63 |  | 1 |  | 44.63 | HBB | 19/10/10 | M/S shah Abdul Jubber | 42.39 | 13/02/11 | 13/02/12 | 20%
4 | Patiya | 415615072 | Hillichia Lowarkhil Road | WD-VZR-CTG-PATIYA-11/13 | Not DPP | [5 empty] | 29.36 | 2011-12-05 | 1.05 | 2 | 29.36 | HBB | 24/10/11 | M/S shah Godi Enterprise | 28.77 | 24/01/12 | 14/08/12 | 80%
5 | Patiya | 415613002 | Shagadi Road(Uzirpur-Unayinpura Bodha Mondir Road.) | WD-VZR-CTG-PATIYA-11/17 | Not DPP |  |  |  | 1 |  | 38.27 | 2011-04-08 | 1 | 2.4 | 38.27 | BC | 20/09/11 | M/S Pavel Godi Enterpri | 50.71 | 27/11/11 | 18/06/12 RR30/06/13 | 50%
6 | Patiya | 415615208 | 5.Non Ferighat Road. | WD-VZR-CTG-PATIYA-11/14 | Not DPP |  |  |  | 1 |  | 29.17 | 29/08/11 | 1 |  | 29.17 | HBB | 29/08/11 | M/S Bangladesh Con | 28.38 | 23/10/11 | 13/05/12 R30/06/13 | 80%
7 | Patiya | 415613009 | Juldha Danger Char Road | WD-VZR-CTG-PATIYA-11/15 | Not DPP |  |  |  | 1.64 | 6 | 72.6 | 23/08/11 | 1.64 | 6 | 72.6 | BC | 23/08/11 | M/S Bangladesh Constr. | 81.49 | 22/09/11 | 13/04/12 | 1/0/1900 1:12:00 PM
8 | Patiya | 415614044 | Abbas Road(Kaygram)Road. | WD-VZR-CTG-PATIYA-11/19 | Not DPP |  |  |  | 0.8 |  | 20 | 28/09/11 | 0.38 |  | 19.52 | HBB | 2012-03-01 | M/S Tanin & sons. | 19.51 | 2012-05-04 | 16/10/12 R01/05/13
9 | Patiya | 415614090 415615387 | Hidgou High School Road. | WD-VZR-CTG-PATIYA-12/22 | 1 |  | BC | 32.5 | 1 |  | 32.5 | 2011-04-12 | 0.785 | 1 | 32.42 | BC | 24/04/12
10 | Patiya | 415614067 | Haidgaon Annada Datta Road. | WD-VZR-CTG-PATIYA-14/20 | 1 |  | BC | 32.5 | 1 |  | 32.5 | 2011-04-12 | 1 |  | 28.42 | BC | 2014-10-07
11 | Patiya | 415614054 | Beside Habilasdip High School Road. | WD-VZR-CTG-PATIYA-12/21 |  | NOT DPP |  |  | 1 |  | 25 | 13/12/11 | 0.92 |  | 24.48 | HBB | 28/03/12 | M/S Sha Gadhi Traders | 29.62
12 | Patiya | 415615046 | Hulain-Amin Sarif Primary school. | WD-VZR-CTG-PATIYA-12/23 |  | NOT DPP |  |  | 1 |  | 25 | 28/12/11 | 0.63 |  | 24.54 | HBB | 24/04/12 | M/s N Huda Enterprise | 29.95
13 | Patiya | 415615130 | Const.of 3.5m x 3.5m Long RCC Box Culvert On Haidgaon Ziar Para Bazlur Rahman Road. | WD-VZR-CTG-PATIYA-12/27 |  | NOT DPP |  |  |  | 3.5 | 11.12 | 2012-05-12 |  | 3.5 | 11.12 | ST | 2012-05-12
14 | Patiya | 415645059 415615045 | Budhpura To Mahira Perpara Connecting Road. | WD-VZR-CTG-PATIYA-12/25 | 1 |  | BC | 32.5 | 1 |  | 32 | 2012-10-01 | 1 | 2.5 | 31.62 | HBB | 2012-07-05 | M/S Pavel Enterprise | 38.25
15 | Patiya | 415615216 | Dhalghat Bagdandi Nandarkhil Sitabari Road . | WD-VZR-CTG-PATIYA-13/30 |  | NOT DPP |  |  | 1 |  | 35 |  | 1.2 |  | 32.39 | HBB | 27/02/13 | M/S Safi & Sons | 34.01
16 | Patiya |  | Bir Muktijodha S.M Yosuf (Abdul wazed )Road By HBB. | WD-VZR-CTG-PATIYA-13/32 |  | NOT DPP |  |  | 1 |  | 35 |  | 1.223 |  | 46.05 | BC | 13/03/13 | M/S Fokor Ahammed & Co | 49.28
17 | Patiya | 415614053 | Kachuai Forest Office Road By HBB. | WD-VZR-CTG-PATIYA-13/28 |  | NOT DPP |  |  | 1.5 |  | 45 |  | 1.5 | 1.6 | 40.62 | HBB | 27/02/13 | M/S Mahabub & Co. | 43.86
18 | Patiya |  | Monosa Abbas Shikder Road By HBB | WD-VZR-CTG-PATIYA-13/31 |  | NOT DPP |  |  | 0.5 |  | 18 |  | 0.49 |  | 20.5 | BC | 13/03/13 | M/S Fokor Ahammed & Co | 21.53
19 | Patiya | 415614021 | Chanara Faizur Rahman By HBB(Remaining Part) | WD-VZR-CTG-PATIYA-13/29 |  | NOT DPP |  |  | 1 |  | 35 |  | 0.82 | 3.2 | 31.33 | BC | 27/02/13
20 | Patiya | 415614024 | Dhalghat Union Alampur Road. | WD-VZR-CTG-PATIYA-13/33 |  | NOT DPP |  |  | 0.97 |  | 23.94 |  | 0.97 |  | 23.94 | HBB | 13/03/13 | M/S Rupali Trading | 25.13
21 | Patiya | 415614006 | Monir Ahamad Road | WD-VZR-CTG-PATIYA-13/36 |  | NOT DPP |  |  | 1 |  | 40.24 | 29/08/13 | 1 |  | 40.24 | BC |  | M/S.Julda Briks Manu | 42.25
22 | Patiya | 415614092 | Uttar Charlokhya GPS Road | WD-VZR-CTG-PATIYA-13/37 |  | NOT DPP |  |  | 0.45 |  | 23.94 | 29/08/13 | 0.45 |  | 19.86 | BC |  | M/S.Julda Briks Manu | 20.86
22 | Patiya | 415615236 | Hazi Amju Miah Road | WD-VZR-CTG-PATIYA-14/39 | 0.5 |  | BC | 28 | 0.5 |  | 25 | 2013-11-12 | 0.68 |  | 21.49 | BC | 31/03/14
|  | 415615127 | Charlaikha Hospital Road | WD-VZR-CTG-PATIYA-14/40 | 0.5 |  | BC | 28 | 0.5 |  | 26 | 2014-02-01 | 0.95 |  | 25.29 | HBB | 31/03/14
22 | Patiya | 415615083 | Bakkhain-Nishchintapur Road | WD-VZR-CTG-PATIYA-14/38 | 1.5 |  | HBB | 42 | 1 |  | 26 | 2014-02-01 | 1 | 0.6 | 24.223 | HBB | 31/03/14
22 |  |  | Sub - Total |  | 7.5 | 0 |  | 245.5 | 21.86 |  | 774.52 |  | 22.738 | 22.8 | 761.333 |  |  |  | 633.97 |  |  |  | 38.32
35 |  |  | Total |  | 16.3 | 38 |  | 716.1 | 36.29 | 93.05 | 1656.32 |  | 37.798 | 115.65 | 1628.733 |  |  |  | 1548.27 |  |  |  | 174.2
|  |  | Chittagong Grand Total |  | 445.416 | 1641.435 |  | 20721.38 | 573.353 | 1366.585 | 23128.48 |  | 494.169 | 1825.705 | 20361.843 |  |  |  | 18258.29 |  |  |  | 4773.54
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Moheshkhali | 422493004 | Gorokghata-Ghatibhanga Sonadia Road | WD-UNR-COX-MOHES-10/01 | 2 | 130 | BC | 409 | 2 | - | 84 |  | 2 |  | 81.14 | BC | 29/04/10 | Md. Abdur Rashid | 55.02 | 13/6/10 | 13/6/11 | 100% | 53.3 | F-bill Paid
2 | Moheshkhali | 422493016 422493008 | Shipahipara-Modirchara Road | WD-UNR-COX-MOHES-10/03 | 1.2 | 0 | BC | 71.86 | 1 | - | 33.3 | 29/11/10 | 1.02 |  | 33.3 | Bc | 13/02/11 | M/s Isahaq Traders | 49.57 | 27/03/11 | 9/12/2011 RR30/12/12 | 65% | 33.3 | Termina 21/01/13
2 | Moheshkhali | 422493016 422493008 | Shipahipara-Modirchara Road(Remaining Work) | WD-UNR-COX-MOHES-13/05 | [6 empty] | 25.39 |  |  |  | 23.13 | Bc | 2013-05-05 | M/s N M Construct. | 21.96 | 26/06/13 | 2013-10-11 | 0% |  | Termina 03/04/14
3 | Moheshkhali | 422493013 R422493007 | Kalaramarchara JM Ghat Dhala Road. | WD-UNR-COX-MOHES-11/04 | 1.5 |  | HBB | 45 | 1 | - | 30 | 28/09/11 | 0.76 |  | 32.68 | HBB | 29/11/11 | M/S Moheshkhali Enterpri | 32.68 | 25/01/12 | 25/04/12 | 100% | 32.64 | REvised 19/12/12
3 |  |  | Sub Total |  | 4.7 | 130 |  | 525.86 | 4 | 0 | 172.69 |  | 3.78 |  | 170.25 |  |  |  | 159.23 |  |  |  | 119.24
Village Road
1 | Moheshkhali | 422495141 | Chotamoheskhali Kachim Ali Road (Muktijoddha Comander Bochamia Road) | WD-VZR-COX-MOHES-10/02 | 0.78 |  | HBB | 12.4 | 0.784 |  | 22.77 | 1/12/10 | 0.78 |  | 22.77 | HBB | 1/12/10 | M/S Lemon Construction | 21.63 | 26/1/11 | 26/07/11 R31/05/12 | 100% | 12.4 | F-bill Paid
1 |  |  | Sub - Total |  | 0.78 | 0 | 0 | 12.4 | 0.784 |  | 22.77 |  | 0.78 |  | 22.77 |  |  |  | 21.63 |  |  |  | 12.4
4 |  |  | Total |  | 5.48 | 130 |  | 538.26 | 4.784 |  | 195.46 |  | 4.56 |  | 193.02 |  |  |  | 180.86 |  |  |  | 131.64
Union Road
1 | Teknaf | 422903010 | Notun palla para - beach Road | WD-UNR-COX-TEKNA-10/01 | 2 | 1.05 | BC | 86.625 | 2 | 1.05 | 86.63 |  | 1.977 |  | 75.65 | BC | 29/04/10 | M/S Zia Enterprise | 59.51 | 13/6/10 | 13/3/10 | 100% | 56.2 | F/B Paid
2 | Teknaf | 422904041 | Munder Dail Sea Beach(Subrang munder dail Darul UlumMadrasha House Road) | WD-UNR-COX-TEKNA-11/03 | 1 | 0 | BC | 42 | 1 |  | 40 | 11/11/10 | 0.95 |  | 39.78 | BC | 25/10/11 | M/S Shohel Construction | 37.31 | 19/12/11 | 19/06/12 R31/01/13 | 100% | 37.17 | F/B Paid
3 | Teknaf | 422243005 | Teknaf Nutun UP Off-Langurbil Parjaton Bazar Road. | WD-UNR-COX-TEKNA-11/04 | 1.5 |  | BC | 63 | 1.5 |  | 60 | 17/01/11 | 1.445 |  | 60.09 | BC | 25/10/12 | M/S Rezvee Construction | 56.13 | 19/12/11 | 19/09/12 RR15/12/13 | 100% | 54.94 | F/B Paid
4 | Teknaf | 422903002 | Subrang UP Officer- SubrangPanchari Para Road. | WD-UNR-COX-TEKNA-11/02 | 1.38 |  | BC | 57.96 | 1.38 |  | 55 | 17/01/11 | 1.2 | 3 | 54.64 | BC | 21/09/11 | M/S Isfa Enterprise | 51.12 | 19/12/11 | 19/09/12 | 100% | 51.37 | F/B Paid
5 | Teknaf | GC | Hirla UP Bhabon GC/Hat Bazar |  |  |  |  | 30 |  |  | 30 | 17/01/11
6 | Teknaf | 422905021 | Subrang Kochububia Puran Para(Kataboniya Primary Schoo to Hariyakhali Cyclon Centerl)Road, | WD-UNR-COX-TEKNA-12/06 | 0.55 |  | HBB | 23.87 | 0.552 |  | 22 | 14/02/12 | 0.55 |  | 21.71 | HBB | 2013-02-01 | M/S Haque Traders | 21.7 | 17/02/13 | 24/06/13 | 90% | 7 | Cancelled
7 | Teknaf | 422905279 | Subrang BOP-Wabda Embankment(Noyapara Jalil Munshir Bari To East BOP Camp)Road. | WD-UNR-COX-TEKNA-12/05 | 0.505 |  | HBB | 23.84 | 0.465 |  | 22 | 14/02/12 | 0.505 |  | 21.7 | HBB | 2013-02-01 | M/S Ahmed & Brothers | 21.67 | 17/02/13 | 24/06/13 R30/12/13 | 100% | 17.19 | F/B Paid
8 | Teknaf | 422905108 | Subrang Hariyakhali Cyclon Center Cum Primary School to Lafarghona Jalil Master Bari(Noyapara Jalil Munsibari-Hariyakhali Cyclon Center) | WD-UNR-COX-TEKNA-12/07 | 0.691 |  | HBB | 23.78 | 0.5 |  | 22 | 14/02/12 | 0.691 |  | 21.69 | HBB | 2013-02-01 | M/S Haque Traders | 21.61 | 17/02/13 | 24/06/13 RR30/12/13 | 100% | 21.11 | F/B Paid
9 | Teknaf | 422945041 | Jahalia Para Road | WD-UNR-COX-TEKNA-13/09 | 0.645 | 0.47 | HBB | 20.9 | 0.7 |  | 19 | 27/02/13 | 0.645 | 0.47 | 19 | HBB | 2013-03-07 | M/S Ma-Baba Ent. | 18.05 | 15/09/13 | 21/01/14 | 90%
10 | Teknaf | 422904023 | Godar Bill Sea-Beach Pollanpara Road(BRACK office to Govt. Primary School) | WD-UNR-COX-TEKNA-13/10 | 0.68 | 0.47 | HBB | 20.9 | 0.68 |  | 19 | 27/02/13 | 0.68 |  | 19 | HBB | 2013-03-07 | M/S Ma-Baba Ent. | 18.05 | 15/09/13 | 21/01/14 | 30%
11 | Teknaf | 422904029 | Whai-kong Feroz Ahammed Chowdhury Road | WD-UNR-COX-TEKNA-13/08 | 0.495 |  | HBB | 18.7 | 0.6 |  | 17 | 27/02/13 | 0.495 |  | 17 | HBB | 2013-03-07 | M/S Ma-Baba Ent. | 16.15 | 15/09/13 | 21/01/14 | 100% | 14.22 | F/B Paid
11 |  |  | Total |  | 9.446 | 1.99 |  | 411.575 | 9.377 | 1.05 | 392.63 |  | 9.138 |  | 350.26 |  |  |  | 321.3 |  |  |  | 259.2
Union Road
1 | Chakaria | 422163004 | Badarkhali UP Office-Natun Bazar Road | WD-UNR-COX-CHAKA-10/01 | 2 | 10 | HBB | 85 | 2 | 10 | 85 |  | 2.45 | 0.6 | 84.6 | BC | 29/04/10 | MTC-YC-JV | 61 | 13/6/10 | 30/05/11 | 100% | 60.01 | F/B Paid
2 | Chakaria | 422163002 | Harbang RSD/UP office to Shilkhali Road. | WD-UNR-COX-CHAKA-10/03 | 1 |  | HBB | 36.8 | 1 | - | 10.85 |  | 0.95 | 0.6 | 10.85 | BC | 13/02/11 | M/S Mohammadia trad | 18.51 | 27/03/11 | 11/8/2011 R20/16/12 | 60% | 9.95 | Termina 22/01/13
2 | Chakaria | 422163002 | Harbang RSD/UP office to Shilkhali Road. | WD-UNR-COX-CHAKA-13/10 |  |  | BC |  |  |  | 22.98 |  |  |  | 22.98 | HBB | 2013-02-07 | M/S Baba Ma Enter. | 21.82 | 15/09/13 | 21/01/14 | 60% | 9.9
3 | Chakaria | 422163007 | Chringa Up Office MogBazar Palakata Jeti Road |  | 1 | 22 | BC | 97 | 1 | 22 | 92 | 2010-11-11 | [11 empty] | LandDispute
4 | Chakaria | 422163010 | Chiringa UP Office -Charandeep-Sagirshakata-Malumgati Road. | WD-UNR-COX-CHAKA-11/04 | 3.1 | 0.6 | BC | 116.25 | 2.1 | 0.6 | 87.59 | 2010-11-11 | 2 | 0.6 | 84.07 | BC | 2013-02-01 | Md.Hosna.Ilias | 83.21 | 29/03/12 | 17/04/13 | 50% | 29.53 | Termina 22/01/13
5 | Chakaria | 422163010 | Chiringa UP Office -Charandeep-Sagirshakata-Malumgati Road.(Remaining Part) | WD-UNR-COX-CHAKA-12/07 |  |  |  |  | 1 |  | 30 | 25/04/12 | 1.095 |  | 30 | HBB | 2012-11-06 | Abdur Rashid | 33.8 | 2012-06-08 | 31/12/12 | 100% | 31.45 | Final bill paid
| Chakaria | 422163011 | Chiringa UP Office -Charandeep-Sagirshakata-Malumgati Road.(Remaining Part) | WD-UNR-COX-CHAKA-14/16 |  |  |  |  | 1 |  | 25 |  | 0.8 | 2.3 | 24.06 | BC | 17/06/14
6 | Chakaria | 422163005 | Fasiakhali UP Office Vangarmuk Via Fakira Bazar Road. | WD-UNR-COX-CHAKA-12/06 | 1.07 |  | BC | 55.69 | 1 |  | 30 | 27/02/12 | 0.765 |  | 29.51 | BC | 28/03/12 | M/S Chowdhury & Others | 28.03 |  | R30/06/13 | 65% | 12.87
7 | Chakaria | 422163005 | Fasiakhali UP Office Vangarmuk Via Fakira Bazar Road(Remaining Part). | WD-UNR-COX-CHAKA-14/14 | 1.07 |  | BC | 55.69 | 0.5 |  | 22 | 2013-02-12 | 0.7 |  | 20.12 | BC | 17/06/14
8 | Chakaria | 4221164001 | Hindupara Khodarkum Road (Upazila Grameen Bank to Pouro Bus stand via Ashain high way Ahammed Kabir house). | WD-UNR-COX-CHAKA-10/02 | 1.5 |  | BC | 41.13 | 1.5 |  | 50 | 2010-05-09 | 1.5 |  | 43.3 | BC |  | M/S Baba Ma Enterpr | 41.13 | 13/12/10 | 13/6/11 | 100% | 41.12 | Final bill paid
9 | Chakaria | 422164034 | North Surajpur Katakhali ghat-Guniarmuk Via Olisha Bazar Road. | WD-UNR-COX-CHAKA-12/05 | 0.9 |  | HBB | 24.56 | 1 |  | 25 | 27/02/12 | 0.9 |  | 24.62 | HBB | 28/03/12 | M/S G.C International | 23.39 | 15/05/12 | 5/9/2012 R31/03/13 | 50% | 9.79 | Visit This Road
10 | Chakaria | 422164054 | Demoshia Hetaliya Para Road. | WD-UNR-COX-CHAKA-12/08 | 1 |  | HBB | 25 | 1 |  | 25 | 19/04/12 | 0.655 | 3 | 24.1 | HBB | 2012-11-06 | M/S H.K.C Enterprise | 27.74 | 2012-06-08 | 31/12/12 R31/03/13 | 100% | 27.64 | Final bill paid
11 | Chakaria | 422695069 | Kodda Chara -Salahnagar Road | WD-UNR-COX-CHAKA-13/09 | 0.76 | 2.3 | HBB | 27.25 | 1 |  | 28 | 26/02/13 | 0.76 | 2.3 | 27.31 | HBB | 2013-08-04 | A Par Bangla Constr. | 27.31 | 15/05/13 | 24/06/13 R28/02/14 | 40% | 10 | 2012-2013
12 | Chakaria | 422165026 | Manickpur Nurusamad- Shahan Ghat Road | WD-UNR-COX-CHAKA-13/11 | 1 |  | HBB | 27.48 | 1 |  | 28 |  | 1.01 |  | 27.47 | HBB |  | M/S Jannat Ent. | 26.1 | 19/11/13 | 25/03/14 | 100% | 26.1 | Final bill paid
13 | Chakaria | 422165022 | Manickpur Faitong Road | WD-UNR-COX-CHAKA-13/13 | 1 |  | HBB | 28 | 1 |  | 28 | 15/08/13 | 0.94 |  | 27.23 | HBB | 29/10/13 | M/S Faisal Ent. | 25.87 | 2013-10-12 | 16/04/14 | 100% | 25.86 | Final bill paid
14 | Chakaria | 422165026 | Manickpur Nurusamad Soshan Ghat Road |  | Not DPP |  |  |  | 1 |  | 28 | 30/06/13
15 | Chakaria | 422165047 | Mosniakata Road | WD-UNR-COX-CHAKA-13/12 | 0.5 |  | BC | 20 | 0.5 |  | 20 | 30/06/13 | 0.45 |  | 17.77 | BC | 29/10/13 | M/S Arakan Traders | 16.88 | 2013-10-12 | 16/04/14 | 100% | 9.97
16 | Chakaria | 422165048 422164097 | BM Char Dargamora-Krishnapur Primary School Road | WD-UNR-COX-CHAKA-14/15 | 0.5 |  | HBB | 28 | 1 |  | 25 | 2013-02-12 | 0.81 |  | 24.57 | HBB | 17/06/14 | [6 empty] | 2012-2013
16 |  |  | Total |  | 16.4 | 34.9 |  | 667.85 | 18.6 | 32.6 | 662.42 |  | 15.785 | 9.4 | 522.56 |  |  |  | 434.79 |  |  |  | 304.19
Union Road
1 | Ramu | 422663008 | Gorjonia bazar - Dochari Road | WD-UNR-COX-RAMU-10/01 | 1 | 7 | HBB | 47.5 | 1 | 7 | 47.5 |  | 1.22 | 1.88 | 42.92 | BC | 29/04/10 | M/S Tohidul Islam | 40.83 | 13/6/10 | 50/05/11 | 100% | 39.93 | F-bill Paid
2 | Ramu | 422663011 | Ukhir Ghona-Gorjoniya Road. | WD-UNR-COX-RAMU-11/05 | 2.5 |  | BC | 105 | 1.5 |  | 64 | 28/09/11 | 0.9 | 11.1 | 63.89 | BC | 19/01/12 | M/S Cox Bay Const. | 63.88 | 2012-11-03 | 10/7/2012 R30/06/13 | 55% | 24.75
3 | Ramu | 422663011 | Buddist Temple Merongloa( Merongloa Hindu Para)Road. | WD-UNR-COX-RAMU-11/04 | 0.2 | 1 | HBB | 10.94 | 0.3 |  | 13 |  | 0.3 |  | 12.47 | HBB | 25/10/11 | M/S Bazal & Brothers | 11.37 | 19/12/11 | 19/03/12 | 100% | 10.93 | F-bill Paid
4 | Ramu | 422663014 | Con. Of 99.00m Long PC Girder Bridge Over Alekhong Khal On Eidgar Bazar-Boughat Road. | WD-VZR-COX-RAMU-10/06 | 1.5 | 68.5 | BC | 234.25 |  | 99 | 515.51 |  |  | 99 | 515.51 | Bridge |  | DI-AC-NH(JV) | 529.99 | 22/10/12 | 30/06/12 R31/03/14 | 98% | 505.44 | REVEISED 17/06/14
4 | Ramu | 422663014 | Eidgar Bazar-Boughat Road. | WD-VZR-COX-RAMU-13/14 |  |  |  |  | 1 |  | 42 |  | 1.183 | 1.75 | 39.07 | HBB | 18/12/13 | M/S Kajol Cons. | 37.12 | 41792 | 2014-12-06 | 70% | 13
5 | Ramu | 422663006 | RamuChumahni-Fakira Bazar(Rakhin Buddah Mondir Front)Road | WD-VZR-COX-RAMU-13/11 | 0.06 |  | BC | 1.16 | 0.6 |  | 1.15 | 18/06/13 | 0.6 |  | 1.15 |  | 18/06/13 | M/S Palak Barua Appu | 1.15 | 28/07/13 | 20/08/13 | 100% | 1.16 | F-bilPaid
6 | Ramu | 422663014 | Techipul-Joarianala Bazar Road | WD-UNR-COX-RAMU-14/15 | 1 |  | BC | 67 | 1 |  | 62 | 2013-02-12 | 1.177 |  | 55.81 |  | 26/02/14 | M/S Nazrul Cons. | 53.02 | 2014-07-04 | 13/10/14 | 60% | 19.44
7 | Ramu | 422665015 | Arakan Road-Dhechuapalong-Tulabagan Road | WD-VZR-COX-RAMU-14/16 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-02-12 | 1.105 |  | 25.19 | HBB | 26/12/14 | M/S Soha Ent. | 23.93 | 41824 | 13/10/14 | 100% | 20
7 |  |  | Sub-Total |  | 7.26 | 76.5 |  | 493.85 | 6.4 | 106 | 771.16 |  | 6.485 | 113.73 | 756.01 |  |  |  | 761.29 |  |  |  | 634.65
Village Road
1 | Ramu | 422664019 | Merin drive goalia teknaf connecting road carpeting | WD-VZR-COX-RAMU-10/02 | 1.1 | 0.6 | HBB | 46.41 | 2 | - | 50 |  | 1.112 | 2 | 49.3 | BC | 29/04/10RC08/05/11 | Brothers Construction | 46.84 | 13/6/10 | 30/05/11 | 100% | 46.4 | F-bilPaid
2 | Ramu | 422665074 | Kalika mura - Khazbeel Road | WD-VZR-COX-RAMU-10/03 | 0.68 | 4 | HBB | 21.96 | 1 | - | 23.75 | 11.11.10 | 0.675 | 4 | 23.71 | HBB | 2011-06-01 | M/S Hakim & Brothers | 22.52 | 20/03/11 | 20/07/11 R30/04/12 | 100% | 21.95 | F-bilPaid
3 | Ramu | 422664008 | Arakan Road-Tulabagan Road. | WD-VZR-COX-RAMU-13/07 | 1.45 |  | HBB | 37.15 | 1 | - | 40 | 2012-12-12 | 1.45 |  | 38.62 | HBB | 28/01/13 | M/S O R & Sons | 37.14 | 2013-07-03 | 21/07/13 | 100% | 37.05 | F-bilPaid
4 | Ramu | 422663012 422665153 | Kal-Ghar bazar to Fatay Ali Mattabar Bari to Mistry Para Road | WD-VZR-COX-RAMU-13/08 | 0.95 | 1.5 | BC | 36.67 | 1 | - | 35 | 17/01/13 | 0.95 | 1.5 | 34.92 | BC | 19/02/13 | M/S Ashrafia ENT. | 34.91 | 31/03/13 | 14/08/13 | 100% | 34.88 | F-bilPaid
5 | Ramu | 422665098 | Moulavi Para (Joyarianala-Malapara) Road | WD-VZR-COX-RAMU-13/09 | 1 |  | HBB | 24.24 | 1 | - | 21.9 |  | 1 |  | 21.9 | HBB | 18/04/13 | M/S Kajal Constr. | 24.23 | 29/05/13 | 2013-12-10 | 100% | 20.37 | F-bilPaid
6 | Ramu | 422665036 | Amtolia Para(Arakan Road-Seema Bihar Buddah Mondir)Road | WD-VZR-COX-RAMU-13/10 | 0.62 |  | BC | 33.84 | 0.298 | - | 24.95 | 18/06/13 | 0.298 |  | 24.98 | HBB | 18/06/13 | M/S Nehal Enterprise. | 24.95 | 28/07/13 | 2013-04-09 | 100% | 24.95 | F-bilPaid
7 | Ramu | 422665205 | Bimukti Bidorson Vabna Kendra-Jahirer Bari Road | WD-VZR-COX-RAMU-13/12 | 0.15 |  | HBB | 4.04 | 0.15 |  | 4.04 | 18/08/13 | 0.15 |  | 4.04 | HBB |  | M/S Sima cons.. | 4.04 |  |  | 100% | 3.95 | F-bilPaid
8 | Ramu | 422665036 | Amtalia Para(Seema Bihar Buddah Mondir –PDB Office)(Remaining Part) | WD-VZR-COX-RAMU-13/13 | 0.62 |  | BC | 33.84 | 0.325 | - | 7.28 | 18/08/13 | 0.33 |  | 7.27 | HBB |  | M/S Cox Bay Const. | 7.27 |  |  | 100% | 7.26 | F-bilPaid
| Ramu | 422664009 | Dhechuapalong Purbomogchar Road | WD-VZR-COX-RAMU-14/17 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 1 |  | 24.99 | HBB | 17/06/14
8 |  |  | Sub - Total |  | 6.57 | 6.1 |  | 238.15 | 7.773 | 0 | 231.92 |  | 6.965 | 7.5 | 229.73 |  |  |  | 201.9 |  |  |  | 196.81
13 |  |  | Total |  | 13.83 | 82.6 |  | 732 | 14.173 | 106 | 1003.08 |  | 13.45 | 121.23 | 985.74 |  |  |  | 963.19 |  |  |  | 831.46
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Kutubdia | 422453001 | Kutubdia Upzila H/Q to Collage Road to Lemshikhali UP Road. | WD-UNR-COX-KUTUB-10/01 | 5 | 5.5 | BC | 223.75 | 2 | 5.5 | 97.75 |  | 1.5 |  | 62.27 | BC | 29/04/10 | M/S Alam & Brothers | 45.49 | 13/6/10 | 30/05/11 | 50% | 15.45 | Termination
2 | Kutubdia | 422453001 | Kutubdia Upzila H/Q to Collage Road to Lemshikhali UP Road(Remaining Part) | WD-UNR-COX-KUTUB-12/03 |  |  |  |  | 1.5 |  | 48.63 | 2012-03-07 | 1.05 |  | 60.69 | BC |  | M/S Shaheen Enterprise | 69.73 | 27/09/12 | 18/02/13 | 100% | 69.72 | Final Bill Paid
1 |  |  | Sub Total |  | 5 | 5.5 |  | 223.75 | 2 | 5.5 | 97.75 |  | 2.55 |  | 62.27 |  |  |  | 45.49 |  |  |  | 15.45
Village Road
1 | Kutubdia | 422455016 | Puttinna para-Nasierpara Road | WD-VZR-COX-KUTUB-10/02 | 1 | 3.87 | BC | 40.24 | 1 | 3.87 | 38.2 | 29/11/10 | 1.05 | 4.5 | 35.59 | BC | 27/01/11 | M/S Baba Ma Enterprise | 36.61 | 20/03/11 | 16/10/11 | 100% | 36.55 | Final Bill Paid
2 | Kutubdia | 422454020 | Cross Dam Road. | WD-VZR-COX-KUTUB-13/04 | 2.6 | 12 | BC | 262.1 | 1.1 |  | 87.74 |  | 1.1 |  | 115.74 | BC | 2014-08-01 | M/S Hasan Ent. | 121.41 | 21/05/14 | 31/12/14 | 25% | 13
2 |  |  | Sub Total |  | 1 | 3.87 |  | 40.24 | 1 | 3.87 | 38.2 |  | 1.05 | 4.5 | 35.59 |  |  |  | 36.61 |  |  |  | 36.55
4 |  |  | Total |  | 6 | 9.37 |  | 263.99 | 3 | 9.37 | 135.95 |  | 3.6 | 4.5 | 97.86 |  |  |  | 82.1 |  |  |  | 52
Proposed Scheme List under Union Connecting Road & Structure Development Project Greater Chittagong
District : Cox's Bazar
Sl. No. | Upazila | ID No. | Name of Road/Scheme | Package No. | DPP Cost |  |  |  | Allocation |  |  |  | Estimate Approval |  |  |  |  | Name of Contractor/firm | Contract Value | Start Date | Completation Date | Progress | Fund Spent | Remarks
[5 empty] | Proposed Length |  | Type | Total Cost (in Lakh)
[5 empty] | (Km) | Span(m) |  |  | (Km) | Span (m) | Taka | Date | (Km) | Span (m) | Taka | Type | Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 26
Union Road
1 | Ukhia | 422943002 | Palongkhli Bazar-Palongkhli UP Office via Anguman para Road | WD-UNR-COX-UKHIA-10/01 | 1.5 |  | BC | 63 | 1.5 | - | 63 | 29/04/10 | 1.27 | 4 | 62.57 | BC | 2012-01-02 | M/Ssayam Rnterprise | 59.44 | 29/03/12 | 17/01/13 R30/06/13 | 50% | 25.46 | Cancelled
2 | Ukhia | 422943004 | Rotnopal UP Office Chakboitha bazar Via Goalmara(Yousuf Ali Rotnopalong Koroibonia)Road by HBB. | WD-UNR-COX-UKHIA-11/07 | 2 | 1.45 | HBB | 63.63 | 1 |  | 34 | 27/10/11 | 1 | 1.5 | 33.98 | HBB | 2012-01-02 | M/S Chali Enterprise | 33.19 | 29/03/12 | 29/08/12 | 100% | 33.12 | Final bill
3 | Ukhia | GC | Dorga Bazar GC | WD-UNR-COX-UKHIA-12/10 |  |  |  | 30 |  |  | 30 | 17/01/11 |  |  | 29.16 |  | 24/05/12 | M/S Al Noor Ent. | 27.7 | 2012-02-07 | 2/11/12 RRRR30/07/14 | 95% | 21.36
4 | Ukhia | 422942005 | Moricha GC-Naiklongachari GC via Paglir Bill Nutun Para Road | WD-UNR-COX-UKHIA-13/11 | 1 |  | BC | 57 | 1 |  | 49.46 | 2013-10-10 | 1 |  | 49.46 | BC |  | M/S Shimul Ent. | 46.99 | 2013-12-12 | 18/04/14 | 75% | 29
5 | Ukhia | 422942002 | Congtruction of 2 vent 6.00mx6.00m RCC Box Culvert on Ukhiya Daraga Bazar GC Moricha Patabari road | WD-UNR-COX-UKHIA-13/12 |  | 6 | BRIDGE | 65.48 |  | 12 | 59.66 | 29/10/13 |  | 12 | 59.66 | ST | 29/10/13 | M/S Subarna Ent. | 56.67 | 2013-12-12 | 2014-12-04 | 100% | 52.34 | Final bill
5 |  |  |  |  | 4.5 | 7.45 |  | 279.11 | 3.5 | 12 | 236.12 |  | 3.27 | 17.5 | 234.83 |  |  |  | 223.99 |  |  |  | 161.28
Village Road
1 | Ukhia | 422944010 | Gilatoli Moskaria Road | WD-VZR-COX-UKHIA-10/03 | 1.2 | 0.63 | BC | 40.26 | 1.2 | 0.63 | 38.25 | 2010-05-09 | 0.856 |  | 38.12 | BC | 26/10/10 | Atique & Brothers | 36.21 | 30/12/10 | 30/6/11 | 100% | 36.21 | Final bill
2 | Ukhia | 422944058 | Hatimura Road | WD-VZR-COX-UKHIA-10/02 | 1 |  | HBB | 25 | 1 |  | 24.75 | 2010-05-09 | 0.76 |  | 24.72 | BC | 26/10/10 | N.S Enterprise | 23.49 | 30/12/10 | 30/5/12 | 100% | 23.42 | Final bill
3 | Ukhia | 422944056 | Raja Palong Asrayon Road. | WD-VZR-COX-UKHIA-10/05 | 1.65 | 7 | BC | 67.63 | 1.65 | 7 | 64 | 2010-11-11 | 0.67 | 1.5 | 33.38 | BC | 27/01/11 | M/S Shayan enterprise | 61.67 | 20/03/11 | 2011-12-10 | 100% | 31.66 | Final bill
4 | Ukhia | 422944051 | Rumkha Napitpara Road. | WD-VZR-COX-UKHIA-10/04 | 0.55 | 1.35 | HBB | 16.45 | 0.55 | 1.35 | 15.6 | 29/11/10 | 0.6 | 0.9 | 15.72 | HBB | 2011-06-01 | Rafique Uddin | 14.94 | 2011-10-04 | 10/6/2011 R30/06/12 | 100% | 14.37 | Final bill
5 | Ukhia | 422944045 | Gayalmara -Amtoli Road | WD-VZR-COX-UKHIA-11/06 | 1.5 | 4 | HBB | 49.98 | 1.5 |  | 48 | 27/12/11 | 1.5 | 4 | 48.56 | HBB | 19/01/12 | M/S SS Construction | 50.99 | 26/06/12 | 19/12/13 | 100% | 49.98 | Final bill
6 | Ukhia | 422944024 | Goyalmara-Chakbatta Bazar-Digila Road. | WD-VZR-COX-UKHIA-12/08 | 0.76 | 0.75 | BC | 33.61 | 1 |  | 32 | 2012-10-01 | 0.76 | 0.75 | 33.69 | BC | 28/03/12 | M/S jahangir Alam | 32 | 15/15/12 | 28/09/12 R30/06/13 | 100% | 31.88 | Final bill
7 | Ukhia | 422944091 | Muktijuddha Somshar Alam Chowdhury. | WD-VZR-COX-UKHIA-12/09 | 1 | 0.6 | BC | 31.8 | 1 |  | 32 | 15/01/12 | 1 | 0.6 | 31.89 | BC | 28/03/12 | M/S Alam & Brothers | 30.29 | 15/05/12 | 15/09/12 | 65% | 13.88 | Termination 24/04/14
| Ukhia | 422944084 | Karaibania-BDR Camp Road | WD-VZR-COX-UKHIA-14/13 | 0.5 |  | HBB | 14 | 0.5 |  | 12 | 31/03/14 | 0.5 |  | 12 | HBB | 17/06/14
7 |  |  | Sub Total |  | 7.66 | 14.33 |  | 264.73 | 8.4 | 8.98 | 266.6 |  | 6.646 | 7.75 | 238.08 |  |  |  | 249.59 |  |  |  | 201.4
12 |  |  | Total |  | 12.16 | 21.78 |  | 543.84 | 11.9 | 20.98 | 502.72 |  | 9.916 | 25.25 | 472.91 |  |  |  | 473.58 |  |  |  | 362.68
Union Road
1 | Sadar | 422243009 | Edgau UP Office - MeherGhona Forest Office bazar road | WD-UNR-COX-SADAR-10/01 | 3 |  | BC | 126 | 3 | - | 126 |  | 3.41 | 2 | 122.65 | BC | 29/04/10 | M/S Bazal & Brothers | 93.86 | 13/6/10 | 13/3/11 R30/03/12 | 100% | 93.27 | F/B Paid
2 | Sadar | 422243019 422244073 | Eidgon UP-Eidgon College Road.(Azim Master Road) | WD-UNR-COX-SADAR-10/07 | 1.26 | 0.45 | HBB | 27.62 | 1 | - | 30 |  | 1.263 | 0.45 | 30.25 | HBB | 25/10/11 | M/S Shshriar Enterprise | 28.46 | 19/12/11 | 19/04/12 | 100% | 27.62 | F/B Paid
3 | Sadar | 422243017 | Eadgau UP Office-Vomria Forest office bazar Via Baditola Road Road. | WD-UNR-COX-SADAR-10/08 | 1.5 |  | HBB | 45 | 1.5 | - | 45 | 28/09/11 | 1.63 |  | 44.98 | HBB | 29/11/11 | M/S Cilicon Construction | 42.73 | 25/01/12 | 25/04/12 | 100% | 41.7 | F/B Paid
4 | Sadar | 422243017 | Eadgau UP Office-Vomria Forest office bazar Via Baditola Road Road.(Remaining Part) | WD-UNR-COX-SADAR-12/09 | 2.03 | 3 | HBB | 45 | 2.03 | 3 | 61.08 | 21/03/12 | 2.03 | 3 | 61.08 | HBB | 15/04/12 | M/S Chakaria Dev.Soc. | 73.21 | 29/7/2012 | 28/12/12 R28/03/13 | 100% | 80.55 | F/B Paid Reveised
5 | Sadar | 422243007 | PM- khali UP Offfice - Noor Mohammad Chowdhury Road.. | WD-UNR-COX-SADAR-12/10 | 1.95 | 0.625 | BC | 125.02 | 1 |  | 52 | 2012-06-11 | 0.9 | 0.625 | 48.99 | BC | 2013-02-01 | M/S Bazal & Brother. | 52.06 | 17/02/13 | 24/06/13 R30/12/13 | 100% | 48.92 | F/B Paid
6 | Sadar | 422243007 | PM- khali UP Offfice - Noor Mohammad Chowdhury Road.. | WD-UNR-COX-SADAR-14/18 |  |  |  |  | 1.9 |  | 67 | 2013-11-12 | 1.265 | 1.875 | 63.95 | BC | 2014-02-02 | M/S Kadar Ent. | 64.96 | 18/03/14 | 24/07/14 | 40%
7 | Sadar | 422243008 | Islamabad UP-Gagaria Road Via Yosup Road. | WD-UNR-COX-SADAR-13/15 | 0.98 |  | BC | 34.59 | 1 |  | 40 | 2012-12-12 | 0.98 |  | 34.67 | BC | 18/04/13 | M/S Alam & Brother. | 32.94 | 29/05/13 | 2013-12-10 | 70% | 13.78
8 | Sadar | 422243010 | Pokekhali UP-Palakata Bazar(Palakata Mohanvila ) Road | WD-UNR-COX-SADAR-13/16 | 1 |  | BC | 50.41 | 1 |  | 47 | 2013-02-12 | 1.25 |  | 45.93 | BC | 41852 | M/S Ruma Cons. | 43.62 | 19/02/14 | 25/06/14 | 70% | 19.22
9 | Sadar | 422243013 | Zhilongja UP Office - Cherangghar Bazar via Moulovi Para Road | WD-UNR-COX-SADAR-14/21 | 0.5 |  | BC | 34 | 0.5 |  | 31 | 31/03/14 | 1 |  | 31.47 | BC | 17/06/14
9 |  |  | Sub-Total |  | 11.72 | 4.075 |  | 453.64 | 12.93 | 3 | 499.08 |  | 13.728 | 7.95 | 483.97 |  |  |  | 431.84 |  |  |  | 325.06
Village Road
1 | Sadar | 422244064 | Sugondha point to Cox's Bazar Cultural centre Connecting road. | WD-VZR-COX-SADAR-10/02 | 0.67 |  | BC | 46.83 | 0.667 |  | 49.36 |  | 0.667 |  | 49.36 | BC | 12/10/10 | M/S Arid Construction | 46.89 | 2010-05-12 | 2011-05-06 | 100% | 46.83 | Final Bill Paid
2 | Sadar | 422245011 | Mukterkul Churutia madrasa to meagi bari via Bakkali river side East Mukterkul jame mosque carpeting road dev. | WD-VZR-COX-SADAR-10/04 | 1 |  | BC | 32.5 | 1 |  | 30.9 | 2010-05-09 | 1 |  | 30.44 | BC | 31/03/11 | M/S Bahar Construction | 33.34 | 2011-10-05 | 9/10/2011 RR28/02/13 | 90% | 33.29 | Final Bill Paid
3 | Sadar | 422245139 422244029 | PM- khali Jumchari Bazar to Masuakhali Bazar Road. | WD-VZR-COX-SADAR-10/03 | 1 |  | BC | 32.5 | 1 |  | 30.75 | 2010-11-11 | 1.25 |  | 30.58 | Bc | 13/02/11 | M/S KazAl construct | 29.05 | 27/03/11 | 2011-10-08 | 100% | 28.93 | Final Bill Paid
4 | Sadar | 422243006 | P.M khali UP office- Khurulia Bazar Via Mohasniapara Bazar Road. | WD-VZR-COX-SADAR-10/05 | 2.4 |  | BC | 94.73 | 1.25 | 10 | 44.74 | 23/03/11 | 2.4 |  | 44.74 | Bc | 18/05/11 | M/S H.K.C Enterprise | 66.04 | 28/08/11 | 25/05/12 | 70% | 44.22 | Final Bill Paid
5 | Sadar | 422243006 | P.M khali UP office- Khurulia Bazar Via Mohasniapara Bazar Road. | WD-VZR-COX-SADAR-13/14 | [6 empty] | 50.5 |  |  |  | 50.5 | Bc | 2014-08-07
6 | Sadar |  | Cox;s Bazar hotel-Motel Zone Road ,No 5. | WD-VZR-COX-SADAR-10/06 | 0.21 |  | BC | 23.38 | 0.205 |  | 26.67 |  | 0.205 |  | 26.67 | Bc | 18/05/11 | M/S Baba Ma Enterprise | 24.62 | 2011-03-08 | 3/12/2011 RR30/03/13 | 100% | 23.37 | Final Bill Paid
7 | Sadar | 422245489 | Link Road Kacha Bazar - South Mohuri Para Road. | WD-VZR-COX-SADAR-12/11 | 1.15 | 0.6 | HBB | 38.99 | 1 |  | 40 | 2012-06-11 | 1.156 | 0.6 | 39.77 | HBB | 2013-02-01 | M/S Nadim & Brother | 39.82 | 17/02/13 | 24/06/13 | 100% | 38.99 | Final Bill Paid
8 | Sadar | 422245008 | Baruakhali Ghonarpara Road & Motaher Hossain House Road. | WD-VZR-COX-SADAR-13/13 | 1.35 | 0.63 | HBB | 40.14 | 1 |  | 40 | 2012-12-12 | 1.35 | 0.625 | 38.22 | HBB | 20/02/13 | M/S Julakha Enterprise | 38 | 31/03/13 | 14/08/13 | 100% | 38.16 | Final Bill Paid
9 | Sadar | 422245005 | South Kharulia Gov.primary School Road. | WD-VZR-COX-SADAR-13/12 | 0.7 |  | BC | 28.96 | 1 |  | 40 | 2013-01-01 | 0.7 |  | 29.03 | BC | 29/01/13 | M/S Julakha Enterprise | 27.58 | 22/03/13 | 21/07/13 | 100% | 26.32 | Final Bill Paid
10 | Sadar | 422244031 | Motaher Hossain Connecting Road-Ghonar Para Central Jame Mosque-Anur Shop Road | WD-VZR-COX-SADAR-13/17 | 1 |  | HBB | 28 | 1 |  | 25 | 2013-02-12 | 0.845 | 1.25 | 22.7 | HBB | 2014-08-01 | Md Abdur Rahim | 21.55 | 17/06/14 | 16/07/14 | 10%
11 | Sadar | 422245161 | South Hajee Para Food Godown Road | WD-VZR-COX-SADAR-14/19 | 1 |  | HBB | 28 | 1 |  | 26 | 2013-11-12 | 0.867 |  | 25.23 | HBB | 2014-02-02 | M/S Shovon Ent. | 25.55 | 18/03/14 | 2014-06-08 | 80% | 15
12 | Sadar | 422245175 | Chander Para Abdur Rahman Member Road | WD-VZR-COX-SADAR-14/20 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.816 |  | 24.82 | HBB | 17/06/14
13 | Sadar | 422245003 | Kharulia Ghat Para Road | WD-VZR-COX-SADAR-14/22 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.993 |  | 24.78 | HBB | 17/06/14
13 |  |  | Sub-Total |  | 10.48 | 1.23 |  | 394.03 | 10.122 | 10 | 428.92 |  | 12.249 | 2.475 | 436.84 |  |  |  | 352.44 |  |  |  | 295.11
22 |  |  | Total |  | 22.2 | 5.305 |  | 847.67 | 23.052 | 13 | 928 |  | 25.977 | 10.425 | 920.81 |  |  |  | 784.28 |  |  |  | 620.17
Union Road
1 | Pekua | 422953002 422953008 | Shilkali Paharchad Mardasa via RHD Road | WD-UNR-COX-PEKUA-10/01 | 1.5 | 3 | BC | 70.5 | 1.5 | 3 | 70.5 |  | 1.7 | 1.875 | 66.16 | BC | 29/04/10 | Arire International | 47.31 | 13/6/10 | 13/3/11 | 100% | 47.27 | Final bill paid
2 | Pekua | 422953018 | Rajakhali UP Office to Amin Bazar Road. | WD-UNR-COX-PEKUA-11/02 | 1 | 2 | HBB | 35 | 1 | 2 | 33.25 | 29/11/10 | 0.86 |  | 30.27 | BC | 27/01/11 | M/S Nazrul Construction | 28.76 | 20/03/11 | 2011-03-10 | 100% | 28.71 | Final bill paid
3 | Pekua | 422953010 | Mognama RHD via Mognama High School Road | WD-UNR-COX-PEKUA-11/03 | 2.1 | 2 | BC | 93.2 | 2.1 | 2 | 49.28 | 17/01/11 | 1.8 |  | 49.28 | BC | 31/03/11 | M/S Arakan T^raders | 86.99 | 2011-10-05 | 2012-10-05 | 65% | 49.11 | Termina 22/01/13
3 | Pekua | 422953010 | Mognama RHD via Mognama High School Road | WD-UNR-COX-PEKUA-13/07 | [6 empty] | 92.89 |  |  |  | 92.89 | BC |  | M/S
4 | Pekua | 422953009 | Tatong-Barbakia Rajakhali-Darbarhat(Jaliakata Bridge-Rajakhali Natun Ghona Gaderpara) | WD-UNR-COX-PEKUA-12/06 | 0.614 |  | HBB | 16.14 | 0.6 |  | 18 | 27/02/12 | 0.614 |  | 16.98 | HBB | 15/04/12 | M/S Suchana Enterprise | 16.13 | 2012-05-02 | 2012-08-07 | 100% | 16.13 | Final bill paid
5 | Pekua | 422953008 | Shilkali Paharchad Mardasa via RHD Road. | WD-UNR-COX-PEKUA-13/08 | 2.7 | 1.875 | BC | 77.51 | 1 |  | 28 | 30/06/13 | 0.67 |  | 26.54 | BC |  | M/S Hakim & Brothers | 25.21 | 20/11/13 | 19/03/14 R15/10/14 | 60% | 10.61
Village Road
1 | Pekua | 422954018 | Mognama-RHD To Mayadia- Seradia-Balichara-PABT Road. | WD-UNR-COX-PEKUA-11/04 | 1.5 | 2.5 | BC | 56.18 | 1.5 |  | 48 | 27/11/11 | 1.5 | 2.5 | 56.31 | BC | 19/01/12 | M/S Hosna International | 53.49 | 18/04/12 | 17/01/13 R30/06/13 | 70% | 26.84 | Termina
2 | Pekua | 422954023 | Rajakhali GC-Barabakia Jaliakata Bridge Road(Laljanpara Tekghona Road.) | WD-UNR-COX-PEKUA-12/05 | 0.88 |  | HBB | 23.16 | 1 |  | 25 | 27/02/12 | 0.875 |  | 24.42 | HBB | 15/04/12 | M/S Chakaria Dev.Ltdl | 23.2 | 2012-05-02 | 9/4/2012 R30/06/13 | 100% | 23.15 | Final bill paid
3 | Pekua | 422954019 | Toitong UP-Bonkanon Moulana Muzharul Haque Road | WD-UNR-COX-PEKUA-14/09 | 1 |  | HBB | 28 | 1 |  | 25 | 31/03/14 | 0.68 | 1.5 | 20.35 | HBB | 17/06/14
7 |  |  | Total |  | 9.414 | 11.375 |  | 348.53 | 8.7 | 7 | 389.92 |  | 8.699 | 4.375 | 383.2 |  |  |  | 281.09 |  |  |  | 178.67
|  |  | Cox's Bazar Grand Total |  | 94.93 | 297.32 |  | 4353.715 | 93.586 | 190 | 4210.18 |  | 91.125 | 175.18 | 3926.36 |  |  |  | 3521.19 |  |  |  | 2740.01
|  |  | Chittagong & Cox's Bazar Grand Total |  | 540.346 | 1938.755 |  | 25075.095 | 666.939 | 1556.585 | 27338.66 |  | 585.294 | 2000.885 | 24288.203 |  |  |  | 21779.48 |  |  |  | 7513.55
Note on D803: Flora:
Note on D804: Flora:
Note on D805: Flora:
Note on E263: Flora:
Note on E264: Flora:
Note on E265: Flora:
Note on E266: Flora:
Note on E339: Flora:
Note on E341: Flora:
Note on F804: Flora:
Note on F805: Flora:
Note on R147: Flora:
Note on R844: Flora:
Note on T226: Flora: an Enterprise
Note on T227: Flora:
Note on T427: Flora:
Note on U227: Flora:
Note on U427: Flora:
Note on V184: Flora:
Note on V227: Flora:
Note on V353: Flora:
Note on V427: Flora:
Note on W105: Flora:
Note on Y496: Flora:

## Summary Progress
Summary Progress of Grater Chittagong Project
Dt: 01/10/13
Sl. No. | Upazila | DPP Cost |  |  |  | Allocation |  |  | Remarks
|  | Proposed Length |  | Type | Total Cost (in Lakh)
|  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka (in Lakh)
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9
1 | Boalkhali | 25.76 | 79.75 |  | 1194.745 | 17.3 | 23.5 | 724.05
2 | Fatikchari | 38.95 | 335 |  | 2260.65 | 44.35 | 244.3 | 1957.97
3 | Raozan | 60.89 | 256.96 |  | 2804.86 | 128.99 | 208.76 | 3806.55
4 | Hathazari | 23.6452 | 85 |  | 1104.78 | 25.432 | 127.15 | 1265.22
5 | Sandwip | 14.75 | 37.5 |  | 632 | 7.15 | 10 | 287.8
6 | Satkania | 17.64 | 96.45 |  | 816.005 | 17.76 | 100.1 | 1014.92
7 | Sitakunda | 35.25 | 100.5 |  | 1557 | 21.861 | 6.8 | 754.84
8 | Lohagara | 25.9 | 44.8 |  | 929 | 30.475 | 86.2 | 1230.77
9 | Banshkhali | 35.194 | 131.2 |  | 1686.685 | 40.93 | 41.3 | 1427.04
10 | Mirsharai | 70.7 | 98.9 |  | 2840.75 | 58.05 | 105.725 | 2410.9
11 | Chandanish | 30.16 | 175 |  | 1460.95 | 19.09 | 3 | 745.4
12 | Rangunia | 110.15 | 615.3 |  | 5615.07 | 84.805 | 218.1 | 3873.92
13 | Anowara | 55.25 | 135 |  | 2449.5 | 40.87 | 98.6 | 1841.78
14 | Patiya | 30.65 | 140.14 |  | 1402.83 | 36.29 | 93.05 | 1656.32
Total |  | 574.8892 | 2331.5 |  | 26754.825 | 573.353 | 1366.585 | 22997.48
District : Cox's Bazar
Sl. No. | Upazila | DPP Cost |  |  |  | Allocation |  |  | Remarks
|  | Proposed Length |  | Type | Total Cost (in Lakh)
|  | (Km) | Span (m) |  |  | (Km) | Span (m) | Taka (in Lakh)
1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9
1 | Moheshkhali | 9.55 | 136 |  | 673.1 | 4.784 | 0 | 195.46
2 | Teknaf | 11.98 | 11.05 |  | 455.785 | 9.377 | 1.05 | 392.63
3 | Chakaria | 11.5 | 62 |  | 549 | 18.6 | 32.6 | 662.42
4 | Ramu | 13 | 107 |  | 710 | 14.173 | 106 | 1003.08
5 | Kutubdia | 10.82 | 22.37 |  | 428.59 | 3 | 9.37 | 135.95
6 | Ukhia | 11.5 | 18.305 |  | 427.21 | 11.9 | 20.98 | 502.72
7 | Sadar | 26 | 24.5 |  | 966.25 | 23.052 | 13 | 928
8 | Pekua | 13.1 | 12.63 |  | 490.21 | 8.7 | 7 | 389.92
Total |  | 107.45 | 393.855 |  | 4700.145 | 93.586 | 190 | 4210.18
Grand Total |  | 682.3392 | 2725.355 |  | 31454.97 | 666.939 | 1556.585 | 27207.66

## Summary Progress (Update)
Summary Progress of Grater Chittagong Project
District : Chittagong Dt:31.03.2011 | [22 empty] | Taka in lakh
Sl. No. | Upazila | As per DPP | [7 empty] | Allocation | [6 empty] | Rest Allocation
|  | Proposed Length (UNR) |  |  | Proposed Length (VZR) |  |  | Growth Center | Grand Total Cost (UNR&VZR) | Approved Length (UNR) |  |  | Approved Length (VZR) |  |  | Grand Total Cost (UNR&VZR) | Rest Length (UNR) |  |  | Rest Length (VZR) |  |  | Grand Total Cost (UNR&VZR)
|  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost |  |  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost |  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Boalkhali | 22.11 | 78 | 1087.62 | 3.65 | 1.75 | 107.125 |  | 1194.745 | 16.3 | 23.5 | 698.05 | 1 | 0 | 26 | 724.05 | 5.81 | 54.5 | 389.57 | 2.65 | 1.75 | 81.125 | 470.695
2 | Fatikchari | 23.95 | 295 | 1719.4 | 15 | 40 | 541.25 |  | 2260.65 | 10.57 | 201.3 | 890.54 | 33.78 | 43 | 1067.43 | 1957.97 | 13.38 | 93.7 | 828.86 | -18.78 | -3 | -526.18 | 302.68
3 | Raozan | 29.73 | 176.16 | 1653.06 | 31.16 | 80.8 | 1151.8 | 30 | 2834.86 | 17.21 | 62.86 | 931.97 | 111.78 | 145.9 | 2874.58 | 3806.55 | 12.52 | 113.3 | 721.09 | -80.62 | -65.1 | -1722.78 | -971.69
4 | Hathazari | 19.43 | 85 | 999.4 | 4.2152 | 0 | 105.38 |  | 1104.78 | 11.28 | 90.15 | 940.32 | 14.152 | 37 | 324.9 | 1265.22 | 8.15 | -5.15 | 59.08 | -9.9368 | -37 | -219.52 | -160.44
5 | Sandwip | 11.75 | 25 | 532 | 3 | 12.5 | 100 | 30 | 662 | 7.15 | 10 | 287.8 |  |  |  | 287.8 | 4.6 | 15 | 244.2 | 3 | 12.5 | 100 | 374.2
6 | Satkania | 6.64 | 66.45 | 421.005 | 11 | 30 | 395 | 30 | 846.005 | 7.2 | 4 | 351.4 | 10.56 | 96.1 | 663.52 | 1014.92 | -0.56 | 62.45 | 69.605 | 0.44 | -66.1 | -268.52 | -168.915
7 | Sitakunda | 21.75 | 100.5 | 1140.75 | 13.5 | 0 | 416.25 | 30 | 1587 | 4.942 | 5 | 299.1 | 16.919 | 1.8 | 586.74 | 885.84 | 16.808 | 95.5 | 841.65 | -3.419 | -1.8 | -170.49 | 701.16
8 | Lohagara | 9 | 44.8 | 466 | 16.9 | 0 | 463 | 30 | 959 | 7 | 23 | 341.02 | 23.475 | 63.2 | 889.75 | 1230.77 | 2 | 21.8 | 124.98 | -6.575 | -63.2 | -426.75 | -271.77
9 | Banshkhali | 28.04 | 121.2 | 1456.68 | 7.154 | 10 | 230.005 |  | 1686.685 | 16.93 | 19.2 | 686.01 | 24 | 22.1 | 741.03 | 1427.04 | 11.11 | 102 | 770.67 | -16.846 | -12.1 | -511.025 | 259.645
10 | Mirsharai | 37.5 | 55.9 | 1690.75 | 33.2 | 43 | 1150 | 30 | 2870.75 | 24.65 | 33.5 | 1031.69 | 33.4 | 72.225 | 1379.21 | 2410.9 | 12.85 | 22.4 | 659.06 | -0.2 | -29.225 | -229.21 | 459.85
11 | Chandanish | 8.5 | 175 | 794.5 | 21.66 | 0 | 666.45 | 30 | 1490.95 | 2 | 0 | 153.84 | 17.09 | 3 | 591.56 | 745.4 | 6.5 | 175 | 640.66 | 4.57 | -3 | 74.89 | 745.55
12 | Rangunia | 74.31 | 290.3 | 3822.77 | 35.84 | 325 | 1792.3 | 30 | 5645.07 | 50.455 | 90.4 | 2408.41 | 34.35 | 127.7 | 1465.51 | 3873.92 | 23.855 | 199.9 | 1414.36 | 1.49 | 197.3 | 326.79 | 1771.15
13 | Anowara | 37.25 | 135 | 1902 | 18 | 0 | 547.5 | 30 | 2479.5 | 23.87 | 98.6 | 1336.28 | 17 | 0 | 505.5 | 1841.78 | 13.38 | 36.4 | 565.72 | 1 | 0 | 42 | 637.72
14 | Patiya | 15.15 | 58 | 757.3 | 15.5 | 82.14 | 645.53 | 30 | 1432.83 | 14.43 | 93.05 | 881.8 | 21.86 | 0 | 774.52 | 1656.32 | 0.72 | -35.05 | -124.5 | -6.36 | 82.14 | -128.99 | -223.49
Total |  | 345.11 | 1706.31 | 18443.235 | 229.7792 | 625.19 | 8311.59 | 300 | 27054.825 | 213.987 | 754.56 | 11238.23 | 359.366 | 612.025 | 11890.25 | 23128.48 | 131.123 | 951.75 | 7205.005 | -129.5868 | 13.165 | -3578.66 | 3926.345
District : Cox's Bazar
Sl. No. | Upazila | As per DPP Allocation | [7 empty] | Approved Allocation | [6 empty] | Rest Allocation
|  | Proposed Length (UNR) |  |  | Proposed Length (VZR) |  |  | Growth Center | Grand Total Cost (UNR&VZR) | Approved Length (UNR) |  |  | Approved Length (VZR) |  |  | Grand Total Cost (UNR&VZR) | Rest Length (UNR) |  |  | Rest Length (VZR) |  |  | Grand Total Cost (UNR&VZR)
|  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost |  |  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost |  | Length (Km) | Span (m) | Total Cost | Length (Km) | Span (m) | Total Cost
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Moheshkhali | 8.55 | 136 | 648.1 | 1 | 0 | 25 |  | 673.1 | 4 | 0 | 172.69 | 0.784 | 0 | 22.77 | 195.46 | 4.55 | 136 | 475.41 | 0.216 | 0 | 2.23 | 477.64
2 | Teknaf | 9.98 | 1.05 | 385.785 | 2 | 10 | 70 | 30 | 485.785 | 9.377 | 1.05 | 392.63 |  |  |  | 392.63 | 0.603 | 0 | -6.845 | 2 | 10 | 70 | 93.155
3 | Chakaria | 7.5 | 62 | 434 | 4 | 0 | 115 | 30 | 579 | 18.6 | 32.6 | 662.42 |  |  |  | 662.42 | -11.1 | 29.4 | -228.42 | 4 | 0 | 115 | -83.42
4 | Ramu | 7 | 107 | 537.5 | 6 | 0 | 172.5 | 30 | 740 | 6.4 | 106 | 771.16 | 7.773 | 0 | 231.92 | 1003.08 | 0.6 | 1 | -233.66 | -1.773 | 0 | -59.42 | -263.08
5 | Kutubdia | 6.82 | 8.5 | 285.85 | 4 | 13.87 | 142.74 |  | 428.59 | 2 | 5.5 | 97.75 | 1 | 3.87 | 38.2 | 135.95 | 4.82 | 3 | 188.1 | 3 | 10 | 104.54 | 292.64
6 | Ukhia | 6 | 7.45 | 246.625 | 5.5 | 10.855 | 180.585 | 30 | 457.21 | 3.5 | 12 | 236.12 | 8.4 | 8.98 | 266.6 | 502.72 | 2.5 | -4.55 | 10.505 | -2.9 | 1.875 | -86.015 | -45.51
7 | Sadar | 12 | 21.5 | 527.75 | 14 | 3 | 438.5 |  | 966.25 | 12.93 | 3 | 499.08 | 10.122 | 10 | 428.92 | 928 | -0.93 | 18.5 | 28.67 | 3.878 | -7 | 9.58 | 38.25
8 | Pekua | 7.6 | 12 | 325.2 | 5.5 | 0.63 | 165.01 |  | 490.21 | 8.7 | 7 | 389.92 |  |  |  | 389.92 | -1.1 | 5 | -64.72 | 5.5 | 0.63 | 165.01 | 100.29
Total |  | 65.45 | 355.5 | 3390.81 | 42 | 38.355 | 1309.335 | 120 | 4820.145 | 65.507 | 167.15 | 3221.77 | 28.079 | 22.85 | 988.41 | 4210.18 | -0.057 | 188.35 | 169.04 | 13.921 | 15.505 | 320.925 | 609.965
Grand Total |  | 410.56 | 2061.81 | 21834.045 | 271.7792 | 663.545 | 9620.925 | 420 | 31874.97 | 279.494 | 921.71 | 14460 | 387.445 | 634.875 | 12878.66 | 27338.66 | 131.066 | 1140.1 | 7374.045 | -115.6658 | 28.67 | -3257.735 | 4536.31