## Khul
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Khulna
Sl. No. | Upazila | Name of Scheme with Chainage | Package Nos. | Road ID Number | Approving date (H/Q) | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | DACOPE | Batbunia GC-Mozamnagar Bazar via Tildanga UP office Road; at Ch. 0.00-3180m | RAILA/KLN/W01 | 247173003 | 24/08/2011 | 3.18 | - | 10165318 | 787920 | 29-01-2012 | 15-05-2012 | 15-05-2013 30-12-2014 | 11497594 | 3124289 | 70% | 27% | M/S Ankhi Enterprise Dacope, Khulna.
2 |  | Construction of 3vent Box culvert (3x4.00x4.30m) on Kalinagar GC-Garaikhali GC (Paikgacha) Road Low cost bridge at Ch 2982 m. | RAILA/KLN/W02 | 247172009 | 24/08/2011 | - | 12 | 2174299 | - | 2011-05-09 | 2011-08-12 | 2012-10-06 | 2065584 | 2062835 | 100% | 100% | M/s Bappa Enterprise | Final
3 |  | Chunkuri Dakatia Khal to WDB Embk. Road; at Ch. 00-1200 m | RAILA/KLN/W20 | 247175011 | 24/1/2012 | 1.2 | - | 2824058 | - | 29-01-2012 | 15-05-2012 | 2013-09-03 | 2965267.11 | 2345537 | 100% | 100% | M/S Asif Enterprise Dacope, Khulna. | Final
4 |  | Khutakhali (Bajua) GC-Mongla port(Banisanta Bazar) ViaBanisanta UP Office Road; at Ch. 6520-8570 m | RAILA/KLN/W21 | 247172006 | 17-12-2012 | 2.05 | - | 8394942 | - | 2013-03-01 | 2013-07-03 | 30-07-2013 Ex-30-01-2014 | 8388226 | 6363637 | 100% | 76% | Md. Asgar Ali khan
5 |  | Construction of 5vent 5.00x5.00m RCC Box Culvert on Batbunia GC-Mozamnagar Bazar via Tildanga UP office Road at Ch. 2045m; | RAILA/KLN/W19 | 247173003 | 23-01-2013 | - | 25 | 7228627 | - | 24-01-2013 | 2013-05-04 | 2014-05-01 | 6867195.65 | 6851375 | 100% | 99.77% | M/S Habiba Enterprise
6 |  | Rehabilation of Kailashgong Bhutiamari bazar to Kailashgong Denash mondal house via Bangabandhu H/School & Dolkhola Hospital road at Ch. 0.00-1000m; | RAILA/KLN/W33 | 247175035 | 2014-05-12 | 1 |  | 6594141 | 197822 | 28-05-2014 |  |  | 7681431.16 |  | 0% |  | M/S Tutul & Co. Khulna
7 |  | Rehabilation of Kailashgong Bhutiamari bazar to Kailashgong Denash mondal house via Bangabandhu H/School & Dolkhola Hospital road at Ch. 1000-2000m; | RAILA/KLN/W34 | 247175035 | 2014-05-12 | 1 |  | 5761434 | 113078 | 25-05-2014 | 13-08-2014 | 31-03-2015 | 6456087.68 |  | 0% |  | M/S Tutul & Co. Khulna
Sub-Total Dacope: |  |  | 7 |  |  | 8.43 | 37 | 43142819 | 1098820 |  |  |  | 45921385.6
1 | DUMURIA | Kaiya-Salua Bazzar WAPDA; Ch. 00-2132m | RAILA/KLN/W03 | 247304022 | 24/08/2011 | 2.132 |  | 11560788 |  | 2011-05-09 | 15-01-2012 | 15-11-2012 30-06-2014 | 11560788 | 4038953 | 75% | 35% | M/S Mizan Enterprise, 51 Zahidur Rahman Road, Khulna | Carpeting material stacked at site
2 |  | Kaiya-Salua Bazzar WAPDA; Ch. 2132-3300 m & 4450-10250 m; | RAILA/KLN/W04 | 247304022 | 2011-08-24 | 6.968 |  | 17668790 | 114379 | 2011-11-27 | [7 empty] | Contract to be cancelled by XEN, directed by PD on dated 12-08-2014 (App-17668790.00 Salv-114379.00) | 9660179.7
3 |  | Muktijoddha Gazi Nazim Uddin Road & Low cost bridge ; Ch. 00-690 m; | RAILA/KLN/W05 | 247305223 | 24/08/2011 | 0.69 |  | 2535276 | 47957 | 2011-05-09 | 14-12-2011 | 14-05-2012 Ex-30-12-2013 | 2454071 | 1475397 | 70% | 60% | M/s Shahajan Jamader |  | 9911075.32
4 |  | One Low cost bridge (3x4.5mx5m RCC Box Culvert) on Muktijoddha Gazi Nazim Uddin ; at Ch. 192 m; | RAILA/KLN/W06 | 247305223 | 24/08/2011 |  | 13.5 | 2159496 |  | 2011-05-09 | 2011-08-12 | 2012-06-07 | 2051521 | 2050619 | 100% | 100% | M/S M H Traders | Final | 3479971.95
5 | DUMURIA | Ramkrisnopur-Santinagar Road & Low cost bridge; Ch. 00-1000 m; | Recast RAILA/KLN/W07 | 247305225 | 24/8/2011 R-31/12/2012 | 1 |  | 3723775 | 134793 | 2011-05-09 | 14-12-2011 | 30-04-2013 Ex-30-12-2013 | 3665639 | 900153 | 50% | 25% | Abul Kalam Azad |  | 7077767
6 |  | One Low cost bridge (3x4.5mx5m RCC Box Culvert) on Ramkrisnopur-Santinagar Road; at Ch. 490 m; | RAILA/KLN/W08 | 247305225 | 24/08/2011 |  | 13.5 | 2159496 |  | 2011-05-09 | 2011-08-12 | 2012-08-07 | 2051521 | 2015393 | 100% | 100% | M/s Ashraf Trader | Final | 17783169
7 |  | Bosundiadanga-Magurkhali UP Road; Ch. 1000-2400 m ; | RAILA/KLN/W09 | 247304036 | 24/08/2011 | 1.4 |  | 5993143 | 643787 | 2011-05-09 | 2011-08-12 | 08-06-2012 Ex-15-03-2013 | 6305083 | 6211209 | 100% | 100% | M/s Ma-Moni Traders | Final | 47912162.97
8 |  | Gilerdanga RHD-Lata Khamarbari Road; Ch.650-2380 m; | RAILA/KLN/W10 | 247304032 | 24/08/2011 | 1.73 |  | 2311127 |  | 2011-05-09 | 14-12-2011 | 28-06-2012 | 2195570 | 2190535 | 100% | 100% | Md. Karimul Islam Biswas | Final
9 |  | Gilerdanga RHD-Lata Khamarbari Road; Ch.2380-4150 m; | RAILA/KLN/W11 | 247304032 | 2014-05-12 | 1.77 |  | 10174021 | 854602 | 25-05-2014 | 13-08-2014 | 31-03-2015 | 12109828.08 |  | 0% |  | M/S Faisal Traders
10 |  | Rudaghora Halderpara (H/O Dr. Nikhil) Road; Ch. 00-1100 m; | RAILA/KLN/W12 | 247305026 | 24/08/2011 | 1.1 |  | 4085972 |  | 2011-05-09 | 14-12-2011 | 20-08-2012 | 3881673 | 2331315 | 100% | 60% | M/s Ma-Moni Traders
11 |  | Baliyakhali Bazar (Tipna R & H) -kadamtala-Madartola Via Shovna UP Road; Ch. 7800-9100 m; | RAILA/KLN/W13 | 247303003 | 24/08/2011 | 1.3 |  | 6149867 | 196505 | 2011-05-09 | 2011-08-12 | 08-06-2012 Ex-30-12-2012 | 6029053 | 5895779 | 100% | 100% | M/s KCC International | Final
12 |  | Shahapur Sarder Bari Road; Ch. 00-1500 m; | RAILA/KLN/W14 | 247305227 | 24/08/2011 | 1.5 |  | 5214804 | 217805 | 2011-05-09 | 20-12-2011 | 20-05-2012 Ex-31-04-2013 10-06-2014 | 5160978 | 5153534 | 100% | 100% | M/s Rakib Enterprise
13 |  | Raghunathpur Moshjid - Gour Shaha (Fakir Bari) Road; Ch. 00-1000 m; | RAILA/KLN/W15 | 247305194 | 24/08/2011 | 1 |  | 1482817 | 100076 | 2011-05-09 | 14-12-2011 | 2012-10-07 | 1503748 | 1502502 | 100% | 100% | M/s Karimul Islam Biswas | Final
14 |  | Rehab. Of Kaiya-Salua Bazzar WAPDA Road Ch. 3300-5500m; | RAILA/KLN/W30 | 247304022 | 19-01-2014 | 2.2 |  | 6306362 | 86372 | 2014-10-03 | 2014-08-06 | 2014-12-07 | 5320676 |  | 0% |  | M/S Faisal Traders
Sub-Total Dumuria: |  |  | 13 |  |  | 15.822 | 27 | 63856944 | 2281897 |  |  |  | 64290149.08
1 | KOYRA | Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 00-2400 m; | RAILA/KLN/W23 | 247532003 | 24/1/2012 | 2.4 | - | 7120615 | - | 29-01-2012 | 2012-07-05 | 07-03-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 7476624.47 | 6808389 | 100% | 100% | Md. Zahangir Munshi, Terokhada, Khulna. | Final
2 |  | Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 2400-4900 m; | RAILA/KLN/W24 | 247532003 | 24/1/2012 | 2.5 | - | 2769083 | - | 29-01-2012 | 2012-07-05 | 07-03-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 2769083 | 2769083 | 40% | 31% | M/S Shahin & Brothers, Terokhada, Khulna. | W/O Cancle
|  | Remaining work of Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 2400-4900 m; | RAILA/KLN/W24 (RW) |  | 2014-07-07 |  |  | 5757060 |  | 15-07-2014 |  |  | 5635745.87 |  | 0% |  | Md. Obydul Islam
3 |  | Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 4900-10600 m; | RAILA/KLN/W25 | 247532003 | 24/1/2012 | 5.7 | - | 4828597 | - | 29-01-2012 | 2012-10-04 | 20-01-2013 | 5069972.02 | 4945432 | 100% | 100% | M/S Shahid Enterprise, Khulna | Final
4 |  | Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 10600-13100 m; | RAILA/KLN/W26 | 247532003 | 24/1/2012 | 2.5 | - | 2214088 | - | 29-01-2012 | 2012-07-05 | 07-02-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 2214088 | 2214088 | 40% | 35% | M/S Shahin & Brothers, Terokhada, Khulna. | W/O Cancle
|  | Remaining work of Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 10600-13100 m; | RAILA/KLN/W26 (RW) |  | 2014-07-07 |  |  | 4931711 |  | 15-07-2014 |  |  | 4882342.53 |  | 0% |  | M/S Faisal Traders
5 |  | Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 13100-15700 m; | RAILA/KLN/W27 | 247532003 | 24/1/2012 | 2.6 | - | 1416978 | - | 29-01-2012 | 2012-07-05 | 07-02-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 1416978 | 1416978 | 40% | 23% | Md Zahingir Munshi, Terokhada, Khulna. | W/O Cancle
|  | Remaining work of Rehabilation of Upazila H.Q-Haitkhali GC-Gilabari GC Road; at Ch 13100-15700 m; | RAILA/KLN/W27 (RW) |  | 2014-07-07 |  |  | 4163225 |  | 15-07-2014 |  |  | 4163225
6 |  | Rehabilation of Koyra UP-4 No Koyra Bazar; at Ch 00-4330 m; | RAILA/KLN/W28 | 247533001 | 24/1/2012 | 4.3 | - | 1012481 | - | 29-01-2012 | 2012-07-05 | 07-02-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 1012481 | 1012481 | 65% | 23% | M/S Shahin & Brothers, Terokhada, Khulna. | W/O Cancle
|  | Remaining work of Rehabilation of Koyra UP-4 No Koyra Bazar; at Ch 00-4300 m; | RAILA/KLN/W28 (RW) |  | 2014-07-07 |  |  | 3915338 |  | 15-07-2014 |  |  | 3876147.8 |  | 0% |  | M/S Faisal Traders
7 |  | Rehabilation of Koyra UP-Suti Bazar; at Ch 00-5800 m; | RAILA/KLN/W29 | 2475323003 | 24/1/2012 | 2.33 | - | 1043697 | - |  | 24-04-2012 | 07-02-2013 Ex-30-12-2013 (1st) Ex-30-05-2014 (2nd) | 1043697 | 1043697 | 60% | 23% | Md. Zahangir Munshi, Terokhada, Khulna. | W/O Cancle
|  | Remaining work of Rehabilation of Koyra UP-Suti Bazar; at Ch 00-2330 m; | RAILA/KLN/W29 (RW) |  | 2014-07-07 |  |  | 4264926 |  |  |  |  | 4011346.74 |  | 0% |  | M/S Baig Enterprise
8 |  | Rehab. Of Jaygir mohal bazar-Gilabari GC road Ch. 1500-2298m; | RAILA/KLN/W32 | 2475322010 | 19-01-2014 | 0.798 | - | 4968623.54 | 381733 | 2014-10-03 | 2014-08-06 | 2014-07-12 | 4975718.46 |  | 0% |  | M/S Faisal Traders
|  | Sub-Total Koyra: | 8 |  |  | 23.128 | 0 | 48406422.54 | 381733 |  |  |  | 48547449.89
1 | PAIKGACHA | Gozalia Chowrasta - Chowmohoni Bazar; at Ch 500-1831.37m ; | Recast RAILA/KLN/W16 | 247644029 | 24-08-2011 | 1.331 | - | 3119009 | - | 2011-05-09 | 2011-08-12 | 2012-05-08 | 3119009 | 1874165 | 100% | 60% | M/s Agrani Construction | Final
2 |  | Paikgacha GC-Baintola bazer-Bogular chalk bazer-Surikhali bazer-Gilabari GC (Paikgacha portion); at Ch 2000-10000 m; | RAILA/KLN/W17 | 247642012 | 24/8/2011 | 8 | - | 2583626 | 190701 | 2011-05-09 | 2011-08-12 | 2012-05-07 | 2635610 | 2341369 | 100% | 100% | Sk. Akbar Hossain | Final
3 |  | Paikgacha R&H- Baka GC road; at Ch 00-6150 m; | RAILA/KLN/W18 | 247642003 | 24/8/2011 | 6.15 | - | 924999 | - | 2011-05-09 | 2011-08-12 | 19-03-2012 | 878749 | 878749 | 100% | 100% | M/s S M Shafi | Final
Sub-Total Paikgacha: |  |  | 3 |  |  | 15.481 | 0 | 6627634 | 190701 |  |  |  | 6633368
1 | Rupsha | Rehab. Of Narikali Raton dey house-Chara Battala via Bablu Sheik house road Ch. 0.00-500.0m | RAILA/KLN/W31 | 247755290 | 19-01-2014 | 0.5 | - | 2033469 | 264788 | 2014-10-03 | 30-06-2014 | 30-12-2014 | 2159211.86 |  | 0% |  | M/S Ananna Enterprise
Sub-Total Paikgacha: |  |  | 1 |  |  | 0.5 | 0 | 2033469 | 264788 |  |  |  | 2159211.86
Total : Khulna District |  |  | 32 |  |  | 63.361 | 64 | 164067288.54 | 4217939 |  |  |  | 167551564.43 | 79817493 | 69.06%
Total Package -33 (1 Package Cancle)

## Bagerhat
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Bagerhat
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date (H/Q) | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Tk) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Polerhat GC-Jattrapur GC road; at Ch 2880-8610 m; | RAILA/BGT/W06 | 201082003 | 2011-11-30 | 4.6 | - | 3006109 | 10186 | 2011-12-07 | 20-02-2012 | 19-12-2012 | 2865480.25 | 2855293 | 100% |  | Sarder Jasim, Bagerhat | FB Paid
2 |  | Barakpur-Polerhat-Chulkati R&H road; at Ch 00-7880 m; | RAILA/BGT/W07 | 201082004 | 2011-11-30 | 7.88 | - | 5439923 | 5519 | 2011-12-07 | 2012-01-03 | 2013-10-01 | 5173169.9 | 4961605 | 100% |  | S.K Kamrul Hasan, Nonadanga, Bagerhat | FB Paid
3 |  | Baitpur R&H Kandapara GC raod; at Ch 1200-2700 m; | RAILA/BGT/W08 | 20108 2007 | 2011-11-30 | 1.5 | - | 1456236 | 8179 | 2011-12-07 | 16-02-2012 | 25-08-2012 | 1391194.25 | 1380143 | 100% |  | M/S Bebakanandha Enterprise, Chitalmari, Bagerhat | FB Paid
4 |  | Jattrapur GC-Fakirhat-Chitalmari RHD; at Ch 0.00-8200.00m; | RAILA/BGT/W09 | 20108 2008 | 2011-11-30 | 7.4 | - | 9401433 | 54436 | 2011-12-07 | 19-02-2012 | 28-12-2012 | 8983075.55 | 8806628 | 100% |  | M/S Shovo Enterprise, Bagerhat | FB Paid
5 |  | Barakpur-Taterhat-Guchchagram road; at Ch 0-7600 m; | RAILA/BGT/W10 | 201082010 | 2011-11-30 | 7.6 | - | 9983127 | 9734 | 2011-12-07 | 26-02-2012 | 25-12-2012 | 9493217.95 | 9483251 | 100% |  | M/s Ifat International, New Market, Bagerhat | FB Paid
6 |  | Kashimpur GC-Mollikerber up office vie dema UP; at Ch 00-2600 m; | Variation RAILA/BGT/W11 | 20108 3009 | 11/30/2011 V-11-06-2012 | 2.6 | - | 2417434 | 142701 | 2011-12-07 | 14-02-2012 | 23-08-2012 | 2791985 | 2645901 | 100% |  | M/s Moon Enterprise, Horinkhana, Bagerhat | FB Paid
7 |  | Bariopara up-Haderaht bazar via kartrickdia road; at Ch 40 m; | RAILA/BGT/W12 | 20108 3011 | 2011-11-30 | - | 12 | 2314054 | - | 2011-12-07 | 19-02-2012 | 28-08-2012 | 2198351.3 | 2198244 | 100% |  | M/S Bhuiyan Construction, Kachua, Bagerhat | FB Paid
8 |  | Gotapara-Noapara road; at Ch 1100 m; | RAILA/BGT/W13 | 20108 5169 | 2011-11-30 | - | 2 | 408891 | - | 2011-12-07 | 16-04-2012 | 25-06-2012 | 388446.45 | 382218 | 100% |  | M/s Akon Traders, Sharankhola, Bagerhat | FB Paid
|  | Sub-Total Sadar: | 8 |  |  | 31.58 | 14 | 34427207 | 230755 |  |  |  | 33284920.65
1 | CHITOLMARI | Chitalmari UP-Aruaborni-Puraton Kalsera (Barosia bazar) road; at Ch 00-2000 m; | RAILA/BGT/W01 | 201143008 | 26-09-2011 | 1.14 | - | 3849815 | - | 16-01-2012 | 2012-11-04 | 2012-07-05 | 4042305.75 | 4005494 | 100% |  | M/S Alif Store, Chitalmari, Bagerhat. | FB Paid
2 |  | Chitalmari UP-Aruaborni-Puraton Kalsera (Barosia bazar) road; at Ch 2140-3090 m; | RAILA/BGT/W24 | 201143008 | 2012-04-17 | 0.95 |  | 4928593 | 470216 | 2012-07-10 | 2013-07-01 | 15-11-2013 30-06-2014 | 4926128 | 4455649 | 100% |  | M/S Shawon Enterprise | FB Paid
|  | Sub-Total Chitolmari: | 2 |  |  | 2.09 | 0 | 8778408 | 470216 |  |  |  | 8968433.75
1 | KACHUA | Kachua -Banagam road; at Ch 3000-5470 m; | RAILA/BGT/W03 | 201382003 | 2011-09-26 | 2.47 | - | 8015471 | 3353589 | 24-10-2011 | 16-01-2012 | 15-11-2013 | 11312155 | 2407841 | 90% |  | M/S Raha Enterprise, Fultala, Khulna
2 |  | Larahat-Lararkul VRA road Iron bridge replace by RCC Box/Culvert; at Ch 2000 m; | RAILA/BGT/W02 | 201384045 | 2011-09-26 |  | 4.3 | 1079324 |  | 24-10-2011 | 26-01-2012 | 2012-04-08 | 1025357.8 | 1025357 | 100% |  | M/S Raha Enterprise, Fultala, Khulna | FB Paid
|  | Sub-Total Kachua: | 2 |  |  | 2.47 | 4.3 | 9094795 | 3353589 |  |  |  | 12337512.8
1 | MONGLA | Mongla Thana H/Q-Chaterhat Care Bazar road; at Ch 4500-8000 m; | RAILA/BGT/W04 | 201582001 | 2011-09-26 | 2.85 | - | 9052915 | 4479972 | 24-10-2011 | 29-03-2012 | 2013-07-02 | 13531647 | 9051521 | 100% |  | M/S Habib Enterjprise, Bagerhat | 5th R/A
2 |  | Digraj-Jhalmolia Dighi road ; at Ch 1350-2500 m; | Recast RAILA/BGT/W05 | 201582007 | 9/26/2011 R-14-03-2013 | 1.15 | - | 3997093 | 328270 | 2011-11-14 | 2012-07-02 | 2013-05-08 | 4730705 | 2573669 | 100% |  | M/S Saymon Enterprise, Sharankhola, Bagerhat. | 3rd R/A
3 |  | Re- Construction of 2.00M X 2.00M Size RCC Box Culvert on Mongla – Joymonoghol Road | RAILA/BGT/W23 | 201582003 | 23-02-2012 | - | 2 | 617425 | - | 2012-11-03 | 27-05-2012 | 2012-05-08 | 648296.25 | 648172 | 100% |  | M/S Antor Enterprise, Mongla, Bagerhat | FB Paid
|  | Sub-Total Mongla: | 3 |  |  | 4 | 2 | 13667433 | 4808242 |  |  |  | 18910648.25
1 | MORELGONJ | Matham-Teligati-Malomgacha barhman kati kakerbil; at Ch 00-1643 m; | RAILA/BGT/W19 | 201602013 | 2012-01-29 | 1.64 | - | 6749085 | 817232 | 31-01-2012 | 2012-08-04 | 17-08-2012 30-10-2013 Ex-30-03-2014 | 7528485.42 | 6268458 | 100% |  | M/S Sundarban Enterprise Sharankhola, Bagerhat | FB Paid
2 |  | Daibajanhati-Teligati chomra-thuligati bazar-teligat; at Ch. 1150-3550 m ; | RAILA/BGT/W20 | 201602010 | 2012-10-08 | 2.2 | - | 6747199 | 1295569 | [8 empty] | Postponded by Project Director on dated 23-07-2014 (App-6747199.00 Sal-1295569.00)
3 |  | Rehabilation of Baniakhali GC-Morrelgonj GC road; at Ch 00-2500 m ; | RAILA/BGT/W29 | 201602001 | 2012-10-08 | 2.5 | - | 4225715 | 502202 | 2310-2012 | 23-01-2013 | 2013-02-08 | 4491521.48 | 3967401 | 100% |  | S.K. Almas Ali Harinkhana, | FB Paid
4 |  | Rehabilation of Baniakhali GC-Morrelgonj GC road; at Ch 2500.0-4870.0 m ; | RAILA/BGT/W30 | 201602001 | 2012-10-08 | 2.37 | - | 3757384 | - | 23-10-2012 | 22-01-2013 | 2013-02-08 | 3569486.41 | 3538914 | 100% |  | M/S Alif Store Chitalmari | FB Paid
5 |  | Rehabilation of Baniakhali GC-Morrelgonj GC r oad; at Ch 8200.0-11161.0 m ; | RAILA/BGT/W31 | 201602001 | 2012-10-08 | 2.961 | - | 6072472 | - | 23-10-2012 | 20-01-2013 | 29-11-2013 | 5768848.33 | 3998000 | 100% |  | M/S Sonia Enterprise | 1st R/A
6 |  | Rehabilation of Baniakhali GC-Morrelgonj GC road; at Ch 11161.0-12287.0 m ; | RAILA/BGT/W32 | 201602001 | 2012-10-08 | 1.126 | - | 5577119 | 2538706 | 23-10-2012 | 22-01-2013 | 2013-02-12 | 7710034.22 | 5145947 | 100% |  | M/S Alif Store Chitalmari | FB Paid
|  | Sub-Total Morelgonj: | 5 |  |  | 12.797 | 0 | 33128974 | 5153709 |  |  |  | 29068375.86
1 | RAMPAL | Rampal-Bashtola road; Ch. 00-540m ; | RAILA/BGT/W14 | 201733006 | 2012-01-08 | 0.54 |  | 1255325 |  | 16-01-2012 | 2012-03-04 | 2012-11-08 | 1318091.25 | 856000 | 100% |  | M/S Mizan Enterprise, Fakirhat, Bagerhat. | 2nd
2 |  | Mollikerber Up-Kashimpur GC (Rampal protion); Ch. 00-4000m | Recast RAILA/BGT/W15 | 201733012 | 1/8/2012 R-15-05-2013 | 4 |  | 3401982 | 201147 | 16-01-20152 | 23-04-2012 | 2012-02-09 | 3749192 | 3404719 | 100% |  | M/S Moon Enterprise, Horinkhana, Bagerhat. | FB Paid
3 |  | Babur bari-Bujbunia road; Ch. 00-1130m | RAILA/BGT/W16 | 201732014 | 2012-01-08 | 1.13 |  | 3314259 |  | 16-01-2012 | 23-04-2012 | 18-08-2012 | 3479971.95 |  | 40% |  | M/S Mizan Enterprise, Fakirhat, Bagerhat. | Contract to be cancelled by XEN, directed by PD on dated 11-08-2014 (App-3314259 Contract-3479971.95)
4 |  | Perilhai GC-Hurka UP; Ch. 00-750m & 2100-3000m | RAILA/BGT/W17 | 201733009 | 2012-01-08 | [12 empty] | WO Cancle (APP-29,54,853.00 Salv-1,17,424.00 Contra-32,25,890.00)
5 |  | Modhakhali-kheyahat-east banstail cyclone shelter; Ch.15 00-2500m | RAILA/BGT/W18 | 201734033 | 19-09-2012 | 1 |  | 1334621 |  | 2012-07-10 | 2013-06-01 | 15-04-2013 | 1334621 | 1292164 | 100% |  | M/S Rina Enterprise | FB Paid
6 |  | Construction of 4.00mx4.00m Single vent Box culvert on Pitta Ibrahim shake house-sogunia nagan pall via pitta soguna mosque at Ch 700 m; | RAILA/BGT/W25 | 201734118 | 2012-10-08 |  | 4 | 1843310.4 |  | 23-10-2012 | 23-01-2013 | 29-07-2013 | 1843310.4 | 1683000 | 100% |  | Md. Alamgir Khan | 1st R/A
7 |  | Construction of Two vent 4.00mx4.00m RCC Box culvert on Gilatala-GC-Bhospatia UP; at Ch 9850 m | RAILA/BGT/W26 | 201733002 | 2012-10-08 |  | 8 | 2243017 |  | 23-10-2012 | 13-01-2013 | 22-07-2013 | 2242568.39 | 2203147 | 100% |  | Md. Sakender Ali | FB Paid
8 |  | Construction of 4.00mx4.00m Single vent Box culvert on Hurka jalmalia dhigi-Chara khali gona khal gorra char; at Ch 1250 m; | RAILA/BGT/W27 | 201734130 | 2012-10-08 |  | 4 | 1843310.4 |  | 23-10-2012 | 2013-03-02 | 02-08-2013 Ex-31-01-2014 | 1843310.4 | 524500 | 100% |  | M/S S.S. Brothers | 2nd
9 |  | Construction of Two vent 4.00mx4.00m RCC Box culvert on Rajanagor Soshon ghat-Solikhali gora Road; at Ch 457 m; | RAILA/BGT/W28 | 201734032 | 2012-10-08 |  | 8 | 2243017 |  | 23-10-2012 | 17-01-2013 | 26-07-2013 Ex-31-12-2013 | 2243016.58 | 2218671 | 100% |  | M/S Rupa Enterprise | FB Paid
|  | Sub-Total Rampal: | 7 |  |  | 5.54 | 24 | 14164582.8 | 201147 |  |  |  | 14574110.02
1 | SHRONKHOLA | Rehabilation of Rayenda GC-Banikhali GC; at Ch5705-8490 m; | RAILA/BGT/W21 | 201772003 | 30-01-2012 | 2.285 | - | 4670147 | - | 31-01-2012 | 2012-03-05 | 30-11-2012 | 4436639.65 | 3236050 | 100% |  | M/S Joy Enterprise Basabati, Bagerhat | 2nd
2 |  | Rehabilation of Khontakata up -Baniakhali GC; at Ch 00-2500 m; | RAILA/BGT/W22 | 201773002 | 2012-01-29 | 2.5 | - | 5372734 | - | 31-01-2012 | 15-04-2012 | 24-08-2012 10-07-2014 | 5104097.3 | 1257960 | 100% |  | M/S Akon Traders Sharankhola Bagerhat
|  | Sub-Total Shronkhola: | 2 |  |  | 4.785 | 0 | 10042881 | 0 |  |  |  | 9540736.95
|  | Total : Bagerhat District | 29 |  |  | 63.262 | 44.3 | 123304280.8 | 14217658 |  |  |  | 126684738.28 | 96475917 | 101%
Total Package -32(3 Package cancle)

## Sat
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Satkhira
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SHAYAMNAGAR | Noabenki-Munshiganj-Haarinagar-Vetkhali-Zada hat-Noornagar road; at Ch 1600-8548 m; | Recast RAILA/SRT/W01 | 287862002 | 09/10/2011 R-13-06-2012 | 6.948 |  | 9029571 |  | 2011-10-25 | 2012-03-01 | 13-01-2013 | 8577343 | 8577343 | 100% | 100% | M/S Lalin Traders, Gopalgonj | Final
2 |  | Noabenki-Munshiganj-Haarinagar-Vetkhali-Zada hat-Noornagar road; at Ch 8548-15500 m; C/A-66,76,249.00 | Variation RAILA/SRT/W02 | 287862002 | 09/10/2011 V-09-05-2012 | 6.952 |  | 7027631 |  | 2011-10-25 | 16-01-2012 | 26-01-2013 | 7673519 | 7673513 | 100% | 100% | S.M.Enamul Haque, Katiya, Satkhira | Final
3 |  | Noabenki-Munshiganj-Haarinagar-Vetkhali-Zada hat-Noornagar road; at Ch 18800-19800 m; | RAILA/SRT/W16 | 287862002 | 2014-10-07 | 1 | - | 7108408 | 1099333 | [8 empty] | Postponded by Project Director on dated 15-07-2014 (App-7108408.00 Salv- 1099333.00 Contrac-8207741.00) | 6593471
4 |  | Kalbari hat-Nildumur hat road; at Ch 3200-5880 m; | Recast RAILA/SRT/W03 | 287863001 | 09/10/2011 R-22-04-2012 | 2.48 |  | 6237581 |  | 2011-10-25 | 2012-04-01 | 14-01-2013 | 5308328 | 4975511 | 100% | 100% | Shek Sherajul Haque Labsa, Satkhira | Final | 5882178.59
5 |  | Nokipur-Kashimari-Jhapali road; at Ch 9500-12250 m; | RAILA/SRT/W04 | 287863002 | 2011-09-10 | 2.75 |  | 7599306 |  | 25-10-2011 | 16-01-2012 | 26-01-2013 | 7219341.65 | 2398511 | 45% | 33% | M/S Habib Enterprise, Assasuni,Satkhira | WO Cancelled on 10-04-2014 (App-75,99,307.00 Contrac-72,19,342.00) | 5619905
6 |  | Ramjannagar UP(Manikkhali)-Ramjannagar kheyaghat-Paranpur road; at Ch 1320-3420 m; | Recast RAILA/SRT/W05 | 287863008 | 09-10-2011 R-24-05-2012 | 2.1 |  | 5537676 |  | 2011-10-25 | 16-01-2012 | 26-01-2013 | 3789893 | 3789893 | 100% | 100% | M/S Habib Enterprise, Assasuni,Satkhira | Final | 4092468
7 |  | Ramjannagar UP(Manikkhali)-Ramjannagar kheyaghat-Paranpur road; at Ch 3420-5500 m; | RAILA/SRT/W06 | 287863008 | 2011-09-10 | 2.08 |  | 5494946 |  | 2011-10-25 | 15-01-2012 | 25-01-2013 | 3788471 | 3788471 | 100% | 100% | Md. Abdul Hakim, Kaligong,Satkhira | Final | 8207741
8 |  | Iswaripur UP-Gumantali-Jabakhali hat road; at Ch 4230-7900m; | RAILA/SRT/W07 | 287863006 | 2011-09-10 | 3.67 |  | 3201589 |  | 2011-10-25 | 2012-04-01 | 14-01-2013 | 3041509 | 3041509 | 100% | 100% | M/S Gama Construction, Itgacha,Satkhira | Final | 8042768
9 |  | Rehabilation of Kalbari hat-Nil Dumur hat road at Ch. 0.00-3200m | RAILA/SRT/W18 | 287863001 | 2014-02-02 | 3.2 |  | 6861017 |  | 14-05-2014 | 17-07-2014 | 15-02-2015 | 6560735.97 |  | 0% |  | Md. Abdul Hakim, Kaligong,Satkhira |  | 38438531.59
10 |  | Rehab. Of Kashimari U/P-Hamid house road at Ch. 0.00-1000m | RAILA/SRT/W19 | 287864002 | 30-01-2014 | 1 | - | 5337717 | 282188 | [8 empty] | Postponded by Project Director on dated 21-07-2014 (App-5337717.00 Salv-282188.00 ) | 86350694.56
11 |  | Rehabilation of Bohera bazar R&H Ellerchar Shasadanga, Shamnagar via Bandoho GC road at Ch. 5704-6704m; | RAILA/SRT/W20 | 287252008 | 24-03-2014 | 1 |  | 5923286.41 |  | 15-04-2014 | 19-06-2014 | 31-12-2014 | 5554392.98 |  | 0% |  | M/S Joint Bricks Traders Itagacha Satkhira
|  | Sub-Total Shyamnagar: | 8 |  |  | 28.43 | 0 | 49313297.41 | 0 |  |  |  | 44294191.95 |  |  | 100%
1 | ASASUNI | Bardal UP-Durgapur UP Via Tetulia Khayghat; at Ch 1910-2850 m; C/A- 38,33,644.00 | Variation RAILA/SRT/W08 | 287043009 | 2011-10-09 | 0.94 | - | 2720314 | 1113330 | 2011-10-25 | 22-01-2012 | 15/09/2013 | 4092468 |  | 30% |  | Kazi Anowarul Enterprise Gigorgacha,Jossore | WO Cancelled on 10-04-2014 (APP-27,20,314.00 Salv- 11,13,330.00 Contract- 40,92,468.00)
2 |  | Bardal UP-Durgapur UP Via Tetulia Khayghat; at Ch 2850-4685 m; C/A- 77,94,899.00 | Variation RAILA/SRT/W09 | 287043009 | 9/10/2011 V-10-05-2012 | 1.835 | 1.25 | 4510295 | 2913437 | 2011-10-25 | 22-01-2012 | 30-06-2013 | 7961216 | 4009335 | 100% | 50% | M /S Ani Enterprise Assasuni, Satkhira. | Final (part)
3 |  | Bardal UP-Durgapur UP Via Tetulia Khayghat; at Ch 4685-6795 m; C/A- 60,32,174.00 | Variation RAILA/SRT/W10 | 287043009 | 9/10/2011 V-10-05-2012 | 1.91 | 1.25 | 5026375 | 718553 | 2011-10-25 | 22-01-2012 | 30-09-2013 | 6578255 | 5705650 | 100% | 100% | M /S Ani Enterprise Assasuni, Satkhira. | Final
4 |  | Kallyanpure northpara-late mozdul haque; at Ch 1580-2100 m; | Recast RAILA/SRT/W11 | 287045015, | 9/10/2011 R-24-12-2012 | 4.51 | 11.25 | 1349668 |  | 30-01-2012 | 2013-03-07 | 31-12-2013 | 11820833 | 8457792 | 90% | 71% | M/S Shahin Enterprise | 3rd R/A
|  | Bardal - Madia - Murarikati road at Ch. 3800-7000m |  | 287044029 |  |  |  | 6802751
|  | Protapnagar - Karmakarpara road at Ch. 0.00-910.00 m |  | 287045007 |  |  |  | 2371244
5 |  | Khazra-Bardal road; at Ch 00-2010 m; | RAILA/SRT/W12 | 287043002 | 2012-11-07 | 2.1 | 1.88 | 8379017 | 1537870 | 2011-10-25 | 2013-06-02 | 16-02-2014 | 10412731.73 | 4162978 | 60% | 40% | Md. Rokunuzzan, Batkhali, Satkhira | 2nd R/A
6 |  | Khazra-Bardal road; at Ch 2010-4250 m; | Recast RAILA/SRT/W13 | 287043002 | 9/10/2011 R-13-03-2013 | 2.24 |  | 4619674 | 2624195 | 2011-10-25 | 22-01-2012 | 2013-01-02 | 8063043 | 4362167 | 100% | 54% | M /S Asha Enterprise Debhata, Satkhira. | Final (part)
7 |  | Khazra-Bardal road; at Ch 4250-6330 m; | Recast RAILA/SRT/W14 | 287043002 | 9/10/2011 R-13-03-2013 | 2.08 |  | 6249793 | 1683422 | 2011-12-14 | 13-02-2012 | 23-02-2013 | 8815525 | 7126368 | 100% | 100% | M/S Sardar Bricks, Kalaroa, Satkhira | Final
8 |  | Khazra-Bardal road; at Ch 6330-8180 m; | Recast RAILA/SRT/W15 | 287043002 | 9/10/2011 R-13-03-2013 | 1.85 | 1.25 | 7343406 | 219642 | 2011-12-14 | 27-02-2012 | 2013-08-03 | 8007150 | 6716122 | 100% | 84% | Janata Papers Traders, Satkhira | Final (part)
9 |  | Rehabilation of Khazra-Bardal GC road at Ch. 2215-2577m; | RAILA/SRT/W17 | 287043002 | 27-01-2013 | 0.362 |  | 1637077 | 0 | 2013-06-02 | 2013-07-04 | 17-04-2014 | 1714838.19 | 1714837 | 100% | 100% | Md. Fazlur Rahman, Debhata, Satkhira | Final (part)
|  | Sub-Total Asasuni: | 8 |  |  | 16.887 | 16.88 | 48289300 | 9697119 |  |  |  | 63373591.92 |  |  | 100%
|  | Total : Satkhira District | 16 |  |  | 45.317 | 16.88 | 97602597.41 | 9697119 |  |  |  | 107667783.87 | 76500000 | 89.06% | 100%
Total Package -20(4Package cancle)
Note on E7: Jami:

## Barisal
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Barisal
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Taltoli-Lamchari Road; at Ch 2000-3000 m; | RAILA/BSL/W01 | 506514139 | 2011-12-09 | 1 | - | 1790516 |  | 24-10-2011 | 23-01-2012 | 13-05-2012 | 1700915.26 | 1700915 | 100% | 100% | Md. Lokman Hossen | FBP
2 |  | Rehab. Of Sarchi bot tola Jollat molla Khayeghat road at Ch. 0.00-450m | RAILA/BSL/W28 | 506515139 | 2014-01-04 | 0.45 | - | 2525374 |  | 22/05/14 | 21/07/14 | 27-01-2015 | 2841160.02 |  | 0% | 0% | M/S Auditi Enterprise
|  | Sub-Total Sadar: | 2 |  |  | 1.45 | 0 | 4315890 |  |  |  |  | 4542075.28
1 | AGAILJHARA | 4.30X4.30m RCC Box/Culvart in Kalurpar Dusumi road; at Ch 1000 m; | RAILA/BSL/W02 | 506023003 | 2011-12-09 | - | 4.3 | 1784144 |  | 2012-08-01 | 16-02-2012 | 2012-09-06 | 1784144 | 1753753 | 100% | 100% | M/S S S Engineering | FBP
2 |  | 4.30X4.30m RCC Box/Culvart in DSB Hat Road to Misripara Hat Road, at Ch 3385 m; | RAILA/BSL/W03 | 506023012 | 2011-12-09 | - | 4.3 | 1784144 |  | 2012-08-01 | 16-02-2012 | 2012-09-06 | 1784144 | 1765492 | 90% | 90% | M/S Shafiq Enterprise
|  | Sub-Total Agailjhara: | 2 |  |  | 0 | 8.6 | 3568288 | 0 |  |  |  | 3568288
1 | BABUGONJ | HBB road from Rahamatpur-Darogar Hat via ATI; at Ch 1000-4900 m & 2300 m; & Ch. 2300m 20..x2.00 o1nos & Ch 3250m , 4215m 1.00x1.00-2nos RCC box culvert; | Variation RAILA/BSL/W19 | 506034055 | 21-12-2011 | 3.9 | - | 9287499 | 1677372 | 2012-08-01 | 16-02-2012 | 09-07-2012 Ex-31-12-2013 30-06-2014 | 12075400.67 | 5750000 | 75% | 47% | M/S Nupur Enterprise | 200 m box cuting complete
2 |  | Culvert on Rampatti GPS - Rampatty Dhali Bari; | RAILA/BSL/W04 | 506035048 | 2011-12-09 | - | 4.3 | 1491211 | 202965 | 2012-08-01 | 16-02-2012 | 2012-09-06 | 1694176 | 1490017 | 100% | 88% | M/s Khan Traders | Final
|  | Sub-Total Babugonj: | 2 |  |  | 3.9 | 4.3 | 10778710 | 1880337 |  |  |  | 13769576.67
1 | BAKERGONJ | Laxmipasha Bazar (Golder Bari RHD) to Nutan Hat; at Ch 3410 m; | RAILA/BSL/W20 | 506073005 | 21-12-2011 |  | 12 | 3593425 |  | 2012-08-01 | 16-02-2012 | 09-06-2012 Ex-31-12-2013 | 3593425 | 1724140 | 65% | 48% | M/S S.R. Construction | Base casting completed work stop
2 |  | Bakergonj HQ-Neamati Hat GCCR (From RHD Bargana -Batagi); at Ch 15825 m; | RAILA/BSL/W05 | 506072001 | 2011-09-12 | - | 1.3 | 272431 | [7 empty] | WO Cancle App-2,72,431.00
3 |  | Bakergonj to Gobindopurhat. (From RHD, Bakergonj) Via Rabipur, Shialguni, kakorda; at Ch 0 - 20660 m; | RAILA/BSL/W06 | 506072002 | 2011-09-12 | 3.34 | - | 1609171 | [7 empty] | WO Cancle App-16,09,171.00
4 |  | Rehab. Of Bolia Bazar to house of Chandu Master via house of Engineer Mehedi hasan Effective length=632m | RAILA/BSL/W29 | 506074273 | 2014-01-04 | 0.632 |  | 2961480 |  | 22-05-2014 | 21-07-2014 | 27-01-2015 | 3331672.29 |  | 0% | 0% | M/S Auditi Enterprise
|  | Sub-Total Bakergonj: | 2 |  |  | 0.632 | 12 | 6554905 | 0 |  |  |  | 6925097.29
1 | BANARIPARA | Mirer hat GC-Banaripara HQ via Chakher,Bakpur & Uttarpar Bazar; at Ch 6800m- 4x4 m; | Recast RAILA/BSL/W07 | 506102002 | 2011-12-09 | - | 4 | 1806173 | - | 24-10-2011 | 23-01-2012 | 31-03-2013 | 1842460 | 1842453 | 100% | 100% | M/S H.S Engineers | FBP
2 |  | Rehab. Of Haque Shaheber hat - Laskorpur Road at Ch. 2850-3200m | RAILA/BSL/W27 | 506103005 | 24-01-2013 | 0.35 |  | 1165718 | 38761 | 2013-10-02 | 2013-08-04 | 2013-05-08 | 1144255.05 | 1101539 | 100% | 100% | Md. Jahangir Hossain Talukder | FBP
|  | Sub-Total Banaripara: | 2 |  |  | 0.35 | 4 | 2971891 | 38761 |  |  |  | 2986715.05
1 | Gouronodi | Construction of 20.00m long RCC Girder Bridge mear the Ahammed Kathi Mosque under Khanjapur UP-Nuton Bazar via Ahmed kathi at Ch. 2000m; | Variation RAILA/BSL/W26 | 506323030 | 31-12-2012 V-08-09-2014 | - | 20 | 9225725.54 |  | 2013-03-11 | 2014-08-01 | 2014-05-06 | 9910776 | 4500000 | 70% | 51%
|  | Sub-Total Gouronodi: | 1 |  |  | 0 | 20 | 9225725.54 | 0 | 2013-03-11 |  |  | 9910776 |  | 0.7 | 51% | 0
1 | HIZLA | Memania UP office-Tulatala Launch Ghat Via Char Durgapur Launch Ghat. , at ch 3000-3250 m; | RAILA/BSL/W08 | 506363002 | 2011-12-09 | 0.25 | - | 686108 |  | 24-10-2011 | 23-01-2012 | 13-05-2012 | 651777.5 | 651777 | 100% | 100% | M/S Habib Enterprise | FBP
2 |  | Iron Bridge on Taker Bazar-Kaisma. replace by RCC Bridge at ch 1000 m; | RAILA/BSL/W23 | 506363007 | 21-12-2011 | - | 12.5 | 2735833 | - | 2012-08-01 | 16-02-2012 | 2012-09-06 | 2735833 | 2024970 | 98% | 74% | M/S Lima Enterprise | 1st R/A
3 |  | Construction of 12.50m RCC Bridge on Hizla Horinathpur road-Kalikapur GPS road at ch 1000 m | RAILA/BSL/W22 | 506364012 | 21-12-2011 | - | 12.5 | 2735833 | - | 2012-08-01 | 16-02-2012 | 09-06-2012 Ex-30-06-2013 31-12-2013 | 2599041.35 | 1800000 | 100% | 60% | M/S Tapader Construction | Final(Part)
4 |  | Hizla Teker Bazar-Bawshia Launch Ghat. , at ch 1000-1200 m | RAILA/BSL/W09 | 506362010 | 2011-12-09 | 0.2 | - | 548886 |  | 24-10-2011 | 23-01-2012 | 13-05-2012 | 521437 | 521437 | 100% | 100% | M/S Habib Enterprise | FBP
|  | Sub-Total Hizla: | 4 |  |  | 0.45 | 25 | 6706660 | 0 |  |  |  | 6508088.85
1 | MEHENDIGONJ | Paschim Kautia Abashon connecting road; at Ch 00-2500 m; | RAILA/BSL/W10 | 506625181 | 2011-12-09 | 0.45 |  | 697519 | 215607 | 24-10-2011 | 23-01-2012 | 2012-09-03 | 867435.42 | 634617 | 100% | 100% | M/S Hasan Construction | FBP
2 |  | Ghoraghat Abashon connecting road; at Ch 90-990 m; | RAILA/BSL/W11 | 506625045 | 2011-12-09 | 0.9 |  | 1180146 | 911071 | 24-10-2011 | 23-01-2012 | 13-06-2012 | 1986553.5 | 1029518 | 100% | 100% | M/S Tonima Enterprise | FBP
3 |  | Char Mohisha Cyclone Shelter to Char Dia Abashon Project; at Ch 00-2500 m; | RAILA/BSL/W12 | 506625335 | 2011-12-09 | 0.45 |  | 332237 | 335505 | 24-10-2011 | 23-01-2012 | 13-06-2012 | 667422.67 | 331917 | 100% | 100% | Md. Farid Uddin | FBP
4 |  | Ulania to Lalmiar hat road, at Ch 900-1400 m | RAILA/BSL/W13 | 506624010 | 2011-12-09 | 0.5 |  | 1108441 |  | 24-10-2011 | 23-01-2012 | 13-05-2012 Ex-30-06-2013 | 1108147 | 944757 | 100% | 100% | Md. Farid Uddin | FBP
5 |  | Sinnerchar Abashon connecting Road-1, at Ch 00-2500 m; | RAILA/BSL/W14 | 506625195 | 2011-09-12 | 2.5 | - | 6674856 | 2569795 | 2011-10-24 | 23-01-2012 | 13-05-2012 | 9244143.75 |  | 0% |  | M/S Sumi Enterprise | WO Cancle (App-66,74,856.00 Salv-25,69,795.00 Contract-92,44,143.00)
6 |  | Culvert on Bnagla Bazar - Nutan Khasherhat via Lata UP (Gubtoli Bazar) Hurarhat box culvert on 1vent-3.0mx3.0m at Ch. 3440m. | RAILA/BSL/W15 | 506623002 | 2011-12-09 |  | 3 | 1243287 |  | 24-10-2011 | 23-01-2012 | 13-05-2012 | 1181077.71 | 1160035 | 100% | 100% | M/S H S Enterprise | FBP
7 |  | Construction of 1-ventx3.0mx3.0m RCC Box Culvert on Char Shafali to Bholanath road; | RAILA/BSL/W21 | 500625194 | 21-12-2011 |  | 3 | 1079000 |  | 2012-08-01 | 16-02-2012 | 2012-09-06 | 1099000 | 1089504 | 100% | 100% | M/S Hasan Construction | FBP
|  | Sub-Total Mehendigonj: | 6 |  |  | 2.3 | 6 | 5640630 | 1462183 |  |  |  | 6909636.3
1 | MULADI | Iron bridge in front of Saheber Char GPS at Nazirpur; | RAILA/BSL/W24 |  | 2011-12-21 | - | 12 | 2297783 |  | 2012-08-01 | 16-02-2012 | 09-06-2012 Ex-28-02-2013 | 2182924.25 | 2150483 | 100% | 100% | Md. Zakir Hossain Mia | FBP
|  | Sub-Total Muladi: | 1 |  |  | 0 | 12 | 2297783 | 0 |  |  |  | 2182924.25
1 | UZIRPUR | Guthia UP-Ideal College-Ponchogram Bazar Road; at Ch 2000-4000 m; | RAILA/BSL/W16 | 506943006 | 2011-12-09 | 2 | - | 7058741 | 2352613 | 2012-08-01 | 16/2/2011 | 2012-09-07 | 9387825.62 | 6825457 | 100% | 100% | M/S Nahid Enterprise | FBP
2 |  | Daserhat -Saner Hat Road, at Ch 1810 m box culvert on 3vent-4.0mx4.0m | Variation RAILA/BSL/W17 | 506944061 | 2011-12-09 | - | 12 | 2029592 | - | 24-10-2011 | 23-01-2012 | 13-05-2012 | 2159572.89 | 800000 | 100% | 37% | M/S Mitro & Co. | Final (Part)
3 |  | Otra Poshu Hospital-Otra Bazar Road; at Ch 1250 m box culvert on 3vent-4.0mx4.0m; | RAILA/BSL/W18 | 506945016 | 2011-12-09 | - | 12 | 2029592 | - | 24-10-2011 | 23-01-2012 | 13-05-2012 Ex-30-06-2013 30-11-2013 | 1928100.54 | 1115955 | 100% | 60% | M/S Lucky Traders | Final (Part)
4 |  | Chowdhurir Hat - Hastishunda via Daberkul Road, at Ch 0.00-7600.00 m; | RAILA/BSL/W25 | 506943004 | 2012-02-02 | 7.6 | - | 5764168 | 382502 | 22-02-2012 | 30-04-2012 | 21-08-2012 Ex-30-07-2013 30-12-2014 | 6146670 | 3129264 | 75% |  | M/s Mitra & Co.
|  | Sub-Total Uzirpur: | 4 |  |  | 9.6 | 24 | 16882093 | 2735115 |  |  |  | 19622169.05
|  | Total : Barisal District | 26 |  |  | 18.682 | 115.9 | 68942575.54 | 6116396 | 2013-03-11 | 0 | 0 | 76925346.74 | 45838000 | 90.12%
Total Package -29(3 Package cancle)
Formulas:
Tender Invitation date (IFT) = SUM([Tender Invitation date (IFT), row above])
Tender Invitation date (IFT) = SUM([Tender Invitation date (IFT), row above]+K43+K41+K33+K26+K23+K18+K15+K12+K28)

## Barguna
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Barguna
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Barguna Fuljhuri Kakchira Road; at Ch 1205-3750 m ; | RAILA/BGN/W01 | 504282003 | 2011-09-07 | 2.54 |  | 1823037 |  | 2011-12-09 | 2011-01-12 | 26-02-2012 | 1731885.15 | 1730673 | 100% | 100% | ‡gmvm© Lvb †UªWvm© | Final bill paid
2 |  | Construction of 1vent-2.50mx2.50m RCC box culvart at Ch 1130.0 m on Barguna Fuljhuri Kakchira Road; ID No: 504282003 | RAILA/BGN/W11 | 504282003 | 2011-12-04 |  | 2.5 | 1001349 | - |  | 17-04-2012 | 30-08-2012 | 951281 |  | 0% |  | M/S Daimond Builders | Cancelled due to land problem App-10,01,349.00 Contract-9,51,281.00
3 |  | Rehab. & maint. Of Barguna-Bashbunia-Chalitatali Road; at Ch 6311-8804 m; | Recast RAILA/BGN/W12 | 504282005 | 2011-12-14 | 2.493 |  | 3475896 | 223507 | 2012-01-03 | 2012-01-05 | 30-10-2012 | 3514113 | 3511931 | 100% | 100% | M/S Sigir Traders | Final bill paid
4 |  | Kumrakhali Abdul Haque ABASHAN -Fuljhuri Bazar Road; at Ch 00-1210 m; | Recast RAILA/BGN/W02 | 504284046 | 2011-09-07 | 1.21 |  | 1118057 |  | 2011-12-09 | 2011-01-12 | 30-04-2012 | 1062154.15 | 1060946 | 100% | 100% | ‡gv: †Mvjvg wKewiqv | Final bill paid
5 |  | Bashebunia Upazila Road-Kalirtak Sluice Rayertabak High School Road; at Ch 710-1384 m; | RAILA/BGN/W03 | 504284054 | 2011-09-07 | 0.67 |  | 623411 |  | 2011-12-09 | 2011-01-12 | 2012-09-02 | 592240.45 | 591894 | 100% | 100% | ‡gmvm© i“`ª G›UvicÖvBR | Final bill paid
|  | Sub-Total Sadar: | 4 |  |  | 6.913 | 0 | 7040401 | 223507 |  |  |  | 6900392.75
1 | AMTOLI | Patuakhali Amtali RHD (Khakuani High School)-GhulishaKhali UP Office Road; at Ch 2930-5220 m; | Recast RAILA/BGN/W14 | 504093018 | 2011-12-14 | 2.99 |  | 8347529 | 172355 | 2012-02-01 | 20-05-2012 | 30-03-2014 | 8554752.63 | 1874436 | 70% | 22% | M/S Atom Enterprise
2 |  | Ghulishakhali UP-Kukua UP via Hazartakaer Bandth Road; at Ch 1400-4300 m; | RAILA/BGN/W04 | 504093006 | 2011-09-07 | 1.1 |  | 889480 | - | 2011-09-12 | 2012-02-01 | 30-05-2013 | 845006 |  | 0% |  | ‡gmvm© wn‡gj †UªWvm© | WO cancel App-8,89,480.00 contract-8,45,006.00
3 |  | Repair of Amtali-Sunarchar (Parjatan Kanrra) via Taltali, Fakirhat, Laupara Bazar Road ch 00-200m and maintanence of existing & Const of new 3.5x3.5m Box Culvert at , at Ch 5750 m | RAILA/BGN/W13 | 504092003 | 14-12-2011 | 0.2 | 3.5 | 2001417 | [7 empty] | Suspended due to Duplication Cancel App-20,01,417.00
|  | Sub-Total Amtoli: | 1 |  |  | 2.99 | 0 | 8347529 | 172355 |  |  |  | 8554752.63
1 | BAMNA | Rehab. of road from Bamna UP office-Sonakhali Bazar by carpeting, at Ch 7000-8640 m; | RAILA/BGN/W05 | 504193010 | 2011-09-07 | 1.64 |  | 2496133 | - | 2011-12-09 | 2011-01-12 | 2012-12-12 | 2371326.35 | 2364259 | 100% | 100% | ‡gmvm© AvwL KbóªvKkb | Final bill paid
2 |  | Rehab. of road from Bamna UP-Bamna Upazila H/Q via Shasipur Bazar by carpeting, at Ch 510-976 m; | RAILA/BGN/W06 | 504193003 | 2011-09-07 | 0.466 |  | 1065599 | - | 2011-12-09 | 2011-01-12 | 2012-11-04 | 1012319.05 | 881781 | 100% | 100% | ‡gmvm© Avdmvi GÛ †Kvs | Final bill paid
3 |  | Rehab. of Bamna-Kholpatua GC road bridge approach, at Ch 4000-7000 m; | RAILA/BGN/W07 | 504192001 | 2011-09-07 | 2.9 |  | 2326679 | - | 2011-12-09 | 2011-01-12 | 25-05-2012 | 2210345.05 | 2202985 | 100% | 100% | †gmvm© nvIjv`vi G›UvcÖvBR | Final bill paid
4 |  | Rehab. of road from Bukabunia UP-Kholpatua GC by carpeting, at Ch 3100-7800 m; | RAILA/BGN/W08 | 504193002 | 2011-09-07 | 4.7 |  | 2897837 | - | 2011-12-09 | 2011-01-12 | 25-05-2012 | 2752945.15 | 2752654 | 100% | 100% | †gmvm© wjqb KbóvKkb | Final bill paid
5 |  | Rehab. of road from H/O Aboni Mistry to Bamna- Kholpatua GC by carpeting, at Ch 3240-4240 m; | RAILA/BGN/W09 | 504195018 | 2011-09-07 | 1 |  | 3178579 | 916339 | 2011-12-09 | 2011-01-12 | 30-06-2012 Ex-28-02-2014 | 3890172.1 | 3889923 | 100% | 100% | †gvt †Mvjvg m‡ivqvi | Final bill paid
6 |  | Rehab. of road from Bamna UP-Bamna Upazila H/Q via Shasipur Bazar by carpeting, at Ch 00-510 m; | Recast RAILA/BGN/W15 | 504193003 | 2012-01-02 | 0.51 |  | 1451407 | - | 19-02-2012 | 2012-10-05 | 2013-10-01 | 1059427.94 | 1059398 | 100% | 100% | M/S Samir & Brothers | Final bill paid
7 |  | Rehab. of 3 nos bridge approach road length=320m on Amua-Pipulia; ; | Recast RAILA/BGN/W16 | 504192003 | 31-01-2012 | 0.32 |  | 2001700 | 407499 | 19-02-2012 | 2012-10-05 | 30-01-2013 | 2032154.76 | 2032154 | 100% | 100% | M/S Shithil Enterprise | Final bill paid
|  | Sub-Total Bamna: | 7 |  |  | 11.536 | 0 | 15417934 | 1323838 |  |  |  | 15328690.4
1 | PATHORGHATA | Rehab. of road from Maserkhal-Khalifar Hat-Charduani GC by BC , at Ch 00-10950 m; | RAILA/BGN/W10 | 504852006 | 2011-07-09 | 10.45 |  | 7263546 | 106803 | 2011-12-09 | 26-12-2011 | 30-05-2013 | 7001831.55 | 6895009 | 100% | 100% | †gmvm© gywbqv G›UvicÖvBR | Final Bill paid
1 |  | Sub-Total Pathorghata: | 1 |  |  | 10.45 | 0 | 7263546 | 106803 |  |  |  | 7001831.55
|  | Total : Barguna District | 13 |  |  | 31.889 | 0 | 38069410 | 1826503 |  |  |  | 37785667.33 | 30848043 | 97.69%
Total Package -16 (3 Package cancle)

## Bhola
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Bhola
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date (H/Q) | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Bhola by pass - Santir hat - Veluma UP Road, at Ch 1000-3080 m; | RAILA/BHL/W01 | 509183006 | 21/8/2011 | 1.88 | - | 5584080 | 167731 | 2012-07-12 | 27-03-2012 | 25-05-2013 | 5584080 | 5551684 | 100% | 100% | Md. Nazimuddin | F.B.P
2 |  | Bhola by pass - Santir hat - Veluma UP Road, at Ch 3080-3280 and 5180-8680m & 2x1.6x1.6m Box/culvart | RAILA/BHL/W02 | 509183006 | 21/08/2011 | 4 | - | 4926343 | - | 2011-07-12 | 27-03-2012 | 18-11-2012 | 4926343 | 4886343 | 100% | 100% | Md. Nazimuddin | F.B.P
3 |  | Rehabilation of Gazaria GC - Naziur Rahman bari -Vharryerhat Road, at Ch. 0.00-6680m; | RAILA/BHL/W29 | 509182006 | 21/08/2011 | 3.7 | 3.2 | 4214312 | - | 29/12/2011 | 18-03-2012 | 2013-06-01 | 4214288 | 3730500 | 100% | 88% | Md. Akter Hossain
4 |  | Rehabilation of Parangonj RHD bazar - Kachia UP via khorki road, at Ch 0.00 - 2500 m; | RAILA/BHL/W30 | 509183004 | 2012-12-02 | 2.5 | - | 3298682 | - | 21/03/2012 | 19-06-2012 | 15-10-2012 | 3298682 | 3298681 | 100% | 100% | Md. Hourn-or-rashed | F.B.P
5 |  | a) Estimate for (Re-seal) Rashid khan shop-WDB Embk. Road, at Ch 00-550m; b) Rehabilation of Rashid khan shop-WDB Embk. Road, at Ch 550.00-1400m; c) Estimate for const. of 1.60mx1.60m box culvert on Rashid khan shop-WDB Embk. Road at Ch. 815.00m and d) Estimate for const. of 2nos cross drain of (0.750mx0.750m) on Rashid khan shop-WDB Embk. Road at Ch. 1815m & 1390 m; | RAILA/BHL/W34 | 509184013 | 2012-08-04 | 1.4 | 3.1 | 4013369 | 9408 | 27-6-12 | 21-10-12 | 15-05-2013 | 4020765 | 2647085 | 100% | 66% | M/S Samota Enterprise | F.B.P
6 |  | a) Improvement of Bhola by pass-Santirhat-Velumia up Bhola by pass-Santirhat-Velumia up road at Ch. 0.00-1200.00m (Part-A); b) Construction of 0.75mx0.75m cross drain on Bhola by pass-santirhat-velumia up road at Ch. 680m, 820m(Part-B) | RAILA/BHL/W38 | 509183006 | 18/06/2013 | 1.2 | 0.75 | 4166902 | - | 2013-09-04 | 2013-11-09 | 2014-10-03 | 3958650 | 3953758 | 100% | 100% | Md. Shahidulla | F.B.P
7 |  | Pachim Ilisha UP - Malerhat - Santirhat Road, at Ch 750-1000 m; including 1x1.5mx1.5m box/culvart | RAILA/BHL/W03 | 509183012 | 21/8/2011 | 0.25 | 1.5 | 855755 | [7 empty] | This road is taken from IRIDP recommend for Cancle App-8,55,755.00
|  | Sub-Total Sadar: | 6 |  |  | 14.68 | 7.05 | 26203688 | 177139 |  |  |  | 26002808
1 | BORHANUDDIN | Khaerhat- Joyerhat- Borhanuddin- Bangla Bazer road , at Ch 5550-7200m; | Recast RAILA/BHL/W04 | 509212002 | 21/8/2011 | 2.6 | 4.25 | 7682127 | 298368 | 2011-07-12 | 2013-05-06 | 2013-10-10 | 7348429 | 7340429 | 100% | 100% | Md. Rafiqul Islam
2 |  | Khaerhat- Joyerhat- Borhanuddin- Bangla Bazer road , at Ch 7200-8500m | Recast RAILA/BHL/W05 | 509212002 | 22/08/2011 | 3.75 | 4.25 | 5792930 | 200579 | 2011-07-12 | 2013-05-06 | 28-06-2013 | 5759501 | 5558922 | 100% | 93% | Md. Rafiqul Islam
3 |  | Khaerhat- Joyerhat- Borhanuddin- Bangla Bazer road , at Ch 8500-9572m and 10410-10910m | Recast RAILA/BHL/W06 | 509212002 | 21/8/2011 | 2.5 | - | 5649025 | 201062 | 2011-07-02 | 2013-11-06 | 15-01-2014 | 5554952 | 2585689 | 100% | 100% | Md. Rafiqul Islam
4 |  | Khaerhat- Joyerhat- Borhanuddin- Bangla Bazer road , at Ch 10910-11510m | Recast RAILA/BHL/W07 | 509212002 | 22/8/2011 | 1 | - | 2504345 | 85586 | 2011-07-02 | 2013-10-06 | 28-01-2014 | 2461249 | 1128000 | 100% | 46% | Md. Rafiqul Islam
5 |  | Rehab. Of Khaerhat-Joyerhat-Borhanuddin-Bangla Bazar road, at Ch. 11510-14010m, | Recast RAILA/BHL/W39 | 509212007 | 7/11/2013 Rec-23-04-2014 | 2.5 | - | 7982750 | - | 19-11-2013 | 20-05-2014 | 15-07-2014 | 10896216 | 1600000 | 100% | 15% | Md. Rafiqul Islam
6 |  | Rehab. Of Khaerhat-Joyerhat-Borhanuddin-Bangla Bazar road, at Ch. 14010m-16010m, | Recast RAILA/BHL/W40 | 509212007 | 7/11/2013 Rec-23-04-2014 | 2 | - | 7696349 | - | 21-05-2014 | 19-07-2014 | 19-07-2014 | 10518567.58 | 5000000 | 100% | 48% | Md. Rafiqul Islam
|  | Sub-Total Borhanuddin: | 6 |  |  | 14.35 | 8.5 | 37307526 | 785595 |  |  |  | 42538914.58
1 | CHARFASHION | Shashibusion GC - AnjurhatGC, at Ch 00-2800 m; | RAILA/BHL/W09 | 509252002 | 22/8/2011 | 2.8 | - | 8837180 | 657992 | 2011-07-12 | 23-02-2012 | 2013-11-04 | 9494100 | 8832448 | 100% | 100% | M/S Babul Traders, Charfession | FBP
2 |  | 18m Wooden bridge replace by RCC foot bridge ( 3 x4.5m x 5.00m RCC Box Culvert) over shamraj khal in front of Gafurpur Govt. Primary School, at Ch 0.03 m; | RAILA/BHL/W10 | 509254021 | 21/8/2011 |  | 13.5 | 2172687 | - | 2011-07-12 | 23-02-2012 | 2013-01-04 | 2173000 | 2161874 | 100% | 100% | M/S Babul Traders, Charfession | FBP
3 |  | Kashemgonj Bazar-Jahanpur U HQ. WDB embankment, at Ch 3900-9100 m; | RAILA/BHL/W11 | 509253003 | 22/8/2011 | 5.2 |  | 8469997 | 670232 | 2011-07-12 | 23-02-2012 | 22-02-2013 | 9139172 | 8466940 | 100% | 100% | M/s Jashim Construction, Cherfassion | FBP
4 |  | 15m iron bridge replace by RCC foot bridge ( 3 x4.5m x 5.00m RCC Box Culvert) on kukri mukri bazar to Aminpur bazar, at Ch 0.950 m; | RAILA/BHL/W14 | 509254042 | 21/8/2011 |  | 13.5 | 2039669 | 78948 | 2011-07-12 | 26-02-2012 | 2013-04-06 | 2118617 | 1819915 | 100% | 100% | M/S Babul Traders | FBP
5 |  | Nurabad UP - Chowkiderhat via Hajirhat, Chowmohoni hat, at Ch 500-4060 m | RAILA/BHL/W12 | 509253002 | 22/8/2011 | 3.56 | - | 4808352 | 493311 | 2011-07-12 | 23-02-2012 | 22-02-2013 | 5301205 | 4806170 | 100% | 100% | M/s Jashim Construction, Cherfassion
6 |  | Charfession (Kutubgonj)-Char Madraz UP, at Ch 00-2450 m; | RAILA/BHL/W13 | 509253008 | 21/8/2011 | 2.45 | - | 5493369 | 136712 | 2011-07-12 | 23-02-2012 | 22-02-2013 | 5629873 | 5488503 | 100% | 100% | M/S Babul Traders, Charfession
7 |  | 18m iron bridge replace by RCC foot (4 x4.5m x 5.00m RCC Box Culvert) bridge on Charfession R&H road(kutubgonj)-Dularhat-Hazirhat road, at Ch 8.5 m; | RAILA/BHL/W15 | 509254015 | 22/8/2011 |  | 18 | 2420039 | 249062 | 2011-07-12 | 18-03-2012 | 17-07-2013 | 2420039 | 2416683 | 100% | 100% | Md. Morshed | F.B.P
8 |  | 15m long iron bridge replace by RCC foot bridge ( 3 x4.5m x 4.50m RCC Box Culvert) on Kukrimukri Launchghat Asrayan road, at Ch 1.05 m; | RAILA/BHL/W16 | 509253007 | 21/8/2011 |  | 13.5 | 2949638 | 143053 | 2011-07-12 | 25-04-2012 | 24-04-2013 | 2122000 | 1963149 | 100% | 100% | M/s Khan Enterprise | F.B.P
9 |  | 24m long iron bridge replace by RCC foot bridge ( 4 x4.5m x 5.00m RCC Box Culvert) on Charfession GC(BRDB)-Majirhat road, at Ch 5 m; | RAILA/BHL/W17 | 509253017 | 22/8/2011 |  | 18 | 2577422 | 133887 | 2011-07-12 | 18-03-2012 | 17-02-2013 | 2710644 | 2576007 | 100% | 100% | Md. Morshed | F.B.P
10 |  | Rehabilation of R & H Road (H/Q Salam Chairman) To Boatir khal Road, at Ch. 00-1763.00m | RAILA/BHL/W37 | 509254019 | 28-02-2013 | 1.763 |  | 4082431 | 56270 | 2013-08-05 | 19/09/2013 | 18-03-2014 | 4131094 | 4130389 | 100% | 100% | M/S Jashim Construction
11 | CHARFASHION | UZ HQ - Abu bakarpur Chawmohonirhat via Aminabad UP office road., at Ch 3800-5150 m; | RAILA/BHL/W08 | 509253013 | 21/8/2011 | 1.3 | - | 2391630 | 696849 | 2011-12-07 | 23-02-2012 | 22-02-2013 | 3088382 |  |  |  | M/s Jashim Construction, Cherfassion | Maintennace programm Cancle App-23,91,630.00 Salv-6,96,849.00 Contract-30,88,382.00
|  | Sub-Total Charfashion: | 10 |  |  | 15.773 | 76.5 | 43850784 | 2619467 |  |  |  | 45239744 |  |  | 100%
1 | DAULATKHAN | Noor miar hat to Chailtatali hat UZR, at Ch 00-1000 m; | RAILA/BHL/W18 | 509294006 | 2011-09-06 | 1 | - | 2319866 | - | 2011-07-12 | 27-03-2012 | 26-03-2013 | 2319855 | 2319706 | 100% | 100% | M/S Monir Traders
2 |  | Noor miar hat to Chailtatali hat UZR, at Ch 1000-2000 m; | RAILA/BHL/W19 | 509294006 | 2011-09-06 | 1 | - | 2311177 | - | 2011-07-12 | 27-03-2012 | 26-03-2013 | 2311177 | 2311177 | 100% | 100% | M/S Monir Traders
3 |  | Noor miar hat to Chailtatali hat UZR, at Ch 2000-4000 m; | RAILA/BHL/W20 | 509294006 | 2011-09-06 | 1 | - | 2286833 | - | 2011-07-12 | 27-03-2012 | 26-03-2013 | 2286833 | 2286833 | 100% | 100% | M/S Monir Traders
Sub-Total Daulatkhan: |  |  | 3 |  |  | 3 | 0 | 6917876 | 0 |  |  |  | 6917865 |  |  | 100%
1 | LALMOHAN | Karter hat -Raychand road , at Ch 00-2000 m; | RAILA/BHL/W21 | 509542001 | 2011-09-06 | 2 | - | 4160389 | 90317 | 21/03/2012 | 2012-07-05 | 2013-07-04 | 4250706 | 4157660 | 100% | 100% | Md. Nazrul Islam Chonnu
2 |  | Karter hat -Raychand road , at Ch 2000-5100 m; | RAILA/BHL/W22 | 509542001 | 2011-09-06 | 3.1 | - | 9929314 | 62820 | 21/03/2012 | 2012-07-12 | 2013-07-11 | 9992134 | 3885474 | 100% | 39% | Md. Akter Hossain
3 |  | Lalmohan chowmohani-Bahurchar bazar, at Ch 00-2100 m; | RAILA/BHL/W23 | 509543004 | 2011-09-06 | 2.1 | - | 5307715 | 74712 | 21/03/2012 | 20-06-2012 | 25-05-2013 | 5382427 | 1800300 | 100% | 33% | M/S Jahanara Const.
4 |  | Mongal sikder bazar- Fatamad BC, at Ch 00-2500 m; | RAILA/BHL/W24 | 509543007 | 2011-09-06 | 2.5 | - | 4620921 | - | 21/03/2012 | 15-7-2012 | 14-07-2013 | 4620921 | 761000 | 100% | 16% | Md. Akter Hossain
5 |  | (A) Re-construction of Zeepable bridge on Kumarkhali Khal at Farajgong UP; (B) Re-construction of Zeepable bridge near south side of house of Golam Ali Faraji Bari on Peskarhat Khal at Farajgong UP; and | RAILA/BHL/W25 |  | 2011-09-06 | - | 26 | 3141656 | - | 21/03/2012 | 28-06-2012 | 27-06-2013 | 3141655 | 3140359 | 100% | 100% | M/s Rubel Enterprise | F.B.P
6 |  | i) Rehabilation of Abugong bazar -Forajgonj UP UNR road, at Ch 00-1400 m; ID No: 509543005; ii) Rehabilation of Lalmohan HQ (R&H) - Satani Bazar (Mozammel road) union road; at Ch 3104-4250 m; ID No: 509543003; iii) Const. of 01 (one) nos 1.50x1.50m size box culvert at Lalmohan H/Q (R&H) - Satani Bazar (Mozammel road) union road at Ch. 3148m; iv) Const. of 01(One) nos cross drain at Lalmohan H/Q (R&H) - Satani Bazar (Mozammel road) union road at Ch. 3479m. | RAILA/BHL/W35 | 509543005 509543003 | 22-05-2012 | 2.46 | 2.1 | 6671500 | - | 27-06-2012 | 21-10-2012 | 27-07-2013 | 6337925 | 6332258 | 100% | 100% | Md. Rahul Amin | F.B.P
7 |  | Const. of 2x4.50x3.00m RCC Double vent box culvert on Gaimara khal adjacent West Side of Anisol Miar Hat infront H/Q Satok Patoary under Farajgong UP. | RAILA/BHL/W36 |  | 22-05-2012 | - | 9 | 1294353 | - | 27-06-2012 | 2012-09-12 | 29-03-2013 | 1229635 | 1228506 | 100% | 100% | M/S Howlader & Co. Bhola Sadar | F.B.P
|  | Sub-Total Lalmohan : | 7 |  |  | 12.16 | 37.1 | 35125848 | 227849 |  |  |  | 34955403
1 | MONPURA | Hazirhat -Koralia road, at Ch 20050-24950 m; | Recast RAILA/BHL/W26 | 509652001 | 2011-09-06 | 4.5 | - | 4325513 |  | 2011-07-12 | 2012-04-09 | 2013-08-04 | 4316592 | 2843445 | 100% | 66% | M/S Z.H. Enterprise
2 |  | Hazirhat Up-Bhoyerhat via Fakir hat, at Ch 3000-6000 m; | RAILA/BHL/W27 | 509653001 | 2011-09-06 | 3 | - | 3008531 |  | 2011-07-12 | 2012-04-09 | 2013-08-04 | 3007495 | 3090287 | 100% | 100% | M/S Z.H. Enterprise
3 |  | Rehabilatation of FRB – Shakuchia Lunch ghat via Master Hat Road; at Ch.00-1622 m: | RAILA/BHL/W31 | 509654027 | 19/3/2012 | 1.62 | - | 6646074 | - | 29/3/2012 | 13-05-2012 | 2013-05-12 | 6643677 | 6515060 | 100% | 100% | M/S Jashim Construction
4 |  | Rehabilatation of Hazir Hat Up Bhuyer hat Road; at Ch. 1500-3000 m: | RAILA/BHL/W32 | 509653001 | 19/3/2012 | 1.5 | - | 5635164 | - | 29/3/2012 | 13-05-2012 | 2013-05-12 | 5633182 | 5048006 | 100% | 100% | M/S Jashim Construction | F.B.P
5 |  | Rehabilatation of Hazir Hat Up Bhuyer hat Road; at Ch. 6000-8250 m: | RAILA/BHL/W33 | 509653001 | 19/3/2012 | 2.25 | - | 8394237 | - | 29/3/2012 | 13-05-2012 | 2013-05-12 | 8390803 | 8186760 | 100% | 100% | Md. Younus Al-Mamum | F.B.P
|  | Sub-Total Monpura: | 5 |  |  | 12.87 | 0 | 28009519 | 0 |  |  |  | 27991749
1 | TOJUMUDDUN | Muchibari-Mongol sikder via khasherhat GC, at Ch 6000-9673 m; B) Shashigong Bazar Bmbankment at Ch. 0.00-1110m; | Recast RAILA/BHL/W28 | 509912001 509914003 | 2011-03-06 | 3.673 | - | 3949039 |  | 2011-07-12 | 13-03-2012 | 2013-12-09 | 3323474 | 3150000 | 100% | 100% | Md. Iqbal Hossain
|  | Sub-Total Tojumuddin: | 1 |  |  | 3.673 | 0 | 3949039 | 0 |  |  |  | 3323474 |  |  | 100%
|  | Total : Bhola District | 38 |  |  | 76.506 | 129.15 | 181364280 | 3810050 |  |  |  | 186969957.58 | 147000000 | 100% | 95%
Total Package -40 (2 Package cancle)
20667662

## Patua
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Patuakhali
Sl. No. | Upazila | Name of Scheme with Chainage | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Rehab. of road from Patuakhali H/Q-Muradia GC via SreeRampur Bazer (Sadar Part), at Ch 3700-6100 m; | RAILA/PTK/W02 | 578952009 | 29/9/2011 | 2.4 |  | 7546048 | 4002607 | 18-12-2011 | 2012-10-01 | 2013-03-01 | 10686000 |  | 20% |  | M/S Mamun Construction | Contract termination under process (App-75,46,048.00 Salv-40,02,607.00 Contract-1,06,86,000.00)
2 |  | Rehab. Of road from Badarpur UP - Patuakhali H/Q (New market kheya ghat) at Ch. 5570-6000m; | RAILA/PTK/W22 | 578953002 | 20/05/2011 | 0.43 |  | 995210 |  |  | 15/11/2012 | 14/04/2013 | 994000 | 991161 | 100% |  | Md. Jalal Ahmed | FBP
3 |  | Rehab. of road from Patuakhali Khalishakhali Ferryghat Bazer-(Pukurjana bazar)Itbaria UP. , at Ch 00-3000 m; | RAILA/PTK/W01 | 578953011 | 29/9/2011 | 3 |  | 3149488 |  |  | 2012-01-10 | 30-01-2013 | 2788000 |  | 0% |  | M/S. L.S. Traders | Dropped (App-31,49,488.00 Contract-27,88,000.00)
4 |  | Rehabilation of road from Patuakhali H/Q (Shiali Bazar) - Moukaran GC via Lowkathi Bazar; Ch. 3000-4000m; | RAILA/PTK/W21 | 578952003 | 20/05/2011 | 1 |  | 1883862 | 52228 |  | 15/11/2012 | 14/11/2013 | 1695000 |  | 0% |  | M/S Brothers Traders | Dropped (App-18,83,862.00 Salv-52,228.00 Contract-16,95,000.00)
|  | Sub-Total Sadar: | 1 |  |  | 0.43 | 0 | 995210 | 0 |  |  |  | 994000
1 | BAUPHAL | Maintenance of Mominpur GC-Kalisuri GC-Baherchar GC, at ch 00-2500 m; | RAILA/PTK/W03 | 578382005 | 29/9/2011 | 2.5 |  | 4219411 |  | 29-09-2011 | 2012-01-10 | 03/01/2013 Ex-30-06-2013 | 4209000 | 4208353 | 100% |  | M/S Hosen & Brothers | FBP
2 |  | Maintenance of Mominpur GC-Kalisuri GC-Baherchar GC, at ch 2500-4800 m; | RAILA/PTK/W16 | 578382005 | 2012-03-18 | 2.3 |  | 4478855 |  | 29-09-2011 | 26-12-2012 | 25-12-2013 | 4998476.29 | 4995419 | 100% |  | M/S Mahmuda Entertrise | FBP
3 |  | Maintenance of Mominpur GC-Kalisuri GC-Baherchar GC, at ch 7000-14000 m; | RAILA/PTK/W18 | 578382005 | 28/3/2012 | 7 |  | 2193836 |  | 29-09-2011 | 2012-01-10 | 31-01-2013 30-01-2014 | 1844000 | 1680525 | 100% |  | M/S Mahmuda Entertrise | FBP
4 |  | Bauphal UP (Sher-E-Bangla Road)-Naomala BDC Road., at ch 00-4700 m | RAILA/PTK/W04 | 578383021 | 29/9/2011 | 4.7 |  | 5988734 |  | 29-09-2011 | 2012-01-10 | 31-10-2013 | 6593471 |  | 35% |  | M/S Masud & Brothers | Postponded by Project Director on dated 14.08.2014 (App-5988734.00 Contract-6593471.00)
5 |  | a) Rehab. of road from Nazirpur UP- Dhandi GPS -Chandapara Bazer Road., at Ch 1500-1850 m; b) Matborerhat-Kalisuri-Kachipara-Gopalia Bazar (Jamal Munshi Bari) Road; 3x3m RCC box/culvart at Ch.800 m; SL No.-6 | RAILA/PTK/W05 | 578383039 578384120 | 29/9/2011 | 0.35 | 3 | 2399729 | 330785 | 29-09-2011 | 2012-01-10 | 30-01-2013 Ex-31-12-2013 | 2399000 | 2060500 | 100% |  | Md. Shafiqur Rahman | FBP
6 |  | Rehab. of road from Kachipara UP-Joybangla Bazar-Karkhana Bazar- Paier Hat- Dariabad UZR., at Ch 0.00-4038 m; | RAILA/PTK/W06 | 578383037 | 29/9/2011 | 4.038 |  | 5392099 |  | 29-09-2011 | 2012-01-10 | 31-01-2013 | 5882178.59 |  | 15% |  |  | Postponded by Project Director on dated 14.08.2014 (App-5392099.00 Contract-5882178.59)
7 |  | Rehab. of road from Nazirpur UP-Upazila H/Q-Daspara UP- Moisadi Bazar Road, at Ch 1500-3055 m; | RAILA/PTK/W15 | 538383013 | 2012-01-03 | 1.555 |  | 6902311 | 2216525 |  | 2012-01-10 | 03-02-2013 Ex-31-12-2013 | 10031892.77 | 7770577 | 100% |  | M/S Hosen & Brothers | FBP
8 |  | Maintenance of Mominpur GC-Kalisuri GC-Baherchar GC, at ch 4800-7000 m; | RAILA/PTK/W17 | 578382005 | 28/03/2012 | 2.2 |  | 4802900 |  |  | 2012-01-10 | 2013-03-01 | 4020000 |  |  |  |  | Dropped (App-48,02,900.00 Contrac-40,20,000.00)
9 |  | Part-A) Rehabilation of Rabayer Bazer to Mehendipur bazer road at Ch. 0.00-900.00m; Part-B) Const. of 01 Nos 1.60x1.60m RCC Box culvert on the same road at Ch. 710m; | RAILA/PTK/W39 | 578383027 | 2014-02-03 | 0.9 | 1.6 | 5543828 |  | 2014-02-03 | 22-06-2014 | 27-03-2015 | 6357415.69 | 2703330 | 50% |  | Md. Abdul Aziz
10 |  | Part-A) Rehabilation of Rabayer Bazer to Mehendipur bazer road at Ch. 900.00-1900.00m; Part-B) Const. of 02 Nos U-drain culvert on the same road at Ch. 940m & 1410m; | RAILA/PTK/W40 | 578383027 | 2014-02-03 | 1 | 1.25 | 5984257 |  | 2014-02-03 | 22-06-2014 | 27-03-2015 | 6870516.09 | 2172500 | 50% |  | Md. Abdul Aziz
11 |  | Part-A) Rehabilation of Rabayer Bazer to Mehendipur bazer road at Ch. 1900.00-3000.00m; Part-B) Const. of 01 Nos U-drain culvert on the same road at Ch. 2080m; | RAILA/PTK/W41 | 578383027 | 2014-02-03 | 1.1 | 0.65 | 6384139 |  | 2014-02-03 | 22-06-2014 | 27-03-2015 | 7338845.5 |  | 30% |  | Md. Abul Kalam Azad
|  | Sub-Total Bauphal: | 8 |  |  | 16.705 | 6.5 | 38106366 | 2547310 |  |  |  | 44049146.34
1 | DASHMINA | Dashmina-Hajiorhat Launchghat Road, at Ch 00-827 m; | RAILA/PTK/W07 | 578522003 | 29/9/2011 | 0.827 | - | 3435914 | 1563796 | 29-09-2011 | 26/12/2012 | 25/12/2013 | 5474681.98 |  | 50% |  | M/S Shafi Enterprise
2 |  | Dashmina UP-Khair Hat Road, at Ch 00-500 m; | RAILA/PTK/W11 | 578523001 | 2011-01-12 | 0.5 | - | 684255 | - | 2011-12-01 | 21/03/2012 | 20-06-2012 | 650000 | 649445 | 100% |  | M/S Rohan Traders | FBP
3 |  | Rehabilation of Dashmina-Hajiorhat Launchghat Road at Ch 827.00-1643.00 m; | RAILA/PTK/W19 | 578522003 | 2012-02-05 | 0.816 | - | 3545787 | 1453133 | 2012-05-02 | 26/12/2012 | 25/12/2013 30-11-2014 | 5448816.82 | 2183651 | 100% |  | M/S Rony Enterprise
4 |  | Rehabilation of Dashmina-Hajiorhat Launchghat Road at Ch 1643.00-2500.00 m; | RAILA/PTK/W20 | 578522003 | 2012-02-05 | 0.857 | - | 3748049 | 1520803 | 2012-05-02 | 26/12/2012 | 25/12/2013 30-11-2014 | 5742963.99 | 2285224 | 100% |  | M/S Aktaurzzam, Town Bhalgashia Patuakhali
|  | Sub-Total Dashmina: | 4 |  |  | 3 | 0 | 11414005 | 4537732 |  |  |  | 17316462.79
1 | GALACHIPA | Bridge on Charbiswas UP-Char Aguesty, at Ch 3700 m | RAILA/PTK/W08 | 578573018 | 29/9/2011 | - | 10 | 1674271 | - |  | 21/03/2012 | 20-08-2012 | 2848000 |  | 100% |  | Md Mijanur Rahman Shikder | FBP
2 |  | Box Culvert on Katichiabunia F.P. Office-Pashirbunia, at Ch 1500, 1860, 2030 m |  | 578574062 |  |  |  | 441314 | -
[8 empty] | 441314 | -
[8 empty] | 441314 | -
|  | Sub-Total Galachipa: | 1 |  |  | 0 | 10 | 2998213 | 0 |  |  |  | 2848000
1 | KOLAPARA | Kalapara-Tarikata R&H , at Ch 00-5900 m; | Recast RAILA/PTK/W12 | 578662004 | 2011-01-12 | 5.9 |  | 5007790 | 644125 | 2011-12-01 | 21/03/2012 | 20-08-2012 | 5348828.15 | 4704703 | 100% |  | M/S Shikder Enterprise | FBP
2 |  | Rehab. of road from Lalua UP - Chinguria - Teakhali UP, at Ch 00-1000 m; | RAILA/PTK/W09 | 578663009 | 29/9/2011 | 1 | 1.5 | 4522087 | 1357474 | 29-09-2011 | 2012-01-10 | 30-01-2013 Ex-13-05-2013 | 5220000 | 3849485 | 100% |  | S.M. Shahidul Islam | FBP
3 |  | Rehab. of road from Solimpur Bazar - West Sonatola Nilgonj UP, at Ch 00-960 m; | RAILA/PTK/W10 | 578663008 | 29/9/2011 | 0.96 | - | 2724735 | 82575 | 29-09-2011 | 20/07/2012 | 30-01-2013 Ex-15-05-2013 | 2310000 | 2223816 | 100% |  | Md. Abul Kalam Azad | FBP
|  | Sub-Total Kolapara: | 3 |  |  | 7.86 | 1.5 | 12254612 | 2084174 |  |  |  | 12878828.15
1 | MIRJAGONJ | Mehindabad RHD-Dewly Bazar-Lamua Madrasha UZR Rd, at ch 1000-3660 m | RAILA/PTK/W13 | 578764009 | 2011-01-12 | 2.66 |  | 2205571 | - | 2011-12-01 | 21/03/2012 | 20-08-2012 | 2095000 | 2070557 | 100% |  | M/S Hazera & Sons | FBP
2 |  | RHD at Polerhat-Amragachia Bazar-Laxmipur Keyaghat, at ch 00-3500 m | RAILA/PTK/W14 | 578764057 | 2011-01-12 | 1.97 |  | 1332640 | 168618 |  | 21/03/2012 | 20-08-2012 Ex-20-06-2013 | 1332640 | 1332640 | 60% |  | M/S Mridha Traders | Contract Termination paid amount of work done Tk. 13,32,640.00
|  | Remaining work of Rehabilation of RHD at Polerhat-Amragachia Bazar-Laxmipur Keyaghat, at ch 00-1970 m | RAILA/PTK/W14 (RW) |  | 2014-10-06 |  |  | 4382160 |  |  |  |  | 3859990.41 |  | 0% |  | M/S Selim Stores, Selim Plaza, College road, Patuakhali
3 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 7542m - 8250m. (Part 1) | RAILA/PTK/W23 | 578762003 | 2012-06-05 | 0.67 |  | 3235339 | 1080777 |  | 15/11/2012 | 14/11/2013 20-08-2014 | 3272000 |  | 80% |  | M/S Khan Enterprise
4 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 8250m - 8850m. (Part 2) | RAILA/PTK/W24 | 578762003 | 2012-06-05 | 0.6 |  | 2956469 | 987316 |  | 15/11/2012 | 14/11/2013 20-08-2014 | 3138000 | 326611 | 80% |  | M/S Khan Enterprise
5 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 8850m - 9600m. (Part 3) | RAILA/PTK/W25 | 578762003 | 2012-06-05 | 0.72 |  | 3368215 | 1242017 |  | 15/11/2012 | 14/11/2013 20-08-2014 | 3670000 | 423389 | 80% |  | M/S Khan Enterprise
6 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 9600m - 10200m (Part 4) | RAILA/PTK/W26 | 578762003 | 2012-06-05 | 0.59 |  | 2798308 | 996743 |  | 15/11/2012 | 14/11/2013 | 3619000 | 2621223 | 100% |  | Md. Jalal Ahmed | FBP
7 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 10200m - 10800m (Part 5) | RAILA/PTK/W27 | 578762003 | 2012-06-05 | 0.6 |  | 2697983 | 1035014 |  | 15/11/2012 | 14/11/2013 | 3592000 | 2550245 | 100% |  | M/S Koushik Industrise | FBP
8 |  | Rehabilitation of Kathaltali GC (Chaita RHD /Trimukhi)- Shishur hat-Sailabunia Sluice Rd, at ch 10800m - 11500m (Part 6) | RAILA/PTK/W28 | 578762003 | 2012-06-05 | 0.7 |  | 3416913 | 1207517 |  | 15/11/2012 | 14/11/2013 30-06-2014 | 4360000 | 2909156 | 100% |  | Md. Mizanur Rahman Shikder | FBP
9 |  | Construction of 3.0x3.0m Double vent box culvert of Kathaltali GC (Chaita RHD/Trimukhi)-Shishur hat-Sailabunia Sluice Rd. at Ch. 7691m | RAILA/PTK/W34 | 578762003 | 17-06-2013 | - | 6 | 2054844.25 | - |  | 2013-07-12 | 30-09-2014 | 1763177.03 | 1746957 | 100% |  | M/S Shampa Traders | FBP
10 |  | Construction of 3.0x3.0m Double vent box culvert of Kathaltali GC (Chaita RHD/Trimukhi)-Shishur hat-Sailabunia Sluice Rd. at Ch. 7970m | RAILA/PTK/W35 | 578762003 | 17-06-2013 | - | 6 | 2054476.15 | - |  | 2013-07-12 | 30-09-2014 | 1750555.99 |  | 20% |  | M/S Mitushi Traders
11 |  | Construction of 4.0x4.0m Three vent box culvert of Kathaltali GC (Chaita RHD/Trimukhi)-Shishur hat-Sailabunia Sluice Rd. at Ch. 8970m | RAILA/PTK/W36 | 578762003 | 24-06-2013 | - | 12 | 5138150 | - |  | 2013-07-12 | 30-09-2014 | 4231698.13 | 2253000 | 100% |  | M/S Shampa Traders
|  | Sub-Total Mirjagonj: | 11 |  |  | 8.51 | 24 | 35641068.4 | 6718002 |  |  |  | 36684061.56
1 | Rangabali | Construction of Double vent 4.00x4.00 RCC Box Culvert on Gabbunia Earthen Killa-Katakhali Launch ghat, at Ch 95 m | Variation RAILA/PTK/W29 | 578574051 | 28-02-2013 |  | 8 | 2871667.49 | - |  | 20-05-2013 | 20-11-2013 31-06-2014 | 3117994 | 2962188 | 100% |  | ‡gmvm© ZvjyK`vi G›UvicÖvBR | FBP
2 |  | Construction of Double vent 4.00x4.00 RCC Box Culvert on Satianpara to Tulatali L.Ghat, at Ch 1710 m | RAILA/PTK/W30 | 578524159 | 28-02-2013 |  | 8 | 2871667.49 | - |  | 20-05-2013 | 20-11-2013 | 2728000 | 2707809 | 100% |  | ‡gmvm© Øxc G›UvicÖvBR | FBP
3 |  | Construction of Double vent 4.00x4.00 RCC Box Culvert on Chailtabunia UP-Borrobaisda UP-Moudube Mukharbandha Shelter, at Ch 3200 m; | Variation RAILA/PTK/W31 | 578573013 | 28-02-2013 |  | 8 | 2871667.49 | - |  | 20-05-2013 | 20-11-2013 31-05-2014 | 3117200 | 3113405 | 100% |  | ‡gvt Avãym †mvevnvb wgqv | FBP
4 |  | Construction of Double vent 3.00x3.00 RCC Box Culvert on Chailtabunia UP-Borrobaisda UP-Moudube Mukharbandha Shelter, at Ch 14900 m | RAILA/PTK/W32 | 578573013 | 28-02-2013 |  | 6 | 1885562.73 | - |  | 20-05-2013 | 20-11-2013 30-06-2014 | 1791000 | 1154902 | 100% |  | ‡gmvm© kvIb G›UvicÖvBR | FBP
5 |  | Construction of Double vent 3.00x3.00 RCC Box Culvert on Maj neta-Rangabali Ghat, at Ch 500 m | Variation RAILA/PTK/W33 | 578574063 | 28-02-2013 |  | 6 | 1879488.7 | - |  | 20-05-2013 | 20-11-2013 30-06-2014 | 2041459 | 2038519 | 100% |  | ‡gmvm© gwnb avbwmwo †UªWvm© | FBP
6 |  | Const. of 22.00m RCC Girder Bridge on Chaltabunia UP-Borobaisda up Moudubi Bazar-Mukurbandha Shelter Road at Ch. 3900m; | RAILA/PTK/W37 | 578583013 | 23/01/2014 |  | 22 | 9660179.7 | - |  |  |  | 8500541.76 |  |  |  |  | Postponded by Project Director on dated 23-07-2014 (App-96,60,179.70)
7 |  | Const. of 22.00m RCC Girder Bridge on Moudubi Bazar-Kazikanda road at Ch. 10.00m; | RAILA/PTK/W38 | 578585059 | 23/01/2014 |  | 22 | 9911075.32 | - |  |  |  | 8525432.89 |  |  |  |  | Postponded by Project Director on dated 23-07-2014 (App-99,11,075.32)
|  | Sub-Total Rangabali: | 5 |  |  | 0 | 36 | 12380053.9 |  |  |  |  | 12795653
|  | Total : Patuakhali District | 33 |  |  | 36.505 | 78 | 113789528.3 | 15887218 |  |  |  | 127566151.84 |  | 90%
Total Package -41 (8 Package cancle)

## Perojpur
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Perojpur
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | Bridge on Kalikati UZR to Uttar Gazipur hat via Horina High School, at Ch 1586 m; | RAILA/PRJ/W11 | 579805040 | 2012-01-12 |  | 12.5 | 900387 |  | 22-01-2012 | 13-03-2012 | 2012-10-10 | 899000 | 898581 | 100% | 100% | Suhana Trade Link International Prop. Md. Akteruzzaman Manik Parerhat Road, Pirojpur | Final
2 |  | Nimar Bridge to Kadamtola Bazar via Khanakuniari Madrasha L=3.50km, at Ch 00-3500 m and Bridge at Ch. 2990m ; | RAILA/PRJ/W12 | 579804031 | 2012-01-12 | 3.5 | 14 | 4069774 |  | 22-07-2012 | 13-03-2012 | 10-10-2012 Ex-10/5/2013 | 4068000 | 4037144 | 100% | 100% | M/S Zaman Enterprise Prop. Md. Kamruzzaman Mukta Amlapara, Pirojpur | Final
3 |  | Bagri to Kachubunia Road, 1Nos 2.00x2.00m Rcc Box Culvert at Ch 300m & 1Nos 3.00x3.00m Rcc Box Culvert at Ch. 500m ; | RAILA/PRJ/W02 | 579804004 | 20-09-2011 |  | 5 | 1013514 |  | 22-01-2012 | 13-03-2012 | 2012-10-10 | 1013000 | 1004121 | 100% | 100% | M/S Talukder Enterprise | Final
4 |  | Sikder Mallik UP-Kolakhali UP upto Gojalia lanchghat via Ghop hat Ch. 00-2246m and Bridge & Culvart at Ch.1252m-1x4.30x4.30m, Ch.1330m-1x 4.00x4.00m, Ch.1495m- 12.00m long bridge, Ch. 1790m- 1x2.00x2.00m, Rcc Box Culvert. | RAILA/PRJ/W14 | 579803009 | 2012-12-01 | 2.24 | 22.3 | 6962916 | 117483 |  | 13-03-2012 | 10-10-2012 Ex-10-07-2013 | 7077767 | 1770078 | 45% |  | M/S Alif Builders | Contract to be cancelled by XEN, directed by PD on dated 12.08.2014 (app-6962916.00 Salv-117483.00 Contract-7077767.00)
|  | Sub-Total Sadar: | 3 |  |  | 3.5 | 31.5 | 5983675 | 0 |  |  |  | 5980000 | 7709924
1 | KAWKHALI | Amrajuri Abasion Connacting road. L=3.00km, at Ch 700-1700 m; | RAILA/PRJ/W03 | 579474033 | 2012-12-01 | 0.9 | - | 436170 | - | 22-01-2012 | 13-03-2012 | 2012-10-08 | 436083 | 436083 | 100% | 100% | M/S Gazi Construction | Final
2 |  | Ashoa R&H to Gondarbo Abasion road L=1.86km, at Ch 00-1000 m; | RAILA/PRJ/W04 | 579474032 | 2012-12-01 | 1 | - | 1505136 | 1191856 | 22-01-2012 | 13-03-2012 | 2012-10-10 | 2695288 | 1503110 | 100% | 100% | M/S Gazi Construction | Salvage demand sent to HQ
3 |  | Amrajuri UP Office to Kawkhali GC., at Ch 700-1200 m; | RAILA/PRJ/W05 | 579473002 | 2012-12-01 | 0.5 | - | 756299 | 513247 | 22-01-2012 | 13-03-2012 | 2012-10-10 | 1267924 | 1267924 | 100% | 100% | M/S Talukder Enterprise | Final
4 |  | Kawkhali UP Office to Keundia Bazar.Ch 00-2000 m and Bridge culvert at ch. 1821m-10m, 2842m-10m ; | RAILA/PRJ/W18 | 579473001 | 2012-12-01 | 2 | 20 | 3135019 | - | 22-01-2012 | 13-03-2012 | 2012-10-10 | 3134000 | 3134000 | 100% | 100% | M/S Jeneva International | Final
5 |  | Sialkati Up Office – Sialkati Talukder Hat. Ch 00-500 m and Bridge culvert at ch. 244m-8.53m, 530m-10m, 708m-30m ; | RAILA/PRJ/W19 | 579473006 | 2012-12-01 | 0.5 | 50 | 5036152 | 545946 | 22-01-2012 | 13-03-2012 | 2012-10-10 | 5580000 | 4955579 | 100% | 100% | M/S Jeneva International | Salvage demand sent to HQ
6 |  | Bramon Titna embankment to Rakhal Mondoll House road ch. 00-2000m and Bridge culvert at ch. 258m-12.0m, 911m-12.0m; | RAILA/PRJ/W06 | 579474013 | 2012-12-01 | 2 | 24.3 | 2997352 | - | 22-01-2012 | 13/03/2012 | 2012-10-10 | 2995283 | 2987468 | 100% | 100% | M/S Jeneva International | Final
7 |  | Re-construction of 32.00 long Deck Slab bridge on Sialkati UP office-Sialkati Talukderhat road (Near Sialkati UP office at Ch. 270.00m; | RAILA/PRJ/W20 | 579473006 | 24-07-2014 |  | 32 | 8346879 | - |  | 13/03/2012 | 2012-10-10 | 8346879
|  | Sub-Total Kawkhali: | 7 |  |  | 6.9 | 126.3 | 22213007 | 2251049 |  |  |  | 24455457
1 | MOTHBARIA | Masua RHD to Safa Amua RHD via Mathbaria GC via Algi hat L=9.59km, at Ch 00-1645 m; | RAILA/PRJ/W21 | 579582002 | 2012-12-01 | 1.645 | - | 7256373 | 1524146 | 22-01-2012 | 13-03-2012 | 2012-10-10 | 8777885 | 7186463 | 100% | 100% | M/S Jadman Construction | Salvage demand sent to HQ
2 |  | Sapleza Varani to Kachubaria lanch gate HBB road. L=4.00km (HBB), at Ch 00-2200 m; | RAILA/PRJ/W07 | 579584001 | 2012-12-01 | 2.2 | - | 7437110 | 1239620 | 22-01-2012 | 13-03-2012 | 10/10/2012 Ex-22-04-2013 | 8674127 | 7434506 | 100% | 100% | Md. Tohidul Bashar Kabir | Salvage demand sent to HQ
3 |  | Sapleza Bazar to Vijora HBB road L=3.75km (HBB), at Ch 37-1500 m; | RAILA/PRJ/W23 | 579584105 | 2012-12-01 | 1.463 | - | 4820032 | 1359676 |  | 13-03-2012 | 2012-10-10 | 6177950 | 6177000 | 100% | 100% | M/S Oishi & Co. | Salvage demand sent to HQ
4 |  | Masua bazar to Khejurbaria cyclone shelter HBB road L=2.50km, at Ch 0-1000 m; | RAILA/PRJ/W24 | 579584049 | 2012-12-01 | 1 | - | 3814991 | - | 22-01-2012 | 13-03-2012 | 2012-10-09 | 887554 | 887554 | 100% | 100% | M/S Jadman Construction | Final
5 |  | Tulatala to Angulkata road Box culvert near the house of mollik. at Ch 500 m; | RAILA/PRJ/W25 | 579584072 | 2012-12-01 | - | 3 | 898278 | - | 22-01-2012 | 13-03-2012 | 2012-10-09 | 898099 | 898099 | 100% | 100% | M/S Sabina & Mamun Co. | Final
6 |  | Masua bazar to Khejurbaria cyclone shelter road Bridge near the house of Adiker., at Ch 500m 3x3 m; | RAILA/PRJ/W26 | 579584049 | 2012-12-01 | - | 3 | 887817 |  | 22-01-2012 | 13-03-2012 | 2012-10-10 | 4575452 | 3708164 | 100% | 100% | M/S Jadman Construction | Salvage demand sent to HQ
|  | Sub-Total Mothbaria: | 6 |  |  | 6.308 | 6 | 25114601 | 4123442 |  |  |  | 29991067
1 | NAZIRPUR | Nazirpur- Sreeramkati Road Ch 3600 -3950 m | RAILA/PRJ/W29 | 579762001 | 2012-12-01 | 0.35 | - | 110856 | - | 2012-08-02 | 29-03-2012 | 26-10-2012 | 6673427.86 | 1017970 | 40% | 16% | M/S Bushara Trade International
|  | Chandkati UZR-Madarbari Iron Bridge Road Ch1000-3345 m and 2 nos box culvert on 1.0mx1.0m; |  | 579764010 |  | 2.345 | 2 | 5565041 | -
2 |  | Rehabilation of Chandkati UZR-Madarbari Iron Bridge Road Ch. 3345-4000m and 04 nos 1.50x1.50m, 3550, 3600,3900, 01 no 4.00x4.00m RCC Box culvert at Ch. 3700m, 01no 2.00x2.00m RCC box culvert at ch. 3995m; | RAILA/PRJ/W22 | 579764010 | 2014-05-08 | 0.655 |  | 6276046 |  |  |  |  | 6276046
|  | Sub-Total Nazirpur: | 2 |  |  | 3.35 | 2 | 11951943 | 0 |  |  |  | 12949473.86
1 | NESARABAD | Rehab. of Rajbari-Patikelbari Road Ch 6000-8500 m | RAILA/PRJ/W30 (Duplication RAILA/PRJ/W08) | 579874030 | 2012-07-02 | 2.5 | - | 6929644 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 8310747.5 | 8281757 | 100% | 100% | M/S Rezon Enterprise Prop. Kazi Zaman, Nesarabad, Pirojpur. | Final
2 |  | Rehabilation of 2 nos bridge on Jagannathkati Bazar-Atghar GC-Bermohal GC Road at Ch 6305m & Ch7691m; Total Length = 73m; | RAILA/PRJ/W31 | 579872002 | 2012-07-02 | - | 73 | 4928475 | - |  | 2012-08-07 | 2013-05-02 | 5904706.46 | 5904573 | 100% | 100% | M/S Shasanka Ranjan Samadder, Nesarabad, Pirojpur. | Final
3 |  | Rehab. of madra Boys School to Swarupkati Border road 2 Bridges at Ch1750m-12m Ch2390m-15m; | RAILA/PRJ/W32 | 579874008 | 2012-07-02 | - | 38 | 4302842 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 5157290.23 | 5152872 | 100% | 100% | M/S Shasanka Ranjan Samadder, Nesarabad, Pirojpur. | Final
4 |  | Rehab. of 45.00 m Long Iron Bridge on Jalabari UP Office-Madra Bazar Road infron of Jhalakati GPS , at Ch 2900 m; | RAILA/PRJ/W33 | 579873004 | 2012-07-02 | - | 45 | 3751754 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 4494958.32 | 4493547 | 100% | 100% | M/S Beuty Construction Prop. Md. Delwar Hossain, Sarsina, Nesarabad, Pirojpur | Final
5 |  | Rehab. of 20.00 m Long Iron Bridge on Sarengkati UP Office-Ekota Bazar via Alkirhat Bazar near H/O Habibur Rahman , at Ch 200 m; | RAILA/PRJ/W34 | 579873010 | 2012-07-02 | - | 20 | 1787434 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 2144352.55 | 2141478 | 100% | 100% | M/S Nisha Construction Prop. Md. Jabyer Ahmed Ujjal, Nesarabad, Pirojpur | Final
6 |  | Rehab. of 22.00 m Long Iron Bridge on Baldia UP Office-Dubu Bazar Road (Attached Panchabeki Bazar.), at Ch 2450 m | RAILA/PRJ/W35 | 579873005 | 2012-07-02 | - | 22 | 1951972 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 2338511.07 | 2331356 | 100% | 100% | M/S Adittaya Construction Prop. Md. Nasiruddin, Nesarabad, Pirojpur. | Final
7 |  | Rehab. of 23.00m Long Iron Bridge on Somudaykati UP Office -Sehangalhat Road , at Ch 3660 m; | RAILA/PRJ/W36 | 579873009 | 2012-07-02 | - | 23 | 2862828 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 3432488.75 | 3397518 | 100% | 100% | Md. Mahafuzur Rahman Nesarabad, Pirojpur. | Final
8 |  | Rehab. of 30.00 m Long Iron Bridge on attached Jeluhar Bazar. | RAILA/PRJ/W37 | 579874151 | 2012-07-02 | - | 30 | 4191733 | - | 2012-08-04 | 2012-08-07 | 2013-05-02 | 5026659.78 | 3000000 | 100% | 72% | M/S Shasanka Ranjan Samadder, Nesarabad, Pirojpur.
9 |  | Rehab. of 10 Nos. Structure on Rajbari-Patikelbari Road at Ch 6080m,5560m,6181m,6830m,7180m,7500m,8900m,10845m,& 11815m (10 Nos=32.00m) | RAILA/PRJ/W16 | 579874030 | 16-04-2012 | - | 32 | 8275509 | - | 2012-04-06 | 23-10-2012 | 22-05-2013 Ex-28-01-2014 | 10154301.39 | 6390577 | 100% | 63% | M/S Emran Enterprise
10 |  | Rehab. of 40.00m foot bridge with RCC Decking over khal on Rajbari-Patikelbari Road at Ch. 2400m, | RAILA/PRJ/W44 | 579874030 | 2013-03-12 | - | 40 | 4447837 | - | 29-02-2014 | 24-04-2014 | 15-11-2014 | 4444718.32 |  | 70% | 0% | M/S Imran Traders
11 |  | Rehab. of 25.00m foot bridge with RCC Decking over khal on Sutiakati-Kowerakhalar Nanduhat road inform H/Q Mojibur Rahman over BESIC khal at ch. 720m | RAILA/PRJ/W45 | 579874022 | 2013-03-12 | - | 25 | 1110680 | - | 29-02-2014 | 24-04-2014 | 15-11-2014 | 1110055.41 | 1110055.41 | 100% | 100% | M/S Nisha Construction Prop. Md. Jabyer Ahmed Ujjal, Nesarabad, Pirojpur | Final
12 |  | Rehab. of 12.00m foot bridge with RCC Decking gover khal on Mearhat-Nanduhat Bazar road inform H/Q Jalil Miah at ch. 425m | RAILA/PRJ/W46 | 579872005 | 2013-03-12 | - | 12 | 694666 | - | 27-02-2014 | 24-04-2014 | 15-11-2014 | 694468.74 | 694468 | 100% | 100% | Md. Mahashin Mia | Final
13 |  | (Part-1) Rehab. Of Guarekha U.P office-Rajbari Bazar road at Ch. 0.00-1000.0m & (Part-2) Const. of 1 no.4.00mx4.00m RCC box culvert on the same road at Ch. 533m (Part-3) Const of 2 nos. 1.00mx1.00m RCC box culvert of the samd road at Ch. 270m, Ch. 465m (Part-4) Const. of 625x625mm size U-type culvert on the same road at Ch. 90m 240m, 705m, 840m. | RAILA/PRJ/W50 | 579873001 | 23-12-2013 | 1 | 6 | 9249776 | 619616 |  | 24-04-2014 | 15-11-2014 | 9866202.31 |  | 5% |  | M/S Sikder Traders
14 |  | Rehab. Of Guarekha U.P office-Rajbari bazar road at Ch. 1000-1710m (b) Const. of 2 nos 625x625mm size U-type culvert on the same road at Ch. 1140m & 1500m, © Const. of 1 No. 4.00x4.00m RCC box culvert on the same road at Ch. 1038m | RAILA/PRJ/W51 | 579873001 | 19-01-2014 | 0.71 | 4 | 6714733 | 422409 |  |  |  | 7845991.27 |  |  |  | M/S Jevena International | NOA issue
|  |  | 14 |  |  | 4.21 | 370 | 61199883 | 1042025 |  |  |  | 70925452.1
1 | BHANDARIA | Rehab. of 81.00 m bridge on Telikhali GC-Tushkhali GC via Horinpala Kotcha connecting Road; at Ch.12000m; | RAILA/PRJ/W01 | 579142010 | 14-08-2011 | - | 81 | 20008739 | - |  | 20-12-2011 | 20-05-2013 13-05-2014 | 20008739 |  | 50% |  | M/S Ashik Enterprise Pror.: Md. Asiqul Islam Azad Banaripara, Barisal. | Cancalled
|  | Remaining work Rehab. of 81.00 m bridge on Telikhali GC-Tushkhali GC via Horinpala Kotcha connecting Road; at Ch.12000m; | [5 empty] | 23007771 | - | 2014-11-08 |  |  | 23007771
2 |  | Improvement of Bridge approach at ch.3500m from Telikhali UP Complex-Safahat via 34no.Goalbunia GPS at Ch.2000m-3600m &2Nos 2.00x2.00m RCC Box Cul.on same road at ch.2800m,3280m | RAILA/PRJ/W38 | 579874029 | 2012-07-02 | 1.6 | 4 | 6959588 | - | 2012-08-02 | 29-03-2012 | 26-10-2012 | 8348182.02 | 8340000 | 100% | 100% | M/S Eshan Enterprise, Prop. Md. Salauddin, Harinpala, Bhandaria, Pirojpur. | Final
3 |  | Improvement of Bridge approach at ch.2250m from Goalbunia-Tushkhali TC-30no.Junia Board GPS H/O Mirza Golam Sarwar-Modanjugi UZR road at ch.2150m-3665m & 1 Nos 2.00x2.00m RCC Box Cul. At ch.2750m | RAILA/PRJ/W39 | 579874060 | 2012-07-02 | 1.5 | 2 | 6556811 | - | 2012-08-02 | 29/03/2012 | 26-10-2012 | 7865370.04 | 7864365 | 100% | 100% | M/S Telikhali Construction, Harinpala, Bhandaria, Pirojpur. | Final
4 |  | a) Improvement of road by Flexible Paved from Huzzat Ali Hat-Telikhali Embankment at Ch. 00-2000m road; b) Construction of 2 nos 2.00mx2.00mx7.01m RCC box culvert on the same road at ch. 450m & 1250m; | RAILA/PRJ/W13 | 579144041 | 2012-02-04 | 2 | 4 | 9287669 |  | 2012-09-04 | 24-05-2012 | 2012-11-12 | 11140153.65 | 11127925 | 100% | 100% | M/S Efte Enterprise, Prop. Md. Mirajul Islam, Bhandaria, Pirojpur | Final
5 |  | a) Improvement of road by Flexible Paved from Telikhali UP Complex-Uttar junia Bazar via Shahajan Members house at Ch. 00-1000m; b) Construction of 2.00mx2.00mx7.01m RCC box culvert on the same road at Ch. 300m. ; | RAILA/PRJ/W15 | 579144069 | 2012-04-02 | 1 | 2 | 4778199 |  |  | 24-05-2012 | 2012-11-12 | 5732563.1 | 5732563 | 100% | 100% | M/S Telikhali Construction, Harinpala, Bhandaria, Pirojpur | Final
6 |  | a) Improvement of road by HBB from Horinpala Padma Khal Sluice Get Manzu Market-Adarsho Gram-Abashon UNR at Ch. 0.00 – 2000.00m. b) Construction of 2.00x2.00mx7.32m RCC Box Cuvlert at Ch. 300m on the same road. | RAILA/PRJ/W40 | 579144156 | 30-05-2013 | 2 | - | 7578698 | - | - | 23-06-2013 | 14-01-2014 | 9077323.77 |  | 100% |  | M/S. Efte Enterprise
7 |  | Periodic Maintenance of 12.95m span Girder Bridge on Telikhali UP Complex – Safahat road via 34No. GPS over Geravanga Khal at Ch. 3950m under Telikhali Union; | RAILA/PRJ/W41 | 579144029 | 30-05-2013 | - | 12.95 | 3648315 | - | 30-05-2013 | 23-06-2013 | 14-01-2014 | 4376553.12 | 4376500 | 100% | 100% | M/S Horinpala Traders | Final
8 | BHANDARIA | Periodic Maintenance of Yachin Mowlana’s Madrasha-Charkhali Palli Younnayan Prokalpa road at Ch. 0.00m-1000.00m under Nadmulla Shialkathi; | RAILA/PRJ/W42 | 579144012 | 30-05-2013 | 1 | - | 3779940 | - | 30-05-2013 | 23-06-2013 | 14-01-2014 | 4528856.78 | 4528450 | 100% | 100% | M/S. Efte Enterprise | Final
9 |  | Periodic Maintenance of Ikree U.P Complex – Rayerhat road at Ch. 0.00m – 1000.00m under Ikree Union; | RAILA/PRJ/W43 | 579143012 | 30-05-2013 | 1 |  | 3877479 | - | 30-05-2013 | 23-06-2013 | 14-01-2014 | 4638276.66 | 4638000 | 100% | 100% | M/S. Eashan Enterprise | Final
10 |  | Rehab. Of Sikder Hat at Kaikhali GC-Malierhat GC via Jomaddarhat Ch. 4200-7600m (Part-A), & Const. of 1 nos. 1.30mx1.30mx5.10m RCC Box culvert at Ch. 690m on the same road (Part-B) | RAILA/PRJ/W47 | 579142004 | 2013-10-12 | 3.4 | 1.3 | 9116966 | - | 24-12-2013 | 16-02-2014 | 16-08-2014 | 11225216.56 | 9000000 | 100% | 80% | M/S Telikhali Construction
11 |  | Rehab. Of Sikder Hat at Kaikhali GC-Malierhat GC via Jomaddarhat Ch. 7600-11000m (Part-A), & Const. of 1 nos. 2.0mx2.0mx6.10m RCC Box culvert at Ch. 6650m on the same road (Part-B) | RAILA/PRJ/W48 | 579142004 | 2013-10-12 | 3.4 | 2 | 8978366 | - | 24-12-2013 | 16-02-2014 | 16-08-2014 | 11209524.62 | 9528095 | 85% | 85% | M/S Efte Enterprise,
12 |  | Rehab. Of Bhandaria food Godown-Chankhali RHD road via Dewribari road at Ch. 0.00-1500m (Part-A) & Const. of 1 nos. 2.00mx2.00mx6.10m RCC box culvert at Ch. 9550m on the samd road (Part-B) | RAILA/PRJ/W49 | 579144056 | 2013-10-12 | 1.5 | 2 | 7423000 | - | 24-12-2013 | 16-02-2014 | 16-08-2014 | 9197573.97 | 6881749.53 | 85% | 75% | M/S Telikhali Construction
13 | BHANDARIA | (A) Rehab. Of East Charkhali-Hetalia road at Ch. 00-1012m; (B)Const. of 2 nos 2.00x2.00x5.50m RCC Box Culvert on the same road at Ch. 580m, 685m; © Const. of 1 nos 4.00x4.00x5.50m RCC box culvert on the same road at Ch. 920m; | RAILA/PRJ/W52 | 579144003 | 14-07-2014 | 1.012 |  | 9476953 | 447078 |  |  |  | 11884547.7 |  | 0% |  | M/S. Efte Enterprise
14 |  | (A) Rehab. Of East Charkhali-Hetalia road at Ch. 1012-2012m; (B)Const. of 2 nos 2.00x2.00x5.50m RCC Box Culvert on the same road at Ch. 1440m, 1780m; | RAILA/PRJ/W53 | 579144003 | 14-07-2014 | 1 |  | 6335991 |  |  |  |  | 7599710.02 |  | 0% |  | M/S. Eashan Enterprise
|  | Sub-Total Bhandaria: | 14 |  |  | 20.412 | 111.25 | 130814485 | 447078 |  |  |  | 149840362.01
1 | ZIANAGAR | BaliparaUP-Kholpatua Munshirhat via Chndpur Launchghat HBB Road. at ch 232-1500 m & 3 RCC Foot Bridges and 7 box culvert at defferant Ch 208- 20m, Ch. 1813m & 2062m-12mx2nos; Ch. 880, 1504, 1700, 2007, 2167, 2210, 2292 -1x2.0mx2.0m | RAILA/PRJ/W09 | 579883013 | 2012-01-12 | 1.268 | 58 | 9407605 | - | 2012-08-02 | 29-03-2012 | 26-10-2012 Ex- 31-08-2013 (1st) 28-02-2014 | 9404521.58 | 3480000 | 40% | 37% | M/S Nandina Enterprise
2 |  | Parerhat UP-Pattashi UP via WAPDA hat Ch 00-930m &1RCC Foot Bridges and 6 box culvert at defferant Ch. 1650m -7.5m; Ch. 210, 733, 1098, 1260, 1695, 1850 - 1x2.0mx2.0m | RAILA/PRJ/W10 | 579883002 | 2012-01-12 | 0.93 | 19.5 | 4933948 | - | 2012-08-02 | 29-03-2012 | 26-10-2012 Ex-31-08-2013 | 4932171.94 | 4930301 | 100% | 100% | M/S A.B Enterprise | Final
|  | Sub-Total Zianagar: | 2 |  |  | 2.198 | 77.5 | 14341553 | 0 |  |  |  | 14336693.52 |  | 4020%
|  | Total : Perojpur District | 48 |  |  | 46.878 | 724.55 | 271619147 | 7863594 |  |  |  | 308478505.49 | 180339917.94 | 83.75%
Total Package -49 (1 Package Cancle)

## Jhalok
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Jhalokathi
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per (NOA) | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 23 | 24 | 25
1 | SADAR | Jhalakati RHD, Panjipathipara GC Himanandakati RHD, -Bermohal GC-Gouachita RHD road Paved road, at Ch 4100-4500 m; | RAILA/JHL/W01 | 542402001 | 23/8/2011 | 0.4 | - | 1673685 | 452674 | 15-01-2012 | 18-01-2012 | 17-01-2013 | 2020041.05 | 1565163 | 100% | 100% | M/S . Rob Traders | Final
2 |  | Gabkhan-Gouaton via Sekerhat UP including amrajhuri (UZR # 542), road Paved road, at Ch 3500-3800 m; 2x4.5x5.00m RCC Box culvert | RAILA/JHL/W08 | 542402005 | 2012-01-04 | 0.1 | - | 1223377 | - | 2013-07-08 | 2013-11-08 | 2014-10-08 | 1406136 | 1401277 | 100% | 100% | M/S Shyed Enterprise | Final
3 |  | Rehab. of 2x4.5x5.0m Bridge on Sarengal hat-Shangramnil via Keora UP road, at Ch 4822 m; | Recast RAILA/JHL/W02 | 542403011 | 23/8/2011 | - | 9 | 1793718 | 164909 | 17-01-2012 | 23-01-2012 | 22-01-2013 Ex-15-11-2013 | 1844641.89 | 1675647 | 100% | 100% | M/S . Promi Enterprise
4 |  | Rehabilation of 20.0m Span RCC Girder Bridge on Sarengal hat – Shangramnil via Keora UP road at Ch. 6805m; | RAILA/JHL/W11 | 542403011 | 17-05-2012 | - | 20 | 14186783.34 | - | 2013-05-08 | 2013-11-08 | 2014-10-08 | 17003994.31 | 10860768 | 70% | 64% | M/S Islam Brothers | 2nd
5 |  | Rehab. of 19.00m Span RCC Bridge on Shibgonj GC-Nabogram UP vi Boukathi Bazar road, at Ch 0 m; | RAILA/JHL/W13 | 542403018 | 21-06-2012 | - | 20 | 13007036.48 | - | 2013-05-08 | 2013-11-08 | 2014-10-08 | 15496750.27 | 14844335 | 96% | 96% | M/S Islam Brothers | 4th
|  | Sub-Total Sadar: | 5 |  |  | 0.5 | 49 | 31884599.82 | 617583 |  |  |  | 37771563.52
1 | KATHALIA | Khatalia HQ-Battala RHD Road via Aura GC. (Sikderhat Kachua via Bandaghata) From Road reclassification, at Ch 1500-3300 m & 2 RCC Box culvert ; | RAILA/JHL/W03 | 542432003 | 23/8/2011 | 1.8 |  | 2710464 | - | 2012-08-01 | 14-01-2012 | 13-01-2013 | 2574878 | 2571865 | 100% | 100% | M/S . Shahin Brothers | Final
2 |  | Aoarabunia UP off(Akner hat)-Old UP office- Soulajalia UP Off via Sonerbangla bazar, at Ch 0-7020 m; | Recast RAILA/JHL/W09 | 542433008 | 2012-01-04 | 2.738 | - | 11213047 | 2435535 | 20-08-2013 | 27-08-2013 | 26-02-2014 | 18557802 | 1000000 | 40% | 60% | M/S Shadow Const. | 1st
3 |  | Rehabilation of 20.0m Span RCC Girder Bridge on Amua bazaar – Patikhalghata UP office at Ch. 1227m; | RAILA/JHL/W12 | 542433006 | 2013-02-01 | - | 20 | 13612153 | - | 2013-05-08 | 2013-11-08 | 2014-10-08 | 16243145.81 |  | 15% |  | M/S Islam Brothers
4 |  | a) Rehab. Of Dogona bazar-Binapai bazar Via Malak Member House road at ch.00-1526m; b) Const. of 3Nos 1.30x1.30m size RCC Box Culvert at Ch.398m, 610m, 1000m on the same road; c) Const. of 2Nos 2.50x2.50m size RCC Box Culvert at Ch.885m, 933m on the same road; d) Const. of 1Nos 3.50x3.5m size RCC Box Culvert at Ch.1457m on the same road; | RAILA/JHL/W14 | 542434041 | 26-01-2014 | 1.526 | - | 10740665 | 2828533 |  |  |  | 15589562.83 |  | 0% |  | M/S Sayed Enterprise
5 |  | a) Rehab. Of Dogona bazar-Binapai bazar Via Malak Member House road at ch.1526-2425m; b) Const. of 2Nos 1.30x1.30m size RCC Box Culvert at Ch.2026m, 2323m, on the same road; c) Const. of 1Nos 2Vent 4.00x4.00m size RCC Box Culvert at Ch.2412m on the same road; | RAILA/JHL/W15 | 542434041 | 26-01-2014 | 0.899 | - | 8191238.97 | - |  |  |  | 8191238.97 |  | 0%
6 |  | Rehabilation of Siderer hat-Lodher hat via Abdul Wahab Master house road Ch. 0.00-780m; | RAILA/JHL/W17 | 542434088 | 2014-12-02 | 0.78 | - | 5765778 | 17348 |  |  |  | 6928011.83 |  |  |  | M/S Taluder & co.
7 |  | Rehabilation of Khatalia HQ-Battala RHD Road via Aura GC. (Sikderhat Kachua via Bandaghata) from road reclassification at Ch. 0.00-780.00m; | RAILA/JHL/W19 | 542432003 | 29-06-2014 | 0.78 | - | 9298859 | 998992 |  |  |  | 11837742.88 |  |  |  | M/S Taluder & co.
8 |  | Rehabilation of Khatalia HQ-Battala RHD Road via Aura GC. (Sikderhat Kachua via Bandaghata) from road reclassification at Ch. 780.00-1500.00m; | RAILA/JHL/W20 | 542432003 | 29-06-2014 | 0.72 | - | 5914226 | 40580 |  |  |  | 6838540.6 |  |  |  | M/S Taluder & co.
9 |  | Rehabilation of Aoarabunia UP off (Akner hat) - Old UP office-Soulajalia UP off via Sonerbangla bazar,at Ch. 7020-9200m; | RAILA/JHL/W21 | 542433008 | 14-07-2014 | 2.18 | - | 19016875 | 386615 |  |  |  | 19403490
|  | Sub-Total Kkathalia: | 9 |  |  | 11.423 | 20 | 86463305.97 | 6707603 |  |  |  | 106164412.92
1 | NALCHITI | Amirabad GC to Tahashil Kachari bari road Ch00-2250 m & 4 Box Culvert; | RAILA/JHL/W04 | 542734077 | 23-8-2011 | 1.85 | 8 | 6639661 | 2093615 | 2012-11-01 | 17-01-2012 | 2013-04-12 | 8296612.2 | 6078874 | 100% | 100% | M/S . Shado Construction
2 |  | Barishal-Jhalakati RHD- Pramohar Govt. Pry. school to H/O Anower driver bari Ch 00-2250 m & 4 Box Culvert; | Recast RAILA/JHL/W10 | 542734083 | 2012-04-01 | 2.25 | 4.5 | 13988260.13 | 1270943 | 2013-07-08 | 2013-11-08 | 2014-10-08 | 13988260.13 | 9035941 | 75% | 76% | M/S Shyed Enterprise
3 |  | Hadua Lunch ghat to Mollerhat road Ch00-5900 m & 20m RCC Bridge and 4 Box Culvert on 1.5mx1.5m; | RAILA/JHL/W05 | 542734088 | 23-8-2011 | 5.9 | 6 | 9255276 | 1268740 | 2012-09-01 | 14-01-2012 | 31-05-2014 | 10938724.65 | 8228000 | 80% | 65% | M/S . Islam Enterprise
4 |  | Const. of 2 vent 4.00mx4.00m RCC Box culvert on Masjidbaria-Chandrakanda H/School (H/Q Noab Ali Over Kuter khal) under Siddhakati UP at Ch. 2500m; | RAILA/JHL/W18 | 542735002 | 26-02-2014 | 8 | - | 3202316 | - |  |  | 14-09-2015 | 3822727.51 |  | 0% |  | M/S Talukder & Co
5 |  | Const. of 20.00m RCC Girder bridge on Hadua Lunch ghat to Mollerhat road at Ch. 4435m; | RAILA/JHL/W22 | 542734088 | 18-09-2014 | - | 20 | 13316179 | - |  |  |  | 15713091
|  | Sub-Total Nalchiti: | 5 |  |  | 18 | 38.5 | 46401692.13 | 4633298 |  |  |  | 52759415.49
1 | RAJAPUR | Bagri hat GC to Sangor hat via Suktagor UP road, at Ch 2030-4650 m & 2x1.83x1.83m Box; | RAILA/JHL/W06 | 542843013 | 23-8-2011 | 2.62 | 3.66 | 4160982 | - | 2012-02-01 | 2012-08-01 | 2013-01-07 | 3952932 | 3885333 | 100% | 100% | M/S . Kabir Storses
2 |  | Nalbunia hat to Matibanga road Ch 00-2700 m and 4x1.83x1.83m Box; | Recast RAILA/JHL/W07 | 542844073 | 23-8-2011 | 2 | 7.32 | 2942620 | - | 2012-01-01 | 2012-07-01 | 6/9/2013 30-06-2014 | 2789204 | 2656832 | 100% | 96% | M/S . Sharjil Enterprise
3 |  | Rehabilation of Rajapur-Bhandaria R&H at Khalek shop to Afser Uddin high School at Ch. 0.00-2059m | RAILA/JHL/W16 | 542844089 | 2014-12-02 | 2.059 |  | 9760659 | - |  |  |  | 11205496.01 |  | 0% |  | M/S Arafat Traders
|  | Sub-Total Rajapur: | 3 |  |  | 6.679 | 10.98 | 16864261 | 0 |  |  |  | 17947632.01
|  | Total : Jhalokathi District | 22 |  |  | 36.602 | 118.48 | 181613858.92 | 11958484 |  |  |  | 214643023.94 | 63804035 | 51.24%
193572342.92
4163225
6276046
23007771
9924031
6335991
8191238.97
19403490
77301792.97
11595268.9455
88897061.9155

## Chittag
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Chittagong
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | ANWARA | Engineer Noor Hossain Road. Paved road, at Ch 00-6400 m; | RAILA/CTG/W06 | 415044013 |  | 6 |  | 5349722 | - |  | 26-02-2012 | 18-09-2012 | 5349722 |  | 100% |  | Mr. Md. Abdul Bari Vill+P.O.-Madanpura, Baufal, Patuakhali
|  | Sub-Total Anwara: | 1 | 4: 1; Road Length (Km) 6: 6; Bridge/ Cul. Length (m) 7: 0; Bridge/ Cul. Length (m) 8: 5349722; Bridge/ Cul. Length (m) 9: 0; Bridge/ Cul. Length (m) 14: 5349722
1 | BANSKHALI | Baro Molana road, at Ch 3500-4500 m; | RAILA/CTG/W01 | 415084090 | 2011-09-12 | 0.5 |  | 570450 | 554540 |  | 2012-12-02 | 2012-04-05 | 1068740.03 |  | 100% |  | M/s Janasheba Enterprise, Utter Jaldi, Banshkhali, Ctg.
2 |  | Abdul Halim road., at Ch 1750-1900 m; | RAILA/CTG/W02 | 15084038 | 2011-09-12 | 0.15 |  | 176895 | 170982 |  | 2012-09-02 | 2012-01-05 | 330483.11 |  | 100% |  | M/s Janasheba Enterprise, Utter Jaldi, Banshkhali, Ctg.
3 |  | Dongra Raychota road, at Ch 500-700 m; | RAILA/CTG/W03 | 415084037 |  | 0.1 |  | 128969 | 110908 |  | 2012-09-02 | 2012-01-05 | 227883.18 |  | 100% |  | M/s Janasheba Enterprise, Utter Jaldi, Banshkhali, Ctg.
4 |  | Abdul Hakim road., at Ch 7600-7830 m; | RAILA/CTG/W04 | 415083010 | 2011-09-12 | 0.12 |  | 142491 | 134566 |  | 2012-12-02 | 2012-04-05 | 263203.79 |  | 100% |  | M/s Janasheba Enterprise, Utter Jaldi, Banshkhali, Ctg.
5 |  | Bibi Chowdhury road. (Shahajan Chowdhury ), at Ch 3160-3660 m; | RAILA/CTG/W05 | 415084089 | 2011-09-12 | 0.25 |  | 285304 | 281689 |  | 2012-12-02 | 2012-04-05 | 538643.73 |  | 100% |  | M/s Janasheba Enterprise, Utter Jaldi, Banshkhali, Ctg.
|  | Sub-Total Banskhali: | 5 | 4: 5; Road Length (Km) 6: 1.12; Bridge/ Cul. Length (m) 7: 0; Bridge/ Cul. Length (m) 8: 1304109; Bridge/ Cul. Length (m) 9: 1252685; Bridge/ Cul. Length (m) 14: 2428953.84; Bridge/ Cul. Length (m) 16: 600%
|  | Total : Chittagong District | 6 | 4: 6; Road Length (Km) 6: 7.12; Bridge/ Cul. Length (m) 7: 0; Bridge/ Cul. Length (m) 8: 6653831; Bridge/ Cul. Length (m) 9: 1252685; Bridge/ Cul. Length (m) 14: 7778675.84; Bridge/ Cul. Length (m) 16: 100%

## Laxmi
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Laxmipur
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | SADAR | South Char Ramani Mohon (Matabbarhat) road ch 00-2860m including 1x2mx2m Box culvert & U-drain; | RAILA/LAX/W02 | 451435116 | 2011-12-12 | 2.86 | 5 | 9908110 | - | 15-12-2011 | 2012-09-04 | 13-12-2012 Ex-20-06-2013 | 9413550 |  | 100% |  | Md. Ziaul Hoque | FB Paid
2 |  | Kadirar goza - Bhuiyar hat road ch 1675-4350m including U-drain; | RAILA/LAX/W03 | 451433011 | 2011-12-12 | 2.675 | 9 | 13589457 | - | 15-12-2011 | 2012-01-04 | 07-04-2013 Ex-30-12-2013 (1st) 30-06-2014 | 13553788 |  | 100% |  | M/S Abdul Gafran & others | FB Paid
|  | Sub-Total Sadar: | 2 | 4: 2; Road Length (Km) 6: 5.535; Bridge/ Cul. Length (m) 7: 14; Bridge/ Cul. Length (m) 8: 23497567; Bridge/ Cul. Length (m) 9: 0; Bridge/ Cul. Length (m) 14: 22967338
1 | RAMGATI | GC Char Alexandar UP Road ch 00-1067m. | RAILA/LAX/W01 | 451733019 | 2011-10-02 | 1.067 | - | 2163923 | 469056 | 15-12-2011 | 2012-09-04 | 14-08-2012 Ex-30-08-2013 (1st) Ex-08-04-2014 (2nd) | 2501350 |  | 100% |  | Md. Ali Haider | FB Paid
|  | Sub-Total Ramgati: | 1 | 4: 1; Road Length (Km) 6: 1.067; Bridge/ Cul. Length (m) 7: 0; Bridge/ Cul. Length (m) 8: 2163923; Bridge/ Cul. Length (m) 9: 469056; Bridge/ Cul. Length (m) 14: 2501350
|  | Total : Laxmipur District | 3 | 4: 3; Road Length (Km) 6: 6.602; Bridge/ Cul. Length (m) 7: 14; Bridge/ Cul. Length (m) 8: 25661490; Bridge/ Cul. Length (m) 9: 469056; Bridge/ Cul. Length (m) 14: 25468688; Bridge/ Cul. Length (m) 16: 100%

## Noakha
Monthly Progress Report Under
Rehabilitation of AILA Affected Rural Infrastructure Project ( RAARIP )
Financial Year 2011-2012
Reporting Month: October' 2014
[12 empty] | Reporting Date |  |  | 2026-07-28
District Name: Noakhali
Sl. No. | Upazila | Name of Scheme with Chainage & Package No. | Package Nos. | Road ID Number | Approving date | Approved Length |  | Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Tender Invitation date (IFT) | Date of Commencement as per NOA | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Bridge/ Cul. Length (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | HATIYA | Bondortala-Nijhumdwip road, at Ch 0.00-1500.00 m; | Variation RAILA/NOA/W03 | 475363010 | 2011-07-12 | 1.5 | - | 9118808 | - | 2012-09-01 | 14-02-2012 | 20-05-2013 | 11015481.52 | 11010610 | 100% |  | M/S Rupali Traders | Final
2 |  | Bondortala-Nijhumdwip road, at Ch 1500.00-3750.00 m; | Variation RAILA/NOA/W04 | 475363010 |  | 2.25 | - | 10121858 | - | 2012-09-01 | 14-02-2012 | 20-05-2013 | 11801316.45 | 11798362 | 100% |  | M/S Rupali Traders | Final
3 |  | Bondortala-Nijhumdwip road, at Ch 3750.00-5250.00 m; | Variation RAILA/NOA/W05 | 475363010 |  | 1.5 | - | 9035372 | - | 2012-09-01 | 14-02-2012 | 20-05-2013 | 11288457.45 | 11280854 | 100% |  | G.M Sons | Final
4 |  | Bondortala-Nijhumdwip road, at Ch 5250.00-6900.00 m; | Variation RAILA/NOA/W06 | 475363010 |  | 1.65 | - | 8924828 | - | 2012-09-01 | 14-02-2012 | 20-05-2013 | 10496164.07 | 10490482 | 100% |  | G.M Sons | Final
5 |  | Char changa-Jahajmara road bridge approach, at Ch 00-2000 m; | RAILA/NOA/W01 | 475362002 | 14-09-2011 | 2 | - | 2195431 | - | 2011-09-20 | 27-12-2011 | 29-04-2012 | 2195431 | 2195428 | 100% |  | M/S K.S Trading Kafrul, Mirpur, Dhaka. | Final
6 |  | Rehabilation of Bondortala - najhumdwip (namar Bazaar) raod at Ch. 6900-8900m | Variation RAILA/NOA/W07 | 475363010 | 24-01-2013 | 2 | - | 12182475 | - | 21-07-2013 | 25-09-2013 | 2014-12-10 | 16044246.08 | 8149903 | 100% |  | G.M Sons | 2nd RA
|  | Sub-Total Hhatia: | 6 | 3 |  | 10.9 | 0 | 51578772 | 0 |  |  |  | 62841096.57
1 | SUBARNACHAR | Nuruddin road, at Ch 0-2256 m; | RAILA/NOA/W02 | 475895054 | 2011-12-07 | 2.25 | 2.5 | 9299048 | - | 2012-09-01 | 14-02-2012 | 27-12-2012 | 10678348.83 | 10674361 | 100% |  | M/S Rupali Traders | Final
|  | Sub-Total Subarnachar: | 1 | 1 |  | 2.25 | 2.5 | 9299048 | 0 |  |  |  | 10678348.83
|  | Total : Noakhali District | 7 | 4 |  | 13.15 | 2.5 | 60877820 | 0 |  |  |  | 73519445.4 | 65600000 | 100%

## Total
Summary of Estimates Approved by PIO under | [19 empty] | 25000
Rehabilitation of AILA Affected Rural Infrastructure Project (RAARIP) | [19 empty] | 10000
151800.52
Reporting Month: October' 2014 | [19 empty] | 669287.52
[15 empty] | Date : | 2026-07-28 |  |  |  | 1354193.76
As per approved DPP | [8 empty] | Approved Estimated Cost | [7 empty] | Total Spent up to June'2012 | Final Spent | Total Progress (%) | 24656.74
Sl. No. | District | Total Scheme Nos | Rd (km) | Bdg/Cul (m) | Estimated Cost (Tk) |  |  | Total Scheme | Total Package | Rd (km) | Bdg/Cul (m) | Total Scheme | Approved Estimated Cost (Taka) without salvage | Salvage Cost (Tk) | Gross Approved Estimated Cost (Taka) | Contract Amount (Taka) |  |  |  | 70692.2
[5 empty] | Road | Bridge/ Culvert | Total | [12 empty] | 26035.36
1 | Total : Khulna District | 21 | 67.72 | 128.37 | 200516308.79 | 8232117 | 208748425.79 | 19 | 32 | 63.361 | 64 | 0 | 164067288.54 | 4217939 | 168285227.54 | 167551564.43 | 79817493 |  | 69.06% | 90381.72
2 | Total : Bagerhat District | 39 | 81.83 | 223.8 | 133906253.73 | 55382115.7 | 189288369.43 | 22 | 29 | 63.262 | 44.3 | 0 | 123304280.8 | 14217658 | 137521938.8 | 126684738.28 | 96475917 |  | 101% | 18057.6
3 | Total : Satkhira District | 8 | 58.1 | 0 | 117509292.68 | 0 | 117509292.68 | 8 | 16 | 45.317 | 16.88 | 0 | 97602597.41 | 9697119 | 107299716.41 | 107667783.87 | 76500000 |  | 89.06% | 47020.4
4 | Total : Barisal District | 36 | 23.69 | 271.5 | 50050031.17 | 49581002.87 | 99631034.04 | 25 | 26 | 18.682 | 115.9 | 0 | 68942575.54 | 6116396 | 75058971.54 | 76925346.74 | 45838000 |  | 90.12% | 23296.68
5 | Total : Barguna District | 19 | 46.9 | 67 | 57239486.52 | 7394527 | 64634013.52 | 14 | 13 | 31.889 | 0 | 0 | 38069410 | 1826503 | 39895913 | 37785667.33 | 30848043 |  | 97.69% | 40241.2
6 | Total : Bhola District | 33 | 100.06 | 152.7 | 144721367.96 | 18392803 | 163114170.96 | 26 | 38 | 76.506 | 129.15 | 0 | 181364280 | 3810050 | 185174330 | 186969957.58 | 147000000 |  | 100% | 428328.1
7 | Total : Patuakhali District | 35 | 64.272 | 590 | 115689702.46 | 49145419.07 | 164835121.53 | 16 | 33 | 36.505 | 78 | 0 | 113789528.3 | 15887218 | 129676746.3 | 127566151.84 | 0 |  | 90% | 500137.54
8 | Total : Perojpur District | 31 | 34.95 | 726.83 | 63751207.29 | 96814831 | 160566038.29 | 28 | 48 | 46.878 | 724.55 | 0 | 271619147 | 7863594 | 279482741 | 308478505.49 | 180339917.94 |  | 83.75% | 497037.89
9 | Total : Jhalokathi District | 13 | 24.47 | 125.48 | 47859896.69 | 27517510 | 75377406.69 | 10 | 22 | 36.602 | 118.48 | 0 | 181613858.92 | 11958484 | 193572342.92 | 214643023.94 | 63804035 |  | 51.24% | 116369.91
10 | Total : Chittagong District | 7 | 8.3 | 0 | 7680952.27 | 0 | 7680952.27 | 6 | 6 | 7.12 | 0 | 6 | 6653831 | 1252685 | 7906516 | 7778675.84 | 0 | 6511000 | 100% | 3870777.65
11 | Total : Laxmipur District | 3 | 10.48 | 12 | 25190034 | 1445686 | 26635720 | 3 | 3 | 6.602 | 14 | 3 | 25661490 | 469056 | 26130546 | 25468688 | 0 | 23700000 | 100% | 42436.55
12 | Total : Noakhali District | 4 | 14.55 | 13 | 46856025.98 | 2305888 | 49161913.98 | 3 | 7 | 13.15 | 2.5 | 4 | 60877820 | 0 | 60877820 | 73519445.4 | 65600000 |  | 100% | 74249.88
| Total 12 Districts | 249 | 535.322 | 2310.68 | 1010970559.54 | 316211899.64 | 1327182459.18 | 180 | 273 | 445.874 | 1307.76 | 13 | 1333566107.51 | 77316702 | 1410882809.51 | 1461039548.74 | 786223405.94 | 30211000 | 89.33% | 37538.39
11431.44
| District Name | Tender not yet called | [17 empty] | 27728.08
48915.12
| a) Khulna | 5 | [17 empty] | 14576.07
64608.6
| b) Bagerhat | 1 | [17 empty] | 183.6
4724.4
| c) Barisal | 1 | [17 empty] | 212381.25
33436.8
| d) Bhola | 3 | [17 empty] | 701.33
32395.89
| Total= | 10 | [17 empty] | 195607.2
3000
49789.46
1000
51066
28567.45
762527.38
9660179.68